## AllObjects
Origin | Project | Type | Task Name Original | Task Name | Area | PIC | Classificação | D2C | Priority | Status Migração | Migração Dados | Due Date | Otimizada | Level | Duration | Start | End | Dependencies | PRIORITY2 | MIGRATION_CLASS | DISK_GB | TABLE_TYPE | Qty Dependencies | Referenced | Remark | W35-2025 | W36-2025 | W37-2025 | W38-2025 | W39-2025 | W40-2025 | W41-2025 | W42-2025 | W43-2025 | W44-2025 | W45-2025 | W46-2025 | W47-2025 | W48-2025 | W49-2025 | W50-2025 | W51-2025 | W52-2025 | W01-2026 | W02-2026 | W03-2026 | W04-2026 | Remark
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 325656 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_TESTE_),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_MD.PROC_DIM_VTEX_ORDER_STATUS),(PROCEDURE - OW_LAO.PROC_TESTE),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE),(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.RAW_VTEX_PAYMENTS_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN),(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,4564 | RAW | 0 | [(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_TESTE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 53735 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 10527 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,2317 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0002 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,7697 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD),(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,7722 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VW_SDU_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 14594 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.RAW_VTEX_PAYMENTS_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,217 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA),(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_TESTE),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,1202 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_RAW_VTEX_SSG_BR_B2B_SALES_ORDER_MONITORING_DATASOURCE),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_TESTE)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,2296 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0107 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,1855 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION),(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0006 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0002 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0047 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0004 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0282 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0002 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0377 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0019 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0198 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 17933 | ODS | 0 | [(VIEW - OW_MD.VW_PRICE_MONITORING_AUDIT_PROCESS),(INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0735 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU),(VIEW - OW_MD.VW_PRICE_MONITORING_AUDIT_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 11093 | RAW | 0 | [(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 325656 | RAW | 0 | [(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER),(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 53735 | RAW | 0 | [(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM),(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,2317 | RAW | 0 | [(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS),(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,9546 | RAW | 0 | [(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE),(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 14594 | RAW | 0 | [(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT),(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 10527 | RAW | 0 | [(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,1612 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,9546 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBR_PROMOCARD) | U_PRJ_ECOM.RAW_VTEX_SSGBR_PROMOCARD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0272 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBR_PROMOCARD_ID) | U_PRJ_ECOM.RAW_VTEX_SSGBR_PROMOCARD_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0303 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,002 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0027 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0638 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0298 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_CLIENT_PROFILE_DATA) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_CLIENT_PROFILE_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ID) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,1056 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_KIT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_KIT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0064 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_EPP_DETAIL_HIST_TALEND_PRL_2024) | U_PRJ_ECOM.RAW_VTEX_SSG_EPP_DETAIL_HIST_TALEND_PRL_2024 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,5438 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_EPP_DETAIL_TALEND) | U_PRJ_ECOM.RAW_VTEX_SSG_EPP_DETAIL_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA) | U_PRJ_ECOM.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VIEW_VTEX_BR_SHOP_MASTER) | U_PRJ_ECOM.TMP_VIEW_VTEX_BR_SHOP_MASTER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_EPP2) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_19) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_19 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_9) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_9 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_TALEND_01) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_TALEND_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_TALEND) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_EPP_TALEND) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_EPP_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0329 | TMP | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_INV_SEM_INT) | U_PRJ_ECOM.TMP_VTEX_INV_SEM_INT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0021 | TMP | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.TMP_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED) | U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,002 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST_ADJ),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MAT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_PROD),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,3629 | RAW | 0 | [(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0046 | RAW | 0 | [(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS)] |  | 25/08 - 25/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0148 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - OW_LAO.RAW_VTEX_PAYMENTS) | OW_LAO.RAW_VTEX_PAYMENTS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 18895 | RAW | 0 | [(VIEW - OW_LAO.RAW_VTEX_PAYMENTS_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_GENERATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0411 | RAW | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_AR_SMB),(INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PACKAGE),(INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM),(INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT),(INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL) | U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0139 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL),(INGESTION - JOB.ODS_VTEX_MASTER_DATA_CL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0504 | RAW | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0613 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG)] |  | 25/08 - 25/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0022 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP)] |  | 25/08 - 25/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0022 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,1709 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,4119 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI) | OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0067 | ODS | 0 | [(PROCEDURE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_GENERATE),(PROCEDURE - OW_LAO.PROC_ODS_STOCKOUT_VTEX_GLOBALBI),(PROCEDURE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_SEDA_GENERATE)] |  | 25/08 - 25/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER)] |  | 25/08 - 25/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG)] |  | 25/08 - 25/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER)] |  | 25/08 - 25/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0012 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0011 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0032 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - OW_LAO.RAW_VTEX_PAYMENTS_FILES) | OW_LAO.RAW_VTEX_PAYMENTS_FILES | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0006 | RAW | 0 | [(PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_FILES_GET),(PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_FILES_DEDUP)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP) | OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_PRODUCT_SKU) | U_PRJ_ECOM.ODS_VTEX_PRODUCT_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0507 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_PRODUCT),(PROCEDURE - OW_MD.PROC_FT_PRODUCT_STATUS)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_STATUS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0011 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_AUDIT_VTEX) | U_PRJ_ECOM.RAW_AUDIT_VTEX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0007 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_OK),(VIEW - U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_NOK)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_CL) | U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_CL | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,015 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - OW_LAO.ODS_SEDA_VTEX_KIT_COMPONENTS_REGISTRATION) | OW_LAO.ODS_SEDA_VTEX_KIT_COMPONENTS_REGISTRATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 | [(VIEW - OW_LAO.VW_PMS_TESTE)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS) | OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS)] |  | 25/08 - 25/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_SALES) | OW_LAO.ODS_HYBRIS_SALES | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.2 Ingestion HYBRIS | 0,7395 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(INGESTION - JOB.ODS_HYBRIS_SALES),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS)] |  | 25/08 - 25/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS) | OW_LAO.ODS_HYBRIS_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.2 Ingestion HYBRIS | 0,2854 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS),(INGESTION - JOB.ODS_HYBRIS_PAYMENTS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PAYMENTS),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING)] |  | 25/08 - 25/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_COMBO) | OW_LAO.ODS_HYBRIS_COMBO | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0003 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  | 25/08 - 25/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_CANCELLATIONS) | OW_LAO.ODS_HYBRIS_CANCELLATIONS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0221 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_CANCELLATIONS),(INGESTION - JOB.ODS_HYBRIS_CANCELLATIONS)] |  | 25/08 - 25/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_OFFERS) | OW_LAO.ODS_HYBRIS_OFFERS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 20153 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_OFFERS),(INGESTION - JOB.ODS_HYBRIS_OFFERS)] |  | 25/08 - 25/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_PREORDERS) | OW_LAO.ODS_HYBRIS_PREORDERS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0006 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PREORDERS),(INGESTION - JOB.ODS_HYBRIS_PREORDERS)] |  | 25/08 - 25/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_REFUNDS) | OW_LAO.ODS_HYBRIS_REFUNDS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0186 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REFUNDS),(INGESTION - JOB.ODS_HYBRIS_REFUNDS)] |  | 25/08 - 25/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_RETURNS) | OW_LAO.ODS_HYBRIS_RETURNS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_RETURNS),(INGESTION - JOB.ODS_HYBRIS_RETURNS)] |  | 25/08 - 25/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_REWARDS) | OW_LAO.ODS_HYBRIS_REWARDS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,1916 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REWARDS),(INGESTION - JOB.ODS_HYBRIS_REWARDS)] |  | 25/08 - 25/08
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_INSERT) | U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_INSERT | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 1 | 1.3 Ingestion MAGENTO | 0,0002 | TMP | 0 |  |  | 25/08 - 25/08
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO) | U_PRJ_ECOM.ODS_SELA_API_MAGENTO | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-25 | 2025-08-25 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0,0097 | ODS | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO),(INGESTION - JOB.ODS_SELA_API_MAGENTO)] |  | 25/08 - 25/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS_HOMOLOG) | OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS) | OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS_HOMOLOG) | OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0015 | TMP | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_VTEX_PROFILE) | OW_LAO.TMP_VTEX_PROFILE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID)] |  | 26/08 - 26/08
NERP,VTEX |  | TABLE | (TABLE - OW_SEDA_S.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS) | OW_SEDA_S.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0099 | ODS | 0 | [(INGESTION - JOB.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 2882 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_AR)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_B2B) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_B2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,3744 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_BR_B2B)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_EPP2) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 41824 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_BR_EPP2)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_PY) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_PY | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0022 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_PY)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_UY) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_UY | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0031 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_UY)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,002 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_DOMAIN) | U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_DOMAIN | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0412 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_MASTER_DATA_DOMAIN)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_BY_SKU) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_BY_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0008 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PRICE_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_PRICE_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_SSG_BR_PRICE_LIST)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0037 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0809 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0008 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,002 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 27504 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_BY_REF_ID) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_BY_REF_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0012 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_CT_TRADEIN) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_CT_TRADEIN | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_CT_TRADEIN) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_CT_TRADEIN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_COLLECTION) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_COLLECTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,353 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_INTEGRATION_RAW_VTEX_SALES_COLLECTION)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0057 | RAW | 0 | [(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 44249 | RAW | 0 | [(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0671 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_2020) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_2020 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_INTEGRATION_RAW_VTEX_SALES_COLLECTION)] |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(VIEW - U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN)] |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_SEASA_VTEX_CANCEL) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_SEASA_VTEX_CANCEL | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0804 | ODS | 0 |  |  | 26/08 - 26/08
NERP,VTEX |  | TABLE | (TABLE - OW_LAO.ODS_SEDA_SOLD_NERP_VS_CHANNEL_VTEX) | OW_LAO.ODS_SEDA_SOLD_NERP_VS_CHANNEL_VTEX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 |  |  | 26/08 - 26/08
NERP,VTEX |  | TABLE | (TABLE - OW_LAO.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO_HOMOLOG) | OW_LAO.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO_HOMOLOG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0018 | ODS | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_ACCESS_CODE_PARTNER_LEVEL_VTEX) | OW_LAO.TMP_ACCESS_CODE_PARTNER_LEVEL_VTEX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_ACCESS_CODE_PARTNER_LEVEL_VTEX_SELA) | OW_LAO.TMP_ACCESS_CODE_PARTNER_LEVEL_VTEX_SELA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER_SKU_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SKU_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_2) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_2 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0012 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_AGG_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_AGG_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0009 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_DISCOUNT) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_DISCOUNT | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0036 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_ITEM) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0044 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0011 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS_HOMOLOG_2) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS_HOMOLOG_2 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0043 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_RATEIO) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_RATEIO | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_SKU_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_SKU_AGG_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_SKU_AGG_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0011 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_TOTAL) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_TOTAL | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0105 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_TOTAL_ITEM) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_TOTAL_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0126 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER_AGG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER_SKU_AGG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_PAYMENTS | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER_AGG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER_SKU_AGG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_PAYMENTS | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_FT_D2C_VTEX_PROMOTION_PROM_NAME_REFERENCE) | OW_LAO.TMP_FT_D2C_VTEX_PROMOTION_PROM_NAME_REFERENCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0092 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_FT_D2C_VTEX_PROMOTION_PROM_NAME_REFERENCE_FIX_NULL) | OW_LAO.TMP_FT_D2C_VTEX_PROMOTION_PROM_NAME_REFERENCE_FIX_NULL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0091 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_PROMOTION_01) | OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_PROMOTION_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_PROMOTION_TMP) | OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_PROMOTION_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_TEMP_20250711) | OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_TEMP_20250711 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_ORDER_ITEM_TO_COMPONENTS_PO_VTEX_TEMP_20250711) | OW_LAO.TMP_ORDER_ITEM_TO_COMPONENTS_PO_VTEX_TEMP_20250711 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_PARAMETER_PO_VTEX_TEMP_20250711) | OW_LAO.TMP_PARAMETER_PO_VTEX_TEMP_20250711 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
NERP,VTEX |  | TABLE | (TABLE - OW_LAO.TMP_PAYMENT_VTEX_NERP_SALES_TEMP_20250711) | OW_LAO.TMP_PAYMENT_VTEX_NERP_SALES_TEMP_20250711 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_PROMOTION_01) | OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_PROMOTION_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP_20250711) | OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP_20250711 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_PO_VTEX_PROMOTION) | OW_LAO.TMP_PO_VTEX_PROMOTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
NERP,VTEX |  | TABLE | (TABLE - OW_LAO.TMP_PROMOTION_VTEX_NERP_SALES_TEMP_20250711) | OW_LAO.TMP_PROMOTION_VTEX_NERP_SALES_TEMP_20250711 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_RP_VTEX_2024_06_01_AND_2025_01_29) | OW_LAO.TMP_RP_VTEX_2024_06_01_AND_2025_01_29 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,105 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_SHIPPING_VTEX_TEMP_20250711) | OW_LAO.TMP_SHIPPING_VTEX_TEMP_20250711 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_VTEX_PAYMENTS_2024_06_01_AND_2025_01_29) | OW_LAO.TMP_VTEX_PAYMENTS_2024_06_01_AND_2025_01_29 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,028 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_LAO.TMP_VTEX_PAYMENT_SKU_FINAL) | OW_LAO.TMP_VTEX_PAYMENT_SKU_FINAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0027 | TMP | 0 |  |  | 26/08 - 26/08
NERP,VTEX |  | TABLE | (TABLE - OW_SEDA_S.ODS_ELASTIC_VTEX_NERP_INTERFACE) | OW_SEDA_S.ODS_ELASTIC_VTEX_NERP_INTERFACE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0005 | ODS | 0 |  |  | 26/08 - 26/08
NERP,VTEX |  | TABLE | (TABLE - OW_SEDA_S.TMP_ELASTIC_VTEX_NERP_INTERFACE) | OW_SEDA_S.TMP_ELASTIC_VTEX_NERP_INTERFACE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 26/08 - 26/08
NERP,VTEX |  | TABLE | (TABLE - OW_SEDA_S.TMP_LINKAPI_VTEX_NERP_INTERFACE_ERRORS) | OW_SEDA_S.TMP_LINKAPI_VTEX_NERP_INTERFACE_ERRORS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_SEDA_S.TMP_OST_PLUGG_STATUS_COM_VTEX) | OW_SEDA_S.TMP_OST_PLUGG_STATUS_COM_VTEX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0623 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_SEDA_S.TMP_OST_PLUGG_VTEX) | OW_SEDA_S.TMP_OST_PLUGG_VTEX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,064 | TMP | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_SEDA_S.TMP_OST_PLUGG_VTEX_BASE) | OW_SEDA_S.TMP_OST_PLUGG_VTEX_BASE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0433 | TMP | 0 |  |  | 26/08 - 26/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS) | OW_LAO.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,2573 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS),(INGESTION - JOB.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS)] |  | 26/08 - 26/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_TRADEIN) | OW_LAO.ODS_HYBRIS_TRADEIN | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0083 | ODS | 0 | [(INGESTION - JOB.ODS_HYBRIS_TRADEIN),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_TRADEIN)] |  | 26/08 - 26/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_PRICING) | OW_LAO.ODS_HYBRIS_PRICING | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | ODS | 0 | [(INGESTION - JOB.ODS_HYBRIS_PRICING)] |  | 26/08 - 26/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_CANCELLATIONS) | OW_LAO.RAW_HYBRIS_CANCELLATIONS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0005 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_CANCELLATIONS)] |  | 26/08 - 26/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_COMBO) | OW_LAO.RAW_HYBRIS_COMBO | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0002 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO)] |  | 26/08 - 26/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_OFFERS) | OW_LAO.RAW_HYBRIS_OFFERS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0004 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_OFFERS)] |  | 26/08 - 26/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_PAYMENTS) | OW_LAO.RAW_HYBRIS_PAYMENTS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0004 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PAYMENTS)] |  | 26/08 - 26/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_PREORDERS) | OW_LAO.RAW_HYBRIS_PREORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PREORDERS)] |  | 26/08 - 26/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_REFUNDS) | OW_LAO.RAW_HYBRIS_REFUNDS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0005 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REFUNDS)] |  | 26/08 - 26/08
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP) | U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0,0001 | ODS | 0 |  |  | 26/08 - 26/08
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP_SUB) | U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP_SUB | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-26 | 2025-08-26 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0,0001 | ODS | 0 |  |  | 26/08 - 26/08
VTEX |  | TABLE | (TABLE - OW_SEDA_S.TMP_VTEX_BR_SHOP_MASTER) | OW_SEDA_S.TMP_VTEX_BR_SHOP_MASTER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0018 | TMP | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_ACCOUNT_TOKEN) | U_PRJ_ECOM.ODS_VTEX_ACCOUNT_TOKEN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_MARCOM_SPV) | U_PRJ_ECOM.ODS_VTEX_FEED_MARCOM_SPV | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 16868 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0069 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 29009 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP_LEO) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP_LEO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP_SALES_ORDER_LIST) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP_SALES_ORDER_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,4138 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_TALEND) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | ODS | 0 |  |  | 27/08 - 27/08
NERP,VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO) | U_PRJ_ECOM.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0018 | ODS | 0 |  |  | 27/08 - 27/08
NERP,VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO_AGG) | U_PRJ_ECOM.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO_AGG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0045 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_PRODUCT_SKU) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_PRODUCT_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0016 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_COUPON) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_COUPON | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,2916 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP2_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP2_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0128 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0073 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_PRODUCT_SKU) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_PRODUCT_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0034 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_COUPON) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_COUPON | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,1145 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0763 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ID) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0268 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ITEMS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ITEMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,2596 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_TRANSACTION) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_TRANSACTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,045 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_PRODUCT_SKU) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_PRODUCT_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0199 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_COUPON) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_COUPON | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,5751 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM_HMLG_FIELDS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM_HMLG_FIELDS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_ID_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_ID_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_TRANSACTION_INTERACTIONS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_TRANSACTION_INTERACTIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_WAREHOUSE_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_WAREHOUSE_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_ID_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_ID_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_TRANSACTION_INTERACTIONS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_TRANSACTION_INTERACTIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_WAREHOUSE_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_WAREHOUSE_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_BRIDGE_COMPLIENCE_RATE) | U_PRJ_ECOM.RAW_VTEX_BRIDGE_COMPLIENCE_RATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0009 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_FEED_B2B_INFORMATION) | U_PRJ_ECOM.RAW_VTEX_FEED_B2B_INFORMATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_FEED_EPP2_INFORMATION) | U_PRJ_ECOM.RAW_VTEX_FEED_EPP2_INFORMATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_FEED_INFORMATION) | U_PRJ_ECOM.RAW_VTEX_FEED_INFORMATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,2456 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0067 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0073 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0052 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_PROMOTION) | U_PRJ_ECOM.RAW_VTEX_PROMOTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_EM) | U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_EM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SEDA_MASTER_DATA_CL) | U_PRJ_ECOM.RAW_VTEX_SEDA_MASTER_DATA_CL | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0672 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBREPP2_PROMOCARD) | U_PRJ_ECOM.RAW_VTEX_SSGBREPP2_PROMOCARD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0019 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBREPP2_PROMOCARD_ID) | U_PRJ_ECOM.RAW_VTEX_SSGBREPP2_PROMOCARD_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0018 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT) | U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,003 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_PROMOCARD) | U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_PROMOCARD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0196 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_PROMOCARD_ID) | U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_PROMOCARD_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0195 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_CT_COMPANY_DOMAIN) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_CT_COMPANY_DOMAIN | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM_COMPONENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0333 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PACKAGE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0286 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM_COMPONENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PACKAGE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_B2B_DETAIL_HIST_TALEND_PRL_2024) | U_PRJ_ECOM.RAW_VTEX_SSG_B2B_DETAIL_HIST_TALEND_PRL_2024 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0523 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_2023) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_2023 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 29745 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_DETAIL_TALEND) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_DETAIL_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0882 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST_AT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST_AT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0691 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0813 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP_PROMOTION_TAX) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP_PROMOTION_TAX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_INVENTORY) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_INVENTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_PROMOTION_TAX) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_PROMOTION_TAX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_CLIENT_PROFILE_DATA) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_CLIENT_PROFILE_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_LIST) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,2204 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_VAGNER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_VAGNER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_CDM_REPORT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_CDM_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0109 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_CPF) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_CPF | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0013 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0086 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_TALEND) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0758 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_INVENTORY) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_INVENTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0395 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER2) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0005 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0013 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0026 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_ITEM_ATTACHMENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_ITEM_ATTACHMENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_LIST) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0008 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0053 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_EPP2_DETAIL_HIST_TALEND_PRL_2022) | U_PRJ_ECOM.RAW_VTEX_SSG_EPP2_DETAIL_HIST_TALEND_PRL_2022 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,1153 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_TRADE_UP_SEASA_ORDER) | U_PRJ_ECOM.RAW_VTEX_TRADE_UP_SEASA_ORDER | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,021 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_TRADE_UP_SEDA_ORDER) | U_PRJ_ECOM.RAW_VTEX_TRADE_UP_SEDA_ORDER | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0823 | RAW | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 27/08 - 27/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_RETURNS) | OW_LAO.RAW_HYBRIS_RETURNS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_RETURNS)] |  | 27/08 - 27/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_REWARDS) | OW_LAO.RAW_HYBRIS_REWARDS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0006 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REWARDS)] |  | 27/08 - 27/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_SALES) | OW_LAO.RAW_HYBRIS_SALES | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0007 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES)] |  | 27/08 - 27/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_SALES_HOMOLOG) | OW_LAO.RAW_HYBRIS_SALES_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0004 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_ITEMS_DISCOUNTS)] |  | 27/08 - 27/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_SALES_MONITORING) | OW_LAO.RAW_HYBRIS_SALES_MONITORING | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0005 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES)] |  | 27/08 - 27/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_TRADEIN) | OW_LAO.RAW_HYBRIS_TRADEIN | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0004 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_TRADEIN)] |  | 27/08 - 27/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_ODS_HYBRIS_COMBO) | OW_LAO.TMP_ODS_HYBRIS_COMBO | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO)] |  | 27/08 - 27/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_HYBRIS_COMBO_VALID) | OW_LAO.ODS_HYBRIS_COMBO_VALID | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
HYBRIS | ControlTower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_COMBO_HYBRIS_HOMOLOG) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_COMBO_HYBRIS_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0544 | ODS | 0 |  |  | 27/08 - 27/08
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP_UPDATE) | U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP_UPDATE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO_UPDATE_TEMP) | U_PRJ_ECOM.ODS_SELA_API_MAGENTO_UPDATE_TEMP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-27 | 2025-08-27 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0,0001 | ODS | 0 |  |  | 27/08 - 27/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
NERP,VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_LINKAPI_VTEX_NERP_INTERFACE_ERRORS) | U_PRJ_ECOM.TMP_LINKAPI_VTEX_NERP_INTERFACE_ERRORS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_FEED_SSG_BR_SHOP_SALES_ORDER_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_FEED_SSG_BR_SHOP_SALES_ORDER_LIST | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA_TLD) | U_PRJ_ECOM.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA_TLD | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_ORDER_DATA_SBB) | U_PRJ_ECOM.TMP_ODS_VTEX_ORDER_DATA_SBB | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_PRODUCT_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_PRODUCT_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0011 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU_ID_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU_ID_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU_ID_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU_ID_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_INVENTORY_BY_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_INVENTORY_BY_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0005 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU_ID_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU_ID_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0005 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_SKU_ID_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_SKU_ID_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SKU_ID_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SKU_ID_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_BRSHOP_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_BRSHOP_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0007 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SEASA_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SEASA_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSGBREPP2_PROMOCARD) | U_PRJ_ECOM.TMP_RAW_VTEX_SSGBREPP2_PROMOCARD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSGBREPP2_PROMOCARD_ID) | U_PRJ_ECOM.TMP_RAW_VTEX_SSGBREPP2_PROMOCARD_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSGBRSHOP_PROMOCARD) | U_PRJ_ECOM.TMP_RAW_VTEX_SSGBRSHOP_PROMOCARD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0019 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSGBRSHOP_PROMOCARD_ID) | U_PRJ_ECOM.TMP_RAW_VTEX_SSGBRSHOP_PROMOCARD_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0022 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0207 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_01) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0784 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_02) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_02 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_2024) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_2024 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_AUX) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_AUX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_AUX_TEMP) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_AUX_TEMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_ERROR_2022) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_ERROR_2022 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_TALEND) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0009 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0005 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST__FALSE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST__FALSE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0006 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0005 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_LIST_FALSE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_LIST_FALSE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_LIST_TRUE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_LIST_TRUE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_01) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_TALEND) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0034 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0011 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0005 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0005 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS_2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_UNIQUEID_NULL) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_UNIQUEID_NULL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_UNIQUE_ID_NULL_CLEAN) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_UNIQUE_ID_NULL_CLEAN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST__) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST__ | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE_T) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE_T | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT_2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 28/08 - 28/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.RAW_HYBRIS_PRICING) | OW_LAO.RAW_HYBRIS_PRICING | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | RAW | 0 |  |  | 28/08 - 28/08
HYBRIS | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  |  | 28/08 - 28/08
HYBRIS | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0004 | TMP | 0 |  |  | 28/08 - 28/08
HYBRIS | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  |  | 28/08 - 28/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_OFFERS_DEDUP) | OW_LAO.TMP_HYBRIS_OFFERS_DEDUP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0004 | TMP | 0 |  |  | 28/08 - 28/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_PAYMENTS_DEDUP) | OW_LAO.TMP_HYBRIS_PAYMENTS_DEDUP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  |  | 28/08 - 28/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_PREORDERS_DEDUP) | OW_LAO.TMP_HYBRIS_PREORDERS_DEDUP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  |  | 28/08 - 28/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_REFUNDS_DEDUP) | OW_LAO.TMP_HYBRIS_REFUNDS_DEDUP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_REWARDS_DEDUP) | OW_LAO.TMP_HYBRIS_REWARDS_DEDUP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  |  | 28/08 - 28/08
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_GTM) | U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_GTM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0,0012 | TMP | 0 |  |  | 28/08 - 28/08
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_SUB) | U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_SUB | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-28 | 2025-08-28 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0,0002 | TMP | 0 |  |  | 28/08 - 28/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING_2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SKU_ID_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SKU_ID_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_WAREHOUSE_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_WAREHOUSE_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SKU_ID_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SKU_ID_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_WAREHOUSE_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_WAREHOUSE_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_EPP_DETAIL_HIST_TALEND) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_EPP_DETAIL_HIST_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0227 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_MARCOM_SPV) | U_PRJ_ECOM.TMP_VTEX_FEED_MARCOM_SPV | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_B2B_TALEND) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_B2B_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0005 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_1) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_10) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_10 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_11) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_11 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_12) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_12 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_13) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_13 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_14) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_14 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_15) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_15 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_16) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_16 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_17) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_17 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_18) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_18 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_2) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_20) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_20 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0007 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_21) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_21 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_22) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_22 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_23) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_23 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_3) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_4) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_4 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_5) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_5 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_6) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_6 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_7) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_7 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_8) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_8 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV1) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV2) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV3) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV4) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV4 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV5) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV5 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV6) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV6 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV7) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV7 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD) | U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_ID) | U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_ID_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_ID_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD) | U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_1) | U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_2) | U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0017 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_ID_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_ID_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0019 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_2) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0152 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_2) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0039 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_3) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0026 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_AR_CT_ORDER_DOMAIN) | U_PRJ_ECOM.TMP_VTEX_SSG_AR_CT_ORDER_DOMAIN | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_B2B_PROMOTION_ITEM) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_B2B_PROMOTION_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP2_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP2_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ID) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ITEMS) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ITEMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_PROMOTION_ITEM) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_PROMOTION_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_PAYMENT_TRANSACTION) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_PAYMENT_TRANSACTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0003 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_PRICE_LIST) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_PRICE_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_PROMOTION_ITEM) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_PROMOTION_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0002 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_FEED_QTD_JSON) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_FEED_QTD_JSON | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_FIXED_PRICES) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_FIXED_PRICES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0035 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_INTERACTIONS) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_INTERACTIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,1125 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PRICE_LIST) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PRICE_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_ITEM) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0004 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_T1) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_T1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_T2) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_T2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0008 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0841 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_TRANSACTION_INTERACTIONS) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_TRANSACTION_INTERACTIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SKU_BY_REF_ID) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SKU_BY_REF_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0181 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_TRANSACTION_INTERACTIONS) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_TRANSACTION_INTERACTIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0001 | TMP | 0 |  |  | 29/08 - 29/08
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_VIRTUAL_INV) | U_PRJ_ECOM.TMP_VTEX_VIRTUAL_INV | [5 empty] | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0,0021 | TMP | 0 |  |  | 29/08 - 29/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_SALES_AGG_DEDUP) | OW_LAO.TMP_HYBRIS_SALES_AGG_DEDUP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0003 | TMP | 0 |  |  | 29/08 - 29/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_SALES_DEDUP) | OW_LAO.TMP_HYBRIS_SALES_DEDUP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0004 | TMP | 0 |  |  | 29/08 - 29/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_SALES_DELETE_IDS) | OW_LAO.TMP_HYBRIS_SALES_DELETE_IDS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  |  | 29/08 - 29/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_SALES_VOUCHER_CODE_AGG) | OW_LAO.TMP_HYBRIS_SALES_VOUCHER_CODE_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0,0006 | TMP | 0 |  |  | 29/08 - 29/08
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_VL_ODS_HYBRIS_SALES_ALERT) | OW_LAO.TMP_VL_ODS_HYBRIS_SALES_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  |  | 29/08 - 29/08
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_UPDATE) | U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_UPDATE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-08-29 | 2025-08-29 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0,0002 | TMP | 0 |  |  | 29/08 - 29/08
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 13264 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.PROC_D2C_DIM_SOLD_TO),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(VIEW - OW_LAO.VW_PMS_TESTE),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_TESTE_),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING),(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE),(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(VIEW - OW_LAO.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 16432 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_OUTBOUND_UPDATE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME),(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(PROCEDURE - OW_LAO.PROC_D2C_DIM_SOLD_TO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_OUTBOUND_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST) | OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 184249 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_FORECAST_OST),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER) | OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,0054 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING),(INGESTION - JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_FOLDER),(INGESTION - JOB.ODS_NERP_ZLLEB57910_CLAIM_FOLDER),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,1826 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN),(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(INGESTION - JOB.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS),(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 14001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(INGESTION - JOB.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN),(INGESTION - JOB.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER) | OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,0105 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZRCOS43400_TARGET_FOLDER),(VIEW - OW_LAO.VIEW_NERP_ZRCOS43400_TARGET),(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW) | OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,4139 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_INVENTORY),(INGESTION - JOB.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS),(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_MB51_GR_FOLDER) | OW_LAO.ODS_NERP_MB51_GR_FOLDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,6733 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI),(INGESTION - JOB.RAW_DATA_NERP_MB51_GR_FOLDER),(INGESTION - JOB.ODS_NERP_MB51_GR_FOLDER)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 60427 | RAW | 0 | [(INGESTION - JOB.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING),(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES) | OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,2042 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE) | OW_SEDA_S.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,0072 | RAW | 0 | [(INGESTION - JOB.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE),(INGESTION - JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_MAINTENANCE)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,2907 | RAW | 0 | [(INGESTION - JOB.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN),(INGESTION - JOB.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT) | OW_LAO.ODS_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,1437 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,3371 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_MB51_GR_FOLDER) | OW_LAO.RAW_DATA_NERP_MB51_GR_FOLDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,6733 | RAW | 0 |  |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLLEB57910_CLAIM_FOLDER) | OW_LAO.RAW_DATA_NERP_ZLLEB57910_CLAIM_FOLDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,0054 | RAW | 0 |  |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | OW_LAO.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,0049 | RAW | 0 |  |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM) | U_PRJ_ECOM.FT_ECOM_ORDER_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,5176 | FT | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(INGESTION - JOB.FT_ECOM_ORDER_ITEM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_REFERENCE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_SALES) | OW_LAO.TF_D2C_NERP_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 29117 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_COUPON_KPI),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_MD.PROC_INGESTION_DIM_PRODUCT_GLOBAL),(VIEW - OW_LAO.VW_PMS_TESTE),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(PROCEDURE - OW_LAO.PROC_INSERT_SALES_CANCELLED_FROM_ODS),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI),(PROCEDURE - OW_MD.PROC_INGESTION_DIM_PRODUCT_ESTORE),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PO_TARGET_LAUNCH_S25),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_REWARDS_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_SELLOUT_PLATFORM_KPI),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_TESTE),(PROCEDURE - OW_LAO.PROC_TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_LAO.PROC_INSERT_SALES_FROM_ODS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_FT_D2C_VTEX_O2O_SALES_KPI),(VIEW - OW_LAO.VW_TAB1_PMS_DW),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_O2O_SALES_KPI),(VIEW - OW_SEDA_S.VW_SEDA_PREORDER),(PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_MD.PROC_DIM_PRODUCT_ESTORE_GLOBAL)] |  |  | 01/09 - 01/09
VTEX |  | TABLE | (TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN) | OW_LAO.TF_D2C_PO_VTEX_TRADE_IN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0206 | TF | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_TST),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_SELLOUT_PLATFORM_KPI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST_ADJ),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MAT),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_PROD),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX)] |  |  | 01/09 - 01/09
VTEX |  | TABLE | (TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION) | OW_LAO.FT_D2C_VTEX_PROMOTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 33047 | FT | 0 | [(VIEW - OW_LAO.VW_PMS_TESTE),(PROCEDURE - OW_LAO.PROC_TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES),(VIEW - OW_LAO.VW_TAB2_PMS_DW),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_MD.DIM_SALES_CHANNEL) | OW_MD.DIM_SALES_CHANNEL | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_NERP_GROSS_MARGIN) | OW_LAO.TF_NERP_GROSS_MARGIN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,2184 | TF | 0 | [(VIEW - OW_LAO.VW_TAB3_PMS_DW),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_DIM_TAX_GROSS_MARGIN),(PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA),(PROCEDURE - OW_LAO.PROC_TF_NERP_GROSS_MARGIN_MONITORING_DATASOURCE),(VIEW - OW_LAO.VW_PMS_TESTE),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO) | OW_LAO.DIM_PRODUCT_MAPPING_LAO | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,016 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIM_PRODUCT_MAPPING_LAO_UPDATE),(PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO),(PROCEDURE - OW_MD.PROC_DIM_PRODUCT_ESTORE_GLOBAL),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU) | OW_LAO.TF_D2C_PAYMENT_ITAU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0384 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_TESTE),(PROCEDURE - OW_LAO.PROC_INSERT_SALES_CANCELLED_FROM_ODS),(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(PROCEDURE - OW_LAO.PROC_INSERT_SALES_FROM_ODS)] |  |  | 01/09 - 01/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_ORDER_STATUS) | OW_MD.DIM_VTEX_ORDER_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,001 | DIM | 0 | [(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_MD.PROC_DIM_VTEX_ORDER_STATUS),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING)] |  |  | 01/09 - 01/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS) | OW_MD.DIM_VTEX_PAYMENT_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0009 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] |  |  | 01/09 - 01/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER) | OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0007 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] |  |  | 01/09 - 01/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN) | OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0008 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] |  |  | 01/09 - 01/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION) | OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0954 | DIM | 0 | [(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING)] |  |  | 01/09 - 01/09
VTEX |  | TABLE | (TABLE - OW_LAO.TF_D2C_VTEX_PAYMENT_SKU) | OW_LAO.TF_D2C_VTEX_PAYMENT_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,606 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.FT_D2C_AR_TABLE_MONTH) | OW_LAO.FT_D2C_AR_TABLE_MONTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,5402 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT2),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.FT_D2C_AR_TABLE_WEEK) | OW_LAO.FT_D2C_AR_TABLE_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,5743 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT2)] |  |  | 01/09 - 01/09
VTEX |  | TABLE | (TABLE - OW_LAO.TF_D2C_PO_VTEX_RDD) | OW_LAO.TF_D2C_PO_VTEX_RDD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,1459 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.FT_D2C_AR_ONE_VIEW_TABLE) | OW_LAO.FT_D2C_AR_ONE_VIEW_TABLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0227 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] |  |  | 01/09 - 01/09
GSCM |  | TABLE | (TABLE - OW_LAO.FT_D2C_GSCM_INVENTORY) | OW_LAO.FT_D2C_GSCM_INVENTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,1656 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_GSCM_INVENTORY)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_DELIVERY_PENDING) | OW_LAO.FT_D2C_NERP_DELIVERY_PENDING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0013 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING)] |  |  | 01/09 - 01/09
GSCM,NERP |  | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_GSCM_PSI) | OW_LAO.FT_D2C_NERP_GSCM_PSI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,2972 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_INVENTORY) | OW_LAO.FT_D2C_NERP_INVENTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,314 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_INVENTORY)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_LEAD_TIME) | OW_LAO.FT_D2C_NERP_LEAD_TIME | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0641 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_ORDER_PENDING) | OW_LAO.FT_D2C_NERP_ORDER_PENDING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0037 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_ORDER_PENDING_OVERVIEW) | OW_LAO.FT_D2C_NERP_ORDER_PENDING_OVERVIEW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,2444 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_TO_STOCK_OVERVIEW_BY_PLANT) | OW_LAO.FT_D2C_NERP_TO_STOCK_OVERVIEW_BY_PLANT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0063 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_WH_OPERATION_PENDING) | OW_LAO.FT_D2C_NERP_WH_OPERATION_PENDING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,001 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.FT_D2C_WOS) | OW_LAO.FT_D2C_WOS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0091 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_01) | OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0218 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_02) | OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_02 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,022 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] |  |  | 01/09 - 01/09
GSCM |  | TABLE | (TABLE - OW_LAO.TF_D2C_GSCM_TO_WOS) | OW_LAO.TF_D2C_GSCM_TO_WOS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0035 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS)] |  |  | 01/09 - 01/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_SALES) | OW_LAO.ODS_GLOBAL_BI_SALES | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 16817 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS),(VIEW - OW_LAO.VIEW_ODS_GLOBAL_BI_SALES),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW),(INGESTION - JOB.ODS_GLOBAL_BI_SALES),(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(VIEW - OW_LAO.VIEW_ECOM_ODS_GLOBAL_BI_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_GLOBALBI_UPDATE),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2),(PROCEDURE - OW_LAO.PROC_ODS_GLOBAL_BI_SALES_EMPTY_DIMENSIONS_ALERT),(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_GLOBALBI_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS)] |  |  | 01/09 - 01/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL) | OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0042 | ODS | 0 | [(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_ALL),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2),(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_ALL)] |  |  | 01/09 - 01/09
Diggit |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS) | U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0019 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT)] |  |  | 01/09 - 01/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT) | OW_LAO.ODS_GLOBAL_BI_STOCKOUT | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,8038 | ODS | 0 | [(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(INGESTION - JOB.ODS_GLOBAL_BI_STOCKOUT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PBI),(PROCEDURE - OW_LAO.PROC_D2C_FT_STOCKOUT)] |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2) | OW_LAO.ODS_AFTER_SALES_REFUND_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0004 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREPP2)] |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST) | OW_LAO.ODS_AFTER_SALES_REFUND_EST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0004 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2ESTUDANTES),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP)] |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_RESID) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_RESID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0024 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TMP_D2C_AR_TABLE_MONTH) | OW_LAO.TMP_D2C_AR_TABLE_MONTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,4415 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT2),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TMP_D2C_AR_TABLE_WEEK) | OW_LAO.TMP_D2C_AR_TABLE_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,5614 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT2)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_MD.ODS_MP_ESTORE) | OW_MD.ODS_MP_ESTORE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0007 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI),(PROCEDURE - OW_MD.PROC_INGESTION_ODS_MP_ESTORE)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_MONTH) | OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_MONTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_WEEK) | OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH) | OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_WEEK) | OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)] |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_CONSOLIDATED) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_CONSOLIDATED | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0129 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] |  |  | 01/09 - 01/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE_DISCOUNT) | OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE_DISCOUNT | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0075 | TMP | 0 |  |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TMP_ODS_SALES_LISTINGS) | OW_LAO.TMP_ODS_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_BRSHOP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_BRSHOP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0005 | RAW | 0 |  |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_B2B) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_B2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0389 | RAW | 0 |  |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_BREA) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_BREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | RAW | 0 |  |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_BRSHOP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_BRSHOP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,4324 | RAW | 0 |  |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_B2B) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_B2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0012 | RAW | 0 |  |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BREA) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | RAW | 0 |  |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_EPP2) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0011 | RAW | 0 |  |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_MKP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_MKP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,001 | RAW | 0 |  |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_PARC) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_PARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 1 | 3.1 Migrar ph1 | 0,0002 | RAW | 0 |  |  |  | 01/09 - 01/09
| ControlTower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 3679 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_NAME_AJUSTE),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_ODS_SELA_CUSTOM_ORDERS_ITEMS_UPDATE),(PROCEDURE - OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_OUTBOUND_UPDATE),(PROCEDURE - OW_LAO.PROC_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_ECOM_HQ_ORDERS_TRADEIN_FEED),(VIEW - OW_LAO.VW_APPSFLYER_IN_APP_EVENTS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS_NERP),(PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_MONITORING_DATASOURCE),(PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_STATUS_CANCELED),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_EMPTY_DIMENSIONS_ALERT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MAT),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW),(PROCEDURE - U_PRJ_ECOM.PROC_ECOM_HQ_ORDERS_PRODUCTS_COMBO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI),(PROCEDURE - OW_LAO.PROC_DIVISION_NERP_CONTROL_TOWER_STATUS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_TAXES_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ),(PROCEDURE - OW_LAO.PROC_BLACK_FRIDAY_PBI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_Migrar ph 2_DATASOURCE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_Migrar ph 2_DATASOURCE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_TF_PO_COUPON_ID_CONTROL_TOWER_LIST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PBI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_PROD),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_DEPARA),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_TST),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIM_PRODUCT_MAPPING_LAO_UPDATE),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_GLOBALBI_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ_BKP10032025),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_ITEMS_EXCLUSIVES_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE),(PROCEDURE - OW_LAO.PROC_Migrar ph 2_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PREMIUM_MODELS_UPDATE),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.ODS_PAYMENT_FUNNEL) | OW_LAO.ODS_PAYMENT_FUNNEL | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,3013 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP),(INGESTION - JOB.ODS_PAYMENT_FUNNEL),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP),(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_CAMPAIGN) | OW_LAO.ODS_SALES_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,2956 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V2),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V3),(INGESTION - JOB.TMP_CAMPAIGN_NAME),(INGESTION - JOB.ODS_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_NAME_AJUSTE),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_DAILY_Migrar ph 2),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA) | U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0476 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA) | U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,2827 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA) | U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0482 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA) | U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,2811 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023)] |  |  | 01/09 - 01/09
Visuar |  | TABLE | (TABLE - OW_LAO.ODS_ORDERS_VISUAR) | OW_LAO.ODS_ORDERS_VISUAR | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0135 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR),(INGESTION - JOB.ODS_ORDERS_VISUAR),(INGESTION - JOB.RAW_ORDERS_VISUAR),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_ODS_ORDERS_VISUAR)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS) | OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS),(INGESTION - JOB.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS),(INGESTION - JOB.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS),(INGESTION - JOB.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS),(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_ITEMS_EXCLUSIVES_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  |  | 01/09 - 01/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES) | OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0284 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL)] |  |  | 01/09 - 01/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS) | OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,098 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS) | OW_LAO.RAW_APPLYER_IN_APP_EVENTS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 6625 | RAW | 0 | [(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEDA),(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEM),(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEPR),(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SECH),(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SAMCOL),(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEASA)] |  |  | 01/09 - 01/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES) | OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0272 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA)] |  |  | 01/09 - 01/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS) | OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,4029 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TMP_SALES_CAMPAIGN) | OW_LAO.TMP_SALES_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,2806 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN),(INGESTION - JOB.TMP_CAMPAIGN_NAME),(INGESTION - JOB.TMP_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_NAME_AJUSTE),(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS) | OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0516 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PREMIUM_MODELS_UPDATE),(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS),(PROCEDURE - OW_LAO.PROC_ODS_LAO_PREMIUM_PRODUCTS_TABLE_FROM_GSCM_UPDATE)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS) | OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0191 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS_VALIDATION),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_ODS_SELA_CUSTOM_ORDERS_ITEMS_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS)] |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,021 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2RESIDENCIAL),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2PARCERIAS)] |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC) | OW_LAO.ODS_AFTER_SALES_REFUND_PARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0003 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2PARCERIAS),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2RESIDENCIAL)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE) | OW_LAO.ODS_ERP_EXCHANGE_RATE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0154 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE),(PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE_BKP),(PROCEDURE - OW_LAO.PROC_ODS_EXCHANGE_RATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_FT_AP2_EXCHANGE_RATE_HOMOLOG)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN) | OW_LAO.ODS_TARGETS_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0016 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.ODS_TARGETS_CAMPAIGN),(INGESTION - JOB.TMP_TARGETS_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_DIM_TARGETS_CAMPAIGN_CADASTRA_UPDATE)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR) | OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN),(INGESTION - JOB.TMP_CAMPAIGN_NAME),(INGESTION - JOB.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN)] |  |  | 01/09 - 01/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0158 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_GLOBALBI_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_OUTBOUND_UPDATE_HOMOLOG)] |  |  | 01/09 - 01/09
|  | TABLE | (TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME) | OW_LAO.TMP_UPDATE_CAMPAIGN_NAME | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME),(INGESTION - JOB.TMP_UPDATE_CAMPAIGN_NAME),(INGESTION - JOB.TMP_CAMPAIGN_NAME),(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN)] |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND) | OW_LAO.ODS_AFTER_SALES_REFUND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0028 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND)] |  |  | 01/09 - 01/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B) | OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-01 | 2025-09-01 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0003 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRB2B),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP)] |  |  | 01/09 - 01/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI) | OW_LAO.TMP_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,0008 | TMP | 0 |  |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_NERP_ZRCOS43400_TARGET_FOLDER) | OW_LAO.TMP_NERP_ZRCOS43400_TARGET_FOLDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,0005 | TMP | 0 |  |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_NERP_ZLLEB57910_CLAIM_MAINTENANCE) | OW_SEDA_S.RAW_DATA_NERP_ZLLEB57910_CLAIM_MAINTENANCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,0072 | RAW | 0 |  |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | OW_SEDA_S.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,2907 | RAW | 0 |  |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN) | OW_SEDA_S.TMP_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 1.4 Ingestion NERP | 0,0005 | TMP | 0 |  |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 76947 | RAW | 0 | [(VIEW - OW_LAO.VW_SDU_RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING),(INGESTION - JOB.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN) | OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0094 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_TF_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI_UNPIVOT),(PROCEDURE - OW_LAO.PROC_TF_NERP_ZRCOS43400_SALES_PROGRESS_KPI_UNPIVOT_AGG_DIVISION_GROUP),(INGESTION - JOB.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER) | OW_SEDA_S.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,4483 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER),(INGESTION - JOB.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER),(VIEW - OW_MD.VW_PRICE_MONITORING_AUDIT_PROCESS)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZLMKF03006_CONDITION_CALC) | OW_LAO.ODS_NERP_ZLMKF03006_CONDITION_CALC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0036 | RAW | 0 | [(INGESTION - JOB.RAW_DATA_NERP_ZLMKF03006_CONDITION_CALC),(INGESTION - JOB.ODS_NERP_ZLMKF03006_CONDITION_CALC)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS) | OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 12433 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_AR_CLEARED),(INGESTION - JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,2099 | ODS | 0 | [(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO) | OW_LAO.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0224 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM) | OW_LAO.ODS_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,003 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_LAO.RAW_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 19029 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER) | OW_LAO.RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,3892 | RAW | 0 | [(VIEW - OW_LAO.VW_SDU_RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER)] |  |  | 02/09 - 02/09
NERP | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0007 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.TMP_NERP_ZLLEJ50090_OUTBOUND_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0031 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS) | OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0113 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TF_D2C_MELI_COLETAS) | OW_LAO.TF_D2C_MELI_COLETAS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0013 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_DAILY_SALES_KPI) | OW_LAO.TF_D2C_NERP_DAILY_SALES_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0553 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME) | OW_LAO.TF_D2C_NERP_LEAD_TIME | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,3019 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_01) | OW_LAO.TF_D2C_NERP_LEAD_TIME_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,2866 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_02) | OW_LAO.TF_D2C_NERP_LEAD_TIME_02 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,3125 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_03) | OW_LAO.TF_D2C_NERP_LEAD_TIME_03 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,334 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_01) | OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,1579 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_02) | OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_02 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,2431 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_SALES_BY_CHANNEL_KPI) | OW_LAO.TF_D2C_NERP_SALES_BY_CHANNEL_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0081 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_SALES_BY_HOUR_KPI) | OW_LAO.TF_D2C_NERP_SALES_BY_HOUR_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,2828 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_TO_STOCK_OVERVIEW) | OW_LAO.TF_D2C_NERP_TO_STOCK_OVERVIEW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0068 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_TO_WOS) | OW_LAO.TF_D2C_NERP_TO_WOS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0077 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_WEEKLY_SALES_KPI) | OW_LAO.TF_D2C_NERP_WEEKLY_SALES_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,1895 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TF_WAREHOUSE_OPERATION) | OW_LAO.TF_WAREHOUSE_OPERATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,2893 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION)] |  |  | 02/09 - 02/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOCK) | OW_MD.DIM_VTEX_PURCHASE_ORDER_DOCK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_LAO.FT_NERP_SALES_PROGRESS_KPI) | OW_LAO.FT_NERP_SALES_PROGRESS_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0006 | FT | 0 |  |  |  | 02/09 - 02/09
VTEX |  | TABLE | (TABLE - OW_LAO.FT_VTEX_BR_SHOP_TMP) | OW_LAO.FT_VTEX_BR_SHOP_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0751 | FT | 0 |  |  |  | 02/09 - 02/09
VTEX |  | TABLE | (TABLE - OW_LAO.FT_VTEX_EPP_TMP) | OW_LAO.FT_VTEX_EPP_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0084 | FT | 0 |  |  |  | 02/09 - 02/09
VTEX |  | TABLE | (TABLE - OW_SEDA_S.FT_VTEX_BR_SHOP_MASTER) | OW_SEDA_S.FT_VTEX_BR_SHOP_MASTER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,5447 | FT | 0 |  |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - U_PRJ_ECOM.MAP_CANCELLATION_MESSAGE) | U_PRJ_ECOM.MAP_CANCELLATION_MESSAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 1 | 2.1 Migrar ph1 | 0,0001 | MAP | 0 |  |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - U_PRJ_ECOM.FT_ECOM_ORDER) | U_PRJ_ECOM.FT_ECOM_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 13795 | FT | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP05052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_RETROATIVO_TST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(INGESTION - JOB.FT_ECOM_ORDER),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_BI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_PLATFORM_SEDA),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_REFERENCE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADEIN_PAYMENT),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_SL),(VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_bkp26052022),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_SYNAPCON),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_EPP_STATUS_NEW_RULE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP15062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY) | U_PRJ_ECOM.DIM_SUBSIDIARY | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0002 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - OW_LAO.VIEW_ECOM_EXCHANGE_RATE),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(PROCEDURE - U_PRJ_ECOM.PROC_DIM_EXCHANGE_RATE_RAWDATA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG),(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(PROCEDURE - OW_LAO.PROC_Migrar ph 2_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE) | U_PRJ_ECOM.DIM_EXCHANGE_RATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,003 | DIM | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP05052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_EPP_STATUS_NEW_RULE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_PLATFORM_SEDA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP15062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_RETROATIVO_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_bkp26052022),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_SL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT) | U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,8166 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(INGESTION - JOB.FT_ECOM_ORDER_PAYMENT),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_SYNAPCON),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADEIN_PAYMENT)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - U_PRJ_ECOM.DIM_CUSTOMER) | U_PRJ_ECOM.DIM_CUSTOMER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,6124 | DIM | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707)] |  |  | 02/09 - 02/09
| ControlTower | TABLE | (TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING) | OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(INGESTION - JOB.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT) | U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0486 | FT | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(INGESTION - JOB.FT_ECOM_ORDER_KIT_COMPONENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_REFERENCE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING) | OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP_HOMOLOG)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME) | OW_LAO.DIM_LAO_CRP_CS_STORENAME | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_STORENAME_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING)] |  |  | 02/09 - 02/09
| ControlTower | TABLE | (TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER) | OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_DELIVERY_MODE_DIM_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING) | OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA) | OW_LAO.ODS_AFTER_SALES_REFUND_BREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREA)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL) | OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,005 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOPMKTPL),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,1295 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOP)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0677 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRB2B)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREA),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,4111 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOPMKTPL),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0162 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREPP2)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0238 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2ESTUDANTES)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0103 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2MEMBERS)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS) | OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0003 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2MEMBERS)] |  |  | 02/09 - 02/09
AppsFlyer |  | TABLE | (TABLE - OW_LAO.ODS_APPSFLYER_IN_APP_EVENTS) | OW_LAO.ODS_APPSFLYER_IN_APP_EVENTS | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 6625 | RAW | 0 | [(VIEW - OW_LAO.VW_APPSFLYER_IN_APP_EVENTS),(INGESTION - JOB.RAW_APPLYER_IN_APP_EVENTS),(INGESTION - JOB.ODS_APPSFLYER_IN_APP_EVENTS)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS) | OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0012 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.ODS_TARGETS_CAMPAIGN),(INGESTION - JOB.ODS_CAMPAIGN_TARGET_PRODUCTS)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS) | OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.RAW_FEED_SEND_ESTORE) | OW_LAO.RAW_FEED_SEND_ESTORE | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 16842 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ_BKP10032025),(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ),(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_SAMPLE_HQ)] |  |  | 02/09 - 02/09
Grafana |  | TABLE | (TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS) | OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0238 | RAW | 0 | [(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS)] |  |  | 02/09 - 02/09
Grafana |  | TABLE | (TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS) | OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,4467 | RAW | 0 | [(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_CUT) | OW_LAO.TMP_CAMPAIGN_CUT | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V3),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V2),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_NAME) | OW_LAO.TMP_CAMPAIGN_NAME | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME),(INGESTION - JOB.TMP_CAMPAIGN_NAME)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS) | OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,002 | TMP | 0 | [(INGESTION - JOB.ODS_CAMPAIGN_TARGET_CHANNELS),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR) | OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0014 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.ODS_TARGETS_CAMPAIGN),(INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR) | OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0012 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.ODS_TARGETS_CAMPAIGN),(INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR)] |  |  | 02/09 - 02/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_RESID) | OW_LAO.ODS_AFTER_SALES_REFUND_RESID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_CHANNELS) | OW_LAO.ODS_CAMPAIGN_TARGET_CHANNELS | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,002 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.ODS_CAMPAIGN_TARGET_CHANNELS)] |  |  | 02/09 - 02/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_DA) | OW_LAO.ODS_GLOBAL_BI_TRAFFIC_DA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0034 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_DA),(INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_DA)] |  |  | 02/09 - 02/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_MX) | OW_LAO.ODS_GLOBAL_BI_TRAFFIC_MX | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,004 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_MX),(INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_MX)] |  |  | 02/09 - 02/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_VD) | OW_LAO.ODS_GLOBAL_BI_TRAFFIC_VD | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0037 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_VD),(INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_VD)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT) | OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0009 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(INGESTION - JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT)] |  |  | 02/09 - 02/09
| ControlTower | TABLE | (TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM) | OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0007 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(INGESTION - JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM)] |  |  | 02/09 - 02/09
| ControlTower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0618 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG)] |  |  | 02/09 - 02/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0022 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ALERT) | OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(INGESTION - JOB.TMP_MONITORING_BI_LAO_PROCCESS_ALERT),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT)] |  |  | 02/09 - 02/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE) | OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0906 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_PAYMENT_PAYMENT_TYPE) | OW_LAO.TMP_PAYMENT_PAYMENT_TYPE | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP_HOMOLOG)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_PAYMENT_PAY_GATEWAY) | OW_LAO.TMP_PAYMENT_PAY_GATEWAY | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_TARGETS_CAMPAIGN) | OW_LAO.TMP_TARGETS_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0016 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.TMP_TARGETS_CAMPAIGN)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_UPDATE_ID_CAMPAIGN) | OW_LAO.TMP_UPDATE_ID_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 | [(INGESTION - JOB.TMP_CAMPAIGN_NAME),(INGESTION - JOB.TMP_UPDATE_ID_CAMPAIGN)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_PRODUCTS_COMBO | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0082 | RAW | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - U_PRJ_ECOM.PROC_ECOM_HQ_ORDERS_PRODUCTS_COMBO)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS) | OW_LAO.ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,003 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO) | OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0005 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS) | OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY) | OW_LAO.ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0003 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.ODS_SELA_SALES_COUPONS) | OW_LAO.ODS_SELA_SALES_COUPONS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0009 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_SALES_COUPONS)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.ODS_SELA_SALES_COUPONS_ITEMS) | OW_LAO.ODS_SELA_SALES_COUPONS_ITEMS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0004 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_SALES_COUPONS_ITEMS)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.RAW_FILES_MINIO) | OW_LAO.RAW_FILES_MINIO | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,027 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.RAW_LAO_CRP_CS_STORENAME) | OW_LAO.RAW_LAO_CRP_CS_STORENAME | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_STORENAME_UPDATE)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.RAW_LAO_CRP_CS_VOUCHER_COUPON) | OW_LAO.RAW_LAO_CRP_CS_VOUCHER_COUPON | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_VOUCHER_COUPON_UPDATE)] |  |  | 02/09 - 02/09
| ControlTower | TABLE | (TABLE - OW_LAO.RAW_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER) | OW_LAO.RAW_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_DELIVERY_MODE_DIM_UPDATE)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.RAW_LAO_DIM_PRODUCT_MAPPING_APOIO) | OW_LAO.RAW_LAO_DIM_PRODUCT_MAPPING_APOIO | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0004 | INPUT | 0 | [(PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS) | OW_LAO.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.RAW_LAO_PRODUCT_PREMIUM_ITEMS) | OW_LAO.RAW_LAO_PRODUCT_PREMIUM_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS)] |  |  | 02/09 - 02/09
Visuar |  | TABLE | (TABLE - OW_LAO.RAW_ORDERS_VISUAR) | OW_LAO.RAW_ORDERS_VISUAR | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0135 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_ORDERS_VISUAR)] |  |  | 02/09 - 02/09
|  | TABLE | (TABLE - OW_LAO.TMP_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS) | OW_LAO.TMP_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-02 | 2025-09-02 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)] |  |  | 02/09 - 02/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_SEDA_S.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0053 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)] |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRCOA20250_PA_ALLOC_RES) | OW_SEDA_S.ODS_NERP_ZRCOA20250_PA_ALLOC_RES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0064 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZRCOA20250_PA_ALLOC_RES)] |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO) | OW_SEDA_S.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0343 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO)] |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW) | OW_SEDA_S.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0333 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)] |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS) | OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0016 | ODS | 0 | [(INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS)] |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER) | OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0003 | ODS | 0 | [(INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER)] |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER) | OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0003 | ODS | 0 | [(INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER)] |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER) | OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0005 | ODS | 0 | [(INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER)] |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM) | OW_SEDA_S.TMP_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0014 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM)] |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_SELLIN_2022) | OW_LAO.ODS_NERP_SELLIN_2022 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0033 | ODS | 0 |  |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_SELLIN_2022_TMP) | OW_LAO.ODS_NERP_SELLIN_2022_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0038 | ODS | 0 |  |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZLLEB57970_CLAIM_ANALISYS) | OW_LAO.ODS_NERP_ZLLEB57970_CLAIM_ANALISYS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0008 | ODS | 0 |  |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA) | OW_LAO.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,01 | ODS | 0 |  |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_LAO.ODS_SEDA_CURRENT_PRICE_NERP) | OW_LAO.ODS_SEDA_CURRENT_PRICE_NERP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,001 | ODS | 0 |  |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLMKF03006_CONDITION_CALC) | OW_LAO.RAW_DATA_NERP_ZLMKF03006_CONDITION_CALC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0036 | RAW | 0 |  |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT) | OW_LAO.RAW_DATA_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0 | RAW | 0 |  |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM) | OW_LAO.RAW_DATA_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,2327 | RAW | 0 |  |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_TMP) | OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0396 | RAW | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING) | OW_LAO.DIM_PAYMENT_TYPE_MAPPING | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING) | OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,7779 | FT | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_AFFILIATE) | OW_MD.DIM_VTEX_AFFILIATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0012 | DIM | 0 | [(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP) | OW_MD.DIM_VTEX_PAYMENT_GROUP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0002 | DIM | 0 | [(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP),(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN) | OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0005 | DIM | 0 | [(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON) | OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_VOUCHER_COUPON_UPDATE),(PROCEDURE - OW_LAO.PROC_TF_PO_COUPON_ID_CONTROL_TOWER_LIST),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE) | OW_LAO.DIM_PAYMENT_GATEWAY_CODE | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI),(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE) | OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0008 | DIM | 0 | [(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT) | OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,2606 | FT | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM) | OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,3961 | FT | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.DIM_ECOM_PARTNER_LEVEL) | OW_LAO.DIM_ECOM_PARTNER_LEVEL | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0018 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.DIM_EXCEL_TARGETS_CAMPAIGN) | OW_LAO.DIM_EXCEL_TARGETS_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.DIM_EXCEL_TARGETS_CAMPAIGN)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.DIM_MONITORING_BI_LAO_PROCCESS_ALERT) | OW_LAO.DIM_MONITORING_BI_LAO_PROCCESS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0003 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(INGESTION - JOB.DIM_MONITORING_BI_LAO_PROCCESS_ALERT)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_PAYMENT_TYPE) | OW_LAO.DIM_PAYMENT_PAYMENT_TYPE | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY) | OW_LAO.DIM_PAYMENT_PAY_GATEWAY | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.FT_D2C_ONE_VIEW_TABLE) | OW_LAO.FT_D2C_ONE_VIEW_TABLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,2208 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA),(VIEW - OW_LAO.VW_TAB3_PMS_DW)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_SKU) | OW_MD.DIM_VTEX_SSG_BR_INVENTORY_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0095 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU),(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE) | OW_MD.DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY),(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU) | OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0045 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU),(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE) | OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE),(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.DIM_UNIQUE_ID) | OW_LAO.DIM_UNIQUE_ID | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,9954 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID)] |  |  | 03/09 - 03/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_ALL) | OW_LAO.TF_GLOBAL_BI_TRAFFIC_ALL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0009 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_ALL)] |  |  | 03/09 - 03/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_DA) | OW_LAO.TF_GLOBAL_BI_TRAFFIC_DA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0007 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_DA)] |  |  | 03/09 - 03/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_MX) | OW_LAO.TF_GLOBAL_BI_TRAFFIC_MX | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0008 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_MX)] |  |  | 03/09 - 03/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_VD) | OW_LAO.TF_GLOBAL_BI_TRAFFIC_VD | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0007 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_VD)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.FT_VTEX_SSG_BR_INVENTORY) | OW_MD.FT_VTEX_SSG_BR_INVENTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0005 | FT | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.FT_VTEX_SSG_BR_SHOP_INVENTORY) | OW_MD.FT_VTEX_SSG_BR_SHOP_INVENTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0049 | FT | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_AFFILIATE_01) | OW_MD.TF_VTEX_AFFILIATE_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_AFFILIATE_02) | OW_MD.TF_VTEX_AFFILIATE_02 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0002 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_AFFILIATE_03) | OW_MD.TF_VTEX_AFFILIATE_03 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE)] |  |  | 03/09 - 03/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_ORDER_STATUS_01) | OW_MD.TF_VTEX_ORDER_STATUS_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_ORDER_STATUS)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_DIM_UNIQUE_ID) | OW_LAO.TMP_DIM_UNIQUE_ID | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,3248 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID)] |  |  | 03/09 - 03/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.TMP_GLOBAL_BI_SALES) | OW_LAO.TMP_GLOBAL_BI_SALES | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,09 | TMP | 0 | [(INGESTION - JOB.TMP_GLOBAL_BI_SALES)] |  |  | 03/09 - 03/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_ALL) | OW_LAO.TMP_GLOBAL_BI_TRAFFIC_ALL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,003 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_ALL)] |  |  | 03/09 - 03/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_DA) | OW_LAO.TMP_GLOBAL_BI_TRAFFIC_DA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0031 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_DA)] |  |  | 03/09 - 03/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_MX) | OW_LAO.TMP_GLOBAL_BI_TRAFFIC_MX | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0029 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_MX)] |  |  | 03/09 - 03/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_VD) | OW_LAO.TMP_GLOBAL_BI_TRAFFIC_VD | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0026 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_VD)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ID) | OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ID | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_PAYMENT_FUNNEL_STATUS) | OW_LAO.TMP_PAYMENT_FUNNEL_STATUS | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO) | OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_BRASIL) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0006 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_CHILE) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0005 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_COLOMBIA) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0005 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_MEXICO) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0005 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_PERU) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0006 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_URUGUAY) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_URUGUAY | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0005 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_BRASIL) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0656 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_CHILE) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,007 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_COLOMBIA) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0046 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_MEXICO) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,04 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_PERU) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0014 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU)] |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_URUGUAY) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_URUGUAY | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0028 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY)] |  |  | 03/09 - 03/09
Grafana |  | TABLE | (TABLE - OW_LAO.TMP_SALES_PAYMENTS_GRAFANA_DETAILS) | OW_LAO.TMP_SALES_PAYMENTS_GRAFANA_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0003 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_MD.INPUT_SALES_CHANNELS) | OW_MD.INPUT_SALES_CHANNELS | LAO EStore | r.bojart |  | yes |  | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | INPUT | 0 | [(PROCEDURE - OW_MD.PROC_ODS_SALES_CHANNELS)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_MD.ODS_SALES_CHANNELS) | OW_MD.ODS_SALES_CHANNELS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_ODS_SALES_CHANNELS)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_MD.RAW_MP_ESTORE) | OW_MD.RAW_MP_ESTORE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0007 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_INGESTION_ODS_MP_ESTORE)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_MD.TMP_SALES_CHANNEL_LAO) | OW_MD.TMP_SALES_CHANNEL_LAO | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | TMP | 0 | [(PROCEDURE - OW_MD.PROC_DIM_SALES_CHANNEL)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_MD.TMP_SALES_CHANNEL_SEDA) | OW_MD.TMP_SALES_CHANNEL_SEDA | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | TMP | 0 | [(PROCEDURE - OW_MD.PROC_DIM_SALES_CHANNEL)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ONLINE_SELL_IN) | OW_SEDA_S.ODS_ONLINE_SELL_IN | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_ONLINE_SELL_IN)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_STATUS_MAP) | U_PRJ_ECOM.ODS_SELA_API_STATUS_MAP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | ODS | 0 | [(INGESTION - JOB.ODS_SELA_API_STATUS_MAP)] |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED) | U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,017 | RAW | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_RAW_ECOM_HQ_ORDERS_TRADEIN_FEED)] |  |  | 03/09 - 03/09
Diggit |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_DIGGIT_ECOM_ORDERS) | U_PRJ_ECOM.TMP_DIGGIT_ECOM_ORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0015 | TMP | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS_HIST_HOMOLG)] |  |  | 03/09 - 03/09
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_CANCELATION) | OW_LAO.ODS_AFTER_SALES_CANCELATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0015 | ODS | 0 |  |  |  | 03/09 - 03/09
| ControlTower | TABLE | (TABLE - OW_LAO.ODS_LAO_CONTROL_TOWER_ORIGIN_PROCESS_LAST_UPDATE) | OW_LAO.ODS_LAO_CONTROL_TOWER_ORIGIN_PROCESS_LAST_UPDATE | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | ODS | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_CAMPAIGN_UPDATE) | OW_LAO.ODS_SALES_CAMPAIGN_UPDATE | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0101 | ODS | 0 |  |  |  | 03/09 - 03/09
Visuar | ControlTower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_VISUAR) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_VISUAR | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0012 | ODS | 0 |  |  |  | 03/09 - 03/09
| ControlTower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_SEASA_MIGRATION) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_SEASA_MIGRATION | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0033 | ODS | 0 |  |  |  | 03/09 - 03/09
| ControlTower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_SEDA_HOMOLOG) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_SEDA_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0079 | ODS | 0 |  |  |  | 03/09 - 03/09
| ControlTower | TABLE | (TABLE - OW_LAO.ODS_TABLE_Migrar ph 2_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE) | OW_LAO.ODS_TABLE_Migrarph2_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | ODS | 0 |  |  |  | 03/09 - 03/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.RAW_NUBIMETRICS_CATEGORYIDS) | OW_LAO.RAW_NUBIMETRICS_CATEGORYIDS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.RAW_SALES_LISTINGS) | OW_LAO.RAW_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0061 | RAW | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP2_SOT_SALES_PROGRESS_KPI) | OW_LAO.TMP2_SOT_SALES_PROGRESS_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0773 | TMP | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_NAME_OLDYEAR) | OW_LAO.TMP_CAMPAIGN_NAME_OLDYEAR | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_D2C_AR_ONE_VIEW_TABLE_01) | OW_LAO.TMP_D2C_AR_ONE_VIEW_TABLE_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_D2C_PO_SALES) | OW_LAO.TMP_D2C_PO_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0706 | TMP | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_DIM_ECOM_PARTNER_LEVEL) | OW_LAO.TMP_DIM_ECOM_PARTNER_LEVEL | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_DIM_ECOM_PARTNER_LEVEL_INSERT) | OW_LAO.TMP_DIM_ECOM_PARTNER_LEVEL_INSERT | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 03/09 - 03/09
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_GSCM) | OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_GSCM | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0037 | TMP | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_PRODUCT_CATEGORY) | OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_PRODUCT_CATEGORY | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0123 | TMP | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_PRODUCT_CATEGORY_AJ) | OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_PRODUCT_CATEGORY_AJ | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0004 | TMP | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_SALES) | OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_SALES | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_SALES_DEDUP) | OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_SALES_DEDUP | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0003 | TMP | 0 |  |  |  | 03/09 - 03/09
|  | TABLE | (TABLE - OW_LAO.TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_ORDERING) | OW_LAO.TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_ORDERING | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-09-03 | 2025-09-03 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0076 | TMP | 0 |  |  |  | 03/09 - 03/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_ECOM_NERP_HIST_LAO) | OW_LAO.RAW_ECOM_NERP_HIST_LAO | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,2355 | RAW | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_LAO_NERP_SELL_IN_ONLINE) | OW_LAO.RAW_LAO_NERP_SELL_IN_ONLINE | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0887 | RAW | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_LAO_NERP_SELL_IN_ONLINE_HOMOLOG) | OW_LAO.RAW_LAO_NERP_SELL_IN_ONLINE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,014 | RAW | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_LAO_NERP_SELL_IN_SET_TOTAL) | OW_LAO.RAW_LAO_NERP_SELL_IN_SET_TOTAL | LAO EStore | r.bojart |  |  | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0132 | RAW | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP) | OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0004 | RAW | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP_PREPARE) | OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP_PREPARE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0001 | RAW | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_DATA_NERP_MB51_GR_FOLDER) | OW_LAO.TMP_DATA_NERP_MB51_GR_FOLDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES) | OW_LAO.TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0166 | TMP | 0 |  |  |  | 04/09 - 04/09
NERP | ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_FILTER) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_FILTER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_NERP_DISPLAY_CLOSING_REPORT_NOT_IN_ZKE) | OW_LAO.TMP_NERP_DISPLAY_CLOSING_REPORT_NOT_IN_ZKE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0007 | TMP | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_NERP_DISPLAY_CLOSING_REPORT_NOT_IN_ZKE_COMPLETE) | OW_LAO.TMP_NERP_DISPLAY_CLOSING_REPORT_NOT_IN_ZKE_COMPLETE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0007 | TMP | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_NERP_MB51_GR_FOLDER) | OW_LAO.TMP_NERP_MB51_GR_FOLDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0012 | TMP | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_LAO.TMP_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0021 | TMP | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_NERP_ZLLEB57910_CLAIM_FOLDER) | OW_LAO.TMP_NERP_ZLLEB57910_CLAIM_FOLDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0005 | TMP | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_NERP_ZLLEE50090) | OW_LAO.TMP_NERP_ZLLEE50090 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0089 | TMP | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_RAW_LAO_NERP_SELL_IN_ONLINE) | OW_LAO.TMP_RAW_LAO_NERP_SELL_IN_ONLINE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0023 | TMP | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_LAO.TMP_RAW_LAO_NERP_SELL_IN_SET_TOTAL) | OW_LAO.TMP_RAW_LAO_NERP_SELL_IN_SET_TOTAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0028 | TMP | 0 |  |  |  | 04/09 - 04/09
GSCM,NERP |  | TABLE | (TABLE - OW_MD.TMP_MAP_NERP_GSCM) | OW_MD.TMP_MAP_NERP_GSCM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PAYMENT_GROUP_01) | OW_MD.TF_VTEX_PAYMENT_GROUP_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PAYMENT_STATUS_01) | OW_MD.TF_VTEX_PAYMENT_STATUS_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_COURIER) | OW_MD.TF_VTEX_PURCHASE_ORDER_COURIER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_DOCK) | OW_MD.TF_VTEX_PURCHASE_ORDER_DOCK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_DOMAIN) | OW_MD.TF_VTEX_PURCHASE_ORDER_DOMAIN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_01) | OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,1257 | TF | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_02) | OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_02 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0386 | TF | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_03) | OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_03 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0433 | TF | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_04) | OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_04 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0816 | TF | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_REGION) | OW_MD.TF_VTEX_PURCHASE_ORDER_REGION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0077 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_TRACKING_01) | OW_MD.TF_VTEX_PURCHASE_ORDER_TRACKING_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,6232 | TF | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_TRADE_IN) | OW_MD.TF_VTEX_PURCHASE_ORDER_TRADE_IN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_WAREHOUSE) | OW_MD.TF_VTEX_PURCHASE_ORDER_WAREHOUSE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_SSG_BR_INVENTORY_SKU) | OW_MD.TF_VTEX_SSG_BR_INVENTORY_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_SSG_BR_INVENTORY_WAREHOUSE) | OW_MD.TF_VTEX_SSG_BR_INVENTORY_WAREHOUSE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_SKU) | OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0004 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU)] |  |  | 04/09 - 04/09
VTEX |  | TABLE | (TABLE - OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE) | OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)] |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.DIM_CONTROL_TOWER_TABLE_PO_COUPON) | OW_LAO.DIM_CONTROL_TOWER_TABLE_PO_COUPON | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 |  |  |  | 04/09 - 04/09
CADASTRA |  | TABLE | (TABLE - OW_LAO.DIM_LAO_TARGETS_CAMPAIGN_CADASTRA) | OW_LAO.DIM_LAO_TARGETS_CAMPAIGN_CADASTRA | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0011 | DIM | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.DIM_NUBIMETRICS_CATEGORYID) | OW_LAO.DIM_NUBIMETRICS_CATEGORYID | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.DIM_NUBIMETRICS_CATEGORYID_BRAZIL) | OW_LAO.DIM_NUBIMETRICS_CATEGORYID_BRAZIL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.DIM_NUBIMETRICS_TOKEN) | OW_LAO.DIM_NUBIMETRICS_TOKEN | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.DIM_PARADIGM_SKU) | OW_LAO.DIM_PARADIGM_SKU | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_AUXILIARY_PBI_MEASURES_CURRENCY) | OW_LAO.DIM_PAYMENT_AUXILIARY_PBI_MEASURES_CURRENCY | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_AUXILIARY_PBI_MEASURES_KPI) | OW_LAO.DIM_PAYMENT_AUXILIARY_PBI_MEASURES_KPI | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_CALCULATION_STATUS_FUNNEL) | OW_LAO.DIM_PAYMENT_CALCULATION_STATUS_FUNNEL | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_CALCULATION_STATUS_FUNNEL_2) | OW_LAO.DIM_PAYMENT_CALCULATION_STATUS_FUNNEL_2 | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_MANUAL_INPUT) | OW_LAO.DIM_PAYMENT_MANUAL_INPUT | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_MANUAL_INPUT_HOMOLOG) | OW_LAO.DIM_PAYMENT_MANUAL_INPUT_HOMOLOG | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.DIM_PAYMENT_MAP_FUNNEL_STATUS) | OW_LAO.DIM_PAYMENT_MAP_FUNNEL_STATUS | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.DIM_SUBSIDIARY_ALERT_TIMESTAMP_DEFAULT) | OW_LAO.DIM_SUBSIDIARY_ALERT_TIMESTAMP_DEFAULT | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0052 | TMP | 0 |  |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_SELA_STATUS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_SELA_STATUS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | TMP | 0 |  |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0003 | TMP | 0 |  |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_DISCOUNT) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_DISCOUNT | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0004 | TMP | 0 |  |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_SKU_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0005 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_EPP_PROMOTION) | OW_LAO.TMP_EPP_PROMOTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0226 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_FT_PO_ORDER_ID) | OW_LAO.TMP_FT_PO_ORDER_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0181 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_GROSS_MARGIN_DCR_) | OW_LAO.TMP_GROSS_MARGIN_DCR_ | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0274 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_GROSS_MARGIN_ZKE_) | OW_LAO.TMP_GROSS_MARGIN_ZKE_ | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,055 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING) | OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_SALES_RULE_1) | OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_SALES_RULE_1 | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_SALES_RULE_GSCM) | OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_SALES_RULE_GSCM | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_TABLE_MINIO_2) | OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_TABLE_MINIO_2 | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_HOUR) | OW_LAO.TMP_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_HOUR | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS) | OW_LAO.TMP_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_BRASIL) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_CHILE) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_COLOMBIA) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_MEXICO) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_PERU) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_URUGUAI) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_URUGUAI | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_SALES_LISTINGS) | OW_LAO.TMP_NUBIMETRICS_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_BRASIL) | OW_LAO.TMP_NUBIMETRICS_TOKEN_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_BRASIL_API) | OW_LAO.TMP_NUBIMETRICS_TOKEN_BRASIL_API | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_CHILE) | OW_LAO.TMP_NUBIMETRICS_TOKEN_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_COLOMBIA) | OW_LAO.TMP_NUBIMETRICS_TOKEN_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_MEXICO) | OW_LAO.TMP_NUBIMETRICS_TOKEN_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_PERU) | OW_LAO.TMP_NUBIMETRICS_TOKEN_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_URUGUAY) | OW_LAO.TMP_NUBIMETRICS_TOKEN_URUGUAY | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
| GlobalD2CBI | TABLE | (TABLE - OW_LAO.TMP_ODS_GLOBAL_BI_SALES_KIT) | OW_LAO.TMP_ODS_GLOBAL_BI_SALES_KIT | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | TMP | 0 |  |  |  | 04/09 - 04/09
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_ODS_LAO_PRODUCT_PREMIUM_ITEMS_GSCM_PREMIUM_MODELS) | OW_LAO.TMP_ODS_LAO_PRODUCT_PREMIUM_ITEMS_GSCM_PREMIUM_MODELS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_PARTNER_LEVEL_SMB_SEASA) | OW_LAO.TMP_PARTNER_LEVEL_SMB_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAYMENT_TYPE_NULL) | OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAYMENT_TYPE_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAY_GATEWAY_NULL) | OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAY_GATEWAY_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAY_STATUS_NULL) | OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAY_STATUS_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO_HOMOLOG) | OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO_HOMOLOG | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_RAW_FEED_SEND_ESTORE) | OW_LAO.TMP_RAW_FEED_SEND_ESTORE | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0004 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_RAW_LAO_DIM_PRODUCT_MAPPING_APOIO) | OW_LAO.TMP_RAW_LAO_DIM_PRODUCT_MAPPING_APOIO | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
Numbimetrics |  | TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0204 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_SALES_CAMPAIGN_UPDATE) | OW_LAO.TMP_SALES_CAMPAIGN_UPDATE | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0101 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_SELA_CUSTON_ORDERS) | OW_LAO.TMP_SELA_CUSTON_ORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_SELA_CUSTON_ORDERS_ITEMS) | OW_LAO.TMP_SELA_CUSTON_ORDERS_ITEMS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_SOT_SALES_PROGRESS_KPI) | OW_LAO.TMP_SOT_SALES_PROGRESS_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,1589 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_LAO.TMP_VL_SALES_CHANNEL_TABLE_BIZTYPE_CHANNEL_NULL) | OW_LAO.TMP_VL_SALES_CHANNEL_TABLE_BIZTYPE_CHANNEL_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STATUS_NULL) | OW_LAO.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STATUS_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STORENAME_NULL) | OW_LAO.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STORENAME_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_MD.TMP_DIM_SALES_CHANNELS_PROMOTIONS_GENERATE) | OW_MD.TMP_DIM_SALES_CHANNELS_PROMOTIONS_GENERATE | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 04/09 - 04/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.ODS_AFTER_SALES_ACCOUNT_TOKEN) | OW_SEDA_S.ODS_AFTER_SALES_ACCOUNT_TOKEN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | ODS | 0 |  |  |  | 04/09 - 04/09
|  | TABLE | (TABLE - OW_SEDA_S.ODS_OST_CANCELLATION) | OW_SEDA_S.ODS_OST_CANCELLATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | ODS | 0 |  |  |  | 04/09 - 04/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0006 | RAW | 0 |  |  |  | 04/09 - 04/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_B2B) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_B2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-04 | 2025-09-04 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 |  |  |  | 04/09 - 04/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_PRICES) | OW_SEDA_S.ODS_NERP_PRICES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0008 | ODS | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA) | OW_SEDA_S.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0473 | ODS | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRFIZFX00007_EXCHANGE_RATE) | OW_SEDA_S.ODS_NERP_ZRFIZFX00007_EXCHANGE_RATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0007 | ODS | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A080_SALES_ORDER_LIST) | OW_SEDA_S.ODS_NERP_ZRSDD6A080_SALES_ORDER_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,4251 | ODS | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDK65000_BILLING_LIST) | OW_SEDA_S.ODS_NERP_ZRSDK65000_BILLING_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0128 | ODS | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZSE16_DELETED_DO) | OW_SEDA_S.ODS_NERP_ZSE16_DELETED_DO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0144 | ODS | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.RAW_NERP_ZSE16_DELETED_DO) | OW_SEDA_S.RAW_NERP_ZSE16_DELETED_DO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,6686 | RAW | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS) | OW_SEDA_S.TMP_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0117 | TMP | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST) | OW_SEDA_S.TMP_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0109 | TMP | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_SEDA_S.TMP_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0001 | TMP | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZLLEB57910_CLAIM_MAINTENANCE) | OW_SEDA_S.TMP_NERP_ZLLEB57910_CLAIM_MAINTENANCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0006 | TMP | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZLLEB57910_CLAIM_MAINTENANCE_OLD) | OW_SEDA_S.TMP_NERP_ZLLEB57910_CLAIM_MAINTENANCE_OLD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0 | TMP | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZSE16_DELETED_DO) | OW_SEDA_S.TMP_NERP_ZSE16_DELETED_DO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,001 | TMP | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS) | OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0004 | TMP | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER) | OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0003 | TMP | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER) | OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0003 | TMP | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER) | OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 1.4 Ingestion NERP | 0,0005 | TMP | 0 |  |  |  | 05/09 - 05/09
VTEX |  | TABLE | (TABLE - OW_LAO.DIM_VTEX_SELLER_ORDER_LIST) | OW_LAO.DIM_VTEX_SELLER_ORDER_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0002 | DIM | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - OW_LAO.FT_D2C_FORECAST_OST) | OW_LAO.FT_D2C_FORECAST_OST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | FT | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_LEAD_TIME_ORDER_IOD_KPI) | OW_LAO.FT_D2C_NERP_LEAD_TIME_ORDER_IOD_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0066 | FT | 0 |  |  |  | 05/09 - 05/09
NERP,VTEX |  | TABLE | (TABLE - OW_LAO.FT_D2C_VTEX_NERP_WEEKLY_SALES) | OW_LAO.FT_D2C_VTEX_NERP_WEEKLY_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0372 | FT | 0 |  |  |  | 05/09 - 05/09
VTEX |  | TABLE | (TABLE - OW_LAO.FT_D2C_VTEX_O2O_SALES_KPI) | OW_LAO.FT_D2C_VTEX_O2O_SALES_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0838 | FT | 0 |  |  |  | 05/09 - 05/09
| ControlTower | TABLE | (TABLE - OW_LAO.FT_SALES_CONTROL_TOWER_SELA_Migrar ph 2_SALES) | OW_LAO.FT_SALES_CONTROL_TOWER_SELA_Migrarph2_SALES | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,1091 | FT | 0 |  |  |  | 05/09 - 05/09
VTEX |  | TABLE | (TABLE - OW_LAO.FT_VTEX_SSG_BR_TMP) | OW_LAO.FT_VTEX_SSG_BR_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | FT | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_DB_SALES_ORDER_TRACKING) | OW_LAO.TF_D2C_NERP_DB_SALES_ORDER_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0111 | TF | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_SALES_COUPON_KPI) | OW_LAO.TF_D2C_NERP_SALES_COUPON_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0875 | TF | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_SALES_REWARDS_KPI) | OW_LAO.TF_D2C_NERP_SALES_REWARDS_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,2029 | TF | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_D2C_NERP_TRADEIN_SALES_KPI) | OW_LAO.TF_D2C_NERP_TRADEIN_SALES_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0028 | TF | 0 |  |  |  | 05/09 - 05/09
VTEX |  | TABLE | (TABLE - OW_LAO.TF_D2C_PO_VTEX_SALES_KPI) | OW_LAO.TF_D2C_PO_VTEX_SALES_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0944 | TF | 0 |  |  |  | 05/09 - 05/09
VTEX |  | TABLE | (TABLE - OW_LAO.TF_D2C_VTEX_PO_TARGET_LAUNCH_S25) | OW_LAO.TF_D2C_VTEX_PO_TARGET_LAUNCH_S25 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0059 | TF | 0 |  |  |  | 05/09 - 05/09
VTEX |  | TABLE | (TABLE - OW_LAO.TF_D2C_VTEX_PROMOTION_KPI) | OW_LAO.TF_D2C_VTEX_PROMOTION_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,4388 | TF | 0 |  |  |  | 05/09 - 05/09
VTEX |  | TABLE | (TABLE - OW_LAO.TF_D2C_VTEX_SELLOUT_PLATFORM_KPI) | OW_LAO.TF_D2C_VTEX_SELLOUT_PLATFORM_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0637 | TF | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - OW_LAO.TF_NERP_SALES_PROGRESS_KPI) | OW_LAO.TF_NERP_SALES_PROGRESS_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0003 | TF | 0 |  |  |  | 05/09 - 05/09
VTEX |  | TABLE | (TABLE - OW_LAO.TF_VTEX_MONITORING_SKU) | OW_LAO.TF_VTEX_MONITORING_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,006 | TF | 0 |  |  |  | 05/09 - 05/09
VTEX |  | TABLE | (TABLE - OW_MD.DIM_MAPPING_VTEX_POLICIES_PRODUCT) | OW_MD.DIM_MAPPING_VTEX_POLICIES_PRODUCT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  |  |  | 05/09 - 05/09
VTEX |  | TABLE | (TABLE - OW_SEDA_S.DIM_VTEX_AFFILIATE) | OW_SEDA_S.DIM_VTEX_AFFILIATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0002 | DIM | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.DIM_SELA_API_PARAMETERS) | U_PRJ_ECOM.DIM_SELA_API_PARAMETERS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.DIM_SELA_API_PARAMETERS_QTD) | U_PRJ_ECOM.DIM_SELA_API_PARAMETERS_QTD | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.DIM_SELLER_INSTANCE) | U_PRJ_ECOM.DIM_SELLER_INSTANCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | DIM | 0 |  |  |  | 05/09 - 05/09
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.FT_MAGENTO_ORDER) | U_PRJ_ECOM.FT_MAGENTO_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0003 | FT | 0 |  |  |  | 05/09 - 05/09
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.FT_MAGENTO_ORDER_ITEM) | U_PRJ_ECOM.FT_MAGENTO_ORDER_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0002 | FT | 0 |  |  |  | 05/09 - 05/09
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.FT_MAGENTO_ORDER_PAYMENT) | U_PRJ_ECOM.FT_MAGENTO_ORDER_PAYMENT | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,0001 | FT | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - U_PRJ_ECOM.TF_D2C_NERP_WEEKLY_SALES_KPI) | U_PRJ_ECOM.TF_D2C_NERP_WEEKLY_SALES_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | TF | 0 |  |  |  | 05/09 - 05/09
NERP |  | TABLE | (TABLE - U_PRJ_ECOM.TF_D2C_NERP_WEEKLY_SALES_KPI_SAMPLE) | U_PRJ_ECOM.TF_D2C_NERP_WEEKLY_SALES_KPI_SAMPLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 2.1 Migrar ph1 | 0,2122 | TF | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_EPP2) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,019 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_EST) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_EST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0554 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_MEMBERS) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_MEMBERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0136 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_MKP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_MKP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,6605 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_PARC) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_PARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0282 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_RESID) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_RESID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0006 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_B2B) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_B2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0004 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BREA) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0046 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP_VL) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP_VL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_EPP2) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0004 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_EST) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_EST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0007 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_MEMBERS) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_MEMBERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0005 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_MKP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_MKP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0074 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_PARC) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_PARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0004 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_RESID) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_RESID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_EPP2) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_EST) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_EST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0253 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP_VL) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP_VL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0075 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_EST) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_EST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0029 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_MEMBERS) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_MEMBERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0009 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_MKP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_MKP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0547 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_PARC) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_PARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0015 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_RESID) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_RESID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 |  |  |  | 05/09 - 05/09
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_MEMBERS) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_MEMBERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - OW_SEDA_S.TMP_NUBI_SALES_REPORT) | OW_SEDA_S.TMP_NUBI_SALES_REPORT | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0003 | TMP | 0 |  |  |  | 05/09 - 05/09
| GlobalD2CBI | TABLE | (TABLE - U_PRJ_ECOM.ODS_GLOBAL_BI_STOCKOUT_HISTORY) | U_PRJ_ECOM.ODS_GLOBAL_BI_STOCKOUT_HISTORY | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0049 | ODS | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_OST_SEDA_CANCELLATION_HMLG) | U_PRJ_ECOM.ODS_OST_SEDA_CANCELLATION_HMLG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,018 | ODS | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEIN) | U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEIN | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEIN_SEASA) | U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEIN_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEUP) | U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEUP | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEUP_SEASA) | U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEUP_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | RAW | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_SKU) | U_PRJ_ECOM.RAW_ECOM_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0019 | RAW | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_SKU_SAMSUNG_CARE_PLUS) | U_PRJ_ECOM.RAW_ECOM_SKU_SAMSUNG_CARE_PLUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | RAW | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_DIM_PRODUCT_CATEGORY_SEDA) | U_PRJ_ECOM.TMP_DIM_PRODUCT_CATEGORY_SEDA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_PRODUCTS_COMBO | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_TRADEIN_FEED) | U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_TRADEIN_FEED | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0005 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_TRADEIN_FEED_SEND) | U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_TRADEIN_FEED_SEND | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0002 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_ECOM_SKU_ENABLES) | U_PRJ_ECOM.TMP_ODS_ECOM_SKU_ENABLES | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN) | U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID) | U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID_SEASA) | U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID_SEASA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_ECOM_SKU_SAMSUNG_CARE_PLUS) | U_PRJ_ECOM.TMP_RAW_ECOM_SKU_SAMSUNG_CARE_PLUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_FEED_SEND_ESTORE_SAMPLE) | U_PRJ_ECOM.TMP_RAW_FEED_SEND_ESTORE_SAMPLE | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0343 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_PAYMENTS) | U_PRJ_ECOM.TMP_RAW_PAYMENTS | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_SELA_API_PARAMETERS) | U_PRJ_ECOM.TMP_SELA_API_PARAMETERS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_SELA_API_PARAMETERS_QTD_DIM) | U_PRJ_ECOM.TMP_SELA_API_PARAMETERS_QTD_DIM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_SELA_API_PARAMETERS_QTD_GTM) | U_PRJ_ECOM.TMP_SELA_API_PARAMETERS_QTD_GTM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-09-05 | 2025-09-05 | ['[]'] | 0 | 3.1 Migrar ph1 | 0,0001 | TMP | 0 |  |  |  | 05/09 - 05/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT) | U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  |  |  |  | 08/09 - 08/09
VTEX |  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION) | U_PRJ_ECOM.VIEW_VTEX_PROMOTION | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 08/09 - 08/09
VTEX |  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM) | U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 08/09 - 08/09
VTEX |  | VIEW | (VIEW - OW_LAO.RAW_VTEX_PAYMENTS_HOMOLOG) | OW_LAO.RAW_VTEX_PAYMENTS_HOMOLOG | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | VIEW | (VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM) | OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | VIEW | (VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM) | OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX | GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_DOMAIN)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | VIEW | (VIEW - OW_LAO.VW_TMP_VTEX_CONCAT) | OW_LAO.VW_TMP_VTEX_CONCAT | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  |  |  |  | 08/09 - 08/09
VTEX |  | VIEW | (VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER) | OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.VTEX_SSG_AR_RATES_AND_BENEFITS_DATA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  |  |  |  | 08/09 - 08/09
| ControlTower | VIEW | (VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE) | OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
| ControlTower | VIEW | (VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MAT) | OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MAT | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
| ControlTower | VIEW | (VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_PROD) | OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_PROD | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
| ControlTower | VIEW | (VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_TST) | OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_TST | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION) | OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_COURIER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_DOCK)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOCK)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 08/09 - 08/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED) | U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG) | U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | VIEW | (VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS) | OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 08/09 - 08/09
VTEX |  | VIEW | (VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS) | OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS) | OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS_HOMOLOG)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | Confirmed by r.bojart via knox on 21/11 |  |  | 08/09 - 08/09 | [19 empty] | Confirmed by r.bojart via knox on 21/11
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU) | OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.TF_VTEX_SSG_BR_INVENTORY_SKU)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_BY_REF_ID)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_SKU)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE) | OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_BY_SKU)'", "'(TABLE - OW_MD.TF_VTEX_SSG_BR_INVENTORY_WAREHOUSE)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE) | OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
HYBRIS | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  | SIM | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 3 |  |  |  |  | 08/09 - 08/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.DIM_ECOM_PARTNER_LEVEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  |  |  |  | 08/09 - 08/09
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT) | OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 08/09 - 08/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION) | OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_WAREHOUSE_OPERATION)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.ODS_WMS_PICKING_PACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  |  |  |  | 08/09 - 08/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING) | OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.FT_D2C_NERP_WH_OPERATION_PENDING)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  |  |  |  | 08/09 - 08/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TMP_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  |  |  |  | 08/09 - 08/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  | SIM | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  |  |  |  | 08/09 - 08/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  |  |  |  | 08/09 - 08/09
|  | VIEW | (VIEW - OW_MD.VW_PRICE_MONITORING_AUDIT_PROCESS) | OW_MD.VW_PRICE_MONITORING_AUDIT_PROCESS | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
GSCM,NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI) | OW_LAO.PROC_D2C_NERP_GSCM_PSI |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_MB51_GR_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_D2C_NERP_GSCM_PSI)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  |  |  |  | 08/09 - 08/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI) | OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES)'", "'(TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  |  |  |  | 08/09 - 08/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | VIEW | (VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD) | OW_LAO.VIEW_VTEX_PAYMENTS_OLD | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  |  |  |  | 08/09 - 08/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU) | OW_LAO.PROC_D2C_PAYMENT_ITAU |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  |  |  |  | 08/09 - 08/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TESTE) | OW_LAO.PROC_TESTE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  |  |  |  | 08/09 - 08/09
| GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 08/09 - 08/09
VTEX | GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 08/09 - 08/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES) | OW_LAO.PROC_D2C_PO_HYBRIS_SALES |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 4 |  |  |  |  | 08/09 - 08/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI) | OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES_BY_HOUR_KPI)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 3 |  |  |  |  | 08/09 - 08/09
PMS |  | VIEW | (VIEW - OW_LAO.VW_PMS_TESTE) | OW_LAO.VW_PMS_TESTE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.COGS)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.ODS_SEDA_VTEX_KIT_COMPONENTS_REGISTRATION)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION) | OW_LAO.PROC_D2C_VTEX_PROMOTION |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI) | OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS) | OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP) | OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  |  |  |  | 08/09 - 08/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1) | OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1 |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_AR_TABLE_WEEK)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_D2C_AR_TABLE_WEEK)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  |  |  |  | 08/09 - 08/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING) | OW_LAO.PROC_D2C_NERP_ORDER_PENDING |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.FT_D2C_NERP_ORDER_PENDING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU) | OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TF_D2C_VTEX_PAYMENT_SKU)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 7 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_ORDER_STATUS) | OW_MD.PROC_DIM_VTEX_ORDER_STATUS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.TF_VTEX_ORDER_STATUS_01)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS) | OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.TF_VTEX_PAYMENT_STATUS_01)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 08/09 - 08/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING) | OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.FT_D2C_NERP_DELIVERY_PENDING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  |  |  |  | 08/09 - 08/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_INVENTORY) | OW_LAO.PROC_D2C_NERP_INVENTORY |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.FT_D2C_NERP_INVENTORY)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  |  |  |  | 08/09 - 08/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST) | U_PRJ_ECOM.VIEW_ECOM_ORD_TST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 7 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO) | U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  |  |  |  | 09/09 - 09/09
VTEX |  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN) | U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_CT_TRADEIN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_CT_TRADEIN)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  |  |  |  | 09/09 - 09/09
VTEX |  | VIEW | (VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX) | OW_LAO.VIEW_ECOM_PRODUCT_VTEX | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_REFERENCE) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_REFERENCE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)]']"] | 1 | 2.1 Migrar ph1 |  |  | 3 |  |  |  |  | 09/09 - 09/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME) | OW_LAO.PROC_D2C_NERP_LEAD_TIME |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_03)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME)'", "'(TABLE - OW_LAO.FT_D2C_NERP_LEAD_TIME)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_01)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_02)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  |  |  |  | 09/09 - 09/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW) | OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_D2C_NERP_ORDER_PENDING_OVERVIEW)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_01)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_02)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  |  |  |  | 09/09 - 09/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO) | OW_LAO.PROC_ODS_HYBRIS_COMBO | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_COMBO)'", "'(TABLE - OW_LAO.RAW_HYBRIS_COMBO)'", "'(TABLE - OW_LAO.TMP_ODS_HYBRIS_COMBO)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 5 |  |  |  |  | 09/09 - 09/09
Magento |  | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO) | U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO)]']"] | 1 | 1.3 Ingestion MAGENTO |  |  | 5 |  |  |  |  | 09/09 - 09/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP) | OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 2.1 Migrar ph1 |  |  | 3 |  |  |  |  | 09/09 - 09/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM) | OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  |  |  |  | 09/09 - 09/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 09/09 - 09/09
PMS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA) | OW_LAO.PROC_PMS_DW_UNIFICADA | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.FT_D2C_ONE_VIEW_TABLE)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 |  |  |  |  | 09/09 - 09/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING) | OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 3 |  |  |  |  | 09/09 - 09/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING) | OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_TRACKING_01)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 12 |  |  |  |  | 09/09 - 09/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT) | OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_01)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_02)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_03)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_04)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  |  |  |  | 09/09 - 09/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE) | OW_MD.PROC_DIM_VTEX_AFFILIATE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_AFFILIATE_01)'", "'(TABLE - OW_MD.TF_VTEX_AFFILIATE_02)'", "'(TABLE - OW_MD.TF_VTEX_AFFILIATE_03)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  |  |  |  | 09/09 - 09/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP) | OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.TF_VTEX_PAYMENT_GROUP_01)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 09/09 - 09/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 09/09 - 09/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU) | OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU | [5 empty] | Done |  | 2025-12-09 |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU)'", "'(TABLE - OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_SKU)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 09/09 - 09/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY) | OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_SKU)'", "'(TABLE - OW_MD.FT_VTEX_SSG_BR_INVENTORY)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 09/09 - 09/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY) | OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU)'", "'(TABLE - OW_MD.FT_VTEX_SSG_BR_SHOP_INVENTORY)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 09/09 - 09/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH) | OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_MONTH)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_WEEK)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_WEEK)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 11 |  |  |  |  | 09/09 - 09/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1) | OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1 |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_D2C_AR_TABLE_MONTH)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.FT_D2C_AR_TABLE_MONTH)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5) | U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ) | U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO) | OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO) | OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS) | OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR) | OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  |  |  |  | 09/09 - 09/09
|  | VIEW | (VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW) | OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 5 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI) | OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI | LAO EStore | r.bojart |  | yes | 3 | Done |  |  | SIM | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID) | OW_LAO.PROC_DIM_UNIQUE_ID | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_VTEX_PROFILE)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_UNIQUE_ID)'", "'(TABLE - OW_LAO.TMP_DIM_UNIQUE_ID)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 10/09 - 10/09
NERP | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO) | OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)'", "'(TABLE - OW_LAO.RAW_LAO_DIM_PRODUCT_MAPPING_APOIO)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS) | OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)]']"] | 0 | 2.1 Migrar ph1 |  |  | 4 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS) | OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN) | OW_LAO.PROC_SALES_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  |  | SIM | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR)]']"] | 0 | 3.1 Migrar ph1 |  |  | 4 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_NAME_AJUSTE) | OW_LAO.PROC_NAME_AJUSTE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_BRASIL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_CHILE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_COLOMBIA)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_MEXICO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_PERU)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_BRASIL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_CHILE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_COLOMBIA)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_MEXICO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_PERU)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_URUGUAY)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
Numbimetrics |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_URUGUAY)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
NERP | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG) | OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS) | OW_LAO.PROC_SALES_CAMPAIGN_TARGETS | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_TARGETS_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_CHANNELS)'", "'(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR)'", "'(TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN)'", "'(TABLE - OW_LAO.DIM_EXCEL_TARGETS_CAMPAIGN)]']"] | 0 | 2.1 Migrar ph1 |  |  | 9 |  |  |  |  | 10/09 - 10/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND) | OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA)]']"] | 1 | 3.1 Migrar ph1 |  |  | 18 |  |  |  |  | 10/09 - 10/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA)]']"] | 1 | 3.1 Migrar ph1 |  |  | 18 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN) | OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME)'", "'(TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME)]']"] | 0 | 3.1 Migrar ph1 |  |  | 6 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME) | OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME)'", "'(TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP) | OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.TMP_PAYMENT_PAYMENT_TYPE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 2.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP) | OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.TMP_PAYMENT_FUNNEL_STATUS)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 2.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU) | OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES)'", "'(TABLE - OW_MD.MASTER_TRADE_POLICIES)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_SALES_CHANNEL) | OW_MD.PROC_DIM_SALES_CHANNEL | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_MD.TMP_SALES_CHANNEL_LAO)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_MD.TMP_SALES_CHANNEL_SEDA)]']"] | 1 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 11 |  |  |  |  | 10/09 - 10/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 5 |  |  |  |  | 10/09 - 10/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 4 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 |  |  |  |  | 10/09 - 10/09
VTEX |  | VIEW | (VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX) | OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 24 |  |  |  |  | 10/09 - 10/09
VTEX |  | VIEW | (VIEW - OW_LAO.VW_ECOM_SKUS_VTEX) | OW_LAO.VW_ECOM_SKUS_VTEX | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 24 |  |  |  |  | 10/09 - 10/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  |  |  |  | 10/09 - 10/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  |  |  |  | 10/09 - 10/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  |  |  |  | 10/09 - 10/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 13 |  |  |  |  | 10/09 - 10/09
VTEX |  | VIEW | (VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE) | OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 12 |  |  |  |  | 10/09 - 10/09
VTEX |  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL) | U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)]']"] | 1 | 2.1 Migrar ph1 |  |  | 9 |  |  |  |  | 10/09 - 10/09
VTEX |  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST) | U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)]']"] | 1 | 2.1 Migrar ph1 |  |  | 9 |  |  |  |  | 10/09 - 10/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES) | OW_LAO.PROC_ODS_HYBRIS_SALES | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_HYBRIS_SALES_MONITORING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES)'", "'(TABLE - OW_LAO.RAW_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 6 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM) | OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM | [5 empty] | Done |  | 2025-12-11 |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 13 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT)'", "'(TABLE - OW_LAO.DIM_MONITORING_BI_LAO_PROCCESS_ALERT)'", "'(TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ID)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.RAW_FILES_MINIO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ALERT)'", "'(TABLE - OW_LAO.TIME_DEFINITION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS) | OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS)'", "'(TABLE - OW_LAO.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS) | OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.STG_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.RAW_LAO_PRODUCT_PREMIUM_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA) | U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_CUSTOMER_ID_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  |  |  |  | 10/09 - 10/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES) | OW_LAO.PROC_D2C_PO_VTEX_SALES |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 21 |  |  |  |  | 10/09 - 10/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP) | OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 21 |  |  |  |  | 10/09 - 10/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711) | OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711 | [5 empty] | Not to be migrated |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 20 |  |  |  |  | 10/09 - 10/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS) | OW_LAO.PROC_D2C_MELI_COLETAS |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_LAO.TF_D2C_MELI_COLETAS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_RDD)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 |  |  |  |  | 10/09 - 10/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN) | OW_LAO.PROC_D2C_NERP_GROSS_MARGIN |  |  |  | yes | yes | Done |  |  | SIM | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_MD.REBATE)'", "'(TABLE - OW_LAO.ODS_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_MD.SOLD_TO_CHANNEL)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  |  |  |  | 11/09 - 11/09
Cello,NERP | CelloLogistic | PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI) | OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI | SEDA Logistic |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  |  |  |  | 11/09 - 11/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW) | OW_LAO.PROC_FT_D2C_BIZOVERVIEW |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY)'", "'(TABLE - OW_MD.ODS_MEDALIA_TARGET_NPS)'", "'(TABLE - OW_LAO.ODS_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 3.1 Migrar ph1 |  |  | 6 |  |  |  |  | 11/09 - 11/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2) | OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2 |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY)'", "'(TABLE - OW_MD.ODS_MEDALIA_TARGET_NPS)'", "'(TABLE - OW_LAO.ODS_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 3.1 Migrar ph1 |  |  | 6 |  |  |  |  | 11/09 - 11/09
|  | VIEW | (VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW) | OW_LAO.VW_D2C_ORDER_ONE_VIEW | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)'", "'(TABLE - OW_SEDA_S.ODS_WMS_PICKING_PACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 7 |  |  |  |  | 11/09 - 11/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI) | OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI |  |  |  | yes | yes | Done |  |  | SIM | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.RAW_GSCM_CE_SELL_OUT)'", "'(TABLE - OW_MD.ODS_MP_ESTORE)'", "'(TABLE - OW_LAO.ODS_TARGET_STRETCH)'", "'(TABLE - OW_LAO.RAW_GSCM_MX_SELL_OUT)'", "'(TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES)'", "'(TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_WEEKLY_SALES_KPI)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 10 |  |  |  |  | 11/09 - 11/09
GSCM,NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS) | OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.TF_D2C_NERP_TO_WOS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_TO_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.FT_D2C_NERP_TO_STOCK_OVERVIEW_BY_PLANT)'", "'(TABLE - OW_LAO.TF_D2C_GSCM_TO_WOS)'", "'(TABLE - OW_LAO.ODS_GSCM_FCST_MGMT_D2C)'", "'(TABLE - OW_LAO.FT_D2C_WOS)]']"] | 1 | 1.4 Ingestion NERP |  |  | 7 |  |  |  |  | 11/09 - 11/09
PLUGGTO |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO) | OW_SEDA_S.PROC_FT_OST_PLUGGTO | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  |  |  |  | 11/09 - 11/09
NERP |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM) | OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_SEDA_S.RAW_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)'", "'(TABLE - OW_SEDA_S.TMP_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]']"] | 0 | 1.4 Ingestion NERP |  |  | 3 |  |  |  |  | 11/09 - 11/09
|  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_PRODUCT) | OW_MD.PROC_DIM_PRODUCT | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.ODS_GSCM_PRODUCT_LIST)'", "'(TABLE - OW_MD.ODS_TDF_MARA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_PRODUCT_SKU)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  |  |  |  | 11/09 - 11/09
VTEX |  | VIEW | (VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX) | OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 | [5 empty] | 16/09 - 16/09
Grafana |  | VIEW | (VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS) | OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 7 | [5 empty] | 16/09 - 16/09
|  | VIEW | (VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW) | OW_LAO.VIEW_RAW_BIZ_OVERVIEW | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 1.4 Ingestion NERP |  |  | 7 | [5 empty] | 16/09 - 16/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM)'", "'(TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE)'", "'(TABLE - OW_LAO.ODS_HYBRIS_COMBO)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.DIM_ECOM_PARTNER_LEVEL)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 56 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 30 | [5 empty] | 16/09 - 16/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE) | OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_CONSOLIDATED)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_LAO.FT_D2C_AR_ONE_VIEW_TABLE)'", "'(TABLE - OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_01)'", "'(TABLE - OW_LAO.TF_D2C_VTEX_PAYMENT_SKU)'", "'(TABLE - OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_02)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 28 | [5 empty] | 16/09 - 16/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE) | OW_LAO.PROC_D2C_ONE_VIEW_TABLE |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 | [5 empty] | 16/09 - 16/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5) | OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5 | LAO EStore | r.bojart |  |  |  | Not to be migrated |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 | [5 empty] | 16/09 - 16/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG | TBC | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  | SIM | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 16 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 16 | [5 empty] | 16/09 - 16/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN) | OW_LAO.PROC_D2C_NERP_SALES_TRADEIN |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 14 | [5 empty] | 16/09 - 16/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI) | OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 14 | [5 empty] | 16/09 - 16/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD) | OW_LAO.PROC_D2C_PO_VTEX_RDD |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_RDD)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2 | LAO EStore | r.bojart |  |  |  | Not to be migrated |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | Confirmed by r.bojart via knox on 21/11 |  |  |  | 16/09 - 16/09 | [18 empty] | Confirmed by r.bojart via knox on 21/11
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  | SIM | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 | [5 empty] | 16/09 - 16/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS) | OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 | [5 empty] | 16/09 - 16/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS) | OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  | 2025-12-05 |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 | [5 empty] | 16/09 - 16/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES) | OW_LAO.PROC_D2C_NERP_DAILY_SALES |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.TF_D2C_NERP_DAILY_SALES_KPI)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 | [5 empty] | 16/09 - 16/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL) | OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES_BY_CHANNEL_KPI)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 | [5 empty] | 16/09 - 16/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS) | OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS_HOMOLOG)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 | [5 empty] | 16/09 - 16/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 | [5 empty] | 16/09 - 16/09
Grafana |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS) | OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_GRAFANA_DETAILS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 12 | [5 empty] | 16/09 - 16/09
HYBRIS | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES | LAO EStore | r.bojart |  | yes | 1 | Done |  |  | SIM | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)'", "'(TABLE - OW_LAO.ODS_HYBRIS_COMBO)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 10 | [5 empty] | 16/09 - 16/09
Grafana |  | PROCEDURE | (PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS) | OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS | LAO EStore | r.bojart |  |  |  | Not to be migrated |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 7 |  | Confirmed by r.bojart via knox on 21/11 |  |  |  | 16/09 - 16/09 | [18 empty] | Confirmed by r.bojart via knox on 21/11
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS) | OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS |  |  |  | No |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_04)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM)'", "'(TABLE - OW_LAO.ODS_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT)'", "'(TABLE - OW_MD.MAP_INCENTIVE_TYPE_MAPPING)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_05)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP_HISTORICO)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE_HISTORICO)'", "'(TABLE - OW_MD.MAP_CUSTOMER_EXCEPTION)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE)'", "'(TABLE - OW_LAO.ODS_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_01)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO_CONSOLIDADO)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_02)'", "'(TABLE - OW_LAO.ODS_GSSC_REPORT_TO_SR)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_03)]']"] | 1 | 1.4 Ingestion NERP |  |  | 19 | [5 empty] | 16/09 - 16/09
Cello,NERP | CelloLogistic | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION) | OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION | SEDA Logistic |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_LAO.FT_D2C_CELLO_NERP_RETURN_OPERATION)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_WEEKLY)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | 1.4 Ingestion NERP |  |  | 14 | [5 empty] | 16/09 - 16/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES) | OW_LAO.PROC_D2C_NERP_SALES |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 | [5 empty] | 16/09 - 16/09
Cello,NERP | CelloLogistic | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING) | OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING | SEDA Logistic |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)'", "'(TABLE - OW_LAO.FT_D2C_CELLO_NERP_RETURN_PENDING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 | [5 empty] | 16/09 - 16/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  | SIM | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 2.1 Migrar ph1 |  |  | 14 | [5 empty] | 16/09 - 16/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP) | OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAYMENT_TYPE)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 8 | [5 empty] | 16/09 - 16/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP) | OW_LAO.PROC_FUNNEL_PAYMENTS_MAP | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAYMENT_TYPE)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 7 | [5 empty] | 16/09 - 16/09
Diggit | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 | [5 empty] | 16/09 - 16/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI) | OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI | LAO EStore | r.bojart |  | yes | 6 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 | [5 empty] | 16/09 - 16/09
Visuar | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 | [5 empty] | 16/09 - 16/09
Diggit | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 | [5 empty] | 16/09 - 16/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 | [5 empty] | 16/09 - 16/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST_ADJ) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST_ADJ | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 2 | [5 empty] | 17/09 - 17/09
VTEX |  | VIEW | (VIEW - U_PRJ_ECOM.VW_SDU_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM) | U_PRJ_ECOM.VW_SDU_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
VTEX |  | VIEW | (VIEW - U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN) | U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_MD.RAW_DATA_MD_MAPPING_PROMOTION_PRODUCT)'", "'(TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 2 | [5 empty] | 17/09 - 17/09
VTEX |  | VIEW | (VIEW - U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_NOK) | U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_NOK | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.RAW_AUDIT_VTEX)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
VTEX |  | VIEW | (VIEW - U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_OK) | U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_OK | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.RAW_AUDIT_VTEX)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
VTEX |  | VIEW | (VIEW - U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX) | U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
NERP |  | VIEW | (VIEW - OW_LAO.VIEW_NERP_ZRCOS43400_TARGET) | OW_LAO.VIEW_NERP_ZRCOS43400_TARGET | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 | [5 empty] | 17/09 - 17/09
NERP |  | VIEW | (VIEW - OW_LAO.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_LAO.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 1 | [5 empty] | 17/09 - 17/09
NERP |  | VIEW | (VIEW - OW_LAO.VW_SDU_RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_LAO.VW_SDU_RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 | [5 empty] | 17/09 - 17/09
NERP |  | VIEW | (VIEW - OW_LAO.VW_SDU_RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER) | OW_LAO.VW_SDU_RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - OW_SEDA_S.VW_AR_CLEARED) | OW_SEDA_S.VW_AR_CLEARED | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 | [5 empty] | 17/09 - 17/09
NERP |  | VIEW | (VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER) | OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 | [5 empty] | 17/09 - 17/09
NERP |  | VIEW | (VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - OW_LAO.VIEW_ECOM_EXCHANGE_RATE) | OW_LAO.VIEW_ECOM_EXCHANGE_RATE | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
PMS |  | VIEW | (VIEW - OW_LAO.VW_TAB3_PMS_DW) | OW_LAO.VW_TAB3_PMS_DW | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.FT_D2C_ONE_VIEW_TABLE)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
VTEX |  | VIEW | (VIEW - OW_LAO.VIEW_VTEX_PAYMENTS) | OW_LAO.VIEW_VTEX_PAYMENTS | [5 empty] | Done |  | 2026-01-02 |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.TF_D2C_VTEX_PAYMENT_SKU)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
PMS |  | VIEW | (VIEW - OW_LAO.VW_TAB1_PMS_DW) | OW_LAO.VW_TAB1_PMS_DW | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
PMS |  | VIEW | (VIEW - OW_LAO.VW_TAB2_PMS_DW) | OW_LAO.VW_TAB2_PMS_DW | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - OW_SEDA_S.VW_SEDA_PREORDER) | OW_SEDA_S.VW_SEDA_PREORDER | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_EPP_STATUS_NEW_RULE) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_EPP_STATUS_NEW_RULE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_RETROATIVO_TST) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_RETROATIVO_TST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP05052023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP05052023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP15062023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP15062023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP21062023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP21062023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP27042023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP27042023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_PLATFORM_SEDA) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_PLATFORM_SEDA | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_SL) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_SL | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_bkp26052022) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_bkp26052022 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADEIN_PAYMENT) | U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADEIN_PAYMENT | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_PAYMENT) | U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_PAYMENT | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_SYNAPCON) | U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_SYNAPCON | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PAYMENT) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PAYMENT | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 0 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
| GlobalD2CBI | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_BI) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_BI | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)]']"] | 0 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_2) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_2 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
| GlobalD2CBI | VIEW | (VIEW - OW_LAO.VIEW_ECOM_ODS_GLOBAL_BI_SALES) | OW_LAO.VIEW_ECOM_ODS_GLOBAL_BI_SALES | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)]']"] | 1 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
| GlobalD2CBI | VIEW | (VIEW - OW_LAO.VIEW_ODS_GLOBAL_BI_SALES) | OW_LAO.VIEW_ODS_GLOBAL_BI_SALES | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)]']"] | 1 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
AppsFlyer |  | VIEW | (VIEW - OW_LAO.VW_APPSFLYER_IN_APP_EVENTS) | OW_LAO.VW_APPSFLYER_IN_APP_EVENTS | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_APPSFLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - OW_SEDA_S.VW_ONLINE_SELL_IN) | OW_SEDA_S.VW_ONLINE_SELL_IN | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)'", "'(TABLE - OW_SEDA_S.ODS_ONLINE_SELL_IN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SAMCOL) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SAMCOL | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEASA) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEASA | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SECH) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SECH | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEDA) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEDA | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEM) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEM | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEPR) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEPR | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO | [5 empty] | Done |  |  |  | 3 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TESTE_) | OW_LAO.PROC_TESTE_ | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 2 | [5 empty] | 17/09 - 17/09
|  | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN) | U_PRJ_ECOM.PROC_ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 2 | [5 empty] | 17/09 - 17/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_RAW_VTEX_SSG_BR_B2B_SALES_ORDER_MONITORING_DATASOURCE) | OW_LAO.PROC_RAW_VTEX_SSG_BR_B2B_SALES_ORDER_MONITORING_DATASOURCE |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_INTEGRATION_RAW_VTEX_SALES_COLLECTION) | OW_LAO.PROC_INTEGRATION_RAW_VTEX_SALES_COLLECTION | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_COLLECTION)'", "'(TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_2020)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 2 | [5 empty] | 17/09 - 17/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_GENERATE) | OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_GENERATE | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_SEDA_GENERATE) | OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_SEDA_GENERATE | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_STOCKOUT_VTEX_GLOBALBI) | OW_LAO.PROC_ODS_STOCKOUT_VTEX_GLOBALBI | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_FILES_DEDUP) | OW_LAO.RAW_VTEX_PAYMENTS_FILES_DEDUP | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS_FILES)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_FILES_GET) | OW_LAO.RAW_VTEX_PAYMENTS_FILES_GET | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS_FILES)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_GENERATE) | OW_LAO.RAW_VTEX_PAYMENTS_GENERATE | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
|  | PROCEDURE | (PROCEDURE - OW_MD.PROC_FT_PRODUCT_STATUS) | OW_MD.PROC_FT_PRODUCT_STATUS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_PRODUCT_SKU)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 | [5 empty] | 17/09 - 17/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PAYMENTS) | OW_LAO.PROC_ODS_HYBRIS_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_PAYMENTS)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 2 | [5 empty] | 17/09 - 17/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_CANCELLATIONS) | OW_LAO.PROC_ODS_HYBRIS_CANCELLATIONS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_CANCELLATIONS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_CANCELLATIONS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 | [5 empty] | 18/09 - 18/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_OFFERS) | OW_LAO.PROC_ODS_HYBRIS_OFFERS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_OFFERS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_OFFERS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 | [5 empty] | 18/09 - 18/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PREORDERS) | OW_LAO.PROC_ODS_HYBRIS_PREORDERS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PREORDERS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_PREORDERS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 | [5 empty] | 18/09 - 18/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REFUNDS) | OW_LAO.PROC_ODS_HYBRIS_REFUNDS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_REFUNDS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_REFUNDS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 | [5 empty] | 18/09 - 18/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_RETURNS) | OW_LAO.PROC_ODS_HYBRIS_RETURNS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_RETURNS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_RETURNS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 | [5 empty] | 18/09 - 18/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REWARDS) | OW_LAO.PROC_ODS_HYBRIS_REWARDS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_REWARDS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_REWARDS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 | [5 empty] | 18/09 - 18/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS) | OW_LAO.PROC_ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  | SIM | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS)'", "'(TABLE - OW_LAO.STG_HYBRIS_SALES_PRODUCTS_DISCOUNTS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 | [5 empty] | 18/09 - 18/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_TRADEIN) | OW_LAO.PROC_ODS_HYBRIS_TRADEIN | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_TRADEIN)'", "'(TABLE - OW_LAO.RAW_HYBRIS_TRADEIN)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 | [5 empty] | 18/09 - 18/09
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_ITEMS_DISCOUNTS) | OW_LAO.PROC_ODS_HYBRIS_SALES_ITEMS_DISCOUNTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.RAW_HYBRIS_SALES_HOMOLOG)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 1 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_DIM_SOLD_TO) | OW_LAO.PROC_D2C_DIM_SOLD_TO |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_FORECAST_OST) | OW_LAO.PROC_D2C_FORECAST_OST |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - OW_LAO.RAW_REPASSES_D2C_2022_2024)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 | [5 empty] | 18/09 - 18/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_LAO.PROC_INGESTION_ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.RAW_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 | [5 empty] | 18/09 - 18/09
NERP | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_OUTBOUND_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_OUTBOUND_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 | [5 empty] | 18/09 - 18/09
NERP | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_OUTBOUND_UPDATE_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_OUTBOUND_UPDATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 | [5 empty] | 18/09 - 18/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TF_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI_UNPIVOT) | OW_LAO.PROC_TF_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI_UNPIVOT | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 | [5 empty] | 18/09 - 18/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TF_NERP_ZRCOS43400_SALES_PROGRESS_KPI_UNPIVOT_AGG_DIVISION_GROUP) | OW_LAO.PROC_TF_NERP_ZRCOS43400_SALES_PROGRESS_KPI_UNPIVOT_AGG_DIVISION_GROUP | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT2) | OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT2 |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TMP_D2C_AR_TABLE_MONTH)'", "'(TABLE - OW_LAO.FT_D2C_AR_TABLE_MONTH)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT2) | OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT2 |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.FT_D2C_AR_TABLE_WEEK)'", "'(TABLE - OW_LAO.TMP_D2C_AR_TABLE_WEEK)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
GSCM |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_GSCM_INVENTORY) | OW_LAO.PROC_D2C_GSCM_INVENTORY |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.FT_D2C_GSCM_INVENTORY)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_KPI) | OW_LAO.PROC_D2C_PO_VTEX_SALES_KPI |  |  |  | yes |  | Done |  |  | SIM | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_SELLOUT_PLATFORM_KPI) | OW_LAO.PROC_D2C_VTEX_SELLOUT_PLATFORM_KPI |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_INSERT_SALES_CANCELLED_FROM_ODS) | OW_LAO.PROC_INSERT_SALES_CANCELLED_FROM_ODS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_INSERT_SALES_FROM_ODS) | OW_LAO.PROC_INSERT_SALES_FROM_ODS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
| GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_ALL) | OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_ALL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_ALL)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIM_PRODUCT_MAPPING_LAO_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIM_PRODUCT_MAPPING_LAO_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES) | OW_LAO.PROC_TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_PRODUCT_ESTORE_GLOBAL) | OW_MD.PROC_DIM_PRODUCT_ESTORE_GLOBAL | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_DIM_EXCHANGE_RATE_RAWDATA) | U_PRJ_ECOM.PROC_DIM_EXCHANGE_RATE_RAWDATA | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_COUPON_KPI) | OW_LAO.PROC_D2C_NERP_SALES_COUPON_KPI |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_REWARDS_KPI) | OW_LAO.PROC_D2C_NERP_SALES_REWARDS_KPI |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_O2O_SALES_KPI) | OW_LAO.PROC_D2C_VTEX_O2O_SALES_KPI |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PO_TARGET_LAUNCH_S25) | OW_LAO.PROC_D2C_VTEX_PO_TARGET_LAUNCH_S25 |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_DIM_TAX_GROSS_MARGIN) | OW_LAO.PROC_DIM_TAX_GROSS_MARGIN | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
VTEX |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_D2C_VTEX_O2O_SALES_KPI) | OW_LAO.PROC_FT_D2C_VTEX_O2O_SALES_KPI |  |  |  | yes | yes | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TF_NERP_GROSS_MARGIN_MONITORING_DATASOURCE) | OW_LAO.PROC_TF_NERP_GROSS_MARGIN_MONITORING_DATASOURCE |  | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_MD.PROC_INGESTION_DIM_PRODUCT_ESTORE) | OW_MD.PROC_INGESTION_DIM_PRODUCT_ESTORE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_MD.PROC_INGESTION_DIM_PRODUCT_GLOBAL) | OW_MD.PROC_INGESTION_DIM_PRODUCT_GLOBAL | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_Migrar ph 2_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE) | OW_LAO.PROC_CHECK_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_STORENAME_UPDATE) | OW_LAO.PROC_LAO_CRP_CS_STORENAME_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_LAO.RAW_LAO_CRP_CS_STORENAME)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_VOUCHER_COUPON_UPDATE) | OW_LAO.PROC_LAO_CRP_CS_VOUCHER_COUPON_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON)'", "'(TABLE - OW_LAO.RAW_LAO_CRP_CS_VOUCHER_COUPON)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_DELIVERY_MODE_DIM_UPDATE) | OW_LAO.PROC_LAO_DELIVERY_MODE_DIM_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - OW_LAO.RAW_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
| GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_DA) | OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_DA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_DA)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_DA)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
| GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_MX) | OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_MX | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_MX)'", "'(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_MX)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
| GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_VD) | OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_VD | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_VD)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_VD)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP_HOMOLOG) | OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TF_PO_COUPON_ID_CONTROL_TOWER_LIST) | OW_LAO.PROC_TF_PO_COUPON_ID_CONTROL_TOWER_LIST | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE) | OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE_BKP) | OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE_BKP | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
GSCM |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_LAO_PREMIUM_PRODUCTS_TABLE_FROM_GSCM_UPDATE) | OW_LAO.PROC_ODS_LAO_PREMIUM_PRODUCTS_TABLE_FROM_GSCM_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_GLOBALBI_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_GLOBALBI_UPDATE | LAO EStore | r.bojart |  | yes | 4 | Done |  |  | SIM | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PBI) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PBI | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_GLOBALBI_UPDATE_HOMOLOG) | OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_GLOBALBI_UPDATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_MD.PROC_INGESTION_ODS_MP_ESTORE) | OW_MD.PROC_INGESTION_ODS_MP_ESTORE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_MD.RAW_MP_ESTORE)'", "'(TABLE - OW_MD.ODS_MP_ESTORE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREPP2) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREPP2 | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2ESTUDANTES) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2ESTUDANTES | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
Diggit |  | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS) | U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - U_PRJ_ECOM.STG_DIGGIT_ECOM_ORDERS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_FT_STOCKOUT) | OW_LAO.PROC_D2C_FT_STOCKOUT | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT)]']"] | 1 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
| GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_GLOBAL_BI_SALES_EMPTY_DIMENSIONS_ALERT) | OW_LAO.PROC_ODS_GLOBAL_BI_SALES_EMPTY_DIMENSIONS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)]']"] | 1 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 18/09 - 18/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_ODS_SELA_CUSTOM_ORDERS_ITEMS_UPDATE) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_ODS_SELA_CUSTOM_ORDERS_ITEMS_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 18/09 - 18/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_DEPARA) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_DEPARA |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS_NERP) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS_NERP |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_ITEMS_EXCLUSIVES_UPDATE) | OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_ITEMS_EXCLUSIVES_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS) | OW_LAO.PROC_ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)'", "'(TABLE - OW_LAO.TMP_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
Visuar |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_ORDERS_VISUAR) | OW_LAO.PROC_ODS_ORDERS_VISUAR | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.RAW_ORDERS_VISUAR)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PREMIUM_MODELS_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PREMIUM_MODELS_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_TAXES_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_TAXES_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ) | OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_FEED_SEND_ESTORE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ_BKP10032025) | OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ_BKP10032025 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_FEED_SEND_ESTORE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI) | OW_LAO.PROC_SALES_CAMPAIGN_PBI | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_CUT)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V2) | OW_LAO.PROC_SALES_CAMPAIGN_PBI_V2 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_CUT)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V3) | OW_LAO.PROC_SALES_CAMPAIGN_PBI_V3 | LAO EStore | r.bojart |  |  | 0 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_CUT)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_MD.PROC_ODS_SALES_CHANNELS) | OW_MD.PROC_ODS_SALES_CHANNELS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_MD.INPUT_SALES_CHANNELS)'", "'(TABLE - OW_MD.ODS_SALES_CHANNELS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRB2B) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRB2B | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREA) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREA | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOP) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOP | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOPMKTPL) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOPMKTPL | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2MEMBERS) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2MEMBERS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2PARCERIAS) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2PARCERIAS | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2RESIDENCIAL) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2RESIDENCIAL | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | U_PRJ_ECOM.PROC_ECOM_HQ_ORDERS_PRODUCTS_COMBO | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_PRODUCTS_COMBO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP) | U_PRJ_ECOM.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_PRODUCTS_COMBO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_RAW_ECOM_HQ_ORDERS_TRADEIN_FEED) | U_PRJ_ECOM.PROC_RAW_ECOM_HQ_ORDERS_TRADEIN_FEED | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_BLACK_FRIDAY_PBI) | OW_LAO.PROC_BLACK_FRIDAY_PBI | [5 empty] | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
CADASTRA |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_DIM_TARGETS_CAMPAIGN_CADASTRA_UPDATE) | OW_LAO.PROC_DIM_TARGETS_CAMPAIGN_CADASTRA_UPDATE | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
NERP | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_DIVISION_NERP_CONTROL_TOWER_STATUS) | OW_LAO.PROC_DIVISION_NERP_CONTROL_TOWER_STATUS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_AP2_EXCHANGE_RATE_HOMOLOG) | OW_LAO.PROC_FT_AP2_EXCHANGE_RATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
| GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_ALL) | OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_ALL | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_ALL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
| GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_DA) | OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_DA | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_DA)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
| GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_MX) | OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_MX | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_MX)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
| GlobalD2CBI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_VD) | OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_VD | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_VD)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS) | OW_LAO.PROC_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_EXCHANGE_RATE_HOMOLOG) | OW_LAO.PROC_ODS_EXCHANGE_RATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Not to be migrated |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | Confirmed by r.bojart via knox on 21/11 |  |  |  | 19/09 - 19/09 | [18 empty] | Confirmed by r.bojart via knox on 21/11
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_Migrar ph 2_DATASOURCE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_CHECK_DATASOURCE_HOMOLOG | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_Migrar ph 2_DATASOURCE_HOMOLOG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_CHECK_DATASOURCE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_MONITORING_DATASOURCE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_MONITORING_DATASOURCE |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_EMPTY_DIMENSIONS_ALERT) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_EMPTY_DIMENSIONS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
NERP | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_STATUS_CANCELED) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_STATUS_CANCELED | LAO EStore | r.bojart |  | yes | 2 | Done |  |  | SIM | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
VTEX | ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS) | OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS) | OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS_VALIDATION) | OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS_VALIDATION | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO) | OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS) | OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY) | OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_SALES_COUPONS) | OW_LAO.PROC_ODS_SELA_SALES_COUPONS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_SALES_COUPONS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_SALES_COUPONS_ITEMS) | OW_LAO.PROC_ODS_SELA_SALES_COUPONS_ITEMS | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_SALES_COUPONS_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP_HOMOLOG) | OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Not to be migrated |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_PAYMENT_TYPE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | Confirmed by r.bojart via knox on 21/11 |  |  |  | 19/09 - 19/09 | [18 empty] | Confirmed by r.bojart via knox on 21/11
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_SAMPLE_HQ) | OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_SAMPLE_HQ | LAO EStore | r.bojart |  | yes | 7 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.RAW_FEED_SEND_ESTORE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_DAILY_Migrar ph 2) | OW_LAO.PROC_SALES_CAMPAIGN_DAILY_CHECK | LAO EStore | r.bojart |  | yes | 5 | Done |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
Diggit |  | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS_HIST_HOMOLG) | U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS_HIST_HOMOLG | LAO EStore | r.bojart |  |  |  | Not to be migrated |  |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - U_PRJ_ECOM.TMP_DIGGIT_ECOM_ORDERS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 | [5 empty] | 19/09 - 19/09
|  | TABLE | (TABLE - OW_MD.SALES_CHANNEL) | OW_MD.SALES_CHANNEL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0002 | OTHER | 0 | [(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_MD.PROC_DIM_SALES_CHANNEL),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT)] | [10 empty] | 27/10 - 27/10
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.M_CODE_CELLO) | OW_SEDA_S.M_CODE_CELLO | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0004 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING_AUX),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5)] | [10 empty] | 27/10 - 27/10
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT) | OW_SEDA_S.TF_CELLO_TRACKING_EVENT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,748 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_MD.COGS) | OW_MD.COGS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0007 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN),(VIEW - OW_LAO.VW_PMS_TESTE),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT) | OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,688 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2),(INGESTION - JOB.RAW_DATA_LAO_MEDALLIA_EXPRESS_REPORT),(INGESTION - JOB.ODS_LAO_MEDALLIA_EXPRESS_REPORT),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW)] | [10 empty] | 27/10 - 27/10
MEDALIA |  | TABLE | (TABLE - OW_MD.ODS_MEDALIA_TARGET_NPS) | OW_MD.ODS_MEDALIA_TARGET_NPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW),(PROCEDURE - OW_MD.PROC_INGESTION_ODS_MEDALIA_TARGET_NPS)] | [10 empty] | 27/10 - 27/10
Cello | CelloLogistic | TABLE | (TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE) | OW_LAO.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS),(PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_LAO.ODS_MEDALLIA_EXPRESS_REPORT) | OW_LAO.ODS_MEDALLIA_EXPRESS_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0048 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2)] | [10 empty] | 27/10 - 27/10
GSCM |  | TABLE | (TABLE - OW_SEDA_S.GSCM_TMP) | OW_SEDA_S.GSCM_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0004 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_API_GSCM_TO_ASM),(VIEW - OW_SEDA_S.VW_API_GSCM_TO_ASM_2)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_LAO.ODS_TARGET_STRETCH) | OW_LAO.ODS_TARGET_STRETCH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_LAO.RAW_REPASSES_D2C_2022_2024) | OW_LAO.RAW_REPASSES_D2C_2022_2024 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_FORECAST_OST)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_MD.MASTER_TRADE_POLICIES) | OW_MD.MASTER_TRADE_POLICIES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_MD.REBATE) | OW_MD.REBATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0016 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_MD.SOLD_TO_CHANNEL) | OW_MD.SOLD_TO_CHANNEL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_WEEKLY) | OW_SEDA_S.ODS_GLP_RETURN_RATIO_WEEKLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0799 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_SELA.STAGE2_FACT_STOCK_SALES) | OW_SELA.STAGE2_FACT_STOCK_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0002 | OTHER | 0 | [(PROCEDURE - OW_SELA.ProcMergeDMSDataV2)] | [10 empty] | 27/10 - 27/10
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.VTEX_SSG_AR_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.VTEX_SSG_AR_RATES_AND_BENEFITS_DATA | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,3925 | OTHER | 0 | [(VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_CUSTOMER_RESTRICTION) | OW_APL_POALLOCATION.ODS_CUSTOMER_RESTRICTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_CUSTOMER_SOLDS_AND_SHIPS) | OW_APL_POALLOCATION.ODS_CUSTOMER_SOLDS_AND_SHIPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0042 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_VALIDATION_OPTIMIZATION) | OW_APL_POALLOCATION.ODS_VALIDATION_OPTIMIZATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_VALIDATION_OPTIMIZATION_LOG) | OW_APL_POALLOCATION.ODS_VALIDATION_OPTIMIZATION_LOG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0034 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_WOS) | OW_APL_POALLOCATION.ODS_WOS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0049 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_WOS_WEEK) | OW_APL_POALLOCATION.ODS_WOS_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0101 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_LAO.PRODUCT_COMMENTS) | OW_LAO.PRODUCT_COMMENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 27/10 - 27/10
LINKAPI |  | TABLE | (TABLE - OW_LAO.RAW_DATA_LINKAPI_REPORT) | OW_LAO.RAW_DATA_LINKAPI_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0 | RAW | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_LAO.RAW_DATA_MKP_REPORT_VIA_VAREJO) | OW_LAO.RAW_DATA_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,038 | RAW | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_MD.SOLD_TO_CHANNEL_TMP) | OW_MD.SOLD_TO_CHANNEL_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 27/10 - 27/10
GSCM |  | TABLE | (TABLE - OW_SEDA_S.GSCM_PSI_SALES_DEDUCTION) | OW_SEDA_S.GSCM_PSI_SALES_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0003 | OTHER | 0 | [11 empty] | 27/10 - 27/10
GSCM |  | TABLE | (TABLE - OW_SEDA_S.GSCM_TMP_2) | OW_SEDA_S.GSCM_TMP_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0004 | OTHER | 0 | [11 empty] | 27/10 - 27/10
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0 | RAW | 0 | [11 empty] | 27/10 - 27/10
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_RESID) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_RESID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0 | RAW | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_MKP_REPORT_VIA_VAREJO) | OW_SEDA_S.RAW_DATA_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0501 | RAW | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_CUSTO_SAMSUNG_AEREO_CST) | OW_SEDA_S_COMEX.ODS_CMX_CUSTO_SAMSUNG_AEREO_CST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_CUSTO_SAMSUNG_MARITIMO_CST) | OW_SEDA_S_COMEX.ODS_CMX_CUSTO_SAMSUNG_MARITIMO_CST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_DEMURRAGE_CST) | OW_SEDA_S_COMEX.ODS_CMX_DEMURRAGE_CST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0001 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_ENTREGAS_IMPORTADOS_SVC_CST) | OW_SEDA_S_COMEX.ODS_CMX_ENTREGAS_IMPORTADOS_SVC_CST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0005 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_MAPA_IMPORTACAO_SVC_HEADER) | OW_SEDA_S_COMEX.ODS_CMX_MAPA_IMPORTACAO_SVC_HEADER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,001 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_PROCESSOS_LIBERADOS_SVC_CST) | OW_SEDA_S_COMEX.ODS_CMX_PROCESSOS_LIBERADOS_SVC_CST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0002 | ODS | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_CHANNEL_GROUPING_DAY) | U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_CHANNEL_GROUPING_DAY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0 | RAW | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_DEVICE) | U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_DEVICE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0001 | RAW | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - U_PRJ_ECOM.STG_CT_TRADEIN_SEASA) | U_PRJ_ECOM.STG_CT_TRADEIN_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 1 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING) | OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 0 | Migrar ph 2 | 0,0092 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HISTORICO),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HISTORICO),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_DUEK),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HIST),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_V2),(PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING_1_0),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_DUEK),(PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HIST)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS) | OW_LAO.MONITORING_BI_LAO_PROCCESS | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 0 | Migrar ph 2 | 0,4748 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS_NERP),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_DEPARA),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER) | U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 0 | Migrar ph 2 | 0,0482 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER) | U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 0 | Migrar ph 2 | 0,2788 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE) | OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_V2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_DUEK),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HIST),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HISTORICO),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM) | OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM)] | [10 empty] | 27/10 - 27/10
| ControlTower | TABLE | (TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES) | OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-27 | 2025-10-27 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_TAXES_UPDATE)] | [10 empty] | 27/10 - 27/10
|  | TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS) | OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1) | OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0243 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_2),(PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_1),(PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_5),(PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_4),(PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_3)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING) | OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WERABLES_SITE_MAPPING_MERGE_AUTOMATIC),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC),(VIEW - OW_LAO.VW_CRAWLING_AP1_NPC_SEGMENT)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING) | OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1_V2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1),(VIEW - OW_LAO.VW_CRAWLING_AP1_REF_SEGMENT),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_SITE_MAPPING_MERGE_AUTOMATIC)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING) | OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [(VIEW - OW_LAO.VW_CRAWLING_AP1_TV_SEGMENT),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_SITE_MAPPING_MERGE_AUTOMATIC),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1_V2)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING) | OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1_V2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_SITE_MAPPING_MERGE_AUTOMATIC),(VIEW - OW_LAO.VW_CRAWLING_AP1_WM_SEGMENT)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_MD.OLD_DIM_PRODUCT) | OW_MD.OLD_DIM_PRODUCT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0284 | OTHER | 0 | [(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_PRODUCT)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0093 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA),(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM),(VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA_VIAGEM_ESCOLTA),(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0049 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA_VIAGEM_ESCOLTA),(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA),(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_ESCOLTA),(VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA) | OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,011 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA),(VIEW - OW_SEDA_S.TF_PORTAL_SM_SURSIS_JOIN_1),(INGESTION - JOB.ODS_SURSIS_DELIVERY_DATA),(VIEW - OW_SEDA_S.VW_PORTAL_SM_SURSIS)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SURSIS_ESCORT) | OW_SEDA_S.ODS_SURSIS_ESCORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0065 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_PORTAL_SM_SURSIS),(INGESTION - JOB.ODS_SURSIS_ESCORT),(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA),(VIEW - OW_SEDA_S.TF_PORTAL_SM_SURSIS_JOIN_1)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SELA.DIM_PRODUCT) | OW_SELA.DIM_PRODUCT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0021 | DIM | 0 | [(VIEW - OW_SELA.MISSINGSEGMENT),(PROCEDURE - OW_SELA.ProcMergeDMSDataV2),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(VIEW - OW_SELA.MISSING_MKTNAME)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SELA.FACT_STOCK_SALES) | OW_SELA.FACT_STOCK_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,2849 | OTHER | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(VIEW - OW_SELA.MISSING_MKTNAME),(VIEW - OW_SELA.CURRENTWEEK),(PROCEDURE - OW_SELA.ProcMergeDMSDataV2)] | [10 empty] | 28/10 - 28/10
HYBRIS |  | TABLE | (TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES) | OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,018 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING_KEY) | OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING_KEY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,3527 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2),(PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING_1_0)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_NC) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_NC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0051 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA),(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA),(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_NC)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SURSIS_NC) | OW_SEDA_S.ODS_SURSIS_NC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0052 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_PORTAL_SM_SURSIS),(INGESTION - JOB.ODS_SURSIS_NC),(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SELA.DIM_MN_SEGMENT) | OW_SELA.DIM_MN_SEGMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD),(VIEW - OW_SELA.MISSINGSEGMENT),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SELA.DIM_WEEK) | OW_SELA.DIM_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | DIM | 0 | [(VIEW - OW_SELA.CURRENTWEEK),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES) | U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | ODS | 0 | [(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(INGESTION - JOB.ODS_ECOM_SKU_ENABLES)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_PROCESS_LIST) | OW_LAO.CRAWLER_PROCESS_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0027 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_RETRY_PRODUCTS),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_CRAWLER_STATUS)] | [10 empty] | 28/10 - 28/10
NERP | ControlTower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT) | OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0018 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT_FLOORING) | OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT_FLOORING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0006 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_FLOORING),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SELA.DIM_DC) | OW_SELA.DIM_DC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SELA.FCST_SNAPSHOT) | OW_SELA.FCST_SNAPSHOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,011 | OTHER | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SELA.TMP_DLAKE_HIST) | OW_SELA.TMP_DLAKE_HIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,3991 | TMP | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SELA.TMP_DLAKE_W3) | OW_SELA.TMP_DLAKE_W3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,004 | TMP | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SELA.TMP_DLAKE_W8) | OW_SELA.TMP_DLAKE_W8 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | TMP | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD)] | [10 empty] | 28/10 - 28/10
Cello | CelloLogistic | TABLE | (TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS) | OW_LAO.AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0006 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS)] | [10 empty] | 28/10 - 28/10
YAMI |  | TABLE | (TABLE - OW_LAO.AUX_YAMI_PRODUCT_DETAIL_STATUS) | OW_LAO.AUX_YAMI_PRODUCT_DETAIL_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_STATUS) | OW_LAO.CRAWLER_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0673 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_CRAWLER_STATUS)] | [10 empty] | 28/10 - 28/10
HYBRIS |  | TABLE | (TABLE - OW_LAO.STG_HYBRIS_SALES_PRODUCTS_DISCOUNTS) | OW_LAO.STG_HYBRIS_SALES_PRODUCTS_DISCOUNTS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0006 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS) | OW_LAO.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.STG_LAO_PRODUCT_PREMIUM_ITEMS) | OW_LAO.STG_LAO_PRODUCT_PREMIUM_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.TIME_DEFINITION) | OW_LAO.TIME_DEFINITION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_LAO.TMP_MAP_ESTORE_URL_SKU) | OW_LAO.TMP_MAP_ESTORE_URL_SKU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0006 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_ESTORE_URL_SKU)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_MD.ODS_MD_MAPPING_PROMOTION_PRODUCT) | OW_MD.ODS_MD_MAPPING_PROMOTION_PRODUCT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [(INGESTION - JOB.ODS_MD_MAPPING_PROMOTION_PRODUCT)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_MD.RAW_DATA_MD_MAPPING_PROMOTION_PRODUCT) | OW_MD.RAW_DATA_MD_MAPPING_PROMOTION_PRODUCT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN)] | [10 empty] | 28/10 - 28/10
MEDALIA |  | TABLE | (TABLE - OW_MD.RAW_MEDALIA_TARGET_NPS) | OW_MD.RAW_MEDALIA_TARGET_NPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_INGESTION_ODS_MEDALIA_TARGET_NPS)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ACCOUNT_MANAGEMENT_FLOORSHRE_TT) | OW_SEDA_S.ACCOUNT_MANAGEMENT_FLOORSHRE_TT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_DIRECTSHIP_RAWDATA_GPL) | OW_SEDA_S.ODS_DIRECTSHIP_RAWDATA_GPL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0249 | ODS | 0 | [(INGESTION - JOB.ODS_DIRECTSHIP_RAWDATA_GPL)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ONTIMEGI_RAWDATA_GPL) | OW_SEDA_S.ODS_ONTIMEGI_RAWDATA_GPL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0413 | ODS | 0 | [(INGESTION - JOB.ODS_ONTIMEGI_RAWDATA_GPL)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ONTIMEGR_RAWDATA_GPL) | OW_SEDA_S.ODS_ONTIMEGR_RAWDATA_GPL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,027 | ODS | 0 | [(INGESTION - JOB.ODS_ONTIMEGR_RAWDATA_GPL)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_RP_DOA_INSPECTION_RESULT) | OW_SEDA_S.ODS_RP_DOA_INSPECTION_RESULT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,1115 | ODS | 0 | [(INGESTION - JOB.ODS_RP_DOA_INSPECTION_RESULT)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_RP_DOA_TRACKING_BY_SERIAL) | OW_SEDA_S.ODS_RP_DOA_TRACKING_BY_SERIAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0802 | ODS | 0 | [(INGESTION - JOB.ODS_RP_DOA_TRACKING_BY_SERIAL)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_Migrar ph 2LIST) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_Migrarph2LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0011 | ODS | 0 | [(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_Migrar ph 2LIST)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-28 | 2025-10-28 | ['[]'] | 0 | Migrar ph 2 | 0,0007 | ODS | 0 | [(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA)] | [10 empty] | 28/10 - 28/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | ODS | 0 | [(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS)] | [10 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SURICATO_HR) | OW_SEDA_S.ODS_SURICATO_HR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0038 | ODS | 0 | [(INGESTION - JOB.ODS_SURICATO_HR)] | [10 empty] | 29/10 - 29/10
GFK |  | TABLE | (TABLE - OW_SEDA_S.ODS_TV_WEEKLY_GFK) | OW_SEDA_S.ODS_TV_WEEKLY_GFK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,004 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM)] | [10 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_SEDA_S.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT) | OW_SEDA_S.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,2136 | ODS | 0 | [(INGESTION - JOB.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT)] | [10 empty] | 29/10 - 29/10
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MKP) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MKP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0356 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MKP)] | [10 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_SEDA_S.TMP_ODS_GENERIC_INPUT) | OW_SEDA_S.TMP_ODS_GENERIC_INPUT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0141 | TMP | 0 | [(INGESTION - JOB.TMP_ODS_GENERIC_INPUT)] | [10 empty] | 29/10 - 29/10
GFK |  | TABLE | (TABLE - OW_SEDA_S.VW_MX_FOTA_AND_GFK) | OW_SEDA_S.VW_MX_FOTA_AND_GFK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0021 | OTHER | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK)] | [10 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_SELA.DIM_COUNTRY) | OW_SELA.DIM_COUNTRY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | [10 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_SELA.DIM_COUNTRY_BRANCH) | OW_SELA.DIM_COUNTRY_BRANCH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | DIM | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | [10 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_SELA.DIM_GROWTH) | OW_SELA.DIM_GROWTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | DIM | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | [10 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_SELA.WOS_PARAMETERS) | OW_SELA.WOS_PARAMETERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | [10 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_FASTSHOP) | U_PRJ_ECOM.ODS_MKP_D2C_FASTSHOP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0325 | ODS | 0 | [(INGESTION - JOB.ODS_MKP_D2C_FASTSHOP)] | [10 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_CUSTOMER_ID_SEDA) | U_PRJ_ECOM.RAW_CUSTOMER_ID_SEDA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0059 | RAW | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA)] | [10 empty] | 29/10 - 29/10
Diggit |  | TABLE | (TABLE - U_PRJ_ECOM.STG_DIGGIT_ECOM_ORDERS) | U_PRJ_ECOM.STG_DIGGIT_ECOM_ORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS)] | [10 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.OAUTH_ACCESS_TOKEN) | OW_APL_POALLOCATION.OAUTH_ACCESS_TOKEN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0012 | OTHER | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.OAUTH_REFRESH_TOKEN) | OW_APL_POALLOCATION.OAUTH_REFRESH_TOKEN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0034 | OTHER | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_AIR_CAPACITY) | OW_APL_POALLOCATION.ODS_AIR_CAPACITY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_ALIGNMENT_CRITERIA) | OW_APL_POALLOCATION.ODS_ALIGNMENT_CRITERIA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_ALIGNMENT_CRITERIA_WEEK) | OW_APL_POALLOCATION.ODS_ALIGNMENT_CRITERIA_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT) | OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,007 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT_STOCK) | OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT_STOCK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,003 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT_WEEKLY) | OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT_WEEKLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0259 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_AP1) | OW_APL_POALLOCATION.ODS_AP1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0021 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_AP1_WEEK) | OW_APL_POALLOCATION.ODS_AP1_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0057 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_APPLICATION_CLIENT) | OW_APL_POALLOCATION.ODS_APPLICATION_CLIENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_APPLICATION_CLIENT_GRANT) | OW_APL_POALLOCATION.ODS_APPLICATION_CLIENT_GRANT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_APPLICATION_SCOPE) | OW_APL_POALLOCATION.ODS_APPLICATION_SCOPE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_AVAILABLE_CARS) | OW_APL_POALLOCATION.ODS_AVAILABLE_CARS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_AVERAGE_DIVISION_WEIGHT) | OW_APL_POALLOCATION.ODS_AVERAGE_DIVISION_WEIGHT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_CALENDAR_SAMSUNG) | OW_APL_POALLOCATION.ODS_CALENDAR_SAMSUNG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_CONFIGURATION) | OW_APL_POALLOCATION.ODS_CONFIGURATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_DIVISION_COMPATIBILITY) | OW_APL_POALLOCATION.ODS_DIVISION_COMPATIBILITY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_DIVISION_MAP) | OW_APL_POALLOCATION.ODS_DIVISION_MAP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_DO_NOT_ALIGN_SO) | OW_APL_POALLOCATION.ODS_DO_NOT_ALIGN_SO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_EXECUTION_OPTIMIZATION) | OW_APL_POALLOCATION.ODS_EXECUTION_OPTIMIZATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_EXECUTION_OPTIMIZATION_LOG) | OW_APL_POALLOCATION.ODS_EXECUTION_OPTIMIZATION_LOG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_FILES) | OW_APL_POALLOCATION.ODS_FILES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_FILES_COLUMNS_DATA_BIND) | OW_APL_POALLOCATION.ODS_FILES_COLUMNS_DATA_BIND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_HOLIDAY) | OW_APL_POALLOCATION.ODS_HOLIDAY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_HUB_LOG) | OW_APL_POALLOCATION.ODS_HUB_LOG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_INVOICE_RESTRICTION) | OW_APL_POALLOCATION.ODS_INVOICE_RESTRICTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_KEEP_ALIGNMENT) | OW_APL_POALLOCATION.ODS_KEEP_ALIGNMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_LEAD_TIME) | OW_APL_POALLOCATION.ODS_LEAD_TIME | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_MULTIPLES) | OW_APL_POALLOCATION.ODS_MULTIPLES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0006 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_OPTIMIZATION_RESULT) | OW_APL_POALLOCATION.ODS_OPTIMIZATION_RESULT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0309 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_OUTBOUND) | OW_APL_POALLOCATION.ODS_OUTBOUND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,009 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PLANT_SOURCE_MAP) | OW_APL_POALLOCATION.ODS_PLANT_SOURCE_MAP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PRODUCT) | OW_APL_POALLOCATION.ODS_PRODUCT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-29 | 2025-10-29 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 29/10 - 29/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PRODUCTION_PLAN) | OW_APL_POALLOCATION.ODS_PRODUCTION_PLAN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PRODUCTION_PLAN_MONTH_DAY) | OW_APL_POALLOCATION.ODS_PRODUCTION_PLAN_MONTH_DAY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0014 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PRODUCT_KIT) | OW_APL_POALLOCATION.ODS_PRODUCT_KIT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PRODUCT_RTF_WEEK) | OW_APL_POALLOCATION.ODS_PRODUCT_RTF_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0045 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PROJECTED_STOCK) | OW_APL_POALLOCATION.ODS_PROJECTED_STOCK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0109 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_RDD_HORIZON) | OW_APL_POALLOCATION.ODS_RDD_HORIZON | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0006 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALABLE_STORAGE_LOCATION) | OW_APL_POALLOCATION.ODS_SALABLE_STORAGE_LOCATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALES_MAPPING) | OW_APL_POALLOCATION.ODS_SALES_MAPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0009 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALES_ORDER) | OW_APL_POALLOCATION.ODS_SALES_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0111 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_CANCEL) | OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_CANCEL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0106 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_CREATE) | OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_CREATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0289 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_EDIT) | OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_EDIT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SHIP_COMPATIBILITY) | OW_APL_POALLOCATION.ODS_SHIP_COMPATIBILITY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SKU_CUBAGE_VOLUME) | OW_APL_POALLOCATION.ODS_SKU_CUBAGE_VOLUME | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0051 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_STOCK) | OW_APL_POALLOCATION.ODS_STOCK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_USER) | OW_APL_POALLOCATION.ODS_USER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_USER_LAST_PASSWORD) | OW_APL_POALLOCATION.ODS_USER_LAST_PASSWORD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_USER_PROFILE_ROLE) | OW_APL_POALLOCATION.ODS_USER_PROFILE_ROLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_USER_RESTRICT_ACCOUNTS) | OW_APL_POALLOCATION.ODS_USER_RESTRICT_ACCOUNTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_USER_RESTRICT_PROD_GROUPS) | OW_APL_POALLOCATION.ODS_USER_RESTRICT_PROD_GROUPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_VEHICLE_CAPACITY) | OW_APL_POALLOCATION.ODS_VEHICLE_CAPACITY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_WAREHOUSE_CAPACITY) | OW_APL_POALLOCATION.ODS_WAREHOUSE_CAPACITY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_POALLOCATION.ODS_YOUR_REFERENCE_DATA) | OW_APL_POALLOCATION.ODS_YOUR_REFERENCE_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_ALLOWED_EMAIL) | OW_APL_TRUSTED_AUTH.TB_ALLOWED_EMAIL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_EMAIL_TOKEN) | OW_APL_TRUSTED_AUTH.TB_EMAIL_TOKEN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_EMAIL_VIEW_PATH) | OW_APL_TRUSTED_AUTH.TB_EMAIL_VIEW_PATH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_SYSTEM_CONFIG) | OW_APL_TRUSTED_AUTH.TB_SYSTEM_CONFIG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_SYSTEM_LOG) | OW_APL_TRUSTED_AUTH.TB_SYSTEM_LOG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_USER) | OW_APL_TRUSTED_AUTH.TB_USER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_USER_WRONG_PASSWORD_ENTRY) | OW_APL_TRUSTED_AUTH.TB_USER_WRONG_PASSWORD_ENTRY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 30/10 - 30/10
NERP |  | TABLE | (TABLE - OW_LAO.ADJ_RAW_NERP_ZRSDD6A310_DISPLAY_ESTORE_E2E_MONITORING_INFO) | OW_LAO.ADJ_RAW_NERP_ZRSDD6A310_DISPLAY_ESTORE_E2E_MONITORING_INFO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,089 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.ARIMA_RESULTS) | OW_LAO.ARIMA_RESULTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 30/10 - 30/10
NERP |  | TABLE | (TABLE - OW_LAO.AUX_NERP_ZRCOA20250_FORECAST_SALES_B2C_FILTER) | OW_LAO.AUX_NERP_ZRCOA20250_FORECAST_SALES_B2C_FILTER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.AUX_ODS_CRAWLING_AP1_REF_PRODUCT_DETAIL_DAILY) | OW_LAO.AUX_ODS_CRAWLING_AP1_REF_PRODUCT_DETAIL_DAILY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.BASE64) | OW_LAO.BASE64 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.BIZ_AREA_TESTE_TALEND) | OW_LAO.BIZ_AREA_TESTE_TALEND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.BIZ_AREA_TESTE_TALEND_V2) | OW_LAO.BIZ_AREA_TESTE_TALEND_V2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CONTROLE_JOB_SALES_ORDER_TRACKING) | OW_LAO.CONTROLE_JOB_SALES_ORDER_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CONTROLE_JOB_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.CONTROLE_JOB_ZLLEJ50090_OUTBOUND_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_BANNER_STEPS) | OW_LAO.CRAWLER_BANNER_STEPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_COMMENT_STEPS) | OW_LAO.CRAWLER_COMMENT_STEPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_NEWS_DATA) | OW_LAO.CRAWLER_NEWS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_NEWS_STEPS) | OW_LAO.CRAWLER_NEWS_STEPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_NEWS_URLS) | OW_LAO.CRAWLER_NEWS_URLS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_PARAMETER_SCHEDULE) | OW_LAO.CRAWLER_PARAMETER_SCHEDULE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_PRODUCT_PRICE_STEPS) | OW_LAO.CRAWLER_PRODUCT_PRICE_STEPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_PRODUCT_SPECS_STEPS) | OW_LAO.CRAWLER_PRODUCT_SPECS_STEPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.CRAWLER_SCHEDULE) | OW_LAO.CRAWLER_SCHEDULE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-30 | 2025-10-30 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [11 empty] | 30/10 - 30/10
|  | TABLE | (TABLE - OW_LAO.DELETE_TO_REF) | OW_LAO.DELETE_TO_REF | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0103 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.DELETE_TO_TV) | OW_LAO.DELETE_TO_TV | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0102 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.DELETE_TO_WM) | OW_LAO.DELETE_TO_WM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0093 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.LAO_FT_ORDER_OPERATION_LEAD_TIME) | OW_LAO.LAO_FT_ORDER_OPERATION_LEAD_TIME | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0013 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.LAO_ONLINE_PRICE_LOG) | OW_LAO.LAO_ONLINE_PRICE_LOG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0149 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.LAO_ONLINE_PRICE_STORE_REF) | OW_LAO.LAO_ONLINE_PRICE_STORE_REF | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.LAO_SALES_DEDUCTION_WEEK_REPORT_DATA) | OW_LAO.LAO_SALES_DEDUCTION_WEEK_REPORT_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.LAO_SALES_DEDUCTION_WEEK_REPORT_DATA_TESTE_PENTAHO) | OW_LAO.LAO_SALES_DEDUCTION_WEEK_REPORT_DATA_TESTE_PENTAHO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.MP_COUNTRY) | OW_LAO.MP_COUNTRY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.MP_EMAIL) | OW_LAO.MP_EMAIL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.MP_ESTORE) | OW_LAO.MP_ESTORE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.MP_EVENTS) | OW_LAO.MP_EVENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.MP_MEDIA) | OW_LAO.MP_MEDIA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0006 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.MP_MEDIA_SCRAPING) | OW_LAO.MP_MEDIA_SCRAPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.MP_NEWSROOM) | OW_LAO.MP_NEWSROOM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0022 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.MP_SNS) | OW_LAO.MP_SNS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.MP_VALIDATION_CRAWLING_AP1_PRODUCT_DAILY_PRICE) | OW_LAO.MP_VALIDATION_CRAWLING_AP1_PRODUCT_DAILY_PRICE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.ODS_ITAU_BALLOON_REFUND_INFO) | OW_LAO.ODS_ITAU_BALLOON_REFUND_INFO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0008 | ODS | 0 | [11 empty] | 31/10 - 31/10
LINKAPI |  | TABLE | (TABLE - OW_LAO.ODS_LINKAPI_REPORT) | OW_LAO.ODS_LINKAPI_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0057 | ODS | 0 | [11 empty] | 31/10 - 31/10
LINKAPI |  | TABLE | (TABLE - OW_LAO.ODS_LINKAPI_REVERSE_REFUND_TRACKING) | OW_LAO.ODS_LINKAPI_REVERSE_REFUND_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0038 | ODS | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.ODS_MKP_REPORT_VIA_VAREJO) | OW_LAO.ODS_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0127 | ODS | 0 | [11 empty] | 31/10 - 31/10
PMS |  | TABLE | (TABLE - OW_LAO.ODS_PMS_PRICE_SIMULATION) | OW_LAO.ODS_PMS_PRICE_SIMULATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0203 | ODS | 0 | [11 empty] | 31/10 - 31/10
PMS |  | TABLE | (TABLE - OW_LAO.ODS_PMS_PROMOTION) | OW_LAO.ODS_PMS_PROMOTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0296 | ODS | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.ODS_SNS_DL) | OW_LAO.ODS_SNS_DL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,1026 | ODS | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.PAL_ARIMA_DATA_TBL) | OW_LAO.PAL_ARIMA_DATA_TBL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.RAW_DATA_LAO_MEDALLIA_EXPRESS_REPORT) | OW_LAO.RAW_DATA_LAO_MEDALLIA_EXPRESS_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0734 | RAW | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.RAW_DATA_VOUCHER) | OW_LAO.RAW_DATA_VOUCHER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0038 | RAW | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT) | OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,9447 | RAW | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT_CLEAN) | OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT_CLEAN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,6855 | RAW | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT_PIVOT) | OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0052 | RAW | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.RAW_TALEND_GUIDE_DATA) | OW_LAO.RAW_TALEND_GUIDE_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | RAW | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.RAW_TALEND_GUIDE_FILE_REGISTRATION) | OW_LAO.RAW_TALEND_GUIDE_FILE_REGISTRATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | RAW | 0 | [11 empty] | 31/10 - 31/10
Visuar |  | TABLE | (TABLE - OW_LAO.STG_ORDERS_VISUAR) | OW_LAO.STG_ORDERS_VISUAR | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.TEMPLATETABLE) | OW_LAO.TEMPLATETABLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.TEMP_ACCESS_CODE_PARTNER_LEVEL_SMB_1) | OW_LAO.TEMP_ACCESS_CODE_PARTNER_LEVEL_SMB_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.TEMP_DIM_MAPPING) | OW_LAO.TEMP_DIM_MAPPING | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST) | OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,1322 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST_SSGBR) | OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST_SSGBR | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,1274 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST_V1) | OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST_V1 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,1322 | OTHER | 0 | [11 empty] | 31/10 - 31/10
| ControlTower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MX) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MX | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | OTHER | 0 | [11 empty] | 31/10 - 31/10
NERP | ControlTower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_1) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_1 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | OTHER | 0 | [11 empty] | 31/10 - 31/10
NERP | ControlTower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_FILTER_1) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_FILTER_1 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.TEMP_PARTNER_LEVEL_SMB_SEASA_1) | OW_LAO.TEMP_PARTNER_LEVEL_SMB_SEASA_1 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [11 empty] | 31/10 - 31/10
NERP |  | TABLE | (TABLE - OW_LAO.TEMP_PRD_NERP) | OW_LAO.TEMP_PRD_NERP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,001 | OTHER | 0 | [11 empty] | 31/10 - 31/10
NERP |  | TABLE | (TABLE - OW_LAO.TEMP_PRD_NERP_1) | OW_LAO.TEMP_PRD_NERP_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0011 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.TESTE_TMP_VALIDATION_IM_PT2) | OW_LAO.TESTE_TMP_VALIDATION_IM_PT2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0128 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.TESTE_TMP_VALIDATION_IM_PT3) | OW_LAO.TESTE_TMP_VALIDATION_IM_PT3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0,0156 | OTHER | 0 | [11 empty] | 31/10 - 31/10
|  | TABLE | (TABLE - OW_LAO.TIME_SERIES_DATA) | OW_LAO.TIME_SERIES_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-10-31 | 2025-10-31 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [11 empty] | 31/10 - 31/10
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_CANCELLATIONS_DEDUP) | OW_LAO.TMP_HYBRIS_CANCELLATIONS_DEDUP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | TMP | 0 | [12 empty] | 03/11 - 03/11
HYBRIS |  | TABLE | (TABLE - OW_LAO.TMP_HYBRIS_TRADEIN_DEDUP) | OW_LAO.TMP_HYBRIS_TRADEIN_DEDUP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | TMP | 0 | [12 empty] | 03/11 - 03/11
LINKAPI |  | TABLE | (TABLE - OW_LAO.TMP_LINKAPI_REVERSE_REFUND_TRACKING) | OW_LAO.TMP_LINKAPI_REVERSE_REFUND_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0 | TMP | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_LAO.TMP_MEDALLIA_EXPRESS_REPORT) | OW_LAO.TMP_MEDALLIA_EXPRESS_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0014 | TMP | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_LAO.TMP_MKP_REPORT_VIA_VAREJO) | OW_LAO.TMP_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0009 | TMP | 0 | [12 empty] | 03/11 - 03/11
| ControlTower | TABLE | (TABLE - OW_LAO.TMP_PO_QTY_CONTROL_TOWER) | OW_LAO.TMP_PO_QTY_CONTROL_TOWER | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | TMP | 0 | [12 empty] | 03/11 - 03/11
Visuar |  | TABLE | (TABLE - OW_LAO.TMP_PROC_ODS_ORDERS_VISUAR) | OW_LAO.TMP_PROC_ODS_ORDERS_VISUAR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0016 | TMP | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_LAO_SSC_HR.TB_LABOR_COST) | OW_LAO_SSC_HR.TB_LABOR_COST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_LAO_SSC_HR.TB_LABOR_COST_teste2) | OW_LAO_SSC_HR.TB_LABOR_COST_teste2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_MD.COGS_TMP) | OW_MD.COGS_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_MD.MASTER_TRADE_POLICIES_TMP) | OW_MD.MASTER_TRADE_POLICIES_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_MD.ODS_ERP_MD_CUSTOMER) | OW_MD.ODS_ERP_MD_CUSTOMER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0713 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_MD.RAW_JENKINS_API_REST_PROJECTS) | OW_MD.RAW_JENKINS_API_REST_PROJECTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | RAW | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_MD.REBATE_TMP) | OW_MD.REBATE_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_MD.TARGET_LAUNCH) | OW_MD.TARGET_LAUNCH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_MD.TEMP_INPUT_SALES_CHANNELS_DEDUP) | OW_MD.TEMP_INPUT_SALES_CHANNELS_DEDUP | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.LOG_SDSLA_APAGA_ARQUIVOS) | OW_SDSLA.LOG_SDSLA_APAGA_ARQUIVOS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0102 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_CATALOG_TABLE_COLUMNS_INFO) | OW_SDSLA.ODS_CATALOG_TABLE_COLUMNS_INFO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0007 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_CATALOG_TABLE_INFO) | OW_SDSLA.ODS_CATALOG_TABLE_INFO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0019 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_CATALOG_VIEW_INFO) | OW_SDSLA.ODS_CATALOG_VIEW_INFO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_LISTA_DESLIGADOS) | OW_SDSLA.ODS_LISTA_DESLIGADOS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_BI_ITVOC_MONTHY_REPORT) | OW_SDSLA.ODS_SDSLA_BI_ITVOC_MONTHY_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ACCESS_PER_PROJECT) | OW_SDSLA.ODS_SDSLA_TABLE_ACCESS_PER_PROJECT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,003 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_PROJECTS) | OW_SDSLA.ODS_SDSLA_TABLE_ALL_PROJECTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLE_HIST_ACCESS_VIEW) | OW_SDSLA.ODS_SDSLA_TABLE_HIST_ACCESS_VIEW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0033 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLE_WORKBOOKS_TO_COMPARE) | OW_SDSLA.ODS_SDSLA_TABLE_WORKBOOKS_TO_COMPARE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SDSLA.RAW_DATA_SDSLA_BI_ITVOC_MONTHY_REPORT) | OW_SDSLA.RAW_DATA_SDSLA_BI_ITVOC_MONTHY_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | RAW | 0 | [12 empty] | 03/11 - 03/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.API_GSCM_PSI) | OW_SEDA_S.API_GSCM_PSI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.BI_TRACKING) | OW_SEDA_S.BI_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0642 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.DSM_EDI_TEMP) | OW_SEDA_S.DSM_EDI_TEMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0373 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.DS_CE_MBO) | OW_SEDA_S.DS_CE_MBO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.NPC_CHANNEL_PSI) | OW_SEDA_S.NPC_CHANNEL_PSI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0059 | OTHER | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ALIANCA_TIMETABLE) | OW_SEDA_S.ODS_ALIANCA_TIMETABLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_B2W_REALTIME_IMEI) | OW_SEDA_S.ODS_B2W_REALTIME_IMEI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_B2W_REALTIME_SALES) | OW_SEDA_S.ODS_B2W_REALTIME_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_B2W_REALTIME_STOCK) | OW_SEDA_S.ODS_B2W_REALTIME_STOCK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ESTORE_VISIBILITY_KPI_ORDER_OPERATION_LEAD_TIME) | OW_SEDA_S.ODS_ESTORE_VISIBILITY_KPI_ORDER_OPERATION_LEAD_TIME | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0012 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_GERPAM_WFCHANGE_SOREPORT) | OW_SEDA_S.ODS_GERPAM_WFCHANGE_SOREPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0328 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_GLP_PL) | OW_SEDA_S.ODS_GLP_PL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0073 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_MONTHLY) | OW_SEDA_S.ODS_GLP_RETURN_RATIO_MONTHLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0367 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_GSPN_PARTS_RETURN_UPC_GR_PERFORMANCE) | OW_SEDA_S.ODS_GSPN_PARTS_RETURN_UPC_GR_PERFORMANCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,1035 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_GSPN_PARTS_RETURN_UPC_STOCK_TRANSFER) | OW_SEDA_S.ODS_GSPN_PARTS_RETURN_UPC_STOCK_TRANSFER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0088 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_HR_COMPLETE_BASE_RPA) | OW_SEDA_S.ODS_HR_COMPLETE_BASE_RPA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,001 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_INCENTIVES_POINT_REFERENCE) | OW_SEDA_S.ODS_INCENTIVES_POINT_REFERENCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_INVENTORY_CONSISTENCY) | OW_SEDA_S.ODS_INVENTORY_CONSISTENCY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE) | OW_SEDA_S.ODS_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0112 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_MKP_REPORT_VIA_VAREJO) | OW_SEDA_S.ODS_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0155 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ONTIMEDELIVERY_RAWDATA_GLP) | OW_SEDA_S.ODS_ONTIMEDELIVERY_RAWDATA_GLP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-03 | 2025-11-03 | ['[]'] | 0 | Migrar ph 2 | 0,0321 | ODS | 0 | [12 empty] | 03/11 - 03/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ONTIMEGR_INBOUND_GLP) | OW_SEDA_S.ODS_ONTIMEGR_INBOUND_GLP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ONTIMEGR_INBOUND_GLP_NEW) | OW_SEDA_S.ODS_ONTIMEGR_INBOUND_GLP_NEW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_PRODUCT_TECHNICAL_INFO) | OW_SEDA_S.ODS_PRODUCT_TECHNICAL_INFO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ROBBERY_REPORT) | OW_SEDA_S.ODS_ROBBERY_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,001 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_RP_DOA_AEN_NF_Migrar ph 2) | OW_SEDA_S.ODS_RP_DOA_AEN_NF_Migrarph2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0877 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_RP_DOA_RDO_CREATE_STATUS) | OW_SEDA_S.ODS_RP_DOA_RDO_CREATE_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,1065 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_RP_ETR_ASC_MASTER) | OW_SEDA_S.ODS_RP_ETR_ASC_MASTER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0023 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SAMPLE_MANAGEMENT_BASE_VPS) | OW_SEDA_S.ODS_SAMPLE_MANAGEMENT_BASE_VPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SAMPLE_MANAGEMENT_WH_CODE_DE_PARA) | OW_SEDA_S.ODS_SAMPLE_MANAGEMENT_WH_CODE_DE_PARA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0 | ODS | 0 | [12 empty] | 04/11 - 04/11
OMNITRACKING |  | TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_API_OMNITRACKING_AUX) | OW_SEDA_S.ODS_SEDA_API_OMNITRACKING_AUX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0 | ODS | 0 | [12 empty] | 04/11 - 04/11
OMNITRACKING |  | TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_API_OMNITRACKING_AUX_REPROCESS) | OW_SEDA_S.ODS_SEDA_API_OMNITRACKING_AUX_REPROCESS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_WH_UNLOADING_YMS) | OW_SEDA_S.ODS_WH_UNLOADING_YMS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0114 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.PDI_LOG_INFO) | OW_SEDA_S.PDI_LOG_INFO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0179 | OTHER | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.RAW_AGNES_ADJ_BRSHOP_VIA_ADMIN_15_07_2024) | OW_SEDA_S.RAW_AGNES_ADJ_BRSHOP_VIA_ADMIN_15_07_2024 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0 | RAW | 0 | [12 empty] | 04/11 - 04/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_BREA) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_BREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0 | RAW | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.RAW_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE) | OW_SEDA_S.RAW_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0013 | RAW | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.RAW_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE_PIVOT) | OW_SEDA_S.RAW_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0033 | RAW | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.SALES_DEDUCTION_SERVICE_VALIDATION) | OW_SEDA_S.SALES_DEDUCTION_SERVICE_VALIDATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | OTHER | 0 | [12 empty] | 04/11 - 04/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ST_SDI_CELLO_STAGE) | OW_SEDA_S.ST_SDI_CELLO_STAGE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0072 | OTHER | 0 | [12 empty] | 04/11 - 04/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.TF_BI_CELLO_IOD_TOTAL_PRE1) | OW_SEDA_S.TF_BI_CELLO_IOD_TOTAL_PRE1 | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,5947 | TF | 0 | [12 empty] | 04/11 - 04/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.TF_BI_CELLO_IOD_TOTAL_PRE2) | OW_SEDA_S.TF_BI_CELLO_IOD_TOTAL_PRE2 | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,6088 | TF | 0 | [12 empty] | 04/11 - 04/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_BI_CELLO_IOD_TOTAL) | OW_SEDA_S.TMP_BI_CELLO_IOD_TOTAL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0544 | TMP | 0 | [12 empty] | 04/11 - 04/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_MKP) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_MKP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0066 | TMP | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MKP_REPORT_VIA_VAREJO) | OW_SEDA_S.TMP_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | TMP | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_ODS_GENERIC_INPUT_2) | OW_SEDA_S.TMP_ODS_GENERIC_INPUT_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0507 | TMP | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_ODS_GENERIC_INPUT_R) | OW_SEDA_S.TMP_ODS_GENERIC_INPUT_R | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0034 | TMP | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_ODS_GENERIC_INPUT_R2) | OW_SEDA_S.TMP_ODS_GENERIC_INPUT_R2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0006 | TMP | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_RP_ETR_ASC_MASTER) | OW_SEDA_S.TMP_RP_ETR_ASC_MASTER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0022 | TMP | 0 | [12 empty] | 04/11 - 04/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_API_AFTER_SALES_MKP) | OW_SEDA_S.TMP_SEDA_API_AFTER_SALES_MKP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,001 | TMP | 0 | [12 empty] | 04/11 - 04/11
OMNITRACKING |  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_API_OMNITRACKING) | OW_SEDA_S.TMP_SEDA_API_OMNITRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | TMP | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SURSIS_DELIVERY_DATA) | OW_SEDA_S.TMP_SURSIS_DELIVERY_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,011 | TMP | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SURSIS_ESCORT) | OW_SEDA_S.TMP_SURSIS_ESCORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0066 | TMP | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SURSIS_NC) | OW_SEDA_S.TMP_SURSIS_NC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0052 | TMP | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S.TR1_ORDER_OPERATION_OUTBOUND) | OW_SEDA_S.TR1_ORDER_OPERATION_OUTBOUND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0206 | OTHER | 0 | [12 empty] | 04/11 - 04/11
TrackingTrade |  | TABLE | (TABLE - OW_SEDA_S.VW_TT_AVARIAS_MARCO_ZERO_VM) | OW_SEDA_S.VW_TT_AVARIAS_MARCO_ZERO_VM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | OTHER | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_MAPA_IMPORTACAO_SVC_ITEM) | OW_SEDA_S_COMEX.ODS_CMX_MAPA_IMPORTACAO_SVC_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,001 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_RELATORIO_DARE_CST) | OW_SEDA_S_COMEX.ODS_CMX_RELATORIO_DARE_CST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_VARIACAO_PRECO_CST) | OW_SEDA_S_COMEX.ODS_CMX_VARIACAO_PRECO_CST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_VOLUME_IMPORTADO_CST) | OW_SEDA_S_COMEX.ODS_CMX_VOLUME_IMPORTADO_CST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SELA.DIM_CALENDAR) | OW_SELA.DIM_CALENDAR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | DIM | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SELA.DIM_MN) | OW_SELA.DIM_MN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | DIM | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SELA.DIM_RESELLER) | OW_SELA.DIM_RESELLER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | DIM | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - OW_SELA.STAGE_FACT_STOCK_SALES) | OW_SELA.STAGE_FACT_STOCK_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [12 empty] | 04/11 - 04/11
Cello | CelloLogistic | TABLE | (TABLE - U_PRJ_ECOM.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE) | U_PRJ_ECOM.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [12 empty] | 04/11 - 04/11
Cello | CelloLogistic | TABLE | (TABLE - U_PRJ_ECOM.AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS) | U_PRJ_ECOM.AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | OTHER | 0 | [12 empty] | 04/11 - 04/11
YAMI |  | TABLE | (TABLE - U_PRJ_ECOM.AUX_YAMI_PRODUCT_DETAIL_STATUS) | U_PRJ_ECOM.AUX_YAMI_PRODUCT_DETAIL_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_JOB_HISTORY) | U_PRJ_ECOM.BI_ECOM_JOB_HISTORY | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - U_PRJ_ECOM.CV_EPP_CONTROL) | U_PRJ_ECOM.CV_EPP_CONTROL | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-04 | 2025-11-04 | ['[]'] | 0 | Migrar ph 2 | 0,0039 | OTHER | 0 | [12 empty] | 04/11 - 04/11
|  | TABLE | (TABLE - U_PRJ_ECOM.CV_WOS_AND_STOCKOUT) | U_PRJ_ECOM.CV_WOS_AND_STOCKOUT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0064 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.DATE_DIM) | U_PRJ_ECOM.DATE_DIM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS) | U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS_TOTALS_TEMP) | U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS_TOTALS_TEMP | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS_UPDATE_TEMP) | U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS_UPDATE_TEMP | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ETL_PANAMA_ECOMMERCE_ORDERS) | U_PRJ_ECOM.ETL_PANAMA_ECOMMERCE_ORDERS | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ETL_PANAMA_ECOMMERCE_ORDERS_UPDATE_TEMP) | U_PRJ_ECOM.ETL_PANAMA_ECOMMERCE_ORDERS_UPDATE_TEMP | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ITEM_COMPONENT_TESTE) | U_PRJ_ECOM.ITEM_COMPONENT_TESTE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0396 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.LOG_PROCESSCONTROL_HMLG) | U_PRJ_ECOM.LOG_PROCESSCONTROL_HMLG | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.MONGO_VALIDATION) | U_PRJ_ECOM.MONGO_VALIDATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,1007 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_ASSERTH_CANCELLATION) | U_PRJ_ECOM.ODS_ASSERTH_CANCELLATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,002 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_D2C_ENTITY_ENDLESS_STORE_SSG_BR) | U_PRJ_ECOM.ODS_D2C_ENTITY_ENDLESS_STORE_SSG_BR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_D2C_ENTITY_ENDLESS_STORE_SSG_BR_SHOP) | U_PRJ_ECOM.ODS_D2C_ENTITY_ENDLESS_STORE_SSG_BR_SHOP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_CARREFOUR) | U_PRJ_ECOM.ODS_MKP_D2C_CARREFOUR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0037 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_CARREFOUR_LSPOSITO) | U_PRJ_ECOM.ODS_MKP_D2C_CARREFOUR_LSPOSITO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_FASTSHOP_QUEUE) | U_PRJ_ECOM.ODS_MKP_D2C_FASTSHOP_QUEUE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_LEROY) | U_PRJ_ECOM.ODS_MKP_D2C_LEROY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,001 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_MAGALU) | U_PRJ_ECOM.ODS_MKP_D2C_MAGALU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0171 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_MELI) | U_PRJ_ECOM.ODS_MKP_D2C_MELI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,001 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_MELI_2) | U_PRJ_ECOM.ODS_MKP_D2C_MELI_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_VIA) | U_PRJ_ECOM.ODS_MKP_D2C_VIA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0236 | ODS | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ORDERS_MISSING) | U_PRJ_ECOM.ORDERS_MISSING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.PACKAGE_TESTE) | U_PRJ_ECOM.PACKAGE_TESTE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,2108 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RATES_AND_BENEFITS_TESTE) | U_PRJ_ECOM.RATES_AND_BENEFITS_TESTE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0327 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_CTV_SSG) | U_PRJ_ECOM.RAW_CTV_SSG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | RAW | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_CHANNEL_GROUPING) | U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_CHANNEL_GROUPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | RAW | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_CHANNEL_GROUPING_DAY) | U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_CHANNEL_GROUPING_DAY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | RAW | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_DEVICE) | U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_DEVICE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | RAW | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_DEVICE_DAY) | U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_DEVICE_DAY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | RAW | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_CHANNEL_GROUPING) | U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_CHANNEL_GROUPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | RAW | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_DEVICE_DAY) | U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_DEVICE_DAY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | RAW | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_SAMSUNGBRSHOP_PAYMENT) | U_PRJ_ECOM.RAW_SAMSUNGBRSHOP_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,3675 | RAW | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_SAMSUNGBR_PAYMENT) | U_PRJ_ECOM.RAW_SAMSUNGBR_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,1036 | RAW | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_SAP_SSG_ECOM_ZRMMB34070) | U_PRJ_ECOM.RAW_SAP_SSG_ECOM_ZRMMB34070 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0027 | RAW | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.SEASA_ORDERS_GAP) | U_PRJ_ECOM.SEASA_ORDERS_GAP | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.SHIPPING_TESTE) | U_PRJ_ECOM.SHIPPING_TESTE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,2462 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.STG_CT_O2O_SEASA) | U_PRJ_ECOM.STG_CT_O2O_SEASA | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.STG_MGLU_ORDER_ITEM) | U_PRJ_ECOM.STG_MGLU_ORDER_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0042 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.STG_MGLU_ORDER_PAYMENT) | U_PRJ_ECOM.STG_MGLU_ORDER_PAYMENT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,002 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TABELA_DETALHES) | U_PRJ_ECOM.TABELA_DETALHES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TEMP_DIM_UNIQUE_ID) | U_PRJ_ECOM.TEMP_DIM_UNIQUE_ID | LAO EStore | r.bojart |  | yes | 2 | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0133 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TEMP_ORDERS_CODE_FEED) | U_PRJ_ECOM.TEMP_ORDERS_CODE_FEED | LAO EStore | r.bojart |  | yes | 4 | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0506 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TEMP_SO) | U_PRJ_ECOM.TEMP_SO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_MKP_D2C_CARREFOUR) | U_PRJ_ECOM.TMP_MKP_D2C_CARREFOUR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0023 | TMP | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_MKP_D2C_MAGALU) | U_PRJ_ECOM.TMP_MKP_D2C_MAGALU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0171 | TMP | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_MKP_D2C_VIA) | U_PRJ_ECOM.TMP_MKP_D2C_VIA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | TMP | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_MKP_D2C_LEROY) | U_PRJ_ECOM.TMP_ODS_MKP_D2C_LEROY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0011 | TMP | 0 | [12 empty] | 05/11 - 05/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_MKP_D2C_MELI) | U_PRJ_ECOM.TMP_ODS_MKP_D2C_MELI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-05 | 2025-11-05 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | TMP | 0 | [12 empty] | 05/11 - 05/11
LINKAPI |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_ORDER_ALERT_ORDER_ID_LINKAPI) | U_PRJ_ECOM.TMP_ORDER_ALERT_ORDER_ID_LINKAPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 0 | Migrar ph 2 | 0 | TMP | 0 | [12 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TST_SEASA_LIST) | U_PRJ_ECOM.TST_SEASA_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | OTHER | 0 | [12 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - U_PRJ_ECOM.TST_SEDA_LIST) | U_PRJ_ECOM.TST_SEDA_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 0 | Migrar ph 2 | 0,0021 | OTHER | 0 | [12 empty] | 06/11 - 06/11
| ControlTower | TABLE | (TABLE - U_PRJ_ECOM.VALID_SEND_CONTROL_TOWER) | U_PRJ_ECOM.VALID_SEND_CONTROL_TOWER | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 0 | Migrar ph 2 | 0,0468 | OTHER | 0 | [12 empty] | 06/11 - 06/11
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.VTEX_SSG_AR_SMB_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.VTEX_SSG_AR_SMB_RATES_AND_BENEFITS_DATA | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | OTHER | 0 | [12 empty] | 06/11 - 06/11
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 0 | Migrar ph 2 | 0 | OTHER | 0 | [12 empty] | 06/11 - 06/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_TRACKING) | OW_SEDA_S.CELLO_TRACKING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 61647 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(FUNCTION - OW_SEDA_S.FN_GET_CELLO_EVENT),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING_AUX),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING)] | [11 empty] | 06/11 - 06/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY) | OW_SEDA_S.CELLO_DELIVERY | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 11931 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP_TEST),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING_AUX),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD)] | [11 empty] | 06/11 - 06/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND) | OW_SEDA_S.CELLO_DELIVERY_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,1417 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING)] | [11 empty] | 06/11 - 06/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM) | OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,091 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING)] | [11 empty] | 06/11 - 06/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM) | OW_SEDA_S.CELLO_DELIVERY_ITEM | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,5672 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228)] | [11 empty] | 06/11 - 06/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING) | OW_SEDA_S.CELLO_FUTHER_PROCESSING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0986 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING)] | [11 empty] | 06/11 - 06/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS) | OW_LAO.ODS_GSCM_PREMIUM_MODELS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0455 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_ODS_LAO_PREMIUM_PRODUCTS_TABLE_FROM_GSCM_UPDATE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI),(PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_KPI)] | [11 empty] | 06/11 - 06/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND) | OW_SEDA_S.CELLO_MANIFEST_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0514 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228)] | [11 empty] | 06/11 - 06/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND) | OW_SEDA_S.CELLO_SHIPMENT_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0559 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION)] | [11 empty] | 06/11 - 06/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL) | OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 12948 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | [11 empty] | 06/11 - 06/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS) | OW_SEDA_S.SDI_TSS_TC_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,4706 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W) | OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0125 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W)] | [11 empty] | 06/11 - 06/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND) | OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,3142 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_GSCM_INVENTORY),(INGESTION - JOB.RAW_DATA_GSCM_ACTUAL_ON_HAND),(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI),(PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO),(PROCEDURE - OW_LAO.PROC_D2C_NERP_INVENTORY)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA) | OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0013 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO) | OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 31078 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING) | OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0002 | FT | 0 | [(PROCEDURE - OW_LAO.UPDATE_SALES_WEEKLY_MONITORING),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_MONITORING_STATUS),(VIEW - OW_LAO.VW_LAO_SALES_DEDUCTION_DAILY_MONITORING_MAPPING_STATUS),(PROCEDURE - OW_LAO.PROC_ATU_LAO_SALES_DEDUCTION_MONITORING_STATUS_HIST)] | [11 empty] | 06/11 - 06/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY) | OW_LAO.ODS_GSCM_AP1_ACCURACY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0173 | ODS | 0 | [(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(INGESTION - JOB.ODS_GSCM_AP1_ACCURACY),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW)] | [11 empty] | 06/11 - 06/11
PLUGGTO |  | TABLE | (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER) | OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,2784 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO),(INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY) | OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0123 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY)] | [11 empty] | 06/11 - 06/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_PICKING_PACKING) | OW_SEDA_S.ODS_WMS_PICKING_PACKING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0925 | ODS | 0 | [(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(INGESTION - JOB.ODS_WMS_PICKING_PACKING),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_EXCEPTION) | OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0001 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION)] | [11 empty] | 06/11 - 06/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_CE_SELL_OUT) | OW_LAO.ODS_GSCM_CE_SELL_OUT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,2705 | RAW | 0 | [(INGESTION - JOB.RAW_GSCM_CE_SELL_OUT),(INGESTION - JOB.ODS_GSCM_CE_SELL_OUT)] | [11 empty] | 06/11 - 06/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_FCST_MGMT_D2C) | OW_LAO.ODS_GSCM_FCST_MGMT_D2C | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 3995 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS),(INGESTION - JOB.ODS_GSCM_FCST_MGMT_D2C)] | [11 empty] | 06/11 - 06/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_MX_SELL_OUT) | OW_LAO.ODS_GSCM_MX_SELL_OUT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,4139 | RAW | 0 | [(INGESTION - JOB.RAW_GSCM_MX_SELL_OUT),(INGESTION - JOB.ODS_GSCM_MX_SELL_OUT)] | [11 empty] | 06/11 - 06/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_ABNORMAL_INVENTORY) | OW_SEDA_S.ODS_WMS_ABNORMAL_INVENTORY | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,3011 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_ABNORMAL_INVENTORY),(INGESTION - JOB.ODS_WMS_ABNORMAL_INVENTORY)] | [11 empty] | 06/11 - 06/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD) | OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,015 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SDU_ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD),(INGESTION - JOB.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY) | OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0008 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY)] | [11 empty] | 06/11 - 06/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_CE_SELL_OUT) | OW_LAO.RAW_GSCM_CE_SELL_OUT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,2705 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] | [11 empty] | 06/11 - 06/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_MX_SELL_OUT) | OW_LAO.RAW_GSCM_MX_SELL_OUT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,4139 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_03) | OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_03 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0003 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_04) | OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_04 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0031 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_05) | OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_05 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0036 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [11 empty] | 06/11 - 06/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD) | OW_SEDA_S.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0159 | ODS | 0 | [(INGESTION - JOB.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD)] | [11 empty] | 06/11 - 06/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_MAO) | OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_MAO | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,1685 | ODS | 0 | [(INGESTION - JOB.ODS_WMS_GATE_DOCK_IN_MAO)] | [11 empty] | 06/11 - 06/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_YMS_GATE_DOCK_IN_CAJ) | OW_SEDA_S.ODS_WMS_YMS_GATE_DOCK_IN_CAJ | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0262 | ODS | 0 | [(INGESTION - JOB.ODS_WMS_YMS_GATE_DOCK_IN_CAJ)] | [11 empty] | 06/11 - 06/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_ORDER_OCCURRENCE_RPT) | OW_SEDA_S.SDI_TSS_TC_ORDER_OCCURRENCE_RPT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0208 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE)] | [11 empty] | 06/11 - 06/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_RETURN_BOOKING_REQUEST) | OW_SEDA_S.SDI_TSS_TC_RETURN_BOOKING_REQUEST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0085 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | [11 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_V2) | OW_LAO.FT_LAO_SALES_DEDUCTION_V2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0135 | FT | 0 | [12 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_V3) | OW_LAO.FT_LAO_SALES_DEDUCTION_V3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0119 | FT | 0 | [12 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_VALIDATION_DATA_REPORT) | OW_LAO.FT_LAO_SALES_DEDUCTION_VALIDATION_DATA_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0001 | FT | 0 | [12 empty] | 06/11 - 06/11
|  | TABLE | (TABLE - OW_LAO.RAW_DATA_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC) | OW_LAO.RAW_DATA_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0,0003 | RAW | 0 | [12 empty] | 06/11 - 06/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_ACTUAL_SALES_PIVOT_TABLE) | OW_LAO.RAW_GSCM_ACTUAL_SALES_PIVOT_TABLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-06 | 2025-11-06 | ['[]'] | 1 | Migrar ph2 | 0 | RAW | 0 | [12 empty] | 06/11 - 06/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_AP1_ACCURACY) | OW_LAO.RAW_GSCM_AP1_ACCURACY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,057 | RAW | 0 | [12 empty] | 07/11 - 07/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0005 | RAW | 0 | [12 empty] | 07/11 - 07/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,1428 | RAW | 0 | [12 empty] | 07/11 - 07/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 22537 | RAW | 0 | [12 empty] | 07/11 - 07/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_6W_10W) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_6W_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 3,12 | RAW | 0 | [12 empty] | 07/11 - 07/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_FOTA) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 22938 | RAW | 0 | [12 empty] | 07/11 - 07/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_ORDER_OPERATION) | OW_SEDA_S.FT_ORDER_OPERATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0422 | FT | 0 | [12 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_SDI2) | OW_SEDA_S.FT_TSS_BI_TRACKING_SDI2 | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0022 | FT | 0 | [12 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_ESCORT_SERVICE_MNG) | OW_SEDA_S.FT_TSS_ESCORT_SERVICE_MNG | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0366 | FT | 0 | [12 empty] | 07/11 - 07/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_GI) | OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_GI | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0118 | ODS | 0 | [12 empty] | 07/11 - 07/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_INQUIRY_SPARE_PARTS) | OW_SEDA_S.ODS_WMS_INQUIRY_SPARE_PARTS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0068 | ODS | 0 | [12 empty] | 07/11 - 07/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_JASPER_CANCELATION) | OW_SEDA_S.ODS_WMS_JASPER_CANCELATION | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0029 | ODS | 0 | [12 empty] | 07/11 - 07/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_SPARE_PARTS_WH_CONSOLIDATE) | OW_SEDA_S.ODS_WMS_SPARE_PARTS_WH_CONSOLIDATE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0091 | ODS | 0 | [12 empty] | 07/11 - 07/11
WMS |  | TABLE | (TABLE - OW_SEDA_S.ODS_WMS_SPARE_PARTS_WH_DAILY) | OW_SEDA_S.ODS_WMS_SPARE_PARTS_WH_DAILY | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0749 | ODS | 0 | [12 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_BIG_AREA) | OW_SEDA_S.SDI_TSS_M_BIG_AREA | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0003 | OTHER | 0 | [12 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_BOD) | OW_SEDA_S.SDI_TSS_M_BOD | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0013 | OTHER | 0 | [12 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_SCHEDULE_ORDER) | OW_SEDA_S.SDI_TSS_TC_SCHEDULE_ORDER | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 1 | Migrar ph2 | 0,0005 | OTHER | 0 | [12 empty] | 07/11 - 07/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_PRODUCTS) | OW_SEDA_S.MAP_CE_PRODUCTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0114 | MAP | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA),(VIEW - OW_SEDA_S.VW_MX_SALES_VS_RTF),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY),(INGESTION - JOB.MAP_CE_PRODUCTS),(VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR),(VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI),(VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022),(VIEW - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_TARGET_WEEK_ADJ),(VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX),(PROCEDURE - OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_TT_GABARITO_Migrar ph 2LIST_EXECUCAO_785),(PROCEDURE - OW_SEDA_S.PRC_TT_GABARITO_Migrar ph 2LIST_EXECUCAO),(PROCEDURE - OW_SEDA_S.PRC_CE_MANAGEMENT_INFORMATION),(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK),(VIEW - OW_SEDA_S.VW_CE_META_PROMOTOR),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL),(VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING),(VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE),(PROCEDURE - OW_SEDA_S.PRC_STOCK_OUT_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_DEAD_SKU_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_CE),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MON),(PROCEDURE - OW_SEDA_S.PRC_VC_UPDATE_READY),(PROCEDURE - OW_SEDA_S.PRC_UPDATE_PIN_TO_PIN),(PROCEDURE - OW_SEDA_S.PRC_TV_UPDT_INCH_RANGE),(VIEW - OW_SEDA_S.VW_TT_RUPTURA),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2),(VIEW - OW_SEDA_S.VW_CE_MANAGEMENT_INFORMATION),(VIEW - OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_MX_SALES_VS_RTF_BY_CAPACITY),(PROCEDURE - OW_SEDA_S.PRC_VD_SALES_REVENUE),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS) | OW_SEDA_S.ODS_TSS_M_TRANS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0013 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP)] | [11 empty] | 07/11 - 07/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST) | OW_SEDA_S.CELLO_LAST_LEG_MANIFEST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0165 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst)] | [11 empty] | 07/11 - 07/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_SHIPMENT) | OW_SEDA_S.CELLO_SHIPMENT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,3717 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_CODE) | OW_SEDA_S.ODS_TSS_M_CODE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0009 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FNS_NM2),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION) | OW_SEDA_S.ODS_TSS_M_LOCATION | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0213 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI_v2),(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO)] | [11 empty] | 07/11 - 07/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_MANIFEST) | OW_SEDA_S.CELLO_MANIFEST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,4365 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION) | OW_SEDA_S.ODS_TSS_M_DIVISION | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0002 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP)] | [11 empty] | 07/11 - 07/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_BOOKING) | OW_SEDA_S.CELLO_BOOKING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,7439 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP)] | [11 empty] | 07/11 - 07/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_POD) | OW_SEDA_S.CELLO_POD | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0362 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_ITEM) | OW_SEDA_S.ODS_TSS_M_ITEM | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0206 | ODS | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP) | OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0006 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO),(FUNCTION - OW_SEDA_S.FNS_NM1)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA) | OW_SEDA_S.ODS_TSS_M_MID_AREA | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(FUNCTION - OW_SEDA_S.FNS_NM1)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS) | OW_SEDA_S.SDI_TSS_OD_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,3391 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_UNION_CELLO_TSS_IOD_STATUS)] | [11 empty] | 07/11 - 07/11
|  | TABLE | (TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION) | OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0001 | INPUT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_MONITORING_STATUS),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION)] | [11 empty] | 07/11 - 07/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION) | OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0272 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO),(VIEW - OW_SEDA_S.VW_SELLOUTGERAL),(VIEW - OW_SEDA_S.VW_WALMART),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL),(VIEW - OW_SEDA_S.VW_GSCM_CH_PSI_WARING_SALES_DEDUCTION),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_VALIDATION),(VIEW - OW_SEDA_S.VW_ONLINE_FISICO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_JULIAO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_JULIAO)] | [11 empty] | 07/11 - 07/11
|  | TABLE | (TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION) | OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0006 | INPUT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION)] | [11 empty] | 07/11 - 07/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_CALENDAR) | OW_SEDA_S.MAP_CE_CALENDAR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0003 | MAP | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK),(VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST),(PROCEDURE - OW_SEDA_S.PRC_VD_SALES_REVENUE),(PROCEDURE - OW_SEDA_S.PRC_DEAD_SKU_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT),(VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE),(PROCEDURE - OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION),(VIEW - OW_SEDA_S.VW_CE_META_PROMOTOR),(PROCEDURE - OW_SEDA_S.PRC_STOCK_OUT_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION),(PROCEDURE - OW_LAO.PRC_ODS_LAO_GSCM_EDI_DATA)] | [11 empty] | 07/11 - 07/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS) | OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0006 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_JULIAO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_VALIDATION),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_JULIAO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_AREA) | OW_SEDA_S.ODS_TSS_M_AREA | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0005 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC) | OW_SEDA_S.SDI_TSS_RS_RESULT_LOC | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,3763 | OTHER | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | [11 empty] | 07/11 - 07/11
|  | TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA) | OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W)] | [11 empty] | 07/11 - 07/11
|  | TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES) | OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W)] | [11 empty] | 07/11 - 07/11
WebPrice |  | TABLE | (TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API) | OW_SEDA_S.ODS_CE_WEBPRICE_API | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 147161 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX_HIST_2),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_UPDT_RECENT_PRICE),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_CE),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MON),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST_2)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE) | OW_SEDA_S.SDI_TSS_TC_OCCURRENCE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,2479 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_STATUS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL) | OW_SEDA_S.SDI_TSS_TC_VESSEL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0007 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT) | OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,001 | OTHER | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL_DESTINATION_PORT)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS) | OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG) | OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,1402 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL) | OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,3079 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT) | OW_SEDA_S.SDI_TSS_RS_RESULT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-07 | 2025-11-07 | ['[]'] | 0 | Migrar ph2 | 0,2217 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI)] | [11 empty] | 07/11 - 07/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP) | OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0563 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS) | OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0095 | OTHER | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI)] | [12 empty] | 10/11 - 10/11
|  | TABLE | (TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS) | OW_LAO.MONITORING_EXECUTIONS_RESULTS | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0054 | OTHER | 0 | [(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_GENERATED),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_DEFAULT),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_TMC),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_JENKINS),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_PREPARE),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE)] | [12 empty] | 10/11 - 10/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_VESSEL) | OW_SEDA_S.CELLO_VESSEL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0156 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3)] | [12 empty] | 10/11 - 10/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_JOURNEY) | OW_SEDA_S.MAP_CE_JOURNEY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0117 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR),(INGESTION - JOB.MAP_CE_JOURNEY),(VIEW - OW_SEDA_S.VW_CE_JOURNEY_UNIQUE_MAX_WEEKNUM),(VIEW - OW_SEDA_S.VW_CE_JOURNEY_UNIQUE),(VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS),(VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING),(VIEW - OW_SEDA_S.VW_CE_JOURNEY_COORDINATORS_MAXWEEK)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION) | OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS) | OW_SEDA_S.SDI_TSS_NF_OD_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,3521 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC) | OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,1822 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE) | OW_SEDA_S.SDI_TSS_TC_EVENT_DATE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0733 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_DATE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS) | OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,6239 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI)] | [12 empty] | 10/11 - 10/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS) | OW_SEDA_S.FT_CHEIL_ANSWERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 16178 | FT | 0 | [(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_MX_POSITIVACAO_S24),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL)] | [12 empty] | 10/11 - 10/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES) | OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,288 | FT | 0 | [(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE),(VIEW - OW_SEDA_S.VW_MX_POSITIVACAO_S24),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL)] | [12 empty] | 10/11 - 10/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS) | OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0003 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_MX_POSITIVACAO_S24),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE)] | [12 empty] | 10/11 - 10/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_POS) | OW_SEDA_S.MAP_CHEIL_POS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0051 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_MX_POSITIVACAO_S24),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE) | OW_SEDA_S.ODS_TSS_M_AREA_TYPE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0004 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL) | OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0017 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP) | OW_SEDA_S.ODS_TSS_M_ITEM_GROUP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FNS_NM1)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING) | OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0005 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE) | OW_SEDA_S.ODS_TSS_M_RATE_SERVICE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0091 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM2)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING) | OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0033 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED) | OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,1166 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016)] | [12 empty] | 10/11 - 10/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_KAM) | OW_SEDA_S.MAP_CE_KAM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_MANAGEMENT_INFORMATION),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2),(PROCEDURE - OW_SEDA_S.PRC_CE_MANAGEMENT_INFORMATION),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI)] | [12 empty] | 10/11 - 10/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS) | OW_SEDA_S.MAP_CHEIL_COLLABORATORS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0003 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE)] | [12 empty] | 10/11 - 10/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS) | OW_SEDA_S.MAP_CHEIL_PRODUCTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0006 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE)] | [12 empty] | 10/11 - 10/11
WebPrice |  | TABLE | (TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO) | OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX_HIST_2),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST_2)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA) | OW_SEDA_S.ODS_TSS_M_BIG_AREA | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FN_GET_BOD2)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY) | OW_SEDA_S.ODS_TSS_M_COMPANY | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP) | OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE) | OW_SEDA_S.ODS_TSS_M_VEHICLE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0005 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2)] | [12 empty] | 10/11 - 10/11
WebPrice |  | TABLE | (TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX) | OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,2357 | RAW | 0 | [(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST_2),(INGESTION - JOB.RAW_MX_TMV_INDEX),(INGESTION - JOB.ODS_WEBPRICE_TRACKING_DAILY_MX),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG) | OW_SEDA_S.SDI_TSS_TC_EVENT_LOG | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 11263 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE_SDI)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING) | OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0774 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI)] | [12 empty] | 10/11 - 10/11
|  | TABLE | (TABLE - OW_LAO.MONITORING_EXECUTIONS) | OW_LAO.MONITORING_EXECUTIONS | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0002 | OTHER | 0 | [(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_POST_EXECUTION),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_GENERATED)] | [12 empty] | 10/11 - 10/11
|  | TABLE | (TABLE - OW_LAO.MONITORING_PARAMETERS) | OW_LAO.MONITORING_PARAMETERS | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_PREPARE),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_GENERATED),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS)] | [12 empty] | 10/11 - 10/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W) | OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,023 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION)] | [12 empty] | 10/11 - 10/11
GSCM |  | TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM) | OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0154 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_BOD) | OW_SEDA_S.ODS_TSS_M_BOD | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0013 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI_v2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT) | OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0012 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_CELLO_TSS_IOD_STATUS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI)] | [12 empty] | 10/11 - 10/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_CE_PRICE_STORE) | OW_SEDA_S.FT_CE_PRICE_STORE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,1279 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_TT_UPDT_FLOORSHARE),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(PROCEDURE - OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA)] | [12 empty] | 10/11 - 10/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_CE_SELL_IN_FCST) | OW_SEDA_S.FT_CE_SELL_IN_FCST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0024 | FT | 0 | [(VIEW - OW_SEDA_S.VW_SCM_SALES_AND_SO_LIST_COMPLETE),(VIEW - OW_SEDA_S.VW_SELL_IN_FCST),(INGESTION - JOB.FT_CE_SELL_IN_FCST)] | [12 empty] | 10/11 - 10/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_SR_KAM) | OW_SEDA_S.MAP_CE_SR_KAM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_REASON) | OW_SEDA_S.ODS_TSS_M_REASON | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0006 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS) | OW_SEDA_S.ODS_TSS_OD_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,1051 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_DETAIL) | OW_SEDA_S.ODS_TSS_RS_RESULT_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0016 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM1)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_LOC) | OW_SEDA_S.ODS_TSS_RS_RESULT_LOC | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,1167 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 10/11 - 10/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_CUSTOMER_REJECT) | OW_SEDA_S.ODS_TSS_TC_CUSTOMER_REJECT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,0695 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_REJECT_CNT),(FUNCTION - OW_SEDA_S.FN_GET_DO_CURR_ACTION),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 10/11 - 10/11
WebPrice |  | TABLE | (TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_TV) | OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_TV | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 0,7171 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_CE),(INGESTION - JOB.ODS_WEBPRICE_TRACKING_DAILY_TV),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_UPDT_RECENT_PRICE)] | [12 empty] | 10/11 - 10/11
OMNITRACKING |  | TABLE | (TABLE - OW_SEDA_S.RAW_SEDA_API_OMNITRACKING) | OW_SEDA_S.RAW_SEDA_API_OMNITRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-10 | 2025-11-10 | ['[]'] | 0 | Migrar ph2 | 61356 | RAW | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING_FULL),(PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING),(PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING_WEEKLY)] | [12 empty] | 10/11 - 10/11
|  | TABLE | (TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_STATUS) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_STATUS | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 | [(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.MONITORING_EXECUTIONS_STATUS) | OW_LAO.MONITORING_EXECUTIONS_STATUS | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 | [(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.MONITORING_PROTOCOL_TYPES) | OW_LAO.MONITORING_PROTOCOL_TYPES | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 | [(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.MONITORING_SOURCES_TYPES) | OW_LAO.MONITORING_SOURCES_TYPES | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 | [(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS)] | [12 empty] | 11/11 - 11/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION) | OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0177 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY)] | [12 empty] | 11/11 - 11/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY) | OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0229 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W)] | [12 empty] | 11/11 - 11/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION) | OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION)] | [12 empty] | 11/11 - 11/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA) | OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0175 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 | [(INGESTION - JOB.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_FOTA_01_05W) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_FOTA_01_05W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W)] | [12 empty] | 11/11 - 11/11
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT) | OW_LAO.ODS_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0022 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_MONITORING_STATUS),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION),(INGESTION - JOB.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_FOTA_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_FOTA_01_05W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 | [(INGESTION - JOB.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_FOTA_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_FOTA_01_05W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_01_05W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W),(PROCEDURE - OW_LAO.UPDATE_SALES_WEEKLY_MONITORING)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION) | OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION),(INGESTION - JOB.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_FOTA_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_FOTA_01_05W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W)] | [12 empty] | 11/11 - 11/11
GSCM |  | TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM) | OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0154 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W)] | [12 empty] | 11/11 - 11/11
GSCM |  | TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_FOTA) | OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0093 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W)] | [12 empty] | 11/11 - 11/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.FT_GFK_MX_WEEKLY) | OW_SEDA_S.FT_GFK_MX_WEEKLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,016 | FT | 0 | [(VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST),(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK)] | [12 empty] | 11/11 - 11/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_SDI) | OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_SDI | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,144 | FT | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CARRIER) | OW_SEDA_S.MAP_CARRIER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_SEDA_SALES_IN_TRANSIT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST_MAP_CARRIER)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE) | OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,012 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_TT_RUPTURA),(INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT) | OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,008 | MAP | 0 | [(VIEW - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_TARGET_WEEK_ADJ),(INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_PRICE_COLLECTED) | OW_SEDA_S.MAP_CE_PRICE_COLLECTED | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0152 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS),(VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_SETOR_CENSITARIO_2010) | OW_SEDA_S.MAP_CE_SETOR_CENSITARIO_2010 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0155 | MAP | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_IBGE_INFO),(VIEW - OW_SEDA_S.VW_IBGE_CEP_5_COORDINATES)] | [12 empty] | 11/11 - 11/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_DA) | OW_SEDA_S.ODS_GSCM_SO_FCST_DA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0862 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_D2C_SO_FSCT),(INGESTION - JOB.ODS_GSCM_SO_FCST_DA)] | [12 empty] | 11/11 - 11/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_HHP) | OW_SEDA_S.ODS_GSCM_SO_FCST_HHP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,1631 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_D2C_SO_FSCT),(INGESTION - JOB.ODS_GSCM_SO_FCST_HHP)] | [12 empty] | 11/11 - 11/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_OTHERS) | OW_SEDA_S.ODS_GSCM_SO_FCST_OTHERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,077 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_D2C_SO_FSCT),(INGESTION - JOB.ODS_GSCM_SO_FCST_OTHERS)] | [12 empty] | 11/11 - 11/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_VD) | OW_SEDA_S.ODS_GSCM_SO_FCST_VD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0597 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_D2C_SO_FSCT),(INGESTION - JOB.ODS_GSCM_SO_FCST_VD)] | [12 empty] | 11/11 - 11/11
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM) | OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 15035 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM),(VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)] | [12 empty] | 11/11 - 11/11
PLUGGTO |  | TABLE | (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY) | OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,5782 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO),(INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY)] | [12 empty] | 11/11 - 11/11
PLUGGTO |  | TABLE | (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY) | OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,655 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO),(INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY)] | [12 empty] | 11/11 - 11/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_TC_LEG_PLANNING) | OW_SEDA_S.ODS_TSS_TB_MVW_TC_LEG_PLANNING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0144 | ODS | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 11/11 - 11/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_LEG_PLANNING) | OW_SEDA_S.ODS_TSS_TC_LEG_PLANNING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0141 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL)] | [12 empty] | 11/11 - 11/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_OCCURRENCE) | OW_SEDA_S.ODS_TSS_TC_OCCURRENCE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0466 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_STATUS),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 11/11 - 11/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL) | OW_SEDA_S.ODS_TSS_TC_VESSEL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0006 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO)] | [12 empty] | 11/11 - 11/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_DESTINATION_PORT) | OW_SEDA_S.ODS_TSS_TC_VESSEL_DESTINATION_PORT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0007 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO)] | [12 empty] | 11/11 - 11/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_ORDERS) | OW_SEDA_S.ODS_TSS_TC_VESSEL_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0059 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO)] | [12 empty] | 11/11 - 11/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_DETAIL) | OW_SEDA_S.SDI_TSS_RS_RESULT_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,3206 | OTHER | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI)] | [12 empty] | 11/11 - 11/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT) | OW_SEDA_S.SDI_TSS_TC_EVENT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,1673 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE_SDI)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_SEDA_S.TF_VW_SELLOUTGERAL) | OW_SEDA_S.TF_VW_SELLOUTGERAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0045 | TF | 0 | [(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_LSPOSITO)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_SEDA_S.TF_VW_WALMART) | OW_SEDA_S.TF_VW_WALMART | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TF | 0 | [(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_AL11_VALIDATION_TO_MOVE_FILE) | OW_LAO.FT_LAO_SALES_DEDUCTION_AL11_VALIDATION_TO_MOVE_FILE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0001 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_NERP_AL11_VALIDATION)] | [12 empty] | 11/11 - 11/11
NERP |  | TABLE | (TABLE - OW_LAO.FT_NERP_AL11_VALIDATION) | OW_LAO.FT_NERP_AL11_VALIDATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0001 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_NERP_AL11_VALIDATION)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION) | OW_LAO.FT_SALES_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0014 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-11 | 2025-11-11 | ['[]'] | 0 | Migrar ph2 | 0,0036 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 11/11 - 11/11
|  | TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,3582 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO_CONSOLIDADO) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO_CONSOLIDADO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0013 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE_HISTORICO) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE_HISTORICO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0003 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
NERP |  | TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
NERP |  | TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP_HISTORICO) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP_HISTORICO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0002 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_PRODUCT_LIST) | OW_LAO.ODS_GSCM_PRODUCT_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0158 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_PRODUCT)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.ODS_GSSC_REPORT_TO_SR) | OW_LAO.ODS_GSSC_REPORT_TO_SR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0036 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC) | OW_LAO.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(INGESTION - JOB.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_01_05W) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_01_05W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_06_10W) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_06_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W)] | [12 empty] | 12/11 - 12/11
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_AL11_MCS_SEN) | OW_LAO.ODS_NERP_AL11_MCS_SEN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_NERP_AL11_VALIDATION)] | [12 empty] | 12/11 - 12/11
NERP |  | TABLE | (TABLE - OW_LAO.ODS_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT) | OW_LAO.ODS_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0148 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_01_05W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_06_10W) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_06_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_01_05W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_06_10W) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_06_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_06_10W) | OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_06_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W)] | [12 empty] | 12/11 - 12/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_01) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_01 | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,2802 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | [12 empty] | 12/11 - 12/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_02) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_02 | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,2751 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | [12 empty] | 12/11 - 12/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_ACESSORY) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_ACESSORY | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0133 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | [12 empty] | 12/11 - 12/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_DOWN) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_DOWN | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0021 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | [12 empty] | 12/11 - 12/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_EPP) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_EPP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | [12 empty] | 12/11 - 12/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_HME) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_HME | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,001 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | [12 empty] | 12/11 - 12/11
GSCM |  | TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_EXCEPTION) | OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_BIZ_AREA) | OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_BIZ_AREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_CORES) | OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_CORES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY)] | [12 empty] | 12/11 - 12/11
GSCM |  | TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_GSCM) | OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_GSCM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0142 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION) | OW_LAO.TF_SALES_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,008 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_01) | OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_01 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0024 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_02) | OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_02 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_MD.MAP_CUSTOMER_EXCEPTION) | OW_MD.MAP_CUSTOMER_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_MD.MAP_INCENTIVE_TYPE_MAPPING) | OW_MD.MAP_INCENTIVE_TYPE_MAPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_MD.ODS_TDF_MARA) | OW_MD.ODS_TDF_MARA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,2412 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_PRODUCT)] | [12 empty] | 12/11 - 12/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_SDI) | OW_SEDA_S.FT_TSS_BI_TRACKING_SDI | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0386 | FT | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_ASP_RANGE) | OW_SEDA_S.MAP_CE_ASP_RANGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0029 | MAP | 0 | [(INGESTION - JOB.MAP_CE_ASP_RANGE)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_ASP_RANGE_TABLE) | OW_SEDA_S.MAP_CE_ASP_RANGE_TABLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [(INGESTION - JOB.MAP_CE_ASP_RANGE_TABLE)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_QUALITY_TRACKER) | OW_SEDA_S.MAP_CE_DISTRIBUTION_QUALITY_TRACKER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0409 | MAP | 0 | [(INGESTION - JOB.MAP_CE_DISTRIBUTION_QUALITY_TRACKER)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA) | OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0066 | MAP | 0 | [(INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_MBO_KAM) | OW_SEDA_S.MAP_CE_MBO_KAM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0042 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_PROMOTER_TARGET) | OW_SEDA_S.MAP_CE_PROMOTER_TARGET | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0083 | MAP | 0 | [(INGESTION - JOB.MAP_CE_PROMOTER_TARGET)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_RRP) | OW_SEDA_S.MAP_CE_RRP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_META_PROMOTOR)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_SALES_DEDUCTION) | OW_SEDA_S.MAP_CE_SALES_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0004 | MAP | 0 | [(INGESTION - JOB.MAP_CE_SALES_DEDUCTION)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_TRIPLE_A_PERFORMANCE_SUMMARY) | OW_SEDA_S.MAP_CE_TRIPLE_A_PERFORMANCE_SUMMARY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0006 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_TRIPLE_A_TARGET) | OW_SEDA_S.MAP_CE_TRIPLE_A_TARGET | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0003 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR)] | [12 empty] | 12/11 - 12/11
WebPrice |  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_WEBPRICE_URL) | OW_SEDA_S.MAP_CE_WEBPRICE_URL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0053 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_WEBPRICE_URL)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_PIN_TO_PIN_BF_19) | OW_SEDA_S.MAP_PIN_TO_PIN_BF_19 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [(PROCEDURE - OW_SEDA_S.PRC_UPDATE_PIN_TO_PIN)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_CE_MKT_TRANSMISSORAS) | OW_SEDA_S.ODS_CE_MKT_TRANSMISSORAS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-12 | 2025-11-12 | ['[]'] | 0 | Migrar ph2 | 0,0005 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE)] | [12 empty] | 12/11 - 12/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_CE_SHOPPING_BRASIL_API) | OW_SEDA_S.ODS_CE_SHOPPING_BRASIL_API | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0528 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_CE_SHOPPING_BRASIL_API)] | [12 empty] | 13/11 - 13/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_CE_WEATHER_FCST_API) | OW_SEDA_S.ODS_CE_WEATHER_FCST_API | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0085 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_CE_WEATHER_FCST_API)] | [12 empty] | 13/11 - 13/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_ACTUAL_SALES) | OW_SEDA_S.ODS_GSCM_ACTUAL_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0407 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_ACTUAL_SALES)] | [12 empty] | 13/11 - 13/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_FCST_MGMT_AP1) | OW_SEDA_S.ODS_GSCM_FCST_MGMT_AP1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,1936 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_FCST_MGMT_AP1)] | [12 empty] | 13/11 - 13/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_PROMOTION_PLAN_RAW) | OW_SEDA_S.ODS_GSCM_PROMOTION_PLAN_RAW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0196 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_PROMOTION_PLAN_RAW)] | [12 empty] | 13/11 - 13/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SELL_OUT_ACCOUNT) | OW_SEDA_S.ODS_GSCM_SELL_OUT_ACCOUNT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0154 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_SELL_OUT_ACCOUNT)] | [12 empty] | 13/11 - 13/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_DA) | OW_SEDA_S.ODS_GSCM_SI_FCST_DA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0849 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_SI_FCST_DA)] | [12 empty] | 13/11 - 13/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_MX) | OW_SEDA_S.ODS_GSCM_SI_FCST_MX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,1837 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_SI_FCST_MX)] | [12 empty] | 13/11 - 13/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_VD) | OW_SEDA_S.ODS_GSCM_SI_FCST_VD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0798 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_SI_FCST_VD)] | [12 empty] | 13/11 - 13/11
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM) | OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 1627 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.INGEST_OUTBOUND_TRACKING_SCM)] | [12 empty] | 13/11 - 13/11
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL) | OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0827 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)] | [12 empty] | 13/11 - 13/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW) | OW_SEDA_S.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0667 | ODS | 0 | [(INGESTION - JOB.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_BOOKING_UPDATE_LOG) | OW_SEDA_S.ODS_TSS_BOOKING_UPDATE_LOG | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0399 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_REASON_GRP) | OW_SEDA_S.ODS_TSS_M_REASON_GRP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_RETURN_REASON) | OW_SEDA_S.ODS_TSS_M_RETURN_REASON | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0002 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_NF_OD_ORDERS) | OW_SEDA_S.ODS_TSS_NF_OD_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0845 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_DETAIL) | OW_SEDA_S.ODS_TSS_OD_ORDERS_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0935 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_LOC) | OW_SEDA_S.ODS_TSS_OD_ORDERS_LOC | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0599 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT) | OW_SEDA_S.ODS_TSS_RS_RESULT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0973 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_GROUP) | OW_SEDA_S.ODS_TSS_RS_RESULT_GROUP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0276 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_IOD_STATUS_REPORT) | OW_SEDA_S.ODS_TSS_TB_MVW_IOD_STATUS_REPORT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0013 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_DO_EPOD_RECEIVED) | OW_SEDA_S.ODS_TSS_TC_DO_EPOD_RECEIVED | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0273 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT) | OW_SEDA_S.ODS_TSS_TC_EVENT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0395 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT_DATE) | OW_SEDA_S.ODS_TSS_TC_EVENT_DATE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0247 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT_LOG) | OW_SEDA_S.ODS_TSS_TC_EVENT_LOG | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0571 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_FOLLOW_UP_STATUS) | OW_SEDA_S.ODS_TSS_TC_FOLLOW_UP_STATUS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0275 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_NOTES) | OW_SEDA_S.ODS_TSS_TC_NOTES | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0184 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_ORDERS) | OW_SEDA_S.ODS_TSS_TC_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,1371 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | [12 empty] | 13/11 - 13/11
WebPrice |  | TABLE | (TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MON) | OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MON | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0664 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MON)] | [12 empty] | 13/11 - 13/11
NERP |  | TABLE | (TABLE - OW_SEDA_S.RAW_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM) | OW_SEDA_S.RAW_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 133306 | RAW | 0 | [(PROCEDURE - OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_HEADER_DIVISION) | OW_SEDA_S.SDI_TSS_M_HEADER_DIVISION | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0002 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_TRANS) | OW_SEDA_S.SDI_TSS_M_TRANS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0013 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN) | OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0422 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN_DETAIL) | OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0371 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_PRE_SHIPMENT) | OW_SEDA_S.SDI_TSS_OD_PRE_SHIPMENT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0156 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_OD_PRE_SHIPMENT)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOC) | OW_SEDA_S.SDI_TSS_TC_EVENT_LOC | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 11034 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_LOC)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_IOD) | OW_SEDA_S.SDI_TSS_TC_IOD | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,2817 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_NOTES) | OW_SEDA_S.SDI_TSS_TC_NOTES | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,075 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI)] | [12 empty] | 13/11 - 13/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_WEB_RETURN_REQUEST) | OW_SEDA_S.SDI_TSS_WEB_RETURN_REQUEST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0015 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | [12 empty] | 13/11 - 13/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_CE_FORMAT) | OW_SEDA_S.TMP_CE_FORMAT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0942 | TMP | 0 | [(INGESTION - JOB.TMP_CE_FORMAT)] | [12 empty] | 13/11 - 13/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_B2B) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_B2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0019 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_B2B)] | [12 empty] | 13/11 - 13/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BREA) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BREA)] | [12 empty] | 13/11 - 13/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BRSHOP) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BRSHOP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0238 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BRSHOP)] | [12 empty] | 13/11 - 13/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EPP2) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0015 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EPP2)] | [12 empty] | 13/11 - 13/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EST) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0037 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EST)] | [12 empty] | 13/11 - 13/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MEMBERS) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MEMBERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0017 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MEMBERS)] | [12 empty] | 13/11 - 13/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_PARC) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_PARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,002 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_PARC)] | [12 empty] | 13/11 - 13/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_RESID) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_RESID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-13 | 2025-11-13 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_RESID)] | [12 empty] | 13/11 - 13/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MX_STORE_MAPPING) | OW_SEDA_S.TMP_MX_STORE_MAPPING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [(VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022)] | [12 empty] | 14/11 - 14/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TMP_ODS_GSCM_PROMOTION_PLAN) | OW_SEDA_S.TMP_ODS_GSCM_PROMOTION_PLAN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0085 | TMP | 0 | [(INGESTION - JOB.TMP_ODS_GSCM_PROMOTION_PLAN)] | [12 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION) | OW_SEDA_S.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0026 | TMP | 0 | [(INGESTION - JOB.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION)] | [12 empty] | 14/11 - 14/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_SDI_TSS_OD_ORDERS) | OW_SEDA_S.TMP_SDI_TSS_OD_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,037 | TMP | 0 | [(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI)] | [12 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.ALERT_MONITORING_STATUS_NULL) | OW_LAO.ALERT_MONITORING_STATUS_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION) | OW_LAO.FT_LAO_SALES_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | FT | 0 | [13 empty] | 14/11 - 14/11
SPRINKLR |  | TABLE | (TABLE - OW_LAO.FT_SPRINKLR) | OW_LAO.FT_SPRINKLR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,4368 | FT | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION_V2) | OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION_V2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | INPUT | 0 | [13 empty] | 14/11 - 14/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_SECH_FORECASTMGMT) | OW_LAO.ODS_GSCM_SECH_FORECASTMGMT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [13 empty] | 14/11 - 14/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_GSCM_SELLIN_BIZ_PLAN) | OW_LAO.ODS_GSCM_SELLIN_BIZ_PLAN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,2641 | ODS | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_6_10W) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_6_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_6W_10W) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_6W_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_DAILY_EDI_VALIDATION) | OW_LAO.ODS_SALES_DEDUCTION_DAILY_EDI_VALIDATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_DAILY_EDI_VALIDATION_6_10W) | OW_LAO.ODS_SALES_DEDUCTION_DAILY_EDI_VALIDATION_6_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_6_10W) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_6_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [13 empty] | 14/11 - 14/11
SPRINKLR |  | TABLE | (TABLE - OW_LAO.ODS_SPRINKLR_DL) | OW_LAO.ODS_SPRINKLR_DL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 103172 | ODS | 0 | [13 empty] | 14/11 - 14/11
SPRINKLR |  | TABLE | (TABLE - OW_LAO.ODS_SPRINKLR_EVENTS_DL) | OW_LAO.ODS_SPRINKLR_EVENTS_DL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.RAW_DATA_GSSC_REPORT_TO_SR) | OW_LAO.RAW_DATA_GSSC_REPORT_TO_SR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,1622 | RAW | 0 | [13 empty] | 14/11 - 14/11
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT) | OW_LAO.RAW_DATA_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,3041 | RAW | 0 | [13 empty] | 14/11 - 14/11
NERP |  | TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT) | OW_LAO.RAW_DATA_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 16705 | RAW | 0 | [13 empty] | 14/11 - 14/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_ACTUAL_SALES) | OW_LAO.RAW_GSCM_ACTUAL_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0004 | RAW | 0 | [13 empty] | 14/11 - 14/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_AP1_ACCURACY_PIVOT_TABLE) | OW_LAO.RAW_GSCM_AP1_ACCURACY_PIVOT_TABLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0884 | RAW | 0 | [13 empty] | 14/11 - 14/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,1047 | RAW | 0 | [13 empty] | 14/11 - 14/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,1536 | RAW | 0 | [13 empty] | 14/11 - 14/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_EXCEPTION) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0012 | RAW | 0 | [13 empty] | 14/11 - 14/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_PREMIUM_MODELS) | OW_LAO.RAW_GSCM_PREMIUM_MODELS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0028 | RAW | 0 | [13 empty] | 14/11 - 14/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_GSCM_PREMIUM_MODELS_PIVOT_TABLE) | OW_LAO.RAW_GSCM_PREMIUM_MODELS_PIVOT_TABLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,015 | RAW | 0 | [13 empty] | 14/11 - 14/11
HYBRIS |  | TABLE | (TABLE - OW_LAO.TEMP_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION) | OW_LAO.TEMP_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION | LAO EStore | r.bojart |  | yes | 3 | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | OTHER | 0 | [13 empty] | 14/11 - 14/11
NERP | ControlTower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 | [13 empty] | 14/11 - 14/11
NERP | ControlTower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_2) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_2 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0005 | OTHER | 0 | [13 empty] | 14/11 - 14/11
NERP | ControlTower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_DELETE) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_DELETE | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0012 | OTHER | 0 | [13 empty] | 14/11 - 14/11
NERP | ControlTower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_DELETE_2) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_DELETE_2 | LAO EStore | r.bojart |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0007 | OTHER | 0 | [13 empty] | 14/11 - 14/11
|  | TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_VALIDATION) | OW_LAO.TF_LAO_SALES_DEDUCTION_VALIDATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TF | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_CANCELATION) | OW_LAO.TMP_AFTER_SALES_CANCELATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0014 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND) | OW_LAO.TMP_AFTER_SALES_REFUND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_BRB2B) | OW_LAO.TMP_AFTER_SALES_REFUND_BRB2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_BREA) | OW_LAO.TMP_AFTER_SALES_REFUND_BREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_BRSHOPMKTPL) | OW_LAO.TMP_AFTER_SALES_REFUND_BRSHOPMKTPL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BRB2B) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BRB2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0009 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BREA) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0032 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_EPP2) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_EST) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_EST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-14 | 2025-11-14 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [13 empty] | 14/11 - 14/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_MEMBERS) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_MEMBERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0007 | TMP | 0 | [14 empty] | 17/11 - 17/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_PARC) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_PARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [14 empty] | 17/11 - 17/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_RESID) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_RESID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [14 empty] | 17/11 - 17/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_EPP2) | OW_LAO.TMP_AFTER_SALES_REFUND_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 17/11 - 17/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_EST) | OW_LAO.TMP_AFTER_SALES_REFUND_EST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 17/11 - 17/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_MEMBERS) | OW_LAO.TMP_AFTER_SALES_REFUND_MEMBERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 17/11 - 17/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_PARC) | OW_LAO.TMP_AFTER_SALES_REFUND_PARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 17/11 - 17/11
AFTER_SALES |  | TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_RESID) | OW_LAO.TMP_AFTER_SALES_REFUND_RESID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_LAO.TMP_DIR_BASIC_ATT_AGE) | OW_LAO.TMP_DIR_BASIC_ATT_AGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT) | OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0229 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_6W_10W) | OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_6W_10W | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,023 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_EXCEPTION) | OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_EXCEPTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_FOTA) | OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0175 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_GSCM_PRODUCT_LIST) | OW_LAO.TMP_GSCM_PRODUCT_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0118 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_1) | OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_2) | OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_3) | OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0006 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_1) | OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,001 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_2) | OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_3) | OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0508 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_4) | OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_4 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_1) | OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_2) | OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_3) | OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0012 | TMP | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_LAO.TMP_LAO_SALES_DEDUCTION_WEEKLY_EDI) | OW_LAO.TMP_LAO_SALES_DEDUCTION_WEEKLY_EDI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_LAO.TMP_LAO_SALES_DEDUCTION_WEEKLY_FOTA) | OW_LAO.TMP_LAO_SALES_DEDUCTION_WEEKLY_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_MD.MAP_AR_CLAIM_ADJUSTED) | OW_MD.MAP_AR_CLAIM_ADJUSTED | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_MD.ODS_TDF_ADRC) | OW_MD.ODS_TDF_ADRC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,1775 | ODS | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_MD.ODS_TDF_KNA1) | OW_MD.ODS_TDF_KNA1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,1721 | ODS | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_MD.ODS_TDF_LFA1) | OW_MD.ODS_TDF_LFA1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,2292 | ODS | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_MD.ODS_TDF_MAKT) | OW_MD.ODS_TDF_MAKT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,1175 | ODS | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_MD.ODS_TDF_MARC) | OW_MD.ODS_TDF_MARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,3873 | ODS | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_MD.ODS_TDF_MBEW) | OW_MD.ODS_TDF_MBEW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,1846 | ODS | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_MD.TMP_GSCM_PRODUCT_CATEGORY) | OW_MD.TMP_GSCM_PRODUCT_CATEGORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0187 | TMP | 0 | [14 empty] | 17/11 - 17/11
GSCM |  | TABLE | (TABLE - OW_MD.TMP_MAP_GSCM) | OW_MD.TMP_MAP_GSCM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [14 empty] | 17/11 - 17/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM_FILTERED) | OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM_FILTERED | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0773 | OTHER | 0 | [14 empty] | 17/11 - 17/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_VAGNER) | OW_SEDA_S.CELLO_DELIVERY_INBOUND_VAGNER | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0014 | OTHER | 0 | [14 empty] | 17/11 - 17/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM_2) | OW_SEDA_S.CELLO_DELIVERY_ITEM_2 | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0003 | OTHER | 0 | [14 empty] | 17/11 - 17/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_INBOUND_BOOKING) | OW_SEDA_S.CELLO_INBOUND_BOOKING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0704 | OTHER | 0 | [14 empty] | 17/11 - 17/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST_TEMPO) | OW_SEDA_S.CELLO_LAST_LEG_MANIFEST_TEMPO | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0049 | OTHER | 0 | [14 empty] | 17/11 - 17/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_SUM_LLM) | OW_SEDA_S.CELLO_SUM_LLM | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0006 | OTHER | 0 | [14 empty] | 17/11 - 17/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.CELLO_SUM_SHIPMENT) | OW_SEDA_S.CELLO_SUM_SHIPMENT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0874 | OTHER | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_AMAZON_MX) | OW_SEDA_S.FT_AMAZON_MX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0096 | FT | 0 | [14 empty] | 17/11 - 17/11
ASAP |  | TABLE | (TABLE - OW_SEDA_S.FT_ASAP_FLAGSHIP_NET_GAIN) | OW_SEDA_S.FT_ASAP_FLAGSHIP_NET_GAIN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0004 | FT | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_BF_AVG_SELL_OUT) | OW_SEDA_S.FT_BF_AVG_SELL_OUT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0024 | FT | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_CE_PRICE_TABLE) | OW_SEDA_S.FT_CE_PRICE_TABLE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,117 | FT | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_CE_RM_MEETING_AV) | OW_SEDA_S.FT_CE_RM_MEETING_AV | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0138 | FT | 0 | [14 empty] | 17/11 - 17/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_CE_RM_MEETING_DA) | OW_SEDA_S.FT_CE_RM_MEETING_DA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-17 | 2025-11-17 | ['[]'] | 0 | Migrar ph2 | 0,0128 | FT | 0 | [14 empty] | 17/11 - 17/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.FT_CHEIL_Migrar ph 2INS) | OW_SEDA_S.FT_CHEIL_Migrarph2INS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0275 | FT | 0 | [14 empty] | 18/11 - 18/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.FT_CHEIL_VISITS) | OW_SEDA_S.FT_CHEIL_VISITS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0248 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_DIR_BASIC_ATT) | OW_SEDA_S.FT_DIR_BASIC_ATT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,001 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_DIR_BASIC_ATT_AGE) | OW_SEDA_S.FT_DIR_BASIC_ATT_AGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0045 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_DIR_BASIC_ATT_GENDER) | OW_SEDA_S.FT_DIR_BASIC_ATT_GENDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0024 | FT | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.FT_GFK_MX_MONTHLY_CHANNEL) | OW_SEDA_S.FT_GFK_MX_MONTHLY_CHANNEL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0174 | FT | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.FT_GFK_MX_MONTHLY_ON_OFF) | OW_SEDA_S.FT_GFK_MX_MONTHLY_ON_OFF | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0268 | FT | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.FT_GFK_MX_MONTHLY_REGIONAL) | OW_SEDA_S.FT_GFK_MX_MONTHLY_REGIONAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0402 | FT | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.FT_GFK_NPC_MONTHLY) | OW_SEDA_S.FT_GFK_NPC_MONTHLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0027 | FT | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.FT_GFK_NPC_WEEKLY) | OW_SEDA_S.FT_GFK_NPC_WEEKLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0058 | FT | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.FT_GFK_TAB_MONTHLY) | OW_SEDA_S.FT_GFK_TAB_MONTHLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0011 | FT | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.FT_GFK_TAB_WEEKLY) | OW_SEDA_S.FT_GFK_TAB_WEEKLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0024 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_GROSS_MARGIN_PROMO_DEDUCTION) | OW_SEDA_S.FT_GROSS_MARGIN_PROMO_DEDUCTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0461 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_AI_USAGE_RATE) | OW_SEDA_S.FT_MX_AI_USAGE_RATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0001 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_SAMSUNG_HEALTH) | OW_SEDA_S.FT_MX_SAMSUNG_HEALTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0004 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_SAMSUNG_HEALTH_EVENTS) | OW_SEDA_S.FT_MX_SAMSUNG_HEALTH_EVENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0013 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_SAMSUNG_WALLET) | OW_SEDA_S.FT_MX_SAMSUNG_WALLET | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0002 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_SAMSUNG_WALLET_EVENTS) | OW_SEDA_S.FT_MX_SAMSUNG_WALLET_EVENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0006 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_PARAGUAI_IMPORTS_MX) | OW_SEDA_S.FT_PARAGUAI_IMPORTS_MX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0098 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_SVC_SO_PAR_DAILY) | OW_SEDA_S.FT_SVC_SO_PAR_DAILY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0996 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_SVC_SO_PAR_MONTHLY) | OW_SEDA_S.FT_SVC_SO_PAR_MONTHLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,4741 | FT | 0 | [14 empty] | 18/11 - 18/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING) | OW_SEDA_S.FT_TSS_BI_TRACKING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0707 | FT | 0 | [14 empty] | 18/11 - 18/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HIST) | OW_SEDA_S.FT_TSS_BI_TRACKING_HIST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,1252 | FT | 0 | [14 empty] | 18/11 - 18/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HISTORICO) | OW_SEDA_S.FT_TSS_BI_TRACKING_HISTORICO | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,327 | FT | 0 | [14 empty] | 18/11 - 18/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_BETWEEN_2014_AND_2016) | OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_BETWEEN_2014_AND_2016 | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,1401 | FT | 0 | [14 empty] | 18/11 - 18/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_SDI_6MONTHS) | OW_SEDA_S.FT_TSS_BI_TRACKING_SDI_6MONTHS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0726 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_WRONG_IOD_REPORT) | OW_SEDA_S.FT_WRONG_IOD_REPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,4007 | FT | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_ACCOUNT_MODE) | OW_SEDA_S.MAP_CE_ACCOUNT_MODE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0057 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_BF_PLANOS_ABCD) | OW_SEDA_S.MAP_CE_BF_PLANOS_ABCD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0016 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_CHANNEL_MODE) | OW_SEDA_S.MAP_CE_CHANNEL_MODE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0066 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_HA) | OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_HA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0017 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_LOJAS) | OW_SEDA_S.MAP_CE_LOJAS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0395 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_MBO_TARGETS) | OW_SEDA_S.MAP_CE_MBO_TARGETS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0012 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_MBO_WEIGHT_PORTION) | OW_SEDA_S.MAP_CE_MBO_WEIGHT_PORTION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0002 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_MBO_WOS_TARGET) | OW_SEDA_S.MAP_CE_MBO_WOS_TARGET | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_RAC_LINE) | OW_SEDA_S.MAP_CE_RAC_LINE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0002 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_SUPER_BIG_INCHES_TRACKER) | OW_SEDA_S.MAP_CE_SUPER_BIG_INCHES_TRACKER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0033 | MAP | 0 | [14 empty] | 18/11 - 18/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_ENVIRONMENTS) | OW_SEDA_S.MAP_CHEIL_ENVIRONMENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0 | MAP | 0 | [14 empty] | 18/11 - 18/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES) | OW_SEDA_S.MAP_CHEIL_FORMULARIES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0006 | MAP | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.MAP_GFK_MX_PRODUCTS) | OW_SEDA_S.MAP_GFK_MX_PRODUCTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0 | MAP | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.MAP_GFK_NPC_PRODUCTS) | OW_SEDA_S.MAP_GFK_NPC_PRODUCTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0002 | MAP | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.MAP_GFK_PRODUCTS) | OW_SEDA_S.MAP_GFK_PRODUCTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0004 | MAP | 0 | [14 empty] | 18/11 - 18/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.MAP_GFK_TAB_PRODUCTS) | OW_SEDA_S.MAP_GFK_TAB_PRODUCTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_MX_GTM_TARGETS) | OW_SEDA_S.MAP_MX_GTM_TARGETS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_MX_PRODUCTS) | OW_SEDA_S.MAP_MX_PRODUCTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0003 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_MX_RRP) | OW_SEDA_S.MAP_MX_RRP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0001 | MAP | 0 | [14 empty] | 18/11 - 18/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS_LSPOSITO) | OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS_LSPOSITO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0002 | MAP | 0 | [14 empty] | 18/11 - 18/11
Assurant |  | TABLE | (TABLE - OW_SEDA_S.ODS_ASSURANT_API_INTERFACE) | OW_SEDA_S.ODS_ASSURANT_API_INTERFACE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-18 | 2025-11-18 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [14 empty] | 18/11 - 18/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_FLOORSHARE) | OW_SEDA_S.ODS_CHEIL_FLOORSHARE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0004 | ODS | 0 | [14 empty] | 19/11 - 19/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_FLOR_SHARE) | OW_SEDA_S.ODS_CHEIL_FLOR_SHARE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [14 empty] | 19/11 - 19/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_JOURNEY) | OW_SEDA_S.ODS_CHEIL_JOURNEY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0153 | ODS | 0 | [14 empty] | 19/11 - 19/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_LDU) | OW_SEDA_S.ODS_CHEIL_LDU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0004 | ODS | 0 | [14 empty] | 19/11 - 19/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_POSITIVATION) | OW_SEDA_S.ODS_CHEIL_POSITIVATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0004 | ODS | 0 | [14 empty] | 19/11 - 19/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_PRICES) | OW_SEDA_S.ODS_CHEIL_PRICES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,013 | ODS | 0 | [14 empty] | 19/11 - 19/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_WEEK_OLD) | OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_WEEK_OLD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0429 | ODS | 0 | [14 empty] | 19/11 - 19/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.ODS_GFK_HITLIST_CE_RAC) | OW_SEDA_S.ODS_GFK_HITLIST_CE_RAC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0089 | ODS | 0 | [14 empty] | 19/11 - 19/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.ODS_GFK_HITLIST_CE_REF) | OW_SEDA_S.ODS_GFK_HITLIST_CE_REF | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0106 | ODS | 0 | [14 empty] | 19/11 - 19/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.ODS_GFK_HITLIST_CE_TV) | OW_SEDA_S.ODS_GFK_HITLIST_CE_TV | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0167 | ODS | 0 | [14 empty] | 19/11 - 19/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.ODS_GFK_HITLIST_CE_WM) | OW_SEDA_S.ODS_GFK_HITLIST_CE_WM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0093 | ODS | 0 | [14 empty] | 19/11 - 19/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.ODS_GFK_REGION_CE_TV) | OW_SEDA_S.ODS_GFK_REGION_CE_TV | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0016 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_AP1_SO_FA_MONTH) | OW_SEDA_S.ODS_GSCM_AP1_SO_FA_MONTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_AP1_SO_FA_WEEK) | OW_SEDA_S.ODS_GSCM_AP1_SO_FA_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_AP2_SO_FA_MONTH) | OW_SEDA_S.ODS_GSCM_AP2_SO_FA_MONTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0002 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_AP2_SO_FA_WEEK) | OW_SEDA_S.ODS_GSCM_AP2_SO_FA_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0002 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP1_RAWDATA) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP1_RAWDATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0057 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP1_RAWDATA_MON) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP1_RAWDATA_MON | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0063 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP2_RAWDATA) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP2_RAWDATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0045 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP2_RAWDATA_MON) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP2_RAWDATA_MON | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_AR_GRAPHICS) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_AR_GRAPHICS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0022 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_MON_GRAPHICS) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_MON_GRAPHICS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0005 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_SEDA_GRAPHIC) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_SEDA_GRAPHIC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0063 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_AR_GLOBAL) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_AR_GLOBAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0003 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_AR_SEDA) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_AR_SEDA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0006 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_GLOBAL) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_GLOBAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0048 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_SEDA) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_SEDA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0011 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP1_SO_FA_MONTH) | OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP1_SO_FA_MONTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP1_SO_FA_WEEK) | OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP1_SO_FA_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP2_SO_FA_MONTH) | OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP2_SO_FA_MONTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP2_SO_FA_WEEK) | OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP2_SO_FA_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_RTF) | OW_SEDA_S.ODS_GSCM_RTF | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0009 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_STOCK_BASE) | OW_SEDA_S.ODS_GSCM_STOCK_BASE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0007 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_INCENTIVES_GSCM_CLEAN) | OW_SEDA_S.ODS_INCENTIVES_GSCM_CLEAN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0002 | ODS | 0 | [14 empty] | 19/11 - 19/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.ODS_INCENTIVES_GSCM_DATA) | OW_SEDA_S.ODS_INCENTIVES_GSCM_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0002 | ODS | 0 | [14 empty] | 19/11 - 19/11
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_LOAD_SCM) | OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_LOAD_SCM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,1194 | ODS | 0 | [14 empty] | 19/11 - 19/11
NERP |  | TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SEDA_D2C_VISIB) | OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SEDA_D2C_VISIB | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0354 | ODS | 0 | [14 empty] | 19/11 - 19/11
PLUGGTO |  | TABLE | (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_SHIPMENTS) | OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_SHIPMENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,2313 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_IOD_STATUS_REPORT) | OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_IOD_STATUS_REPORT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0258 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_OTD4_ANALYSIS) | OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_OTD4_ANALYSIS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0288 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_OTD_CARRIER) | OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_OTD_CARRIER | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_TC_LEG_PLANNING) | OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_TC_LEG_PLANNING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0103 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_MVW_OTD4_ANALYSIS) | OW_SEDA_S.ODS_TSS_MVW_OTD4_ANALYSIS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0303 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_HOLIDAY) | OW_SEDA_S.ODS_TSS_M_HOLIDAY | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0005 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_NF_OD_ORDERS_DETAIL) | OW_SEDA_S.ODS_TSS_NF_OD_ORDERS_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0615 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_INBOUND) | OW_SEDA_S.ODS_TSS_OD_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0081 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_INBOUND_DETAIL) | OW_SEDA_S.ODS_TSS_OD_INBOUND_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0112 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_RETURN) | OW_SEDA_S.ODS_TSS_OD_ORDERS_RETURN | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-19 | 2025-11-19 | ['[]'] | 0 | Migrar ph2 | 0,0247 | ODS | 0 | [14 empty] | 19/11 - 19/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_RETURN_DETAIL) | OW_SEDA_S.ODS_TSS_OD_ORDERS_RETURN_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,019 | ODS | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_OTD4_ANALYSIS) | OW_SEDA_S.ODS_TSS_TB_MVW_OTD4_ANALYSIS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0313 | ODS | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_OTD_CARRIER) | OW_SEDA_S.ODS_TSS_TB_MVW_OTD_CARRIER | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0001 | ODS | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_INBOUND) | OW_SEDA_S.ODS_TSS_TC_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0184 | ODS | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_IOD) | OW_SEDA_S.ODS_TSS_TC_IOD | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0321 | ODS | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_ORDER_OCCURRENCE_RPT) | OW_SEDA_S.ODS_TSS_TC_ORDER_OCCURRENCE_RPT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0088 | ODS | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_RETURN_BOOKING_REQUEST) | OW_SEDA_S.ODS_TSS_TC_RETURN_BOOKING_REQUEST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0081 | ODS | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_SCHEDULE_ORDER) | OW_SEDA_S.ODS_TSS_TC_SCHEDULE_ORDER | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0004 | ODS | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_TSS_WEB_RETURN_REQUEST) | OW_SEDA_S.ODS_TSS_WEB_RETURN_REQUEST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0011 | ODS | 0 | [14 empty] | 20/11 - 20/11
WebPrice |  | TABLE | (TABLE - OW_SEDA_S.ODS_WEBPRICE_PRICE_TRACKING_ON_RAC) | OW_SEDA_S.ODS_WEBPRICE_PRICE_TRACKING_ON_RAC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0276 | ODS | 0 | [14 empty] | 20/11 - 20/11
ASAP |  | TABLE | (TABLE - OW_SEDA_S.RAW_ASAP_GLOBAL_REPURCHASE_ANALYSIS) | OW_SEDA_S.RAW_ASAP_GLOBAL_REPURCHASE_ANALYSIS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,078 | RAW | 0 | [14 empty] | 20/11 - 20/11
ASAP |  | TABLE | (TABLE - OW_SEDA_S.RAW_ASAP_SEDA_INSTALLED_BASE) | OW_SEDA_S.RAW_ASAP_SEDA_INSTALLED_BASE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,018 | RAW | 0 | [14 empty] | 20/11 - 20/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.RAW_GFK_MX_MONTHLY) | OW_SEDA_S.RAW_GFK_MX_MONTHLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0213 | RAW | 0 | [14 empty] | 20/11 - 20/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.RAW_GSCM_DAILY_INVENTORY) | OW_SEDA_S.RAW_GSCM_DAILY_INVENTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0008 | RAW | 0 | [14 empty] | 20/11 - 20/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.RAW_GSCM_PRODUCT_LIST) | OW_SEDA_S.RAW_GSCM_PRODUCT_LIST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0003 | RAW | 0 | [14 empty] | 20/11 - 20/11
|  | TABLE | (TABLE - OW_SEDA_S.RAW_MX_HEALTH_APP_WEEKLY_USAGE) | OW_SEDA_S.RAW_MX_HEALTH_APP_WEEKLY_USAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0199 | RAW | 0 | [14 empty] | 20/11 - 20/11
PLUGGTO |  | TABLE | (TABLE - OW_SEDA_S.RAW_PLUGG_CREDENTIALS) | OW_SEDA_S.RAW_PLUGG_CREDENTIALS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0001 | RAW | 0 | [14 empty] | 20/11 - 20/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_CELLO_STAGE) | OW_SEDA_S.SDI_CELLO_STAGE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 16119 | OTHER | 0 | [14 empty] | 20/11 - 20/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_CELLO_STAGE_PRE) | OW_SEDA_S.SDI_CELLO_STAGE_PRE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0001 | OTHER | 0 | [14 empty] | 20/11 - 20/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_CELLO_STAGE_VAGNER) | OW_SEDA_S.SDI_CELLO_STAGE_VAGNER | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0004 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_IF2_PICKUP_SCHEDULE_TRIGGER) | OW_SEDA_S.SDI_TSS_IF2_PICKUP_SCHEDULE_TRIGGER | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0058 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_MVW_OTD4_ANALYSIS) | OW_SEDA_S.SDI_TSS_MVW_OTD4_ANALYSIS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0141 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_AREA) | OW_SEDA_S.SDI_TSS_M_AREA | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0006 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_AREA_TYPE) | OW_SEDA_S.SDI_TSS_M_AREA_TYPE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0004 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_AREA_TYPE_DETAIL) | OW_SEDA_S.SDI_TSS_M_AREA_TYPE_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0017 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_CODE) | OW_SEDA_S.SDI_TSS_M_CODE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,001 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_COMPANY) | OW_SEDA_S.SDI_TSS_M_COMPANY | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0003 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_DIVISION) | OW_SEDA_S.SDI_TSS_M_DIVISION | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0002 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_FOLLOW_UP_STATUS) | OW_SEDA_S.SDI_TSS_M_FOLLOW_UP_STATUS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0002 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_HOLIDAY) | OW_SEDA_S.SDI_TSS_M_HOLIDAY | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0005 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS_DETAIL) | OW_SEDA_S.SDI_TSS_NF_OD_ORDERS_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,3523 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_INBOUND) | OW_SEDA_S.SDI_TSS_OD_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0132 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_INBOUND_DETAIL) | OW_SEDA_S.SDI_TSS_OD_INBOUND_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0278 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_SD_M_ROUTE) | OW_SEDA_S.SDI_TSS_SD_M_ROUTE | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0002 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_BOOKING_REQUEST) | OW_SEDA_S.SDI_TSS_TC_BOOKING_REQUEST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0758 | OTHER | 0 | [14 empty] | 20/11 - 20/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_INBOUND) | OW_SEDA_S.SDI_TSS_TC_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,024 | OTHER | 0 | [14 empty] | 20/11 - 20/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SI_FCST_DA) | OW_SEDA_S.TF_GSCM_SI_FCST_DA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,003 | TF | 0 | [14 empty] | 20/11 - 20/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SI_FCST_MX) | OW_SEDA_S.TF_GSCM_SI_FCST_MX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0031 | TF | 0 | [14 empty] | 20/11 - 20/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SI_FCST_VD) | OW_SEDA_S.TF_GSCM_SI_FCST_VD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0026 | TF | 0 | [14 empty] | 20/11 - 20/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SO_FCST_DA) | OW_SEDA_S.TF_GSCM_SO_FCST_DA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0096 | TF | 0 | [14 empty] | 20/11 - 20/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SO_FCST_HHP) | OW_SEDA_S.TF_GSCM_SO_FCST_HHP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0127 | TF | 0 | [14 empty] | 20/11 - 20/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SO_FCST_OTHERS) | OW_SEDA_S.TF_GSCM_SO_FCST_OTHERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,004 | TF | 0 | [14 empty] | 20/11 - 20/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SO_FCST_VD) | OW_SEDA_S.TF_GSCM_SO_FCST_VD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0047 | TF | 0 | [14 empty] | 20/11 - 20/11
|  | TABLE | (TABLE - OW_SEDA_S.TF_MAP_SALES_DEDUCTION_CORE_LEVELS_SELLOUTGERAL) | OW_SEDA_S.TF_MAP_SALES_DEDUCTION_CORE_LEVELS_SELLOUTGERAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TF | 0 | [14 empty] | 20/11 - 20/11
|  | TABLE | (TABLE - OW_SEDA_S.TF_MAP_SALES_DEDUCTION_CORE_LEVELS_WALMART) | OW_SEDA_S.TF_MAP_SALES_DEDUCTION_CORE_LEVELS_WALMART | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TF | 0 | [14 empty] | 20/11 - 20/11
|  | TABLE | (TABLE - OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_COMPLETO) | OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_COMPLETO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TF | 0 | [14 empty] | 20/11 - 20/11
|  | TABLE | (TABLE - OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL) | OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0006 | TF | 0 | [14 empty] | 20/11 - 20/11
|  | TABLE | (TABLE - OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_WALMART) | OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_WALMART | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-20 | 2025-11-20 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TF | 0 | [14 empty] | 20/11 - 20/11
|  | TABLE | (TABLE - OW_SEDA_S.TF_VW_SELLOUTGERAL_JOIN) | OW_SEDA_S.TF_VW_SELLOUTGERAL_JOIN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0 | TF | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TF_VW_WALMART_JOIN) | OW_SEDA_S.TF_VW_WALMART_JOIN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0 | TF | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_1) | OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_2) | OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_3) | OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0011 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_1) | OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_2) | OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_3) | OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0011 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_1) | OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_2) | OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_3) | OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0011 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_1) | OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_2) | OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_3) | OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0011 | TMP | 0 | [14 empty] | 21/11 - 21/11
ASAP |  | TABLE | (TABLE - OW_SEDA_S.TMP_ASAP_FLAGSHIP_NET_GAIN) | OW_SEDA_S.TMP_ASAP_FLAGSHIP_NET_GAIN | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [14 empty] | 21/11 - 21/11
ASAP |  | TABLE | (TABLE - OW_SEDA_S.TMP_ASAP_REGIONAL_FOTA) | OW_SEDA_S.TMP_ASAP_REGIONAL_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0105 | TMP | 0 | [14 empty] | 21/11 - 21/11
ASAP |  | TABLE | (TABLE - OW_SEDA_S.TMP_ASAP_SEDA_INSTALLED_BASE) | OW_SEDA_S.TMP_ASAP_SEDA_INSTALLED_BASE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 21/11 - 21/11
Assurant |  | TABLE | (TABLE - OW_SEDA_S.TMP_ASSURANT_API_INTERFACE) | OW_SEDA_S.TMP_ASSURANT_API_INTERFACE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_CE_FCST) | OW_SEDA_S.TMP_CE_FCST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0036 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_CE_IDEA_PSI_WARNING) | OW_SEDA_S.TMP_CE_IDEA_PSI_WARNING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0104 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_CE_WEEKLY_UPDATE) | OW_SEDA_S.TMP_CE_WEEKLY_UPDATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0046 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_ANSWERS) | OW_SEDA_S.TMP_CHEIL_ANSWERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0006 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_Migrar ph 2INS) | OW_SEDA_S.TMP_CHEIL_Migrarph2INS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_COLLABORATORS) | OW_SEDA_S.TMP_CHEIL_COLLABORATORS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_ENVIRONMENTS) | OW_SEDA_S.TMP_CHEIL_ENVIRONMENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_FLOORSHARE) | OW_SEDA_S.TMP_CHEIL_FLOORSHARE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_FLOR_SHARE) | OW_SEDA_S.TMP_CHEIL_FLOR_SHARE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_FORMULARIES) | OW_SEDA_S.TMP_CHEIL_FORMULARIES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0006 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_FORMULARIES_QUESTIONS) | OW_SEDA_S.TMP_CHEIL_FORMULARIES_QUESTIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_INTERNAL_IMAGES) | OW_SEDA_S.TMP_CHEIL_INTERNAL_IMAGES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_JOURNEY) | OW_SEDA_S.TMP_CHEIL_JOURNEY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0007 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_LDU) | OW_SEDA_S.TMP_CHEIL_LDU | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_POS) | OW_SEDA_S.TMP_CHEIL_POS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0045 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_POSITIVATION) | OW_SEDA_S.TMP_CHEIL_POSITIVATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_PRICES) | OW_SEDA_S.TMP_CHEIL_PRICES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0132 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_PRODUCTS) | OW_SEDA_S.TMP_CHEIL_PRODUCTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0006 | TMP | 0 | [14 empty] | 21/11 - 21/11
CHEIL |  | TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_VISITS) | OW_SEDA_S.TMP_CHEIL_VISITS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 21/11 - 21/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_B2B) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_B2B | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 21/11 - 21/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_BREA) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_BREA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 21/11 - 21/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_BRSHOP) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_BRSHOP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0038 | TMP | 0 | [14 empty] | 21/11 - 21/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_EPP2) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_EPP2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 21/11 - 21/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_EST) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_EST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0006 | TMP | 0 | [14 empty] | 21/11 - 21/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_MEMBERS) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_MEMBERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [14 empty] | 21/11 - 21/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_PARC) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_PARC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TMP | 0 | [14 empty] | 21/11 - 21/11
AFTER_SALES |  | TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_RESID) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_RESID | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_DIR_BASIC_ATT) | OW_SEDA_S.TMP_DIR_BASIC_ATT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_DIR_BASIC_ATT_AGE) | OW_SEDA_S.TMP_DIR_BASIC_ATT_AGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 21/11 - 21/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_DIR_BASIC_ATT_GENDER) | OW_SEDA_S.TMP_DIR_BASIC_ATT_GENDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-21 | 2025-11-21 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [14 empty] | 21/11 - 21/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TMP_FT_GSCM_RTF) | OW_SEDA_S.TMP_FT_GSCM_RTF | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.TMP_GFK_MX_MONTHLY_CHANNEL) | OW_SEDA_S.TMP_GFK_MX_MONTHLY_CHANNEL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0023 | TMP | 0 | [15 empty] | 24/11 - 24/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.TMP_GFK_MX_MONTHLY_ON_OFF) | OW_SEDA_S.TMP_GFK_MX_MONTHLY_ON_OFF | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0023 | TMP | 0 | [15 empty] | 24/11 - 24/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.TMP_GFK_MX_MONTHLY_REGIONAL) | OW_SEDA_S.TMP_GFK_MX_MONTHLY_REGIONAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0043 | TMP | 0 | [15 empty] | 24/11 - 24/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.TMP_GFK_MX_WEEKLY) | OW_SEDA_S.TMP_GFK_MX_WEEKLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TMP | 0 | [15 empty] | 24/11 - 24/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.TMP_GFK_NPC_MONTHLY) | OW_SEDA_S.TMP_GFK_NPC_MONTHLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [15 empty] | 24/11 - 24/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.TMP_GFK_NPC_WEEKLY) | OW_SEDA_S.TMP_GFK_NPC_WEEKLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TMP | 0 | [15 empty] | 24/11 - 24/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.TMP_GFK_TAB_MONTHLY) | OW_SEDA_S.TMP_GFK_TAB_MONTHLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [15 empty] | 24/11 - 24/11
GFK |  | TABLE | (TABLE - OW_SEDA_S.TMP_GFK_TAB_WEEKLY) | OW_SEDA_S.TMP_GFK_TAB_WEEKLY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0002 | TMP | 0 | [15 empty] | 24/11 - 24/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_DAILY_UPDATE) | OW_SEDA_S.TMP_GSCM_DAILY_UPDATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [15 empty] | 24/11 - 24/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_FCST_CE) | OW_SEDA_S.TMP_GSCM_FCST_CE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,001 | TMP | 0 | [15 empty] | 24/11 - 24/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_1) | OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [15 empty] | 24/11 - 24/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_2) | OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [15 empty] | 24/11 - 24/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_3) | OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0006 | TMP | 0 | [15 empty] | 24/11 - 24/11
GSCM |  | TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_4) | OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_4 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT) | OW_SEDA_S.TMP_MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_HA) | OW_SEDA_S.TMP_MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_HA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MAP_CE_PRODUCTS) | OW_SEDA_S.TMP_MAP_CE_PRODUCTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MAP_CE_STORES) | OW_SEDA_S.TMP_MAP_CE_STORES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
WebPrice |  | TABLE | (TABLE - OW_SEDA_S.TMP_MAP_CE_WEBPRICE_URL) | OW_SEDA_S.TMP_MAP_CE_WEBPRICE_URL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MOVING_AVERAGE_CE) | OW_SEDA_S.TMP_MOVING_AVERAGE_CE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0067 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MX_AI_USAGE_RATE) | OW_SEDA_S.TMP_MX_AI_USAGE_RATE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MX_DAILY_FOTA) | OW_SEDA_S.TMP_MX_DAILY_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MX_HEALTH_APP_WEEKLY_USAGE) | OW_SEDA_S.TMP_MX_HEALTH_APP_WEEKLY_USAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MX_SAMSUNG_HEALTH) | OW_SEDA_S.TMP_MX_SAMSUNG_HEALTH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0003 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MX_SAMSUNG_HEALTH_EVENTS) | OW_SEDA_S.TMP_MX_SAMSUNG_HEALTH_EVENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MX_SAMSUNG_WALLET) | OW_SEDA_S.TMP_MX_SAMSUNG_WALLET | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MX_SAMSUNG_WALLET_EVENTS) | OW_SEDA_S.TMP_MX_SAMSUNG_WALLET_EVENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_PARAGUAI_IMPORTS_MX) | OW_SEDA_S.TMP_PARAGUAI_IMPORTS_MX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [15 empty] | 24/11 - 24/11
PLUGGTO |  | TABLE | (TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER) | OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0012 | TMP | 0 | [15 empty] | 24/11 - 24/11
PLUGGTO |  | TABLE | (TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY) | OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
PLUGGTO |  | TABLE | (TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY_Migrar ph 2) | OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY_Migrarph2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0101 | TMP | 0 | [15 empty] | 24/11 - 24/11
PLUGGTO |  | TABLE | (TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_SHIPMENTS) | OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_SHIPMENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0006 | TMP | 0 | [15 empty] | 24/11 - 24/11
PLUGGTO |  | TABLE | (TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY) | OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0007 | TMP | 0 | [15 empty] | 24/11 - 24/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_SDI_TSS_NF_OD_ORDERS) | OW_SEDA_S.TMP_SDI_TSS_NF_OD_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,031 | TMP | 0 | [15 empty] | 24/11 - 24/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_SDI_TSS_TC_ORDERS) | OW_SEDA_S.TMP_SDI_TSS_TC_ORDERS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0434 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0022 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0207 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0005 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0023 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-24 | 2025-11-24 | ['[]'] | 0 | Migrar ph2 | 0,0022 | TMP | 0 | [15 empty] | 24/11 - 24/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,001 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0197 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0022 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0004 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_3 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0022 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_STORES) | OW_SEDA_S.TMP_SEDA_STORES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0001 | TMP | 0 | [15 empty] | 25/11 - 25/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_TSS_BI_TRACKING) | OW_SEDA_S.TMP_TSS_BI_TRACKING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0644 | TMP | 0 | [15 empty] | 25/11 - 25/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_TSS_BI_TRACKING_2YEARS_SDI) | OW_SEDA_S.TMP_TSS_BI_TRACKING_2YEARS_SDI | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0022 | TMP | 0 | [15 empty] | 25/11 - 25/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_TSS_BI_TRACKING_3MONTHS_SDI) | OW_SEDA_S.TMP_TSS_BI_TRACKING_3MONTHS_SDI | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0423 | TMP | 0 | [15 empty] | 25/11 - 25/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_TSS_BI_TRACKING_6MONTHS_SDI) | OW_SEDA_S.TMP_TSS_BI_TRACKING_6MONTHS_SDI | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0734 | TMP | 0 | [15 empty] | 25/11 - 25/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_TSS_BI_TRACKING_HIST) | OW_SEDA_S.TMP_TSS_BI_TRACKING_HIST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,127 | TMP | 0 | [15 empty] | 25/11 - 25/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_TSS_OD_ORDERS_DETAIL) | OW_SEDA_S.TMP_TSS_OD_ORDERS_DETAIL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0295 | TMP | 0 | [15 empty] | 25/11 - 25/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_TSS_OD_ORDERS_LOC) | OW_SEDA_S.TMP_TSS_OD_ORDERS_LOC | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0168 | TMP | 0 | [15 empty] | 25/11 - 25/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_TSS_RS_RESULT) | OW_SEDA_S.TMP_TSS_RS_RESULT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0413 | TMP | 0 | [15 empty] | 25/11 - 25/11
TSS | TSSLogistic | TABLE | (TABLE - OW_SEDA_S.TMP_TSS_TC_FOLLOW_UP_STATUS) | OW_SEDA_S.TMP_TSS_TC_FOLLOW_UP_STATUS | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0043 | TMP | 0 | [15 empty] | 25/11 - 25/11
WebPrice |  | TABLE | (TABLE - OW_SEDA_S.TMP_WEBPRICE) | OW_SEDA_S.TMP_WEBPRICE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0124 | TMP | 0 | [15 empty] | 25/11 - 25/11
GSCM |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_GSCM_SSG_ACTUAL_SALES) | U_PRJ_ECOM.RAW_GSCM_SSG_ACTUAL_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0032 | RAW | 0 | [15 empty] | 25/11 - 25/11
GSCM |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_GSCM_SSG_FCST_MGMT) | U_PRJ_ECOM.RAW_GSCM_SSG_FCST_MGMT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0,0061 | RAW | 0 | [15 empty] | 25/11 - 25/11
GSCM |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_GSCM_SSG_ACTUAL_SALES) | U_PRJ_ECOM.TMP_RAW_GSCM_SSG_ACTUAL_SALES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT) | OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 BI | 0,0036 | FT | 0 | [(VIEW - OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER) | OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 BI | 0,0027 | FT | 0 | [(VIEW - OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_COUNTRY) | OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_COUNTRY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 BI | 0,0005 | FT | 0 | [(VIEW - OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_COUNTRY)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_DDD) | OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_DDD | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 BI | 0,0002 | FT | 0 | [(VIEW - OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_DDD)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_FBAI_CHURN_IN_DATA) | OW_SEDA_S.FT_FBAI_CHURN_IN_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 BI | 0,0005 | FT | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_FBAI_CHURN_IN_DATA) | OW_SEDA_S.TMP_FBAI_CHURN_IN_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 BI | 0,0001 | TMP | 0 | [15 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_CE_STORES) | OW_SEDA_S.MAP_CE_STORES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,0884 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE),(PROCEDURE - OW_SEDA_S.PRC_TT_RAC_Migrar ph 2LIST_DE_EXECUCAO_785),(VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_STORE_NAME),(PROCEDURE - OW_SEDA_S.PRC_TT_WM_Migrar ph 2LIST_DE_EXECUCAO_785),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(PROCEDURE - OW_SEDA_S.PRC_VD_SALES_REVENUE),(INGESTION - JOB.MAP_CE_STORES),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_IBGE_INFO),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL),(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_ESES_ON_PIVOT),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDT_SHOPPING_W_BRANDSHOP),(VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING),(VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS),(PROCEDURE - OW_SEDA_S.PRC_VC_UPDATE_READY),(PROCEDURE - OW_SEDA_S.PRC_STOCK_OUT_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_DEAD_SKU_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_TT_REF_Migrar ph 2LIST_DE_EXECUCAO_785),(PROCEDURE - OW_SEDA_S.PRC_TT_TV_Migrar ph 2LIST_DE_EXECUCAO_785),(PROCEDURE - OW_SEDA_S.PRC_TT_AV_Migrar ph 2LIST_DE_EXECUCAO_785),(PROCEDURE - OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA),(PROCEDURE - OW_SEDA_S.PRC_TT_TV_Migrar ph 2LIST_DE_EXECUCAO),(VIEW - OW_SEDA_S.VW_TT_STACK_INFO_2023),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_GFK),(PROCEDURE - OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_CE_READY) | OW_SEDA_S.FT_CE_READY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,6369 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL),(INGESTION - JOB.FT_CE_READY),(VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS),(PROCEDURE - OW_SEDA_S.PRC_DEAD_SKU_CALCULATION),(VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING),(PROCEDURE - OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY),(PROCEDURE - OW_SEDA_S.PRC_VC_UPDATE_READY),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY),(PROCEDURE - OW_SEDA_S.PRC_STOCK_OUT_CALCULATION)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_CE_PIVOT) | OW_SEDA_S.FT_CE_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,4591 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_VD_SALES_REVENUE),(VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022),(VIEW - OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM),(VIEW - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_TARGET_WEEK_ADJ),(VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE),(PROCEDURE - OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_CE_STORE_EDI),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_ESES_ON_PIVOT),(VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT) | OW_SEDA_S.FT_CE_DAILY_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,7634 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY),(INGESTION - JOB.FT_CE_DAILY_PIVOT),(PROCEDURE - OW_SEDA_S.PRC_VC_UPDATE_READY),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_ESES_ON_PIVOT),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_DAILY_FOTA) | OW_SEDA_S.FT_MX_DAILY_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,085 | FT | 0 | [(VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST),(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_PIVOT_BY_ITEM) | OW_SEDA_S.FT_MX_PIVOT_BY_ITEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 12818 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT),(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_CE_DB_FCST) | OW_SEDA_S.FT_CE_DB_FCST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,0538 | FT | 0 | [(INGESTION - JOB.FT_CE_DB_FCST)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_CE_DB_FCST_PIVOT) | OW_SEDA_S.FT_CE_DB_FCST_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,0022 | FT | 0 | [(VIEW - OW_SEDA_S.VW_CE_META_PROMOTOR)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_PIVOT) | OW_SEDA_S.FT_MX_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,6868 | FT | 0 | [(VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_MX_PIVOT_2022) | OW_SEDA_S.FT_MX_PIVOT_2022 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,0014 | FT | 0 | [(VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.FT_SEDA_EDI_DATA) | OW_SEDA_S.FT_SEDA_EDI_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,6803 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_CE_STORE_EDI) | OW_SEDA_S.ODS_CE_STORE_EDI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,1593 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_STORE_EDI)] | [14 empty] | 25/11 - 25/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_MX_PIVOT) | OW_SEDA_S.TMP_MX_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0,0068 | TMP | 0 | [15 empty] | 25/11 - 25/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_SHIPMENT) | OW_SEDA_S.ODS_CELLO_SHIPMENT | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 1 | Migrar ph2: Cello | 0,1927 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 25/11 - 25/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_TRACKING) | OW_SEDA_S.ODS_CELLO_TRACKING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 1 | Migrar ph2: Cello | 0,2215 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 25/11 - 25/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_SHIPMENT_INBOUND) | OW_SEDA_S.ODS_CELLO_SHIPMENT_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 1 | Migrar ph2: Cello | 0,0329 | ODS | 0 | [15 empty] | 25/11 - 25/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_VESSEL) | OW_SEDA_S.ODS_CELLO_VESSEL | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 1 | Migrar ph2: Cello | 0,0029 | ODS | 0 | [15 empty] | 25/11 - 25/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_BOOKING) | OW_SEDA_S.ODS_CELLO_BOOKING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2: Cello | 0,1109 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 25/11 - 25/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY) | OW_SEDA_S.ODS_CELLO_DELIVERY | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-25 | 2025-11-25 | ['[]'] | 0 | Migrar ph2: Cello | 0,7559 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 25/11 - 25/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND) | OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Cello | 0,0621 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 26/11 - 26/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND_ITEM) | OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND_ITEM | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Cello | 0,0198 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 26/11 - 26/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_ITEM) | OW_SEDA_S.ODS_CELLO_DELIVERY_ITEM | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Cello | 0,185 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 26/11 - 26/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_FUTHER_PROCESSING) | OW_SEDA_S.ODS_CELLO_FUTHER_PROCESSING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Cello | 0,0162 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 26/11 - 26/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_LAST_LEG_MANIFEST) | OW_SEDA_S.ODS_CELLO_LAST_LEG_MANIFEST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Cello | 0,02 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 26/11 - 26/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_MANIFEST) | OW_SEDA_S.ODS_CELLO_MANIFEST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Cello | 0,2314 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 26/11 - 26/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_POD) | OW_SEDA_S.ODS_CELLO_POD | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Cello | 0,0059 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | [14 empty] | 26/11 - 26/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND_VAGNER) | OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND_VAGNER | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Cello | 0,0004 | ODS | 0 | [15 empty] | 26/11 - 26/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_INBOUND_BOOKING) | OW_SEDA_S.ODS_CELLO_INBOUND_BOOKING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Cello | 0,0228 | ODS | 0 | [15 empty] | 26/11 - 26/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_MANIFEST_INBOUND) | OW_SEDA_S.ODS_CELLO_MANIFEST_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Cello | 0,0214 | ODS | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL) | OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Controlling | 11336 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE),(INGESTION - JOB.ODS_CONTROLLING_FORMAT_ACTUAL),(VIEW - OW_SEDA_S.VW_CE_MANAGEMENT_INFORMATION),(PROCEDURE - OW_SEDA_S.PRC_CE_MANAGEMENT_INFORMATION),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_CONTROLLING_PL) | OW_SEDA_S.ODS_CONTROLLING_PL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Controlling | 0,0721 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_ONLINE_SELL_IN),(VIEW - OW_SEDA_S.VW_CE_MBO_NETSALES_COP_FCST),(INGESTION - JOB.ODS_CONTROLLING_PL),(VIEW - OW_SEDA_S.VW_CE_MBO_NETSALES_COP),(VIEW - OW_SEDA_S.VW_CE_GERENCIAIS_PL_FCST),(VIEW - OW_SEDA_S.VW_CE_GERENCIAIS_PL)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_CONTROLLING_PL_2) | OW_SEDA_S.ODS_CONTROLLING_PL_2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Controlling | 0,0584 | ODS | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_DX_PIVOT) | OW_LAO.FT_LAO_DX_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 11361 | FT | 0 | [(PROCEDURE - OW_LAO.PRC_ODS_LAO_GSCM_EDI_DATA)] | [14 empty] | 26/11 - 26/11
GSCM |  | TABLE | (TABLE - OW_LAO.ODS_LAO_GSCM_EDI_DATA) | OW_LAO.ODS_LAO_GSCM_EDI_DATA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 22802 | ODS | 0 | [(PROCEDURE - OW_LAO.PRC_ODS_LAO_GSCM_EDI_DATA)] | [14 empty] | 26/11 - 26/11
ASAP |  | TABLE | (TABLE - OW_LAO.FT_ASAP_FOTA_GEOLOCATION_SAMCOL) | OW_LAO.FT_ASAP_FOTA_GEOLOCATION_SAMCOL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0212 | FT | 0 | [15 empty] | 26/11 - 26/11
ASAP |  | TABLE | (TABLE - OW_LAO.FT_ASAP_FOTA_GEOLOCATION_SEM) | OW_LAO.FT_ASAP_FOTA_GEOLOCATION_SEM | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0585 | FT | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_CE_PIVOT) | OW_LAO.FT_LAO_CE_PIVOT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,4518 | FT | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_MX_SELLOUT_FOTA) | OW_LAO.FT_LAO_MX_SELLOUT_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0707 | FT | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.FT_LAO_SO_FCST) | OW_LAO.FT_LAO_SO_FCST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0076 | FT | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.MAP_DA_FLOORING_TARGET_ONE_LAUNCH) | OW_LAO.MAP_DA_FLOORING_TARGET_ONE_LAUNCH | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0001 | MAP | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.MAP_DA_ONE_LAUNCH_PIN_TO_PIN_2025) | OW_LAO.MAP_DA_ONE_LAUNCH_PIN_TO_PIN_2025 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0 | MAP | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.MAP_LAO_CALENDAR) | OW_LAO.MAP_LAO_CALENDAR | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0001 | MAP | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.MAP_LAO_DA_ONE_LAUNCH_TRAINING_TARGET) | OW_LAO.MAP_LAO_DA_ONE_LAUNCH_TRAINING_TARGET | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0001 | MAP | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.MAP_LAO_PRODUCTS) | OW_LAO.MAP_LAO_PRODUCTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0005 | MAP | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.MAP_LAO_STORES) | OW_LAO.MAP_LAO_STORES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0026 | MAP | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.MAP_SMART_THING_ZONE_STORES) | OW_LAO.MAP_SMART_THING_ZONE_STORES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0001 | MAP | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.ODS_LAO_PSI_CE_READY) | OW_LAO.ODS_LAO_PSI_CE_READY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,5075 | ODS | 0 | [15 empty] | 26/11 - 26/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_LAO_GSCM_DSM_EDI) | OW_LAO.RAW_LAO_GSCM_DSM_EDI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0606 | RAW | 0 | [15 empty] | 26/11 - 26/11
GSCM |  | TABLE | (TABLE - OW_LAO.RAW_LAO_GSCM_SO_FCST) | OW_LAO.RAW_LAO_GSCM_SO_FCST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0001 | RAW | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.RAW_LAO_MX_SELLOUT_FOTA) | OW_LAO.RAW_LAO_MX_SELLOUT_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,0034 | RAW | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_LAO.RAW_LAO_PSI_VD_HA_INPUT_R) | OW_LAO.RAW_LAO_PSI_VD_HA_INPUT_R | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: LAO RM | 0,024 | RAW | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_IBGE_CEP_5_COORDINATES) | OW_SEDA_S.ODS_IBGE_CEP_5_COORDINATES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0,0018 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_IBGE_CEP_5_COORDINATES)] | [14 empty] | 26/11 - 26/11
ASAP |  | TABLE | (TABLE - OW_SEDA_S.FT_ASAP_REGIONAL_FOTA) | OW_SEDA_S.FT_ASAP_REGIONAL_FOTA | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0,6818 | FT | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SEDA_S.MAP_IBGE_LAT_LONG) | OW_SEDA_S.MAP_IBGE_LAT_LONG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0,0002 | MAP | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_IBGE_CEP_COORDINATES) | OW_SEDA_S.ODS_IBGE_CEP_COORDINATES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0,0069 | ODS | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_IBGE_SETORES_CENSITARIOS_2021) | OW_SEDA_S.ODS_IBGE_SETORES_CENSITARIOS_2021 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0,0001 | ODS | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SEDA_S.RAW_IBGE_POPULACAO) | OW_SEDA_S.RAW_IBGE_POPULACAO | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0,0002 | RAW | 0 | [15 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SEDA_S.EDI_DATA_RAW) | OW_SEDA_S.EDI_DATA_RAW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: SEDA RM | 31799 | OTHER | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT),(PROCEDURE - OW_SEDA_S.CONN_TO_SEDA),(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT_RETAILERS)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_USERS) | OW_SDSLA.ODS_TABLEAU_USERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Tableau | 0,003 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_USERS),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.ODS_TABLEAU_PROJECT_HIERARCHY),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS) | OW_SDSLA.ODS_TABLEAU_GROUP_USERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0016 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_USERS),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS) | OW_SDSLA.ODS_TABLEAU_V_GROUPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0005 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_USERS),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS) | OW_SDSLA.ODS_TABLEAU_V_USERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Tableau | 0,003 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_USERS),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS) | OW_SDSLA.ODS_TABLEAU_EXTRACTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0042 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS) | OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0282 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES) | OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0009 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS) | OW_SDSLA.ODS_TABLEAU_HIST_VIEWS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0075 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS) | OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-26 | 2025-11-26 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0388 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT)] | [14 empty] | 26/11 - 26/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS) | OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0017 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST)] | [14 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS_STATS) | OW_SDSLA.ODS_TABLEAU_VIEWS_STATS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0192 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3)] | [14 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_PROJECTS) | OW_SDSLA.ODS_TABLEAU_PROJECTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0009 | ODS | 0 | [(VIEW - OW_SDSLA.ODS_TABLEAU_PROJECT_HIERARCHY)] | [14 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_SYSTEM_USERS) | OW_SDSLA.ODS_TABLEAU_SYSTEM_USERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0022 | ODS | 0 | [(VIEW - OW_SDSLA.ODS_TABLEAU_PROJECT_HIERARCHY)] | [14 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_WORKBOOKS) | OW_SDSLA.ODS_TABLEAU_WORKBOOKS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0049 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT)] | [14 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.RAW_TABLEAU_DASHBOARDS_MACHINE_STATUS) | OW_SDSLA.RAW_TABLEAU_DASHBOARDS_MACHINE_STATUS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0 | RAW | 0 | [(PROCEDURE - OW_SDSLA.PROC_TABLEAU_DASHBOARDS_MACHINE_STATUS)] | [14 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLEAU_ACCESS_VIEW) | OW_SDSLA.ODS_SDSLA_TABLEAU_ACCESS_VIEW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0033 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_DESKTOP_REPORTING) | OW_SDSLA.ODS_TABLEAU_DESKTOP_REPORTING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0034 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_DOMAINS) | OW_SDSLA.ODS_TABLEAU_DOMAINS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0008 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_FLOWS) | OW_SDSLA.ODS_TABLEAU_FLOWS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0004 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_FLOW_OUTPUT_STEPS) | OW_SDSLA.ODS_TABLEAU_FLOW_OUTPUT_STEPS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0007 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_FLOW_OUTPUT_STEP_RUNS) | OW_SDSLA.ODS_TABLEAU_FLOW_OUTPUT_STEP_RUNS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0004 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_FLOW_RUNS) | OW_SDSLA.ODS_TABLEAU_FLOW_RUNS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0005 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_FLOW_RUN_SPECS) | OW_SDSLA.ODS_TABLEAU_FLOW_RUN_SPECS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0007 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_DISK_USAGE) | OW_SDSLA.ODS_TABLEAU_HISTORICAL_DISK_USAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0056 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_USERS) | OW_SDSLA.ODS_TABLEAU_HISTORICAL_USERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0022 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_COMMENTS) | OW_SDSLA.ODS_TABLEAU_HIST_COMMENTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0001 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_DATASOURCES) | OW_SDSLA.ODS_TABLEAU_HIST_DATASOURCES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0068 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_FLOWS) | OW_SDSLA.ODS_TABLEAU_HIST_FLOWS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0006 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_PROJECTS) | OW_SDSLA.ODS_TABLEAU_HIST_PROJECTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,001 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_SITES) | OW_SDSLA.ODS_TABLEAU_HIST_SITES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0009 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_USERS) | OW_SDSLA.ODS_TABLEAU_HIST_USERS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0026 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_WORKBOOKS) | OW_SDSLA.ODS_TABLEAU_HIST_WORKBOOKS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0056 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HTTP_REQUESTS) | OW_SDSLA.ODS_TABLEAU_HTTP_REQUESTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 31806 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HTTP_REQUESTS_TMP) | OW_SDSLA.ODS_TABLEAU_HTTP_REQUESTS_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0003 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_IDENTITY_BASED_ACTIVATION_ADMIN_VIEW) | OW_SDSLA.ODS_TABLEAU_IDENTITY_BASED_ACTIVATION_ADMIN_VIEW | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0005 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_LICENSES_BY_SUB) | OW_SDSLA.ODS_TABLEAU_LICENSES_BY_SUB | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0005 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_SITES) | OW_SDSLA.ODS_TABLEAU_SITES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0009 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_SITE_ROLES) | OW_SDSLA.ODS_TABLEAU_SITE_ROLES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,001 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_USERS_V1) | OW_SDSLA.ODS_TABLEAU_USERS_V1 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0003 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS) | OW_SDSLA.ODS_TABLEAU_VIEWS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0017 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_BACKGROUND_TASKS) | OW_SDSLA.ODS_TABLEAU_V_BACKGROUND_TASKS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 19601 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_DATASOURCES) | OW_SDSLA.ODS_TABLEAU_V_DATASOURCES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,001 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_DATASOURCES_STATS) | OW_SDSLA.ODS_TABLEAU_V_DATASOURCES_STATS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0013 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_HTTP_REQUESTS) | OW_SDSLA.ODS_TABLEAU_V_HTTP_REQUESTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0106 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_SESSIONS) | OW_SDSLA.ODS_TABLEAU_V_SESSIONS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0014 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_SITES) | OW_SDSLA.ODS_TABLEAU_V_SITES | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph2: Tableau | 0,0008 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_CS_INFORMATION_BSC) | U_PRJ_ECOM.ODS_CS_INFORMATION_BSC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 1 | Migrar ph 2 | 0,0001 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_CE_AMAZON_SELL_OUT_FCST) | OW_SEDA_S.ODS_CE_AMAZON_SELL_OUT_FCST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph 2 | 0,0001 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_AMAZON_PRIME_DAY)] | [14 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_RP_ETR_LOGISTICS_TRACKING) | OW_SEDA_S.ODS_RP_ETR_LOGISTICS_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph 2 | 0,1935 | ODS | 0 | [(INGESTION - JOB.ODS_RP_ETR_LOGISTICS_TRACKING)] | [14 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_SCM_FINANCIAL_FCST) | OW_SEDA_S.ODS_SCM_FINANCIAL_FCST | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph 2 | 0,0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SCM_SALES_AND_SO_LIST_COMPLETE)] | [14 empty] | 27/11 - 27/11
INFRAPAY |  | TABLE | (TABLE - OW_SEDA_S.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG) | OW_SEDA_S.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph 2 | 0 | ODS | 0 | [(INGESTION - JOB.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG)] | [14 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_LAO.ODS_GG_ANALYTICS_DL) | OW_LAO.ODS_GG_ANALYTICS_DL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph 2 | 0,6227 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ERP_INCOMPLETESDOCS_SOREPORT) | OW_SEDA_S.ODS_ERP_INCOMPLETESDOCS_SOREPORT | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph 2 | 0,0032 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED) | OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph 2 | 0,0086 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_DAY) | OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_DAY | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph 2 | 0,0196 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_WEEK) | OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_WEEK | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph 2 | 0,0232 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_RP_ETR_CS_AEN_NF_Migrar ph 2) | OW_SEDA_S.ODS_RP_ETR_CS_AEN_NF_Migrarph2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-27 | 2025-11-27 | ['[]'] | 0 | Migrar ph 2 | 0,0544 | ODS | 0 | [15 empty] | 27/11 - 27/11
|  | TABLE | (TABLE - OW_SEDA_S.ODS_RP_ETR_CS_AGING) | OW_SEDA_S.ODS_RP_ETR_CS_AGING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 0,1904 | ODS | 0 | [15 empty] | 28/11 - 28/11
|  | TABLE | (TABLE - OW_SEDA_S.RAW_ANATEL_ACESSOS_TELEFONIA_MOVEL) | OW_SEDA_S.RAW_ANATEL_ACESSOS_TELEFONIA_MOVEL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 17213 | RAW | 0 | [15 empty] | 28/11 - 28/11
|  | TABLE | (TABLE - OW_SEDA_S.RAW_DATA_SNOWFLAKE_CS_SALES_FORCE) | OW_SEDA_S.RAW_DATA_SNOWFLAKE_CS_SALES_FORCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 0,8206 | RAW | 0 | [15 empty] | 28/11 - 28/11
|  | TABLE | (TABLE - OW_SEDA_S.RAW_MX_TMV_INDEX) | OW_SEDA_S.RAW_MX_TMV_INDEX | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 0,0002 | RAW | 0 | [15 empty] | 28/11 - 28/11
|  | TABLE | (TABLE - OW_SEDA_S.RAW_TECH_INSIGHTS) | OW_SEDA_S.RAW_TECH_INSIGHTS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 0,0005 | RAW | 0 | [15 empty] | 28/11 - 28/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_RP_ETR_CS_AEN_NF_Migrar ph 2) | OW_SEDA_S.TMP_RP_ETR_CS_AEN_NF_Migrarph2 | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 0,0547 | TMP | 0 | [15 empty] | 28/11 - 28/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_RP_ETR_CS_AGING) | OW_SEDA_S.TMP_RP_ETR_CS_AGING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 0,1915 | TMP | 0 | [15 empty] | 28/11 - 28/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_RP_ETR_LOGISTICS_TRACKING) | OW_SEDA_S.TMP_RP_ETR_LOGISTICS_TRACKING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 0,198 | TMP | 0 | [15 empty] | 28/11 - 28/11
|  | TABLE | (TABLE - OW_SEDA_S.TMP_SNOWFLAKE_CS_SALES_FORCE) | OW_SEDA_S.TMP_SNOWFLAKE_CS_SALES_FORCE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 0,0004 | TMP | 0 | [15 empty] | 28/11 - 28/11
PREDIZE |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_PREDIZE_TICKETS) | U_PRJ_ECOM.ODS_PREDIZE_TICKETS | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 16089 | ODS | 0 | [15 empty] | 28/11 - 28/11
PREDIZE |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_PREDIZE_TICKET_MESSAGE) | U_PRJ_ECOM.ODS_PREDIZE_TICKET_MESSAGE | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 47185 | ODS | 0 | [15 empty] | 28/11 - 28/11
PREDIZE |  | TABLE | (TABLE - U_PRJ_ECOM.ODS_PREDIZE_TICKET_ORDER) | U_PRJ_ECOM.ODS_PREDIZE_TICKET_ORDER | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 25348 | ODS | 0 | [15 empty] | 28/11 - 28/11
|  | TABLE | (TABLE - U_PRJ_ECOM.RAW_CS_INFORMATION_BSC) | U_PRJ_ECOM.RAW_CS_INFORMATION_BSC | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | Migrar ph 2 | 0,0009 | RAW | 0 | [15 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO) | OW_SEDA_S.FT_UNION_TSS_CELLO | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 1 | migrar ph2 | 0,1817 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(VIEW - OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO)] | [14 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING) | OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 1 | migrar ph2 | 0,1761 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_SDU_FT_TSS_CELLO_IOD_STATUS_MONITORING)] | [14 empty] | 28/11 - 28/11
Cello,NERP | CelloLogistic | TABLE | (TABLE - OW_LAO.FT_D2C_CELLO_NERP_RETURN_OPERATION) | OW_LAO.FT_D2C_CELLO_NERP_RETURN_OPERATION | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 1 | migrar ph2 | 0,0254 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION)] | [14 empty] | 28/11 - 28/11
Cello,NERP | CelloLogistic | TABLE | (TABLE - OW_LAO.FT_D2C_CELLO_NERP_RETURN_PENDING) | OW_LAO.FT_D2C_CELLO_NERP_RETURN_PENDING | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 1 | migrar ph2 | 0,0008 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING)] | [14 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING_TMP) | OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING_TMP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 1 | migrar ph2 | 0,1761 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING)] | [14 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TRACKING_INBOUND_TMP) | OW_SEDA_S.FT_UNION_TSS_CELLO_TRACKING_INBOUND_TMP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 1 | migrar ph2 | 0,0967 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL) | OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 15735 | FT | 0 | [(VIEW - OW_SEDA_S.VW_UNION_CELLO_TSS_IOD_STATUS),(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST),(VIEW - OW_SEDA_S.VW_SEDA_SALES_IN_TRANSIT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_PHOTO),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO)] | [14 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST) | OW_SEDA_S.FT_UNION_TSS_CELLO_HIST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,2811 | FT | 0 | [(VIEW - OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO_HIST),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST_MAP_CARRIER)] | [14 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TMP) | OW_SEDA_S.FT_UNION_TSS_CELLO_TMP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,182 | FT | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP_TEST)] | [14 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2) | OW_SEDA_S.FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2 | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,2293 | FT | 0 | [(VIEW - OW_SEDA_S.VW_SDU_FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2)] | [14 empty] | 28/11 - 28/11
Cello,NERP | CelloLogistic | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI) | OW_LAO.FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,0001 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello,NERP | CelloLogistic | TABLE | (TABLE - OW_LAO.FT_D2C_NERP_CELLO_YAMI_LEAD_TIME_RETURN_KPI) | OW_LAO.FT_D2C_NERP_CELLO_YAMI_LEAD_TIME_RETURN_KPI | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,001 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_BI_TRACKING_CELLO_TSS_HIST) | OW_SEDA_S.FT_BI_TRACKING_CELLO_TSS_HIST | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,1807 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_BI_TRACKING_CLEAN_CELLO_TSS_ORDER_OPERATION) | OW_SEDA_S.FT_BI_TRACKING_CLEAN_CELLO_TSS_ORDER_OPERATION | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,2848 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.FT_CELLO_TRACKING_INBOUND) | OW_SEDA_S.FT_CELLO_TRACKING_INBOUND | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,0978 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello | CelloLogistic | TABLE | (TABLE - OW_SEDA_S.FT_CELLO_TRACKING_INBOUND_TMP) | OW_SEDA_S.FT_CELLO_TRACKING_INBOUND_TMP | [5 empty] | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,0978 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_EXCLUDED_DO) | OW_SEDA_S.FT_UNION_TSS_CELLO_EXCLUDED_DO | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,0001 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C) | OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 10659 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C_TMP) | OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C_TMP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,0001 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_TMP) | OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_TMP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,3809 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TEMP) | OW_SEDA_S.FT_UNION_TSS_CELLO_TEMP | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,0599 | FT | 0 | [15 empty] | 28/11 - 28/11
Cello,TSS | CelloTSSLogistic | TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TRACKING_INBOUND) | OW_SEDA_S.FT_UNION_TSS_CELLO_TRACKING_INBOUND | SEDA Logistic |  |  |  |  | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 0 | migrar ph2 | 0,1603 | FT | 0 | [15 empty] | 28/11 - 28/11
|  | TABLE | (TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE) | OW_LAO.FT_AP2_EXCHANGE_RATE | LAO EStore | r.bojart |  | yes | 1 | Done |  |  |  | 1 | 1 | 2025-11-28 | 2025-11-28 | ['[]'] | 1 | 4.1 Migrar ph 1 | 0,0052 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1_V2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1_V2),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE_BKP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(VIEW - OW_LAO.VIEW_NERP_ZRCOS43400_TARGET),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HISTORICO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1),(VIEW - OW_LAO.VW_CRAWLING_AP1_NPC_SEGMENT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WERABLES_PT1),(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(VIEW - OW_LAO.VW_CRAWLING_AP1_REF_SEGMENT),(VIEW - OW_LAO.VW_CRAWLING_AP1_REF_DISPLAY_SHARE),(VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE),(VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE),(VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET),(VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET_TEST),(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1_V2),(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_VC_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_V2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_DUEK),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HIST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_ESTORE_URL_SKU),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE_TABLET),(VIEW - OW_LAO.VW_CRAWLING_AP1_WM_SEGMENT),(VIEW - OW_LAO.VW_CRAWLING_AP1_WM_DISPLAY_SHARE),(VIEW - OW_LAO.VW_CRAWLING_AP1_TV_SEGMENT),(VIEW - OW_LAO.VW_CRAWLING_AP1_TV_DISPLAY_SHARE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI),(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_PT1),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - OW_LAO.VIEW_ECOM_EXCHANGE_RATE),(PROCEDURE - U_PRJ_ECOM.PROC_DIM_EXCHANGE_RATE_RAWDATA),(VIEW - OW_LAO.VW_CRAWLING_AP1_ESTORE_DAILY_PRICE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG)] | [14 empty] | 28/11 - 28/11
|  | VIEW | (VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA) | OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-01 | 2025-12-01 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM)'", "'(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA)'", "'(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_NC)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_ESCORT)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_NC)]']"] | 0 | Migrar ph 2 |  |  | 6 | [16 empty] | 01/12 - 01/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_PORTAL_SM_SURSIS) | OW_SEDA_S.VW_PORTAL_SM_SURSIS | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-01 | 2025-12-01 | ["['[(TABLE - OW_SEDA_S.ODS_SURSIS_ESCORT)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_NC)]']"] | 0 | Migrar ph 2 |  |  | 3 | [16 empty] | 01/12 - 01/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA) | OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-01 | 2025-12-01 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM)'", "'(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA)'", "'(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_NC)]']"] | 0 | Migrar ph 2 |  |  | 3 | [16 empty] | 01/12 - 01/12
|  | PROCEDURE | (PROCEDURE - OW_SELA.ProcMergeDMSDataV2) | OW_SELA.ProcMergeDMSDataV2 | [5 empty] | To be migrated |  |  |  | 4 | 1 | 2025-12-01 | 2025-12-01 | ["['[(TABLE - OW_SELA.DIM_PRODUCT)'", "'(TABLE - OW_SELA.FACT_STOCK_SALES)'", "'(TABLE - OW_SELA.STAGE2_FACT_STOCK_SALES)]']"] | 1 | Migrar ph 2 |  |  | 3 | [16 empty] | 01/12 - 01/12
Cello | CelloLogistic | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS) | OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS | SEDA Logistic |  |  |  |  | Done |  |  |  | 4 | 1 | 2025-12-01 | 2025-12-01 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE)'", "'(TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS)'", "'(TABLE - OW_LAO.AUX_YAMI_PRODUCT_DETAIL_STATUS)]']"] | 1 | Migrar ph 2 |  |  | 4 | [16 empty] | 01/12 - 01/12
|  | PROCEDURE | (PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD) | OW_SELA.PROCSNAPSHOTFCST_OLD | [5 empty] | To be migrated |  |  |  | 4 | 1 | 2025-12-01 | 2025-12-01 | ["['[(TABLE - OW_SELA.TMP_DLAKE_W3)'", "'(TABLE - OW_SELA.DIM_WEEK)'", "'(TABLE - OW_SELA.DIM_MN_SEGMENT)'", "'(TABLE - OW_SELA.FCST_SNAPSHOT)'", "'(TABLE - OW_SELA.TMP_DLAKE_W8)'", "'(TABLE - OW_SELA.TMP_DLAKE_HIST)'", "'(TABLE - OW_SELA.DIM_DC)]']"] | 0 | Migrar ph 2 |  |  | 7 | [16 empty] | 01/12 - 01/12
|  | PROCEDURE | (PROCEDURE - OW_SELA.PROCSNAPSHOTFCST) | OW_SELA.PROCSNAPSHOTFCST | [5 empty] | To be migrated |  |  |  | 4 | 1 | 2025-12-01 | 2025-12-01 | ["['[(TABLE - OW_SELA.TMP_DLAKE_W3)'", "'(TABLE - OW_SELA.DIM_PRODUCT)'", "'(TABLE - OW_SELA.FACT_STOCK_SALES)'", "'(TABLE - OW_SELA.WOS_PARAMETERS)'", "'(TABLE - OW_SELA.DIM_GROWTH)'", "'(TABLE - OW_SELA.DIM_WEEK)'", "'(TABLE - OW_SELA.DIM_COUNTRY)'", "'(TABLE - OW_SELA.DIM_COUNTRY_BRANCH)'", "'(TABLE - OW_SELA.DIM_MN_SEGMENT)'", "'(TABLE - OW_SELA.FCST_SNAPSHOT)'", "'(TABLE - OW_SELA.TMP_DLAKE_W8)'", "'(TABLE - OW_SELA.TMP_DLAKE_HIST)'", "'(TABLE - OW_SELA.DIM_DC)]']"] | 0 | Migrar ph 2 |  |  | 13 | [16 empty] | 01/12 - 01/12
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING) | OW_SEDA_S.VW_CELLO_RETURN_TRACKING | SEDA Logistic |  |  |  |  | Done |  | 2026-01-02 |  | 3 | 1 | 2025-12-01 | 2025-12-01 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | Migrar ph 2 |  |  | 11 | [16 empty] | 01/12 - 01/12
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING) | OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING | SEDA Logistic |  |  |  |  | Done |  | 2025-12-29 |  | 3 | 1 | 2025-12-01 | 2025-12-01 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | Migrar ph 2 |  |  | 11 | [16 empty] | 01/12 - 01/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_STATUS_MAPPING) | OW_SEDA_S.VW_STATUS_MAPPING | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-01 | 2025-12-01 | ["['[(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)]']"] | 1 | Migrar ph 2 |  |  | 3 | [16 empty] | 01/12 - 01/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_STATUS_MAPPING_AUX) | OW_SEDA_S.VW_STATUS_MAPPING_AUX | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-02 | 2025-12-02 | ["['[(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)]']"] | 1 | Migrar ph 2 |  |  | 3 | [16 empty] | 02/12 - 02/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_MONITORING_STATUS) | OW_LAO.PROC_SALES_DEDUCTION_MONITORING_STATUS |  |  |  | No |  | Done |  | 2025-12-09 |  | 4 | 1 | 2025-12-02 | 2025-12-02 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)]']"] | 1 | Migrar ph2 |  |  | 3 | [16 empty] | 02/12 - 02/12
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2 | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-29 |  | 3 | 1 | 2025-12-02 | 2025-12-02 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Migrar ph 2 |  |  | 12 | [16 empty] | 02/12 - 02/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-02 | 2025-12-02 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Migrar ph 2 |  |  | 12 | [16 empty] | 02/12 - 02/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-02 | 2025-12-02 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Migrar ph 2 |  |  | 12 | [16 empty] | 02/12 - 02/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-02 | 2025-12-02 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Migrar ph 2 |  |  | 12 | [16 empty] | 02/12 - 02/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-02 | 2025-12-02 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Migrar ph 2 |  |  | 12 | [16 empty] | 02/12 - 02/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-02 | 2025-12-02 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Migrar ph 2 |  |  | 12 | [16 empty] | 02/12 - 02/12
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI) | OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-29 |  | 3 | 1 | 2025-12-02 | 2025-12-02 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Migrar ph 2 |  |  | 12 | [16 empty] | 02/12 - 02/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_MANAGEMENT_INFORMATION) | OW_SEDA_S.VW_CE_MANAGEMENT_INFORMATION | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-02 | 2025-12-02 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_KAM)]']"] | 0 | Migrar ph2 |  |  | 3 | [16 empty] | 02/12 - 02/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_MANAGEMENT_INFORMATION) | OW_SEDA_S.PRC_CE_MANAGEMENT_INFORMATION | [5 empty] | Done |  | 2025-12-24 |  | 4 | 1 | 2025-12-03 | 2025-12-03 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_KAM)]']"] | 0 | Migrar ph2 |  |  | 3 | [16 empty] | 03/12 - 03/12
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3 | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-29 |  | 3 | 1 | 2025-12-03 | 2025-12-03 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph 2 |  |  | 15 | [16 empty] | 03/12 - 03/12
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4 | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-29 |  | 3 | 1 | 2025-12-03 | 2025-12-03 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph 2 |  |  | 15 | [16 empty] | 03/12 - 03/12
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5 | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-29 |  | 3 | 1 | 2025-12-03 | 2025-12-03 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph 2 |  |  | 15 | [16 empty] | 03/12 - 03/12
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst | SEDA Logistic |  |  |  |  | To be migrated |  | 2026-01-05 |  | 3 | 1 | 2025-12-03 | 2025-12-03 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph 2 |  |  | 14 | [16 empty] | 03/12 - 03/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI) | OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-03 | 2025-12-03 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)]']"] | 0 | Migrar ph2 |  |  | 7 | [16 empty] | 03/12 - 03/12
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD) | OW_SEDA_S.VW_UNION_TSS_CELLO_IOD | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-30 |  | 3 | 1 | 2025-12-03 | 2025-12-03 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph 2 |  |  | 18 | [16 empty] | 03/12 - 03/12
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL) | OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-30 |  | 3 | 1 | 2025-12-03 | 2025-12-03 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph 2 |  |  | 17 | [16 empty] | 03/12 - 03/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI) | OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-03 | 2025-12-03 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 28 | [16 empty] | 03/12 - 03/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI) | OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-03 | 2025-12-03 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 28 | [16 empty] | 03/12 - 03/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE) | OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-04 | 2025-12-04 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 28 | [16 empty] | 04/12 - 04/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016) | OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-04 | 2025-12-04 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 28 | [16 empty] | 04/12 - 04/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI) | OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-04 | 2025-12-04 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 27 | [16 empty] | 04/12 - 04/12
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FNS_NM2) | OW_SEDA_S.FNS_NM2 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-04 | 2025-12-04 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)]']"] | 0 | Migrar ph2 |  |  | 8 | [16 empty] | 04/12 - 04/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_MX_POSITIVACAO_S24) | OW_SEDA_S.VW_MX_POSITIVACAO_S24 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-04 | 2025-12-04 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 4 | [16 empty] | 04/12 - 04/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W |  |  |  | No |  | Done |  |  |  | 4 | 1 | 2025-12-04 | 2025-12-04 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO)]']"] | 1 | Migrar ph2 |  |  | 8 | [16 empty] | 04/12 - 04/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W) | OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W |  |  |  | No |  | Done |  |  |  | 4 | 1 | 2025-12-04 | 2025-12-04 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)]']"] | 1 | Migrar ph2 |  |  | 7 | [16 empty] | 04/12 - 04/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION) | OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION |  |  |  | No |  | Done |  |  |  | 4 | 1 | 2025-12-04 | 2025-12-04 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)]']"] | 1 | Migrar ph2 |  |  | 7 | [16 empty] | 04/12 - 04/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2) | OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2 |  |  |  | No |  | Done |  |  |  | 4 | 1 | 2025-12-04 | 2025-12-04 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)]']"] | 1 | Migrar ph2 |  |  | 7 | [16 empty] | 04/12 - 04/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_GENERATED) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_GENERATED |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2025-12-04 | 2025-12-04 | ["['[(TABLE - OW_LAO.MONITORING_EXECUTIONS)'", "'(TABLE - OW_LAO.MONITORING_PARAMETERS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 3 | [16 empty] | 04/12 - 04/12
WebPrice |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX) | OW_SEDA_S.PRC_WEBPRICE_DAILY_MX |  |  |  | No | No | Done |  | 2025-12-10 |  | 4 | 1 | 2025-12-05 | 2025-12-05 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX)'", "'(TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO)]']"] | 0 | Migrar ph2 |  |  | 3 | [16 empty] | 05/12 - 05/12
WebPrice |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST) | OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST |  |  |  | No | No | Done |  | 2025-12-10 |  | 4 | 1 | 2025-12-05 | 2025-12-05 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX)'", "'(TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO)]']"] | 0 | Migrar ph2 |  |  | 3 | [16 empty] | 05/12 - 05/12
WebPrice |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST_2) | OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST_2 |  |  |  | No | No | Done |  | 2025-12-10 |  | 4 | 1 | 2025-12-05 | 2025-12-05 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX)'", "'(TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO)]']"] | 0 | Migrar ph2 |  |  | 3 | [16 empty] | 05/12 - 05/12
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT) | OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT | SEDA Logistic |  |  |  |  | Done |  | 2025-12-30 |  | 3 | 1 | 2025-12-05 | 2025-12-05 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_REASON)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Migrar ph 2 |  |  | 10 | [16 empty] | 05/12 - 05/12
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_BOD2) | OW_SEDA_S.FN_GET_BOD2 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-05 | 2025-12-05 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BOD)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_DETAIL)]']"] | 0 | Migrar ph2 |  |  | 19 | [16 empty] | 05/12 - 05/12
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FNS_NM1) | OW_SEDA_S.FNS_NM1 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-05 | 2025-12-05 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_DETAIL)]']"] | 0 | Migrar ph2 |  |  | 18 | [16 empty] | 05/12 - 05/12
|  | VIEW | (VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS) | OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-05 | 2025-12-05 | ["['[(TABLE - OW_LAO.MONITORING_PROTOCOL_TYPES)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_STATUS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_STATUS)'", "'(TABLE - OW_LAO.MONITORING_PARAMETERS)'", "'(TABLE - OW_LAO.MONITORING_SOURCES_TYPES)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 7 | [16 empty] | 05/12 - 05/12
|  | VIEW | (VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE) | OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-05 | 2025-12-05 | ["['[(TABLE - OW_LAO.MONITORING_PROTOCOL_TYPES)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_STATUS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_STATUS)'", "'(TABLE - OW_LAO.MONITORING_PARAMETERS)'", "'(TABLE - OW_LAO.MONITORING_SOURCES_TYPES)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 7 | [16 empty] | 05/12 - 05/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI) | OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-05 | 2025-12-05 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.MAP_CE_SR_KAM)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_KAM)]']"] | 0 | Migrar ph2 |  |  | 4 | [16 empty] | 05/12 - 05/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX) | OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-05 | 2025-12-05 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.MAP_CE_SR_KAM)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_KAM)]']"] | 0 | Migrar ph2 |  |  | 4 | [16 empty] | 05/12 - 05/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2) | OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-08 | 2025-12-08 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.MAP_CE_SR_KAM)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_KAM)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 08/12 - 08/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W |  |  |  | No |  | Done |  |  |  | 4 | 1 | 2025-12-08 | 2025-12-08 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO)]']"] | 1 | Migrar ph2 |  |  | 8 | [17 empty] | 08/12 - 08/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W |  |  |  | No |  | Done |  |  |  | 4 | 1 | 2025-12-08 | 2025-12-08 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_FOTA)]']"] | 1 | Migrar ph2 |  |  | 8 | [17 empty] | 08/12 - 08/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY |  |  |  | No |  | Done |  |  |  | 4 | 1 | 2025-12-08 | 2025-12-08 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)]']"] | 1 | Migrar ph2 |  |  | 7 | [17 empty] | 08/12 - 08/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA |  |  |  | No |  | Done |  |  |  | 4 | 1 | 2025-12-08 | 2025-12-08 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_FOTA)]']"] | 1 | Migrar ph2 |  |  | 7 | [17 empty] | 08/12 - 08/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION) | OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION | [5 empty] | Done |  | 2025-12-24 |  | 4 | 1 | 2025-12-08 | 2025-12-08 | ["['[(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION)'", "'(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_EXCEPTION)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION)]']"] | 1 | Migrar ph2 |  |  | 5 | [17 empty] | 08/12 - 08/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W) | OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W | [5 empty] | Done |  |  |  | 4 | 1 | 2025-12-08 | 2025-12-08 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_FOTA_01_05W)]']"] | 1 | Migrar ph2 |  |  | 5 | [17 empty] | 08/12 - 08/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W) | OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W | [5 empty] | Done |  |  |  | 4 | 1 | 2025-12-08 | 2025-12-08 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_FOTA_01_05W)]']"] | 1 | Migrar ph2 |  |  | 5 | [17 empty] | 08/12 - 08/12
WebPrice |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_CE) | OW_SEDA_S.PRC_WEBPRICE_DAILY_CE |  |  |  | No | No | Done | 2025-12-09 |  |  | 4 | 1 | 2025-12-08 | 2025-12-08 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_TV)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 3 | [17 empty] | 08/12 - 08/12
|  | VIEW | (VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI) | OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-08 | 2025-12-08 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 27 | [17 empty] | 08/12 - 08/12
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI) | OW_SEDA_S.FN_GET_BOD2_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-09 | 2025-12-09 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BOD)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)]']"] | 0 | Migrar ph2 |  |  | 19 | [17 empty] | 09/12 - 09/12
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FNS_NM1_SDI) | OW_SEDA_S.FNS_NM1_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-09 | 2025-12-09 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)]']"] | 0 | Migrar ph2 |  |  | 18 | [17 empty] | 09/12 - 09/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO) | OW_SEDA_S.VW_VESSEL_TRAVEL_INFO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-09 | 2025-12-09 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS)]']"] | 0 | Migrar ph2 |  |  | 7 | [17 empty] | 09/12 - 09/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_D2C_SO_FSCT) | OW_SEDA_S.VW_D2C_SO_FSCT | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-09 | 2025-12-09 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_VD)'", "'(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_DA)'", "'(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_HHP)'", "'(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_OTHERS)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 09/12 - 09/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-09 | 2025-12-09 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.TF_VW_SELLOUTGERAL)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)'", "'(TABLE - OW_SEDA_S.TF_VW_WALMART)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 09/12 - 09/12
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_NERP_AL11_VALIDATION) | OW_LAO.PROC_SALES_DEDUCTION_NERP_AL11_VALIDATION |  |  |  | No |  | Done |  | 2025-12-18 |  | 4 | 1 | 2025-12-09 | 2025-12-09 | ["['[(TABLE - OW_LAO.ODS_NERP_AL11_MCS_SEN)'", "'(TABLE - OW_LAO.FT_NERP_AL11_VALIDATION)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_AL11_VALIDATION_TO_MOVE_FILE)]']"] | 0 | Migrar ph2 |  |  | 3 | [17 empty] | 09/12 - 09/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION |  |  |  | No |  | Done |  | 2025-12-18 |  | 4 | 1 | 2025-12-09 | 2025-12-09 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_EXCEPTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_EXCEPTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION)]']"] | 1 | Migrar ph2 |  |  | 8 | [17 empty] | 09/12 - 09/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY) | OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY |  |  |  | No |  | Done |  |  |  | 4 | 1 | 2025-12-09 | 2025-12-09 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_GSCM)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_BIZ_AREA)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_CORES)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY)]']"] | 1 | Migrar ph2 |  |  | 7 | [17 empty] | 09/12 - 09/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W) | OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W | [5 empty] | Done |  |  |  | 4 | 1 | 2025-12-09 | 2025-12-09 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY)'", "'(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_01_05W)]']"] | 1 | Migrar ph2 |  |  | 5 | [17 empty] | 09/12 - 09/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W) | OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W | [5 empty] | Done |  |  |  | 4 | 1 | 2025-12-09 | 2025-12-09 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_06_10W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_06_10W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_06_10W)'", "'(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_06_10W)]']"] | 1 | Migrar ph2 |  |  | 5 | [17 empty] | 09/12 - 09/12
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP) | OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP | SEDA Logistic |  |  |  |  | To be migrated |  | 2026-01-05 |  | 3 | 1 | 2025-12-10 | 2025-12-10 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_SDI)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph 2 |  |  | 16 | [17 empty] | 10/12 - 10/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE) | OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-10 | 2025-12-10 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT_FLOORING)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_MBO_KAM)'", "'(TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT)'", "'(TABLE - OW_SEDA_S.ACCOUNT_MANAGEMENT_FLOORSHRE_TT)]']"] | 0 | Migrar ph 2 |  |  | 6 | [17 empty] | 10/12 - 10/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR) | OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-10 | 2025-12-10 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_TRIPLE_A_PERFORMANCE_SUMMARY)'", "'(TABLE - OW_SEDA_S.MAP_CE_TRIPLE_A_TARGET)'", "'(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 5 | [17 empty] | 10/12 - 10/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_META_PROMOTOR) | OW_SEDA_S.VW_CE_META_PROMOTOR | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-10 | 2025-12-10 | ["['[(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_RRP)'", "'(TABLE - OW_SEDA_S.FT_CE_DB_FCST_PIVOT)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 10/12 - 10/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION) | OW_LAO.PROC_SALES_DEDUCTION | LAO Innovation |  |  | No |  | Done |  | 2025-12-09 |  | 4 | 1 | 2025-12-10 | 2025-12-10 | ["['[(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 |  |  | 5 | [17 empty] | 10/12 - 10/12
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE) | OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-30 |  | 3 | 1 | 2025-12-10 | 2025-12-10 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_REASON)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.SDI_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_REASON_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDER_OCCURRENCE_RPT)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph 2 |  |  | 28 | [17 empty] | 10/12 - 10/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM) | OW_SEDA_S.VW_TRACKING_ITEM | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-10 | 2025-12-10 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BOD)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_CUSTOMER_REJECT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 0 | Migrar ph2 |  |  | 39 | [17 empty] | 10/12 - 10/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL) | OW_SEDA_S.VW_BI_IOD_TOTAL | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-10 | 2025-12-10 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_NOTES)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_IOD_STATUS_REPORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 10/12 - 10/12
WebPrice |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MON) | OW_SEDA_S.PRC_WEBPRICE_DAILY_MON |  |  |  | No | No | Done |  | 2025-12-09 |  | 4 | 1 | 2025-12-10 | 2025-12-10 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MON)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 3 | [17 empty] | 10/12 - 10/12
|  | VIEW | (VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI) | OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-10 | 2025-12-10 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.TMP_SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)]']"] | 0 | Migrar ph2 |  |  | 7 | [17 empty] | 10/12 - 10/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-11 | 2025-12-11 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_NOTES)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 11/12 - 11/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM) | OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-11 | 2025-12-11 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.ODS_TV_WEEKLY_GFK)]']"] | 0 | Migrar ph 2 |  |  | 4 | [17 empty] | 11/12 - 11/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_PRICE_STORE) | OW_SEDA_S.VW_CE_PRICE_STORE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-11 | 2025-12-11 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS)'", "'(TABLE - OW_SEDA_S.FT_CE_PRICE_STORE)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 9 | [17 empty] | 11/12 - 11/12
TrackingTrade |  | VIEW | (VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE) | OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-11 | 2025-12-11 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 8 | [17 empty] | 11/12 - 11/12
TrackingTrade |  | VIEW | (VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE) | OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-11 | 2025-12-11 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 8 | [17 empty] | 11/12 - 11/12
TrackingTrade |  | VIEW | (VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES) | OW_SEDA_S.VW_TT_AGGREGATED_PICTURES | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-11 | 2025-12-11 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 7 | [17 empty] | 11/12 - 11/12
TrackingTrade |  | VIEW | (VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL) | OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-11 | 2025-12-11 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 7 | [17 empty] | 11/12 - 11/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022) | OW_SEDA_S.VW_CE_MX_PIVOT_2022 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-11 | 2025-12-11 | ["['[(TABLE - OW_SEDA_S.FT_MX_PIVOT_2022)'", "'(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.TMP_MX_STORE_MAPPING)]']"] | 0 | Migrar ph2 |  |  | 5 | [17 empty] | 11/12 - 11/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS) | OW_SEDA_S.VW_CE_RM_CTV_MEETINGS | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-11 | 2025-12-11 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRICE_COLLECTED)]']"] | 0 | Migrar ph2 |  |  | 5 | [17 empty] | 11/12 - 11/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING) | OW_SEDA_S.VW_CE_RM_DA_MEETING | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-11 | 2025-12-11 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRICE_COLLECTED)]']"] | 0 | Migrar ph2 |  |  | 5 | [17 empty] | 11/12 - 11/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE) | OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-12 | 2025-12-12 | ["['[(TABLE - OW_SEDA_S.ODS_CE_MKT_TRANSMISSORAS)'", "'(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 5 | [17 empty] | 12/12 - 12/12
GFK |  | VIEW | (VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST) | OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-12 | 2025-12-12 | ["['[(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_MX_DAILY_FOTA)'", "'(TABLE - OW_SEDA_S.FT_GFK_MX_WEEKLY)'", "'(TABLE - OW_SEDA_S.FT_MX_PIVOT)]']"] | 0 | Migrar ph2 |  |  | 5 | [17 empty] | 12/12 - 12/12
|  | VIEW | (VIEW - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_TARGET_WEEK_ADJ) | OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_TARGET_WEEK_ADJ | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-12 | 2025-12-12 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT)'", "'(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 3 | [17 empty] | 12/12 - 12/12
GFK |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK) | OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK |  |  |  | No | No | Done |  | 2025-12-15 |  | 4 | 1 | 2025-12-12 | 2025-12-12 | ["['[(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_MX_DAILY_FOTA)'", "'(TABLE - OW_SEDA_S.FT_GFK_MX_WEEKLY)'", "'(TABLE - OW_SEDA_S.FT_MX_PIVOT_BY_ITEM)'", "'(TABLE - OW_SEDA_S.VW_MX_FOTA_AND_GFK)]']"] | 0 | Migrar ph 2 |  |  | 6 | [17 empty] | 12/12 - 12/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA) | OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA | [5 empty] | Done |  | 2025-12-23 |  | 4 | 1 | 2025-12-12 | 2025-12-12 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CE_PRICE_STORE)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 12/12 - 12/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY) | OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY | [5 empty] | Done |  | 2025-12-24 |  | 4 | 1 | 2025-12-12 | 2025-12-12 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 12/12 - 12/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY) | OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY |  |  |  | No | No | Done |  | 2025-12-22 |  | 4 | 1 | 2025-12-12 | 2025-12-12 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 12/12 - 12/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL) | OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL |  |  |  | No | No | Done |  | 2025-12-22 |  | 4 | 1 | 2025-12-12 | 2025-12-12 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 12/12 - 12/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION) | OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION |  |  |  | No | No | Done |  |  |  | 4 | 1 | 2025-12-12 | 2025-12-12 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 12/12 - 12/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_DEAD_SKU_CALCULATION) | OW_SEDA_S.PRC_DEAD_SKU_CALCULATION |  |  |  | No | No | Done |  | 2025-12-12 |  | 4 | 1 | 2025-12-12 | 2025-12-12 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 | [17 empty] | 12/12 - 12/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION) | OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION |  |  |  | No | No | Done |  | 2025-12-12 |  | 4 | 1 | 2025-12-15 | 2025-12-15 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 | [18 empty] | 15/12 - 15/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_STOCK_OUT_CALCULATION) | OW_SEDA_S.PRC_STOCK_OUT_CALCULATION |  |  |  | No | No | Done |  | 2025-12-15 |  | 4 | 1 | 2025-12-15 | 2025-12-15 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 | [18 empty] | 15/12 - 15/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_VC_UPDATE_READY) | OW_SEDA_S.PRC_VC_UPDATE_READY |  |  |  | No | No | Done |  | 2025-12-11 |  | 4 | 1 | 2025-12-15 | 2025-12-15 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 | [18 empty] | 15/12 - 15/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_VD_SALES_REVENUE) | OW_SEDA_S.PRC_VD_SALES_REVENUE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-12-15 | 2025-12-15 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 | [18 empty] | 15/12 - 15/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_ESES_ON_PIVOT) | OW_SEDA_S.PRC_CE_UPDATE_ESES_ON_PIVOT | [5 empty] | Done |  | 2025-12-23 |  | 4 | 1 | 2025-12-15 | 2025-12-15 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 3 | [18 empty] | 15/12 - 15/12
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-30 |  | 3 | 1 | 2025-12-15 | 2025-12-15 | ["['[(TABLE - OW_SEDA_S.ODS_CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_POD)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND_ITEM)]']"] | 1 | Migrar ph2: Cello |  |  | 11 | [18 empty] | 15/12 - 15/12
GSCM |  | PROCEDURE | (PROCEDURE - OW_LAO.PRC_ODS_LAO_GSCM_EDI_DATA) | OW_LAO.PRC_ODS_LAO_GSCM_EDI_DATA |  |  |  | No | No | Done |  | 2026-01-02 |  | 4 | 1 | 2025-12-15 | 2025-12-15 | ["['[(TABLE - OW_LAO.ODS_LAO_GSCM_EDI_DATA)'", "'(TABLE - OW_LAO.FT_LAO_DX_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)]']"] | 0 | Migrar ph2 |  |  | 3 | [18 empty] | 15/12 - 15/12
|  | VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_REPORT) | OW_SDSLA.VW_TABLEAU_REPORT | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-15 | 2025-12-15 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_WORKBOOKS)]']"] | 0 | Migrar ph 2 |  |  | 12 | [18 empty] | 15/12 - 15/12
|  | VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST) | OW_SDSLA.VW_TABLEAU_REPORT_TEST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-15 | 2025-12-15 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS_STATS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS)]']"] | 0 | Migrar ph 2 |  |  | 12 | [18 empty] | 15/12 - 15/12
|  | VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2) | OW_SDSLA.VW_TABLEAU_REPORT_V2 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-15 | 2025-12-15 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS_STATS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS)]']"] | 0 | Migrar ph 2 |  |  | 12 | [18 empty] | 15/12 - 15/12
|  | VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3) | OW_SDSLA.VW_TABLEAU_REPORT_V3 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-16 | 2025-12-16 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS_STATS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS)]']"] | 0 | Migrar ph 2 |  |  | 12 | [18 empty] | 16/12 - 16/12
|  | VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4) | OW_SDSLA.VW_TABLEAU_REPORT_V4 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-16 | 2025-12-16 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS_STATS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS)]']"] | 0 | Migrar ph 2 |  |  | 12 | [18 empty] | 16/12 - 16/12
|  | VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_USERS) | OW_SDSLA.VW_TABLEAU_USERS | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-16 | 2025-12-16 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)]']"] | 0 | Migrar ph2: Tableau |  |  | 4 | [18 empty] | 16/12 - 16/12
|  | VIEW | (VIEW - OW_SDSLA.ODS_TABLEAU_PROJECT_HIERARCHY) | OW_SDSLA.ODS_TABLEAU_PROJECT_HIERARCHY | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-16 | 2025-12-16 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_SYSTEM_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_PROJECTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)]']"] | 0 | Migrar ph2: Tableau |  |  | 3 | [18 empty] | 16/12 - 16/12
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT) | OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT |  |  |  | No | No | Done |  | 2025-12-15 |  | 4 | 1 | 2025-12-16 | 2025-12-16 | ["['[(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.EDI_DATA_RAW)'", "'(TABLE - OW_SEDA_S.FT_SEDA_EDI_DATA)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.FT_MX_PIVOT_BY_ITEM)]']"] | 0 | Migrar ph2 |  |  | 5 | [18 empty] | 16/12 - 16/12
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING) | OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING | SEDA Logistic |  |  |  |  | Done |  | 2025-12-30 |  | 3 | 1 | 2025-12-30 | 2025-12-30 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RETURN_REASON)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_RETURN_BOOKING_REQUEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_REASON)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN)'", "'(TABLE - OW_SEDA_S.SDI_TSS_WEB_RETURN_REQUEST)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_IOD)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph 2 |  |  | 39 | [20 empty] | 30/12 - 30/12
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228) | OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228 | SEDA Logistic |  |  |  |  | To be migrated |  | 2026-01-05 |  | 3 | 1 | 2025-12-30 | 2025-12-30 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_SDI)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | Migrar ph 2 |  |  | 13 | [20 empty] | 30/12 - 30/12
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_CELLO_TSS_IOD_STATUS) | OW_SEDA_S.VW_UNION_CELLO_TSS_IOD_STATUS | SEDA Logistic |  |  |  |  | Done |  | 2025-12-30 |  | 3 | 1 | 2025-12-30 | 2025-12-30 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT)]']"] | 0 | Migrar ph2 |  |  | 3 | [20 empty] | 30/12 - 30/12
Cello,TSS | CelloTSSLogistic | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING) | OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING | SEDA Logistic |  |  |  |  | Done |  |  |  | 4 | 1 | 2025-12-30 | 2025-12-30 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING_TMP)'", "'(TABLE - OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | Migrar ph 2 |  |  | 14 | [20 empty] | 30/12 - 30/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2) | OW_LAO.PROC_CRAWLING_AP1_IM_PT2 | [5 empty] | Done |  |  |  | 4 | 1 | 2025-12-30 | 2025-12-30 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING_KEY)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Migrar ph 2 |  |  | 4 | [20 empty] | 30/12 - 30/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_DUEK) | OW_LAO.PROC_CRAWLING_AP1_IM_PT2_DUEK | [5 empty] | Done |  | 2025-12-09 |  | 4 | 1 | 2025-12-30 | 2025-12-30 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Migrar ph 2 |  |  | 3 | [20 empty] | 30/12 - 30/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HIST) | OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HIST | [5 empty] | Done |  | 2025-12-09 |  | 4 | 1 | 2025-12-30 | 2025-12-30 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Migrar ph 2 |  |  | 3 | [20 empty] | 30/12 - 30/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HISTORICO) | OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HISTORICO | [5 empty] | Done |  | 2025-12-09 |  | 4 | 1 | 2025-12-30 | 2025-12-30 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Migrar ph 2 |  |  | 3 | [20 empty] | 30/12 - 30/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_V2) | OW_LAO.PROC_CRAWLING_AP1_IM_PT2_V2 | [5 empty] | Done |  | 2025-12-10 |  | 4 | 1 | 2025-12-30 | 2025-12-30 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Migrar ph 2 |  |  | 3 | [20 empty] | 30/12 - 30/12
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT2) | OW_LAO.PROC_CRAWLING_AP1_TABLET_PT2 | [5 empty] | Done |  | 2025-12-17 |  | 4 | 1 | 2025-12-30 | 2025-12-30 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Migrar ph 2 |  |  | 3 | [20 empty] | 30/12 - 30/12
Cello,TSS | CelloTSSLogistic | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2) | OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2 | SEDA Logistic |  |  |  |  | Done |  |  |  | 4 | 1 | 2025-12-31 | 2025-12-31 | ["['[(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_01)'", "'(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_02)'", "'(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)'", "'(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_DOWN)'", "'(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_ACESSORY)'", "'(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_EPP)'", "'(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_HME)]']"] | 0 | Migrar ph2 |  |  | 7 | [20 empty] | 31/12 - 31/12
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_NPC_SEGMENT) | OW_LAO.VW_CRAWLING_AP1_NPC_SEGMENT | [5 empty] | Done |  |  |  | 3 | 1 | 2025-12-31 | 2025-12-31 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Migrar ph 2 |  |  | 2 | [20 empty] | 31/12 - 31/12
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_REF_SEGMENT) | OW_LAO.VW_CRAWLING_AP1_REF_SEGMENT | [5 empty] | Done |  |  |  | 3 | 1 | 2025-12-31 | 2025-12-31 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Migrar ph 2 |  |  | 2 | [20 empty] | 31/12 - 31/12
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_TV_SEGMENT) | OW_LAO.VW_CRAWLING_AP1_TV_SEGMENT | [5 empty] | Done |  |  |  | 3 | 1 | 2025-12-31 | 2025-12-31 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING)]']"] | 1 | Migrar ph 2 |  |  | 2 | [20 empty] | 31/12 - 31/12
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_WM_SEGMENT) | OW_LAO.VW_CRAWLING_AP1_WM_SEGMENT | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-31 | 2025-12-31 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Migrar ph 2 |  |  | 2 | [20 empty] | 31/12 - 31/12
GSCM |  | VIEW | (VIEW - OW_SEDA_S.VW_API_GSCM_TO_ASM) | OW_SEDA_S.VW_API_GSCM_TO_ASM | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-31 | 2025-12-31 | ["['[(TABLE - OW_SEDA_S.GSCM_TMP)]']"] | 1 | Migrar ph 2 |  |  | 1 | [20 empty] | 31/12 - 31/12
GSCM |  | VIEW | (VIEW - OW_SEDA_S.VW_API_GSCM_TO_ASM_2) | OW_SEDA_S.VW_API_GSCM_TO_ASM_2 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-31 | 2025-12-31 | ["['[(TABLE - OW_SEDA_S.GSCM_TMP)]']"] | 1 | Migrar ph 2 |  |  | 1 | [20 empty] | 31/12 - 31/12
|  | VIEW | (VIEW - OW_SEDA_S.TF_PORTAL_SM_SURSIS_JOIN_1) | OW_SEDA_S.TF_PORTAL_SM_SURSIS_JOIN_1 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-31 | 2025-12-31 | ["['[(TABLE - OW_SEDA_S.ODS_SURSIS_ESCORT)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA)]']"] | 0 | Migrar ph 2 |  |  | 2 | [20 empty] | 31/12 - 31/12
|  | VIEW | (VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA_VIAGEM_ESCOLTA) | OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA_VIAGEM_ESCOLTA | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-31 | 2025-12-31 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM)'", "'(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA)]']"] | 0 | Migrar ph 2 |  |  | 2 | [20 empty] | 31/12 - 31/12
|  | VIEW | (VIEW - OW_SELA.CURRENTWEEK) | OW_SELA.CURRENTWEEK | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2025-12-31 | 2025-12-31 | ["['[(TABLE - OW_SELA.FACT_STOCK_SALES)'", "'(TABLE - OW_SELA.DIM_WEEK)]']"] | 0 | Migrar ph 2 |  |  | 2 | [20 empty] | 31/12 - 31/12
|  | VIEW | (VIEW - OW_SELA.MISSINGSEGMENT) | OW_SELA.MISSINGSEGMENT | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-01 | 2026-01-01 | ["['[(TABLE - OW_SELA.DIM_PRODUCT)'", "'(TABLE - OW_SELA.DIM_MN_SEGMENT)]']"] | 0 | Migrar ph 2 |  |  | 2 | [20 empty] | 01/01 - 01/01
|  | VIEW | (VIEW - OW_SELA.MISSING_MKTNAME) | OW_SELA.MISSING_MKTNAME | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-01 | 2026-01-01 | ["['[(TABLE - OW_SELA.DIM_PRODUCT)'", "'(TABLE - OW_SELA.FACT_STOCK_SALES)]']"] | 0 | Migrar ph 2 |  |  | 2 | [20 empty] | 01/01 - 01/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT) | OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-01 | 2026-01-01 | ["['[(TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT)]']"] | 0 | Migrar ph 2 |  |  | 1 | [20 empty] | 01/01 - 01/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_FLOORING) | OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_FLOORING | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-01 | 2026-01-01 | ["['[(TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT_FLOORING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [20 empty] | 01/01 - 01/01
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM) | OW_SEDA_S.VW_CELLO_SUM_LLM | SEDA Logistic |  |  |  |  | Done |  | 2025-12-31 |  | 3 | 1 | 2026-01-01 | 2026-01-01 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Migrar ph2 |  |  | 2 | [20 empty] | 01/01 - 01/01
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT) | OW_SEDA_S.VW_CELLO_SUM_SHIPMENT | SEDA Logistic |  |  |  |  | Done |  | 2026-01-02 |  | 3 | 1 | 2026-01-01 | 2026-01-01 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)]']"] | 1 | Migrar ph2 |  |  | 2 | [20 empty] | 01/01 - 01/01
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP_TEST) | OW_SEDA_S.VW_UNION_TSS_CELLO_TMP_TEST | SEDA Logistic |  |  |  |  | Done |  | 2026-01-05 |  | 3 | 1 | 2026-01-01 | 2026-01-01 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TMP)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)]']"] | 1 | Migrar ph2 |  |  | 2 | [20 empty] | 01/01 - 01/01
Cello | CelloLogistic | FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_CELLO_EVENT) | OW_SEDA_S.FN_GET_CELLO_EVENT | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-31 |  | 3 | 1 | 2026-01-01 | 2026-01-01 | ["['[(TABLE - OW_SEDA_S.CELLO_TRACKING)]']"] | 1 | Migrar ph2 |  |  | 1 | [20 empty] | 01/01 - 01/01
|  | VIEW | (VIEW - OW_LAO.VW_LAO_SALES_DEDUCTION_DAILY_MONITORING_MAPPING_STATUS) | OW_LAO.VW_LAO_SALES_DEDUCTION_DAILY_MONITORING_MAPPING_STATUS | [5 empty] | Done |  |  |  | 3 | 1 | 2026-01-01 | 2026-01-01 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING)]']"] | 1 | Migrar ph2 |  |  | 1 | [20 empty] | 01/01 - 01/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_ABNORMAL_INVENTORY) | OW_SEDA_S.VW_ABNORMAL_INVENTORY | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-01 | 2026-01-01 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_ABNORMAL_INVENTORY)]']"] | 1 | Migrar ph2 |  |  | 1 | [20 empty] | 01/01 - 01/01
Cello | CelloLogistic | VIEW | (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT) | OW_SEDA_S.VW_CELLO_TRACKING_EVENT | SEDA Logistic |  |  |  |  | Done |  | 2025-12-31 |  | 3 | 1 | 2026-01-02 | 2026-01-02 | ["['[(TABLE - OW_SEDA_S.CELLO_TRACKING)]']"] | 1 | Migrar ph2 |  |  | 1 | [20 empty] | 02/01 - 02/01
WMS |  | VIEW | (VIEW - OW_SEDA_S.VW_SDU_ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD) | OW_SEDA_S.VW_SDU_ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD | SEDA Logistic |  |  |  |  | To be migrated |  |  |  | 3 | 1 | 2026-01-02 | 2026-01-02 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD)]']"] | 1 | Migrar ph2 |  |  | 1 | [20 empty] | 02/01 - 02/01
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI_v2) | OW_SEDA_S.FN_GET_BOD2_SDI_v2 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-02 | 2026-01-02 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BOD)]']"] | 0 | Migrar ph2 |  |  | 2 | [20 empty] | 02/01 - 02/01
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE) | OW_SEDA_S.FN_GET_LAST_EVENT_DATE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-02 | 2026-01-02 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT_LOG)]']"] | 0 | Migrar ph2 |  |  | 2 | [20 empty] | 02/01 - 02/01
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE_SDI) | OW_SEDA_S.FN_GET_LAST_EVENT_DATE_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-02 | 2026-01-02 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG)]']"] | 0 | Migrar ph2 |  |  | 2 | [20 empty] | 02/01 - 02/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_IBGE_CEP_5_COORDINATES) | OW_SEDA_S.VW_IBGE_CEP_5_COORDINATES | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-02 | 2026-01-02 | ["['[(TABLE - OW_SEDA_S.ODS_IBGE_CEP_5_COORDINATES)'", "'(TABLE - OW_SEDA_S.MAP_CE_SETOR_CENSITARIO_2010)]']"] | 0 | Migrar ph2 |  |  | 2 | [20 empty] | 02/01 - 02/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-02 | 2026-01-02 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 | [20 empty] | 02/01 - 02/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_JULIAO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_JULIAO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-02 | 2026-01-02 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 | [20 empty] | 02/01 - 02/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-02 | 2026-01-02 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 | [20 empty] | 02/01 - 02/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-02 | 2026-01-02 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 | [20 empty] | 02/01 - 02/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_JULIAO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_JULIAO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-05 | 2026-01-05 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 | [21 empty] | 05/01 - 05/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_LSPOSITO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_LSPOSITO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-05 | 2026-01-05 | ["['[(TABLE - OW_SEDA_S.TF_VW_SELLOUTGERAL)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 | [21 empty] | 05/01 - 05/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_VALIDATION) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_VALIDATION | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-05 | 2026-01-05 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 | [21 empty] | 05/01 - 05/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-05 | 2026-01-05 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 | [21 empty] | 05/01 - 05/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART_LSPOSITO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART_LSPOSITO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-05 | 2026-01-05 | ["['[(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)'", "'(TABLE - OW_SEDA_S.TF_VW_WALMART)]']"] | 0 | Migrar ph2 |  |  | 2 | [21 empty] | 05/01 - 05/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SCM_SALES_AND_SO_LIST_COMPLETE) | OW_SEDA_S.VW_SCM_SALES_AND_SO_LIST_COMPLETE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-05 | 2026-01-05 | ["['[(TABLE - OW_SEDA_S.FT_CE_SELL_IN_FCST)'", "'(TABLE - OW_SEDA_S.ODS_SCM_FINANCIAL_FCST)]']"] | 0 | Migrar ph2 |  |  | 2 | [21 empty] | 05/01 - 05/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SEDA_SALES_IN_TRANSIT) | OW_SEDA_S.VW_SEDA_SALES_IN_TRANSIT | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-05 | 2026-01-05 | ["['[(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)'", "'(TABLE - OW_SEDA_S.MAP_CARRIER)]']"] | 0 | Migrar ph2 |  |  | 2 | [21 empty] | 05/01 - 05/01
TrackingTrade |  | VIEW | (VIEW - OW_SEDA_S.VW_TT_RUPTURA) | OW_SEDA_S.VW_TT_RUPTURA | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-05 | 2026-01-05 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 2 | [21 empty] | 05/01 - 05/01
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST) | OW_SEDA_S.VW_UNION_TSS_CELLO_HIST | SEDA Logistic |  |  |  |  | To be migrated |  | 2025-12-31 |  | 3 | 1 | 2026-01-05 | 2026-01-05 | ["['[(TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_SDI)'", "'(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)]']"] | 0 | Migrar ph2 |  |  | 2 | [21 empty] | 05/01 - 05/01
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST_MAP_CARRIER) | OW_SEDA_S.VW_UNION_TSS_CELLO_HIST_MAP_CARRIER | SEDA Logistic |  |  |  |  | Done |  | 2025-12-05 |  | 3 | 1 | 2026-01-05 | 2026-01-05 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST)'", "'(TABLE - OW_SEDA_S.MAP_CARRIER)]']"] | 0 | Migrar ph2 |  |  | 2 | [21 empty] | 05/01 - 05/01
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_DO_CURR_ACTION) | OW_SEDA_S.FN_GET_DO_CURR_ACTION | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-06 | 2026-01-06 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_CUSTOMER_REJECT)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 06/01 - 06/01
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_REJECT_CNT) | OW_SEDA_S.FN_GET_OCCURRENCE_REJECT_CNT | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-06 | 2026-01-06 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_CUSTOMER_REJECT)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 06/01 - 06/01
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_STATUS) | OW_SEDA_S.FN_GET_OCCURRENCE_STATUS | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-06 | 2026-01-06 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_OCCURRENCE)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 06/01 - 06/01
|  | FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_STATUS_SDI) | OW_SEDA_S.FN_GET_OCCURRENCE_STATUS_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-06 | 2026-01-06 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 06/01 - 06/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_JOURNEY_COORDINATORS_MAXWEEK) | OW_SEDA_S.VW_CE_JOURNEY_COORDINATORS_MAXWEEK | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-06 | 2026-01-06 | ["['[(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 06/01 - 06/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_JOURNEY_UNIQUE) | OW_SEDA_S.VW_CE_JOURNEY_UNIQUE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-06 | 2026-01-06 | ["['[(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 06/01 - 06/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_JOURNEY_UNIQUE_MAX_WEEKNUM) | OW_SEDA_S.VW_CE_JOURNEY_UNIQUE_MAX_WEEKNUM | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-06 | 2026-01-06 | ["['[(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 06/01 - 06/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_SHOPPING_BRASIL_API) | OW_SEDA_S.VW_CE_SHOPPING_BRASIL_API | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-06 | 2026-01-06 | ["['[(TABLE - OW_SEDA_S.ODS_CE_SHOPPING_BRASIL_API)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 06/01 - 06/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_WEATHER_FCST_API) | OW_SEDA_S.VW_CE_WEATHER_FCST_API | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-06 | 2026-01-06 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEATHER_FCST_API)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 06/01 - 06/01
WebPrice |  | VIEW | (VIEW - OW_SEDA_S.VW_CE_WEBPRICE_URL) | OW_SEDA_S.VW_CE_WEBPRICE_URL | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-06 | 2026-01-06 | ["['[(TABLE - OW_SEDA_S.MAP_CE_WEBPRICE_URL)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 06/01 - 06/01
GSCM |  | VIEW | (VIEW - OW_SEDA_S.VW_GSCM_CH_PSI_WARING_SALES_DEDUCTION) | OW_SEDA_S.VW_GSCM_CH_PSI_WARING_SALES_DEDUCTION | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-07 | 2026-01-07 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 07/01 - 07/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_MX_SALES_VS_RTF) | OW_SEDA_S.VW_MX_SALES_VS_RTF | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-07 | 2026-01-07 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 07/01 - 07/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_MX_SALES_VS_RTF_BY_CAPACITY) | OW_SEDA_S.VW_MX_SALES_VS_RTF_BY_CAPACITY | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-07 | 2026-01-07 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 07/01 - 07/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_ONLINE_FISICO) | OW_SEDA_S.VW_ONLINE_FISICO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-07 | 2026-01-07 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 07/01 - 07/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO_LSPOSITO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO_LSPOSITO | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-07 | 2026-01-07 | ["['[(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 07/01 - 07/01
NERP |  | VIEW | (VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM) | OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-07 | 2026-01-07 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 07/01 - 07/01
NERP |  | VIEW | (VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL) | OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-07 | 2026-01-07 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 07/01 - 07/01
TSS | TSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_OD_PRE_SHIPMENT) | OW_SEDA_S.VW_SDU_SDI_TSS_OD_PRE_SHIPMENT | SEDA Logistic |  |  |  |  | To be migrated |  | 2026-01-06 |  | 3 | 1 | 2026-01-07 | 2026-01-07 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_OD_PRE_SHIPMENT)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 07/01 - 07/01
TSS | TSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_DATE) | OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_DATE | SEDA Logistic |  |  |  |  | To be migrated |  | 2026-01-06 |  | 3 | 1 | 2026-01-07 | 2026-01-07 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 07/01 - 07/01
TSS | TSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_LOC) | OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_LOC | SEDA Logistic |  |  |  |  | To be migrated |  | 2026-01-06 |  | 3 | 1 | 2026-01-07 | 2026-01-07 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOC)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 07/01 - 07/01
TSS | TSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL) | OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL | SEDA Logistic |  |  |  |  | To be migrated |  | 2026-01-06 |  | 3 | 1 | 2026-01-08 | 2026-01-08 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 08/01 - 08/01
TSS | TSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL_DESTINATION_PORT) | OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL_DESTINATION_PORT | SEDA Logistic |  |  |  |  | To be migrated |  | 2026-01-06 |  | 3 | 1 | 2026-01-08 | 2026-01-08 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 08/01 - 08/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SELLOUTGERAL) | OW_SEDA_S.VW_SELLOUTGERAL | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-08 | 2026-01-08 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 08/01 - 08/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_SELL_IN_FCST) | OW_SEDA_S.VW_SELL_IN_FCST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-08 | 2026-01-08 | ["['[(TABLE - OW_SEDA_S.FT_CE_SELL_IN_FCST)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 08/01 - 08/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE) | OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-08 | 2026-01-08 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_LEG_PLANNING)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 08/01 - 08/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE_SDI) | OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE_SDI | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-08 | 2026-01-08 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 08/01 - 08/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_WALMART) | OW_SEDA_S.VW_WALMART | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-08 | 2026-01-08 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 |  |  | 1 | [21 empty] | 08/01 - 08/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT) | OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-08 | 2026-01-08 | ["['[(TABLE - OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT)]']"] | 0 | Migrar ph2 BI |  |  | 1 | [21 empty] | 08/01 - 08/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER) | OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-08 | 2026-01-08 | ["['[(TABLE - OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER)]']"] | 0 | Migrar ph2 BI |  |  | 1 | [21 empty] | 08/01 - 08/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_COUNTRY) | OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_COUNTRY | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-08 | 2026-01-08 | ["['[(TABLE - OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_COUNTRY)]']"] | 0 | Migrar ph2 BI |  |  | 1 | [21 empty] | 08/01 - 08/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_DDD) | OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_DDD | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-09 | 2026-01-09 | ["['[(TABLE - OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_DDD)]']"] | 0 | Migrar ph2 BI |  |  | 1 | [21 empty] | 09/01 - 09/01
TrackingTrade |  | VIEW | (VIEW - OW_SEDA_S.VW_TT_STACK_INFO_2023) | OW_SEDA_S.VW_TT_STACK_INFO_2023 | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-09 | 2026-01-09 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 | [21 empty] | 09/01 - 09/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_GERENCIAIS_PL) | OW_SEDA_S.VW_CE_GERENCIAIS_PL | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-09 | 2026-01-09 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)]']"] | 0 | Migrar ph2: Controlling |  |  | 1 | [21 empty] | 09/01 - 09/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_GERENCIAIS_PL_FCST) | OW_SEDA_S.VW_CE_GERENCIAIS_PL_FCST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-09 | 2026-01-09 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)]']"] | 0 | Migrar ph2: Controlling |  |  | 1 | [21 empty] | 09/01 - 09/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_MBO_NETSALES_COP) | OW_SEDA_S.VW_CE_MBO_NETSALES_COP | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-09 | 2026-01-09 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)]']"] | 0 | Migrar ph2: Controlling |  |  | 1 | [21 empty] | 09/01 - 09/01
|  | VIEW | (VIEW - OW_SEDA_S.VW_CE_MBO_NETSALES_COP_FCST) | OW_SEDA_S.VW_CE_MBO_NETSALES_COP_FCST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-09 | 2026-01-09 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)]']"] | 0 | Migrar ph2: Controlling |  |  | 1 | [21 empty] | 09/01 - 09/01
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP) | OW_SEDA_S.VW_UNION_TSS_CELLO_TMP | SEDA Logistic |  |  |  |  | Done |  | 2026-01-05 |  | 3 | 1 | 2026-01-09 | 2026-01-09 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TMP)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)]']"] | 1 | migrar ph2 |  |  | 2 | [21 empty] | 09/01 - 09/01
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_SDU_FT_TSS_CELLO_IOD_STATUS_MONITORING) | OW_SEDA_S.VW_SDU_FT_TSS_CELLO_IOD_STATUS_MONITORING | SEDA Logistic |  |  |  |  | Done |  | 2025-12-31 |  | 3 | 1 | 2026-01-09 | 2026-01-09 | ["['[(TABLE - OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING)]']"] | 1 | migrar ph2 |  |  | 1 | [21 empty] | 09/01 - 09/01
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO) | OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO | SEDA Logistic |  |  |  |  | Done |  | 2026-01-02 |  | 3 | 1 | 2026-01-09 | 2026-01-09 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)]']"] | 1 | migrar ph2 |  |  | 1 | [21 empty] | 09/01 - 09/01
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_SDU_FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2) | OW_SEDA_S.VW_SDU_FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2 | SEDA Logistic |  |  |  |  | Done |  | 2026-01-06 |  | 3 | 1 | 2026-01-09 | 2026-01-09 | ["['[(TABLE - OW_SEDA_S.FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2)]']"] | 0 | migrar ph2 |  |  | 1 | [21 empty] | 09/01 - 09/01
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO_HIST) | OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO_HIST | SEDA Logistic |  |  |  |  | Done |  | 2026-01-02 |  | 3 | 1 | 2026-01-12 | 2026-01-12 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST)]']"] | 0 | migrar ph2 |  |  | 1 | [22 empty] | 12/01 - 12/01
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO) | OW_SEDA_S.VW_UNION_TSS_CELLO | SEDA Logistic |  |  |  |  | Done |  | 2026-01-02 |  | 3 | 1 | 2026-01-12 | 2026-01-12 | ["['[(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)]']"] | 0 | migrar ph2 |  |  | 1 | [22 empty] | 12/01 - 12/01
Cello,TSS | CelloTSSLogistic | VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_PHOTO) | OW_SEDA_S.VW_UNION_TSS_CELLO_PHOTO | SEDA Logistic |  |  |  |  | Done |  | 2026-01-02 |  | 3 | 1 | 2026-01-12 | 2026-01-12 | ["['[(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)]']"] | 0 | migrar ph2 |  |  | 1 | [22 empty] | 12/01 - 12/01
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_ESTORE_DAILY_PRICE) | OW_LAO.VW_CRAWLING_AP1_ESTORE_DAILY_PRICE | [5 empty] | Done |  |  |  | 3 | 1 | 2026-01-12 | 2026-01-12 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 4.1 Migrar ph 1 |  |  | 1 | [22 empty] | 12/01 - 12/01
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_REF_DISPLAY_SHARE) | OW_LAO.VW_CRAWLING_AP1_REF_DISPLAY_SHARE | [5 empty] | Done |  |  |  | 3 | 1 | 2026-01-12 | 2026-01-12 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 4.1 Migrar ph 1 |  |  | 1 | [22 empty] | 12/01 - 12/01
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_TV_DISPLAY_SHARE) | OW_LAO.VW_CRAWLING_AP1_TV_DISPLAY_SHARE | [5 empty] | Done |  |  |  | 3 | 1 | 2026-01-12 | 2026-01-12 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 4.1 Migrar ph 1 |  |  | 1 | [22 empty] | 12/01 - 12/01
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_WM_DISPLAY_SHARE) | OW_LAO.VW_CRAWLING_AP1_WM_DISPLAY_SHARE | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-12 | 2026-01-12 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 4.1 Migrar ph 1 |  |  | 1 | [22 empty] | 12/01 - 12/01
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE) | OW_LAO.VW_CRAWLING_ONLINE_PRICE | [5 empty] | Done |  |  |  | 3 | 1 | 2026-01-12 | 2026-01-12 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 4.1 Migrar ph 1 |  |  | 1 | [22 empty] | 12/01 - 12/01
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE) | OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE | [5 empty] | Done |  |  |  | 3 | 1 | 2026-01-12 | 2026-01-12 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 4.1 Migrar ph 1 |  |  | 1 | [22 empty] | 12/01 - 12/01
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE_TABLET) | OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE_TABLET | [5 empty] | Done |  |  |  | 3 | 1 | 2026-01-12 | 2026-01-12 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 4.1 Migrar ph 1 |  |  | 1 | [22 empty] | 12/01 - 12/01
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET) | OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET | [5 empty] | Done |  |  |  | 3 | 1 | 2026-01-13 | 2026-01-13 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 4.1 Migrar ph 1 |  |  | 1 | [22 empty] | 13/01 - 13/01
|  | VIEW | (VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET_TEST) | OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET_TEST | [5 empty] | To be migrated |  |  |  | 3 | 1 | 2026-01-13 | 2026-01-13 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 4.1 Migrar ph 1 |  |  | 1 | [22 empty] | 13/01 - 13/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_ESTORE_URL_SKU) | OW_LAO.PROC_CRAWLING_AP1_ESTORE_URL_SKU | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-13 | 2026-01-13 | ["['[(TABLE - OW_LAO.TMP_MAP_ESTORE_URL_SKU)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Migrar ph 2 |  |  | 2 | [22 empty] | 13/01 - 13/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_PT1) | OW_LAO.PROC_CRAWLING_AP1_NPC_PT1 | [5 empty] | Done |  | 2025-12-10 |  | 4 | 1 | 2026-01-13 | 2026-01-13 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Migrar ph 2 |  |  | 2 | [22 empty] | 13/01 - 13/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1) | OW_LAO.PROC_CRAWLING_AP1_REF_PT1 | [5 empty] | Done |  | 2025-12-11 |  | 4 | 1 | 2026-01-13 | 2026-01-13 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Migrar ph 2 |  |  | 2 | [22 empty] | 13/01 - 13/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1_V2) | OW_LAO.PROC_CRAWLING_AP1_REF_PT1_V2 | [5 empty] | Done |  | 2025-12-11 |  | 4 | 1 | 2026-01-13 | 2026-01-13 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Migrar ph 2 |  |  | 2 | [22 empty] | 13/01 - 13/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1) | OW_LAO.PROC_CRAWLING_AP1_TV_PT1 | [5 empty] | Done |  | 2025-12-18 |  | 4 | 1 | 2026-01-13 | 2026-01-13 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING)]']"] | 1 | Migrar ph 2 |  |  | 2 | [22 empty] | 13/01 - 13/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1_V2) | OW_LAO.PROC_CRAWLING_AP1_TV_PT1_V2 | [5 empty] | Done |  | 2025-12-19 |  | 4 | 1 | 2026-01-13 | 2026-01-13 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING)]']"] | 1 | Migrar ph 2 |  |  | 2 | [22 empty] | 13/01 - 13/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1) | OW_LAO.PROC_CRAWLING_AP1_WM_PT1 | [5 empty] | Done |  | 2025-12-19 |  | 4 | 1 | 2026-01-13 | 2026-01-13 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Migrar ph 2 |  |  | 2 | [22 empty] | 13/01 - 13/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1_V2) | OW_LAO.PROC_CRAWLING_AP1_WM_PT1_V2 | [5 empty] | To be migrated |  |  |  | 4 | 1 | 2026-01-13 | 2026-01-13 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Migrar ph 2 |  |  | 2 | [22 empty] | 13/01 - 13/01
MEDALIA |  | PROCEDURE | (PROCEDURE - OW_MD.PROC_INGESTION_ODS_MEDALIA_TARGET_NPS) | OW_MD.PROC_INGESTION_ODS_MEDALIA_TARGET_NPS | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-14 | 2026-01-14 | ["['[(TABLE - OW_MD.RAW_MEDALIA_TARGET_NPS)'", "'(TABLE - OW_MD.ODS_MEDALIA_TARGET_NPS)]']"] | 1 | Migrar ph 2 |  |  | 2 | [22 empty] | 14/01 - 14/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_CRAWLER_STATUS) | OW_LAO.PROC_CRAWLING_AP1_CRAWLER_STATUS | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-14 | 2026-01-14 | ["['[(TABLE - OW_LAO.CRAWLER_STATUS)'", "'(TABLE - OW_LAO.CRAWLER_PROCESS_LIST)]']"] | 0 | Migrar ph 2 |  |  | 2 | [22 empty] | 14/01 - 14/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING) | OW_LAO.PROC_GSMARENA_MAPPING | [5 empty] | To be migrated |  |  |  | 4 | 1 | 2026-01-14 | 2026-01-14 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING_KEY)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 2 | [22 empty] | 14/01 - 14/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING_1_0) | OW_LAO.PROC_GSMARENA_MAPPING_1_0 | [5 empty] | To be migrated |  |  |  | 4 | 1 | 2026-01-14 | 2026-01-14 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING_KEY)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 2 | [22 empty] | 14/01 - 14/01
HYBRIS |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2026-01-14 | 2026-01-14 | ["['[(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES)]']"] | 0 | Migrar ph 2 |  |  | 2 | [22 empty] | 14/01 - 14/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1) | OW_LAO.PROC_CRAWLING_AP1_IM_PT1 | [5 empty] | Done |  | 2025-12-05 |  | 4 | 1 | 2026-01-14 | 2026-01-14 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 14/01 - 14/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_DUEK) | OW_LAO.PROC_CRAWLING_AP1_IM_PT1_DUEK | [5 empty] | Done |  | 2025-12-05 |  | 4 | 1 | 2026-01-14 | 2026-01-14 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 14/01 - 14/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HIST) | OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HIST | [5 empty] | Done |  | 2025-12-05 |  | 4 | 1 | 2026-01-14 | 2026-01-14 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 14/01 - 14/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HISTORICO) | OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HISTORICO | [5 empty] | Done |  | 2025-12-05 |  | 4 | 1 | 2026-01-14 | 2026-01-14 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 14/01 - 14/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC | [5 empty] | Done |  | 2025-12-10 |  | 4 | 1 | 2026-01-14 | 2026-01-14 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 14/01 - 14/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_REF_SITE_MAPPING_MERGE_AUTOMATIC | [5 empty] | Done |  | 2025-12-11 |  | 4 | 1 | 2026-01-15 | 2026-01-15 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 15/01 - 15/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_RETRY_PRODUCTS) | OW_LAO.PROC_CRAWLING_AP1_RETRY_PRODUCTS | [5 empty] | Done |  | 2025-12-11 |  | 4 | 1 | 2026-01-15 | 2026-01-15 | ["['[(TABLE - OW_LAO.CRAWLER_PROCESS_LIST)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 15/01 - 15/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT1) | OW_LAO.PROC_CRAWLING_AP1_TABLET_PT1 | [5 empty] | Done |  | 2025-12-16 |  | 4 | 1 | 2026-01-15 | 2026-01-15 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 15/01 - 15/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_TV_SITE_MAPPING_MERGE_AUTOMATIC | [5 empty] | Done |  | 2025-12-18 |  | 4 | 1 | 2026-01-15 | 2026-01-15 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 15/01 - 15/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WERABLES_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_WERABLES_SITE_MAPPING_MERGE_AUTOMATIC | [5 empty] | Done |  | 2025-12-19 |  | 4 | 1 | 2026-01-15 | 2026-01-15 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 15/01 - 15/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_WM_SITE_MAPPING_MERGE_AUTOMATIC | [5 empty] | To be migrated |  |  |  | 4 | 1 | 2026-01-15 | 2026-01-15 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 15/01 - 15/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_1) | OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_1 | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-15 | 2026-01-15 | ["['[(TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 15/01 - 15/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_2) | OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_2 | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-15 | 2026-01-15 | ["['[(TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 15/01 - 15/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_3) | OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_3 | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-15 | 2026-01-15 | ["['[(TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 15/01 - 15/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_4) | OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_4 | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-15 | 2026-01-15 | ["['[(TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 15/01 - 15/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_5) | OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_5 | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-16 | 2026-01-16 | ["['[(TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 16/01 - 16/01
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MKP) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MKP | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-16 | 2026-01-16 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MKP)]']"] | 0 | Migrar ph 2 |  |  | 1 | [22 empty] | 16/01 - 16/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.UPDATE_SALES_WEEKLY_MONITORING) | OW_LAO.UPDATE_SALES_WEEKLY_MONITORING |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2026-01-16 | 2026-01-16 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_01_05W)]']"] | 1 | Migrar ph2 |  |  | 2 | [22 empty] | 16/01 - 16/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ATU_LAO_SALES_DEDUCTION_MONITORING_STATUS_HIST) | OW_LAO.PROC_ATU_LAO_SALES_DEDUCTION_MONITORING_STATUS_HIST | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-16 | 2026-01-16 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING)]']"] | 1 | Migrar ph2 |  |  | 1 | [22 empty] | 16/01 - 16/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_PREPARE) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_PREPARE |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2026-01-16 | 2026-01-16 | ["['[(TABLE - OW_LAO.MONITORING_PARAMETERS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 2 | [22 empty] | 16/01 - 16/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_IBGE_INFO) | OW_SEDA_S.PRC_CE_UPDATE_IBGE_INFO |  |  |  | No | No | Done |  | 2025-12-22 |  | 4 | 1 | 2026-01-16 | 2026-01-16 | ["['[(TABLE - OW_SEDA_S.MAP_CE_SETOR_CENSITARIO_2010)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 |  |  | 2 | [22 empty] | 16/01 - 16/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_UPDATE_PIN_TO_PIN) | OW_SEDA_S.PRC_UPDATE_PIN_TO_PIN |  |  |  | No | No | Done |  |  |  | 4 | 1 | 2026-01-16 | 2026-01-16 | ["['[(TABLE - OW_SEDA_S.MAP_PIN_TO_PIN_BF_19)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 2 | [22 empty] | 16/01 - 16/01
WebPrice |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX) | OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX |  |  |  | No | No | Done |  | 2025-12-10 |  | 4 | 1 | 2026-01-16 | 2026-01-16 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO)]']"] | 0 | Migrar ph2 |  |  | 2 | [22 empty] | 16/01 - 16/01
WebPrice |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX_HIST_2) | OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX_HIST_2 |  |  |  | No | No | Done |  | 2025-12-11 |  | 4 | 1 | 2026-01-16 | 2026-01-16 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO)]']"] | 0 | Migrar ph2 |  |  | 2 | [22 empty] | 16/01 - 16/01
WebPrice |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_UPDT_RECENT_PRICE) | OW_SEDA_S.PRC_WEBPRICE_UPDT_RECENT_PRICE |  |  |  | No | No | Done |  | 2025-12-11 |  | 4 | 1 | 2026-01-16 | 2026-01-16 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_TV)]']"] | 0 | Migrar ph2 |  |  | 2 | [22 empty] | 16/01 - 16/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_POST_EXECUTION) | OW_LAO.MONITORING_EXECUTIONS_POST_EXECUTION |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2026-01-19 | 2026-01-19 | ["['[(TABLE - OW_LAO.MONITORING_EXECUTIONS)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 19/01 - 19/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_DEFAULT) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_DEFAULT |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2026-01-19 | 2026-01-19 | ["['[(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 19/01 - 19/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_JENKINS) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_JENKINS |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2026-01-19 | 2026-01-19 | ["['[(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 19/01 - 19/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_TMC) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_TMC |  | r.bojart |  | yes | 3 | Done |  |  |  | 4 | 1 | 2026-01-19 | 2026-01-19 | ["['[(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 19/01 - 19/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.INGEST_OUTBOUND_TRACKING_SCM) | OW_SEDA_S.INGEST_OUTBOUND_TRACKING_SCM | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-19 | 2026-01-19 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 19/01 - 19/01
OMNITRACKING |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING) | OW_SEDA_S.PRC_MX_API_OMNITRACKING | [5 empty] | Done |  | 2025-12-12 |  | 4 | 1 | 2026-01-19 | 2026-01-19 | ["['[(TABLE - OW_SEDA_S.RAW_SEDA_API_OMNITRACKING)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 19/01 - 19/01
OMNITRACKING |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING_FULL) | OW_SEDA_S.PRC_MX_API_OMNITRACKING_FULL | [5 empty] | Done |  | 2025-12-12 |  | 4 | 1 | 2026-01-19 | 2026-01-19 | ["['[(TABLE - OW_SEDA_S.RAW_SEDA_API_OMNITRACKING)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 19/01 - 19/01
OMNITRACKING |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING_WEEKLY) | OW_SEDA_S.PRC_MX_API_OMNITRACKING_WEEKLY | [5 empty] | Done |  | 2025-12-12 |  | 4 | 1 | 2026-01-19 | 2026-01-19 | ["['[(TABLE - OW_SEDA_S.RAW_SEDA_API_OMNITRACKING)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 19/01 - 19/01
TrackingTrade |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_GABARITO_CHECKLIST_EXECUCAO) | OW_SEDA_S.PRC_TT_GABARITO_CHECKLIST_EXECUCAO |  |  |  | No | No | Done |  |  |  | 4 | 1 | 2026-01-19 | 2026-01-19 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 19/01 - 19/01
TrackingTrade |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_GABARITO_CHECKLIST_EXECUCAO_785) | OW_SEDA_S.PRC_TT_GABARITO_CHECKLIST_EXECUCAO_785 |  |  |  | No | No | Done |  | 2025-12-17 |  | 4 | 1 | 2026-01-19 | 2026-01-19 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 19/01 - 19/01
TrackingTrade |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_UPDT_FLOORSHARE) | OW_SEDA_S.PRC_TT_UPDT_FLOORSHARE |  |  |  | No | No | Done |  | 2025-12-18 |  | 4 | 1 | 2026-01-20 | 2026-01-20 | ["['[(TABLE - OW_SEDA_S.FT_CE_PRICE_STORE)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 20/01 - 20/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TV_UPDT_INCH_RANGE) | OW_SEDA_S.PRC_TV_UPDT_INCH_RANGE | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-20 | 2026-01-20 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 20/01 - 20/01
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_B2B) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_B2B | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-20 | 2026-01-20 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_B2B)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 20/01 - 20/01
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BREA) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BREA | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-20 | 2026-01-20 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BREA)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 20/01 - 20/01
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BRSHOP) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BRSHOP | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-20 | 2026-01-20 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BRSHOP)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 20/01 - 20/01
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EPP2) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EPP2 | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-20 | 2026-01-20 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EPP2)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 20/01 - 20/01
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EST) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EST | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-20 | 2026-01-20 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EST)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 20/01 - 20/01
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MEMBERS) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MEMBERS | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-20 | 2026-01-20 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MEMBERS)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 20/01 - 20/01
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_PARC) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_PARC | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-20 | 2026-01-20 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_PARC)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 20/01 - 20/01
AFTER_SALES |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_RESID) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_RESID | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-20 | 2026-01-20 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_RESID)]']"] | 0 | Migrar ph2 |  |  | 1 | [23 empty] | 20/01 - 20/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_STORE_EDI) | OW_SEDA_S.PRC_CE_STORE_EDI |  |  |  | No | No | Done |  |  |  | 4 | 1 | 2026-01-21 | 2026-01-21 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.ODS_CE_STORE_EDI)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 2 | [23 empty] | 21/01 - 21/01
GFK |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_GFK) | OW_SEDA_S.PRC_CE_UPDATE_GFK | [5 empty] | Done |  | 2025-12-23 |  | 4 | 1 | 2026-01-21 | 2026-01-21 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 | [23 empty] | 21/01 - 21/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_STORE_NAME) | OW_SEDA_S.PRC_CE_UPDATE_STORE_NAME |  |  |  | No | No | Done |  | 2025-12-22 |  | 4 | 1 | 2026-01-21 | 2026-01-21 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 | [23 empty] | 21/01 - 21/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDT_SHOPPING_W_BRANDSHOP) | OW_SEDA_S.PRC_CE_UPDT_SHOPPING_W_BRANDSHOP |  |  |  | No | No | Done |  |  |  | 4 | 1 | 2026-01-21 | 2026-01-21 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 | [23 empty] | 21/01 - 21/01
TrackingTrade |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_AV_CHECKLIST_DE_EXECUCAO_785) | OW_SEDA_S.PRC_TT_AV_CHECKLIST_DE_EXECUCAO_785 |  |  |  | No | No | Done |  | 2025-12-15 |  | 4 | 1 | 2026-01-21 | 2026-01-21 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 | [23 empty] | 21/01 - 21/01
TrackingTrade |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_RAC_CHECKLIST_DE_EXECUCAO_785) | OW_SEDA_S.PRC_TT_RAC_CHECKLIST_DE_EXECUCAO_785 |  |  |  | No | No | Done |  | 2025-12-17 |  | 4 | 1 | 2026-01-21 | 2026-01-21 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 | [23 empty] | 21/01 - 21/01
TrackingTrade |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_REF_CHECKLIST_DE_EXECUCAO_785) | OW_SEDA_S.PRC_TT_REF_CHECKLIST_DE_EXECUCAO_785 |  |  |  | No | No | Done |  | 2025-12-17 |  | 4 | 1 | 2026-01-21 | 2026-01-21 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 | [23 empty] | 21/01 - 21/01
TrackingTrade |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_TV_CHECKLIST_DE_EXECUCAO) | OW_SEDA_S.PRC_TT_TV_CHECKLIST_DE_EXECUCAO |  |  |  | No | No | Done |  |  |  | 4 | 1 | 2026-01-21 | 2026-01-21 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 | [23 empty] | 21/01 - 21/01
TrackingTrade |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_TV_CHECKLIST_DE_EXECUCAO_785) | OW_SEDA_S.PRC_TT_TV_CHECKLIST_DE_EXECUCAO_785 |  |  |  | No | No | Done |  | 2025-12-17 |  | 4 | 1 | 2026-01-21 | 2026-01-21 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 | [23 empty] | 21/01 - 21/01
TrackingTrade |  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_WM_CHECKLIST_DE_EXECUCAO_785) | OW_SEDA_S.PRC_TT_WM_CHECKLIST_DE_EXECUCAO_785 |  |  |  | No | No | Done |  | 2025-12-18 |  | 4 | 1 | 2026-01-21 | 2026-01-21 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 | [23 empty] | 21/01 - 21/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.CONN_TO_SEDA) | OW_SEDA_S.CONN_TO_SEDA |  |  |  | No | No | Done |  |  |  | 4 | 1 | 2026-01-22 | 2026-01-22 | ["['[(TABLE - OW_SEDA_S.EDI_DATA_RAW)]']"] | 0 | Migrar ph2: SEDA RM |  |  | 1 | [23 empty] | 22/01 - 22/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT_RETAILERS) | OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT_RETAILERS |  |  |  | No | No | Done |  | 2025-12-15 |  | 4 | 1 | 2026-01-22 | 2026-01-22 | ["['[(TABLE - OW_SEDA_S.EDI_DATA_RAW)]']"] | 0 | Migrar ph2: SEDA RM |  |  | 1 | [23 empty] | 22/01 - 22/01
|  | PROCEDURE | (PROCEDURE - OW_SDSLA.PROC_TABLEAU_DASHBOARDS_MACHINE_STATUS) | OW_SDSLA.PROC_TABLEAU_DASHBOARDS_MACHINE_STATUS | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-22 | 2026-01-22 | ["['[(TABLE - OW_SDSLA.RAW_TABLEAU_DASHBOARDS_MACHINE_STATUS)]']"] | 0 | Migrar ph2: Tableau |  |  | 1 | [23 empty] | 22/01 - 22/01
|  | PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_AMAZON_PRIME_DAY) | OW_SEDA_S.PRC_CE_AMAZON_PRIME_DAY | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-22 | 2026-01-22 | ["['[(TABLE - OW_SEDA_S.ODS_CE_AMAZON_SELL_OUT_FCST)]']"] | 0 | Migrar ph 2 |  |  | 1 | [23 empty] | 22/01 - 22/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_VC_PT1) | OW_LAO.PROC_CRAWLING_AP1_VC_PT1 | [5 empty] | Done |  |  |  | 4 | 1 | 2026-01-22 | 2026-01-22 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 4.1 Migrar ph 1 |  |  | 1 | [23 empty] | 22/01 - 22/01
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WERABLES_PT1) | OW_LAO.PROC_CRAWLING_AP1_WERABLES_PT1 | [5 empty] | Done |  | 2025-12-19 |  | 4 | 1 | 2026-01-22 | 2026-01-22 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Migrar ph 2 |  |  | 1 | [23 empty] | 22/01 - 22/01
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELIGIBLE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELIGIBLE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-10-01 | 2025-10-01 |  | 0 | 4.1 Migrar Ph 1 |  |  |  |  | Checar e incluir para a migração | [22 empty] | Checar e incluir para a migração
| ControlTower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_EPROMOTER_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_EPROMOTER_UPDATE | [5 empty] | Done |  |  |  | 4 | 1 | 2025-10-01 | 2025-10-01 |  | 0 | 4.1 Migrar Ph 1 |  |  |  |  | Checar e incluir para a migração | [22 empty] | Checar e incluir para a migração
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMETNO_ADDITIONAL_INFO) | OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMETNO_ADDITIONAL_INFO | [5 empty] | Done |  |  |  | 4 | 1 | 2025-10-01 | 2025-10-01 |  | 0 | 4.1 Migrar Ph 1
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING |  |  |  | yes |  | Done |  |  |  | 4 | 1 | 2025-10-07 | 2025-10-07 |  | 1 | 4.1 Migrar ph 1 |  |  | 1
NERP |  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING ) | OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  |  | SIM | 4 | 1 | 2025-10-07 | 2025-10-07 |  | 1 | 4.1 Migrar ph 1 |  |  | 1
|  | PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_CUSTOMER_POLICY) | OW_MD.PROC_DIM_CUSTOMER_POLICY | [5 empty] | Done |  |  |  | 4 | 1 | 2025-10-21 | 2025-10-21 |  |  | 4.1 Migrar ph 1 |  |  | 1
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC | [5 empty] | Done |  | 2025-12-10 |  | 4 | 1 | 2025-11-03 | 2025-11-03 |  |  | Migrar ph2 |  |  | 1
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC | [5 empty] | Done |  | 2025-12-10 |  | 4 | 1 | 2025-11-03 | 2025-11-03 |  |  | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.VTEX_SSG_UY_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.VTEX_SSG_UY_RATES_AND_BENEFITS_DATA | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.VTEX_SSG_PY_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.VTEX_SSG_PY_RATES_AND_BENEFITS_DATA | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_TEST) | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_TEST | LAO EStore | r.bojart |  | yes | 2 | Not to be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_SALES) | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_SALES | LAO EStore | r.bojart |  | yes | 2 | Not to be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_ORDER | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_ORDER | LAO EStore | r.bojart |  | yes | 2 | Not to be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_EPP_ORDER) | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_EPP_ORDER | LAO EStore | r.bojart |  | yes | 2 | Not to be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST) | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST | LAO EStore | r.bojart |  | yes | 2 | Not to be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_FT_TST) | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_FT_TST | LAO EStore | r.bojart |  | yes | 2 | Not to be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MASTER_DATA_CL_TST) | U_PRJ_ECOM.TMP_RAW_VTEX_MASTER_DATA_CL_TST | LAO EStore | r.bojart |  | yes | 2 | Not to be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR_TST) | OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR_TST | LAO EStore | r.bojart |  | yes | 5 | Not to be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.TEMP_PARTNER_LEVEL_SMB_SEASA) | OW_LAO.TEMP_PARTNER_LEVEL_SMB_SEASA | LAO EStore | r.bojart |  | yes | 2 | To be migrated | [9 empty] | Migrar ph2
Magento |  | TABLE | (TABLE - U_PRJ_ECOM.TEMP_ODS_SELA_API_MAGENTO_INSERT) | U_PRJ_ECOM.TEMP_ODS_SELA_API_MAGENTO_INSERT | LAO EStore | r.bojart |  | yes | 1 | To be migrated | [9 empty] | Migrar ph2
NERP | ControlTower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_FILTER) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_FILTER | LAO EStore | r.bojart |  | yes | 1 | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.TEMP_DIM_UNIQUE_ID_TF) | OW_LAO.TEMP_DIM_UNIQUE_ID_TF | LAO EStore | r.bojart |  | yes | 2 | To be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.STG_VTEX_ORDER_SEASA_VISUAR_CANCEL) | U_PRJ_ECOM.STG_VTEX_ORDER_SEASA_VISUAR_CANCEL | LAO EStore | r.bojart |  | yes | 2 | Done | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.STG_VTEX_ORDER_SEASA_MIRGOR_CANCEL) | U_PRJ_ECOM.STG_VTEX_ORDER_SEASA_MIRGOR_CANCEL | LAO EStore | r.bojart |  | yes | 2 | Done | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - OW_LAO.STG_STOCKOUT_VTEX_GLOBALBI_SEDA) | OW_LAO.STG_STOCKOUT_VTEX_GLOBALBI_SEDA | LAO EStore | r.bojart |  | yes | 4 | Done | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - OW_LAO.STG_STOCKOUT_VTEX_GLOBALBI_SEASA) | OW_LAO.STG_STOCKOUT_VTEX_GLOBALBI_SEASA | LAO EStore | r.bojart |  | yes | 4 | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.STG_SELA_SALES_COUPONS_ITEMS) | OW_LAO.STG_SELA_SALES_COUPONS_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.STG_SELA_SALES_COUPONS) | OW_LAO.STG_SELA_SALES_COUPONS | LAO EStore | r.bojart |  | yes | 2 | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.STG_SELA_ORDERS_COUPONS_STATUS_HISTORY) | OW_LAO.STG_SELA_ORDERS_COUPONS_STATUS_HISTORY | LAO EStore | r.bojart |  | yes | 2 | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.STG_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS) | OW_LAO.STG_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS | LAO EStore | r.bojart |  | yes | 2 | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.STG_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO) | OW_LAO.STG_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO | LAO EStore | r.bojart |  | yes | 2 | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.STG_SELA_CUSTOM_ORDERS_ITEMS) | OW_LAO.STG_SELA_CUSTOM_ORDERS_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.STG_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS) | OW_LAO.STG_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS | LAO EStore | r.bojart |  | yes | 2 | Done | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_SHIPPING | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_PAYMENT | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_PACKAGE | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_ITEM_COMPONENTS | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_ITEM | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_SHIPPING | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_PAYMENT | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_PACKAGE | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_ITEM_COMPONENTS | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_ITEM | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
VTEX |  | TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
HYBRIS |  | TABLE | (TABLE - OW_LAO.ODS_ECOM_ORDERS_B5Q5_HYBRIS) | OW_LAO.ODS_ECOM_ORDERS_B5Q5_HYBRIS | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.ODS_ECOM_ORDERS_B5Q5_ARGENTINA) | OW_LAO.ODS_ECOM_ORDERS_B5Q5_ARGENTINA | LAO EStore | r.bojart |  |  |  | Not to be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.ODS_ECOM_ORDERS_B5Q5) | OW_LAO.ODS_ECOM_ORDERS_B5Q5 | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN) | U_PRJ_ECOM.ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
AdobeAnalytics |  | TABLE | (TABLE - OW_LAO.ODS_ECOM_ANALYTICS_ADOBE) | OW_LAO.ODS_ECOM_ANALYTICS_ADOBE | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
AdobeAnalytics |  | TABLE | (TABLE - OW_LAO.ODS_ECOM_ADOBE_ANALYTICS_OVERALL) | OW_LAO.ODS_ECOM_ADOBE_ANALYTICS_OVERALL | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
AdobeAnalytics |  | TABLE | (TABLE - OW_LAO.ODS_ECOM_ADOBE_ANALYTICS_B5Q5) | OW_LAO.ODS_ECOM_ADOBE_ANALYTICS_B5Q5 | LAO EStore | r.bojart |  |  |  | Not to be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.LOG_PROCESSCONTROL) | U_PRJ_ECOM.LOG_PROCESSCONTROL | LAO EStore | r.bojart |  | yes | 1 | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.DIM_SUBSIDIARY_B5Q5) | OW_LAO.DIM_SUBSIDIARY_B5Q5 | LAO EStore | r.bojart |  |  |  | Not to be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.DIM_SKU_B5Q5) | OW_LAO.DIM_SKU_B5Q5 | LAO EStore | r.bojart |  |  |  | Not to be migrated | [9 empty] | Migrar ph2
CADASTRA |  | TABLE | (TABLE - OW_LAO.DIM_LAO_CAMPAIGN_TAG_NAME_CADASTRA) | OW_LAO.DIM_LAO_CAMPAIGN_TAG_NAME_CADASTRA | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.DIM_ECOM_STORE) | U_PRJ_ECOM.DIM_ECOM_STORE | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.DIM_ECOM_SKU) | U_PRJ_ECOM.DIM_ECOM_SKU | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM_SYNAPCOM.DIM_ECOM_SKU) | U_PRJ_ECOM_SYNAPCOM.DIM_ECOM_SKU | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.DIM_ECOM_EPP_2) | U_PRJ_ECOM.DIM_ECOM_EPP_2 | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.DIM_ECOM_CHANNEL) | U_PRJ_ECOM.DIM_ECOM_CHANNEL | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.DIM_AFFILIATE_CHANNEL) | OW_LAO.DIM_AFFILIATE_CHANNEL | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - OW_LAO.DIM_ACCESS_CODE) | OW_LAO.DIM_ACCESS_CODE | LAO EStore | r.bojart |  |  |  | Done | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_SITE_FIELD_TYPE) | U_PRJ_ECOM.BI_ECOM_SITE_FIELD_TYPE | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_SITE_EPP) | U_PRJ_ECOM.BI_ECOM_SITE_EPP | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_SITE) | U_PRJ_ECOM.BI_ECOM_SITE | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_SELA_EPP) | U_PRJ_ECOM.BI_ECOM_SELA_EPP | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_SELA) | U_PRJ_ECOM.BI_ECOM_SELA | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_EPP_TYPE) | U_PRJ_ECOM.BI_ECOM_EPP_TYPE | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_EPP_SITE) | U_PRJ_ECOM.BI_ECOM_EPP_SITE | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_EPP_LAO) | U_PRJ_ECOM.BI_ECOM_EPP_LAO | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_EPP_GLOBAL) | U_PRJ_ECOM.BI_ECOM_EPP_GLOBAL | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_EPP) | U_PRJ_ECOM.BI_ECOM_EPP | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_CHANNEL_TYPE) | U_PRJ_ECOM.BI_ECOM_CHANNEL_TYPE | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
|  | TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_B2C_SELA) | U_PRJ_ECOM.BI_ECOM_B2C_SELA | LAO EStore | r.bojart |  |  |  | To be migrated | [9 empty] | Migrar ph2
VTEX | ControlTower | PROCEDURE | (PROCEDURE - CON_SDSLA.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS) | CON_SDSLA.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 2025-12-05 | [7 empty] | Migrar ph2
VTEX | ControlTower | PROCEDURE | (PROCEDURE -CON_SDSLA.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS) | CON_SDSLA.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 2025-12-05 | [7 empty] | Migrar ph2
|  | PROCEDURE | (PROCEDURE -OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN_TARGETS) | OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN_TARGETS | LAO EStore | r.bojart |  |  |  | Not to be migrated | [9 empty] | Migrar ph2 |  |  |  |  | Confirmed by r.bojart via knox on 21/11 | [22 empty] | Confirmed by r.bojart via knox on 21/11
|  | PROCEDURE | (PROCEDURE -OW_LAO.MASTERDATA_SMB_CUIT_DELET) | OW_LAO.MASTERDATA_SMB_CUIT_DELET | LAO EStore | r.bojart |  | yes | 2 | Not found |  | 2025-12-05 | [7 empty] | Migrar ph2
|  | PROCEDURE | (PROCEDURE -OW_LAO.MASTERDATA_SMB_CUIT_UPDATE) | OW_LAO.MASTERDATA_SMB_CUIT_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Not found |  | 2025-12-05 | [7 empty] | Migrar ph2
CADASTRA |  | PROCEDURE | (PROCEDURE -OW_LAO.PROC_DIM_CAMPAIGN_TAG_NAME_CADASTRA_UPDATE) | OW_LAO.PROC_DIM_CAMPAIGN_TAG_NAME_CADASTRA_UPDATE | LAO EStore | r.bojart |  | yes | 5 | Done |  | 2025-12-05 | [7 empty] | Migrar ph2
|  | PROCEDURE | (PROCEDURE -OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP_HOMOLOG) | OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Not to be migrated | [9 empty] | Migrar ph2 |  |  |  |  | Confirmed by r.bojart via knox on 21/11 | [22 empty] | Confirmed by r.bojart via knox on 21/11
|  | PROCEDURE | (PROCEDURE -OW_MD.DIM_SALES_CHANNELS_PROMOTIONS_GENERATE) | OW_MD.DIM_SALES_CHANNELS_PROMOTIONS_GENERATE | LAO EStore | r.bojart |  | yes | 2 | Done |  | 2025-12-05 | [7 empty] | Migrar ph2
|  | PROCEDURE | (PROCEDURE -U_PRJ_ECOM.PROC_SERIES_GENERATE_DATE_FORMATED) | U_PRJ_ECOM.PROC_SERIES_GENERATE_DATE_FORMATED | LAO EStore | r.bojart |  |  |  | Done |  | 2025-12-05 | [7 empty] | Migrar ph2
HYBRIS |  | PROCEDURE | (PROCEDURE -U_R_BOJART.HYBRIS_MELI_FINANCIAL_RECONCILIATION) | U_R_BOJART.HYBRIS_MELI_FINANCIAL_RECONCILIATION | LAO EStore | r.bojart |  |  |  | Not to be migrated | [9 empty] | Migrar ph2
|  | PROCEDURE | (PROCEDURE - OW_MD.PROC_MAP_AR_ASSIGNMENT_ADJUSTED) | OW_MD.PROC_MAP_AR_ASSIGNMENT_ADJUSTED | [5 empty] | Done |  | 2025-12-22
|  | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_VTEX_SEASA_PROMOTION) | OW_LAO.PROC_ODS_VTEX_SEASA_PROMOTION | [5 empty] | Done |  | 2025-12-22
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.PRC_D2C_COST_MGTM) | TGT_SEDA_S.PRC_D2C_COST_MGTM | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-02 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.PRC_D2C_COST_MGTM_FPC10) | TGT_SEDA_S.PRC_D2C_COST_MGTM_FPC10 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-02 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.PRC_D2C_COST_MGTM_MX) | TGT_SEDA_S.PRC_D2C_COST_MGTM_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-02 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.PRC_D2C_COST_MGTM_MX_FPC10) | TGT_SEDA_S.PRC_D2C_COST_MGTM_MX_FPC10 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-02 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.PRC_D2C_FREIGHT_SIMULATION) | TGT_SEDA_S.PRC_D2C_FREIGHT_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-02 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.PRC_D2C_NEWBID_SIMULATION_2NDROUND) | TGT_SEDA_S.PRC_D2C_NEWBID_SIMULATION_2NDROUND | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-03 | [7 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.TRUNCATE_BASES_MACHINE_LEARNING) | TGT_SEDA_S.TRUNCATE_BASES_MACHINE_LEARNING | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-03 | [7 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_001_BASES_MACHINE_LEARNING_ALL_TRK) | TGT_SEDA_S.UPDATE_001_BASES_MACHINE_LEARNING_ALL_TRK | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-03 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_002_BASES_MACHINE_LEARNING_TREINO_IOD) | TGT_SEDA_S.UPDATE_002_BASES_MACHINE_LEARNING_TREINO_IOD | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-03 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_003_BASES_MACHINE_LEARNING_TREINO_TOD40) | TGT_SEDA_S.UPDATE_003_BASES_MACHINE_LEARNING_TREINO_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-03 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_004_BASES_MACHINE_LEARNING_TREINO_TOD50) | TGT_SEDA_S.UPDATE_004_BASES_MACHINE_LEARNING_TREINO_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-04 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_005_BASES_MACHINE_LEARNING_PREDICT) | TGT_SEDA_S.UPDATE_005_BASES_MACHINE_LEARNING_PREDICT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-04 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_BASE_MACHINE_LEARNING_IN_TRANSIT) | TGT_SEDA_S.UPDATE_BASE_MACHINE_LEARNING_IN_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-04 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_BASES_MACHINE_BACKUP) | TGT_SEDA_S.UPDATE_BASES_MACHINE_BACKUP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_EVENT_DELAY) | TGT_SEDA_S.UPDATE_EVENT_DELAY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-04 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_PREV_DELAY) | TGT_SEDA_S.UPDATE_PREV_DELAY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-04 | [7 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_ST_CD_TRANSIT) | TGT_SEDA_S.UPDATE_ST_CD_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-05 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_ST_D2C_MASTER) | TGT_SEDA_S.UPDATE_ST_D2C_MASTER | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-05 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_ST_FREIGHT_TEST) | TGT_SEDA_S.UPDATE_ST_FREIGHT_TEST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_ST_GORDURA_VTEX) | TGT_SEDA_S.UPDATE_ST_GORDURA_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-05 | [7 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_ST_IN_TRANSIT_REPORT) | TGT_SEDA_S.UPDATE_ST_IN_TRANSIT_REPORT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-05 | [7 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_ST_IN_TRANSIT_REPORT_RESUME) | TGT_SEDA_S.UPDATE_ST_IN_TRANSIT_REPORT_RESUME | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-05 | [7 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_ST_LT_ACTUAL_TRK_HUBS) | TGT_SEDA_S.UPDATE_ST_LT_ACTUAL_TRK_HUBS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_ST_PAINEL_FINAL_HUBS) | TGT_SEDA_S.UPDATE_ST_PAINEL_FINAL_HUBS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-05 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_ST_WH_CAP_CONTROL) | TGT_SEDA_S.UPDATE_ST_WH_CAP_CONTROL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-06 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_MD.DIM_CALENDAR),(VIEW - TGT_SEDA_S_SCM.VW_WH_MONTHLY_CAPA),(TABLE - OW_SEDA_S.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - TGT_SEDA_S_SCM.DIM_WH_CAPA_UPDATE),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.CELLO_SHIPMENT),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM),(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_TESTE_SQL) | TGT_SEDA_S.UPDATE_TESTE_SQL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-06 | [7 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_TESTE_SQL_2) | TGT_SEDA_S.UPDATE_TESTE_SQL_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-06 | [7 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_VW_TRK_TEAM_IN_TRANSIT) | TGT_SEDA_S.UPDATE_VW_TRK_TEAM_IN_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-06 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S.UPDATE_ZIP_CODE) | TGT_SEDA_S.UPDATE_ZIP_CODE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-06 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.CT_LOG) | TGT_SEDA_S.CT_LOG | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.D2C_LT_OUT_NEW_BID) | TGT_SEDA_S.D2C_LT_OUT_NEW_BID | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.D2C_MASTER_JAN_2024_FEV_2025) | TGT_SEDA_S.D2C_MASTER_JAN_2024_FEV_2025 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_1) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_BKP) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_DELAYED) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_DELAYED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_TESTE) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_BKP) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_DELAYED) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_DELAYED | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_DELAYED_BACKUP) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_DELAYED_BACKUP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_DELAYED_PT1) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_DELAYED_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_PT1) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_PT1_BKP) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD40_FINAL_PT1_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD50_FINAL) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD50_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD50_FINAL_BKP) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD50_FINAL_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD50_FINAL_PT1) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD50_FINAL_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD50_FINAL_PT1_BKP) | TGT_SEDA_S.FT_BASE_MACHINE_LEARNING_TOD50_FINAL_PT1_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_CARRIER_NAME) | TGT_SEDA_S.FT_CARRIER_NAME | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_ASIS_SIMULATION) | TGT_SEDA_S.FT_D2C_ASIS_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_FREIGHT_SIMULATION) | TGT_SEDA_S.FT_D2C_FREIGHT_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_FREIGHT_SIMULATION_ASIS_BID25) | TGT_SEDA_S.FT_D2C_FREIGHT_SIMULATION_ASIS_BID25 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_FREIGHT_SIMULATION_ASWAS) | TGT_SEDA_S.FT_D2C_FREIGHT_SIMULATION_ASWAS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_GAIN_SHARE_ASWAS) | TGT_SEDA_S.FT_D2C_GAIN_SHARE_ASWAS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_GAIN_SHARE_SIMULATION) | TGT_SEDA_S.FT_D2C_GAIN_SHARE_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_GAIN_SHARE_SIMULATION_ASWAS) | TGT_SEDA_S.FT_D2C_GAIN_SHARE_SIMULATION_ASWAS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_GAIN_SHARE_TO_BE) | TGT_SEDA_S.FT_D2C_GAIN_SHARE_TO_BE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_LOG_UNIT_COST_SIMULATION) | TGT_SEDA_S.FT_D2C_LOG_UNIT_COST_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_LOG_UNIT_COST_SIMULATION_MX) | TGT_SEDA_S.FT_D2C_LOG_UNIT_COST_SIMULATION_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_LOGCOST_COPQ) | TGT_SEDA_S.FT_D2C_LOGCOST_COPQ | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_LOGCOST_COPQ_MX) | TGT_SEDA_S.FT_D2C_LOGCOST_COPQ_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_LOGCOST_MGTM_SIMULATION) | TGT_SEDA_S.FT_D2C_LOGCOST_MGTM_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_LOGCOST_MGTM_SIMULATION_MX) | TGT_SEDA_S.FT_D2C_LOGCOST_MGTM_SIMULATION_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_LOGCOST_UNIT_COST) | TGT_SEDA_S.FT_D2C_LOGCOST_UNIT_COST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_LOGCOST_UNIT_COST_MX) | TGT_SEDA_S.FT_D2C_LOGCOST_UNIT_COST_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_LOGISTICS_NEW_TARIFF_DB) | TGT_SEDA_S.FT_D2C_LOGISTICS_NEW_TARIFF_DB | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_APR1) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_APR1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_APR2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_APR2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_FEB1) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_FEB1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_FEB2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_FEB2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_JAN1) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_JAN1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_JAN2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_JAN2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_MAR1) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_MAR1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_MAR2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_MAR2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_MAY1) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_MAY1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_MAY2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_MAY2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_SEDA) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_SEDA | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_SEDA_2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_SEDA_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_V2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_V2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_V22) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_2NDROUND_V22 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_APR1) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_APR1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_APR2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_APR2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_FEB1) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_FEB1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_FEB2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_FEB2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_JAN1) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_JAN1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_JAN2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_JAN2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_MAR1) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_MAR1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_MAR2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_MAR2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_MAY1) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_MAY1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_MAY2) | TGT_SEDA_S.FT_D2C_NEWBID_SIMULATION_ADJUSTED_MAY2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT1_D2C_LOGCOST_MGTM) | TGT_SEDA_S.FT1_D2C_LOGCOST_MGTM | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT1_D2C_LOGCOST_MGTM_MX) | TGT_SEDA_S.FT1_D2C_LOGCOST_MGTM_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT2_D2C_LOGCOST_MGTM) | TGT_SEDA_S.FT2_D2C_LOGCOST_MGTM | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.FT2_D2C_LOGCOST_MGTM_MX) | TGT_SEDA_S.FT2_D2C_LOGCOST_MGTM_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.PREVISAO_ATRASOS) | TGT_SEDA_S.PREVISAO_ATRASOS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.SIMULACAO_CAIO_1) | TGT_SEDA_S.SIMULACAO_CAIO_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.SIMULACAO_CAIO_2) | TGT_SEDA_S.SIMULACAO_CAIO_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_1_D2C_PGR_LIMIT_20250910) | TGT_SEDA_S.ST_1_D2C_PGR_LIMIT_20250910 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_2_D2C_COVERAGE_SKIP_ZIP_20250910) | TGT_SEDA_S.ST_2_D2C_COVERAGE_SKIP_ZIP_20250910 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_3_D2C_TRANSGENEROSO_CE_ZIP_20250910) | TGT_SEDA_S.ST_3_D2C_TRANSGENEROSO_CE_ZIP_20250910 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_4_D2C_STORE_MX_CE_ZIP_20250910) | TGT_SEDA_S.ST_4_D2C_STORE_MX_CE_ZIP_20250910 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_5_D2C_LOCKER_MELI_TRUCK_BAT_CPU_BRAND_20250910) | TGT_SEDA_S.ST_5_D2C_LOCKER_MELI_TRUCK_BAT_CPU_BRAND_20250910 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC) | TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_FINAL) | TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW) | TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW_2) | TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW_3) | TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW_3 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW_4) | TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW_4 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW_5) | TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW_5 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW_6) | TGT_SEDA_S.ST_ALL_TRK_UPLOAD_OCC_PREVIEW_6 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AS_IS_TARRIF_D2C) | TGT_SEDA_S.ST_AS_IS_TARRIF_D2C | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AS_IS_TARRIF_D2C_2) | TGT_SEDA_S.ST_AS_IS_TARRIF_D2C_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AS_IS_TARRIF_D2C_3) | TGT_SEDA_S.ST_AS_IS_TARRIF_D2C_3 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AS_WAS_AVG) | TGT_SEDA_S.ST_AS_WAS_AVG | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AS_WAS_TARIF_D2C_2025H1) | TGT_SEDA_S.ST_AS_WAS_TARIF_D2C_2025H1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ATENDIMENTO_TOTAL_202509) | TGT_SEDA_S.ST_ATENDIMENTO_TOTAL_202509 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ATTEMPT_DELIVERY) | TGT_SEDA_S.ST_ATTEMPT_DELIVERY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_LT_HUBS_AGROUP) | TGT_SEDA_S.ST_AVG_LT_HUBS_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_LT_HUBS_DELAYED_AGROUP) | TGT_SEDA_S.ST_AVG_LT_HUBS_DELAYED_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_LT_HUBS_DELAYED_DETAIL) | TGT_SEDA_S.ST_AVG_LT_HUBS_DELAYED_DETAIL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_LT_HUBS_IOD_AGROUP) | TGT_SEDA_S.ST_AVG_LT_HUBS_IOD_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_AGROUP) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_AGROUP_FINAL) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_AGROUP_FINAL_BKP) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_AGROUP_FINAL_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_AGROUP_PT1) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP_FINAL) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP_PT1) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD50_AGROUP) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD50_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD50_AGROUP_FINAL) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD50_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD50_AGROUP_FINAL_BKP) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD50_AGROUP_FINAL_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD50_AGROUP_PT1) | TGT_SEDA_S.ST_AVG_RANGE_DATE_TOD50_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREDICT) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREDICT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREDICT_NEW) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREDICT_NEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREDICT_NEW_PREVIEW) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREDICT_NEW_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_0_TOD40) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_0_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_0_TOD40_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_0_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_0_TOD50) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_0_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_0_TOD50_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_0_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_1_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_1_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP_FINAL) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP_FINAL_BKP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP_FINAL_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_TOD40) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_TOD40_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_TOD50) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_TOD50_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_1_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_1_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_1_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_2) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP_FINAL) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP_FINAL_BKP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP_FINAL_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD10) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD10 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD10_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD10_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD40) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD40_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD50) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD50_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_2_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_1_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_1_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD40) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD40_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD50) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD50_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_TOD40) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_TOD40_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_TOD50) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_TOD50_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_3_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP_FINAL) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_DELAY) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_DELAY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_DELAY_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_DELAY_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_DELAY_PT1_BKP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_DELAY_PT1_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW_2) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW_2_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW_2_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW_3) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW_3 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW_3_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW_3_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PREVIEW_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT_ML) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT_ML | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT_ML_BKP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT_ML_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_PREDICT) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_PREDICT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_2) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_3) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_3 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP_FINAL) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP_FINAL_BKP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP_FINAL_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP_FINAL) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP_FINAL_BKP) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP_FINAL_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT_2) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD10) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD10 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD10_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD10_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD40) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD40_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD50) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD50_PT1) | TGT_SEDA_S.ST_BASE_MACHINE_LEARNING_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BOOKING_STATUS) | TGT_SEDA_S.ST_BOOKING_STATUS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BR_REGION) | TGT_SEDA_S.ST_BR_REGION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_BRAZIL_ZIP_CODE) | TGT_SEDA_S.ST_BRAZIL_ZIP_CODE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CALENDARIO) | TGT_SEDA_S.ST_CALENDARIO | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CARRIER_NAME) | TGT_SEDA_S.ST_CARRIER_NAME | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CARRIER_NM_MALHA_RAMPUP_NEWBID_25) | TGT_SEDA_S.ST_CARRIER_NM_MALHA_RAMPUP_NEWBID_25 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CARRIER_NM_MALHA_SET_25) | TGT_SEDA_S.ST_CARRIER_NM_MALHA_SET_25 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CARRIER_PICK_UP) | TGT_SEDA_S.ST_CARRIER_PICK_UP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CARRIER_SIT) | TGT_SEDA_S.ST_CARRIER_SIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CD_TRANSIT) | TGT_SEDA_S.ST_CD_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CE_PERFIL_MX) | TGT_SEDA_S.ST_CE_PERFIL_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CELLO_FUTHER_PROC_TRATADA) | TGT_SEDA_S.ST_CELLO_FUTHER_PROC_TRATADA | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CELLO_TK_HUBS_TRATADA) | TGT_SEDA_S.ST_CELLO_TK_HUBS_TRATADA | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CELLO_TK_HUBS_TRATADA_PREVIEW) | TGT_SEDA_S.ST_CELLO_TK_HUBS_TRATADA_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CELLO_TK_HUBS_TRATADA_PREVIEW_TOD50) | TGT_SEDA_S.ST_CELLO_TK_HUBS_TRATADA_PREVIEW_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CLAIM_PROCESS) | TGT_SEDA_S.ST_CLAIM_PROCESS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_CM_CARRIER) | TGT_SEDA_S.ST_CM_CARRIER | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_CARRIER_ALLOCATION_3ROUND) | TGT_SEDA_S.ST_D2C_CARRIER_ALLOCATION_3ROUND | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_CATEGORY_TRANSIT_ML) | TGT_SEDA_S.ST_D2C_CATEGORY_TRANSIT_ML | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_LOGCOST_HIGHEST_CWGT_CATEGORY) | TGT_SEDA_S.ST_D2C_LOGCOST_HIGHEST_CWGT_CATEGORY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_LOGISTICS_NEW_TARRIF_2NDROUND_DB) | TGT_SEDA_S.ST_D2C_LOGISTICS_NEW_TARRIF_2NDROUND_DB | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_LOGISTICS_NEW_TARRIF_2NDROUND_DB_2) | TGT_SEDA_S.ST_D2C_LOGISTICS_NEW_TARRIF_2NDROUND_DB_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_MASTER) | TGT_SEDA_S.ST_D2C_MASTER | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_MASTER_ML) | TGT_SEDA_S.ST_D2C_MASTER_ML | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_MESO_REGION) | TGT_SEDA_S.ST_D2C_MESO_REGION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_PER_DIV_AND_DAY) | TGT_SEDA_S.ST_D2C_PER_DIV_AND_DAY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_PICKUP_NEW_TARIFF) | TGT_SEDA_S.ST_D2C_PICKUP_NEW_TARIFF | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_PICKUP_SIMULATION) | TGT_SEDA_S.ST_D2C_PICKUP_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_PICKUP_SIMULATION_2) | TGT_SEDA_S.ST_D2C_PICKUP_SIMULATION_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_PICKUP_TARIFF) | TGT_SEDA_S.ST_D2C_PICKUP_TARIFF | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_PICKUP_TARIFF_2) | TGT_SEDA_S.ST_D2C_PICKUP_TARIFF_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_RETURN_NEW_BID_SIMULATION) | TGT_SEDA_S.ST_D2C_RETURN_NEW_BID_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_SIT_NEW_BID_SIMULATION) | TGT_SEDA_S.ST_D2C_SIT_NEW_BID_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_SIT_NEW_TARIFF) | TGT_SEDA_S.ST_D2C_SIT_NEW_TARIFF | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_SIT_SIMULATION) | TGT_SEDA_S.ST_D2C_SIT_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_D2C_SIT_TARIFF) | TGT_SEDA_S.ST_D2C_SIT_TARIFF | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_DELIVERY_FAILURE_REASON) | TGT_SEDA_S.ST_DELIVERY_FAILURE_REASON | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_DELTA_T_LAST_MILE) | TGT_SEDA_S.ST_DELTA_T_LAST_MILE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_DELTA_T_LAST_MILE_RESUME) | TGT_SEDA_S.ST_DELTA_T_LAST_MILE_RESUME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_DIAS_UTEIS) | TGT_SEDA_S.ST_DIAS_UTEIS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_DIAS_UTEIS_2) | TGT_SEDA_S.ST_DIAS_UTEIS_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_EVENT_CODE) | TGT_SEDA_S.ST_EVENT_CODE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_EVENT_DESCRIPTION) | TGT_SEDA_S.ST_EVENT_DESCRIPTION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_EVENT_ETAPA) | TGT_SEDA_S.ST_EVENT_ETAPA | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_EXEMPLO) | TGT_SEDA_S.ST_EXEMPLO | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_FERIADOS) | TGT_SEDA_S.ST_FERIADOS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_FORCAST_BF_2024) | TGT_SEDA_S.ST_FORCAST_BF_2024 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_FREIGHT_TEST) | TGT_SEDA_S.ST_FREIGHT_TEST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_GI_DATE) | TGT_SEDA_S.ST_GI_DATE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_GI_PER_DIV_AND_DAY) | TGT_SEDA_S.ST_GI_PER_DIV_AND_DAY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_GORDURA_VTEX) | TGT_SEDA_S.ST_GORDURA_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_GORDURA_VTEX_PREVIEW) | TGT_SEDA_S.ST_GORDURA_VTEX_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_IN_TRANSIT_REPORT) | TGT_SEDA_S.ST_IN_TRANSIT_REPORT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_IN_TRANSIT_REPORT_PREVIEW) | TGT_SEDA_S.ST_IN_TRANSIT_REPORT_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_IN_TRANSIT_REPORT_RESUME) | TGT_SEDA_S.ST_IN_TRANSIT_REPORT_RESUME | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_IOD_CALCULATED_010425) | TGT_SEDA_S.ST_IOD_CALCULATED_010425 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_IOD_PER_DIV_AND_DAY) | TGT_SEDA_S.ST_IOD_PER_DIV_AND_DAY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ITEM_CATEGORY) | TGT_SEDA_S.ST_ITEM_CATEGORY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ITRR_TEST) | TGT_SEDA_S.ST_ITRR_TEST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_LT_ACTUAL_TRK_HUBS) | TGT_SEDA_S.ST_LT_ACTUAL_TRK_HUBS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_LT_ACTUAL_TRK_HUBS_SUPORTE) | TGT_SEDA_S.ST_LT_ACTUAL_TRK_HUBS_SUPORTE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_LT_CORREIOS) | TGT_SEDA_S.ST_LT_CORREIOS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_LT_P_C) | TGT_SEDA_S.ST_LT_P_C | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_LT_PICK_UP) | TGT_SEDA_S.ST_LT_PICK_UP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_MACHINE_LEARNING_ALL_TRK) | TGT_SEDA_S.ST_MACHINE_LEARNING_ALL_TRK | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_MACHINE_LEARNING_ALL_TRK_PT1) | TGT_SEDA_S.ST_MACHINE_LEARNING_ALL_TRK_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_FP) | TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_FP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_FP_PT1) | TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_FP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_GI) | TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_GI | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_GI_PT1) | TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_GI_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_TRK) | TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_TRK | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_TRK_PT1) | TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_TRK_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_TRK_TOD50) | TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_TRK_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_TRK_TOD50_PT1) | TGT_SEDA_S.ST_MACHINE_LEARNING_CELLO_TRK_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_OCC_ML) | TGT_SEDA_S.ST_OCC_ML | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_OPERATION_BY_ITEM) | TGT_SEDA_S.ST_OPERATION_BY_ITEM | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ORDER_TYPE_RTN) | TGT_SEDA_S.ST_ORDER_TYPE_RTN | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ORIGIN_CARRIER_VTEX) | TGT_SEDA_S.ST_ORIGIN_CARRIER_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_FINAL_HUBS) | TGT_SEDA_S.ST_PAINEL_FINAL_HUBS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_FINAL_HUBS_BKP) | TGT_SEDA_S.ST_PAINEL_FINAL_HUBS_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_IN_TRANSIT) | TGT_SEDA_S.ST_PAINEL_HUBS_IN_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_IN_TRANSIT_AGROUP) | TGT_SEDA_S.ST_PAINEL_HUBS_IN_TRANSIT_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_IN_TRANSIT_ALL_TRK) | TGT_SEDA_S.ST_PAINEL_HUBS_IN_TRANSIT_ALL_TRK | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_IN_TRANSIT_ATRASADOS) | TGT_SEDA_S.ST_PAINEL_HUBS_IN_TRANSIT_ATRASADOS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_IN_TRANSIT_DETAIL) | TGT_SEDA_S.ST_PAINEL_HUBS_IN_TRANSIT_DETAIL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_IOD) | TGT_SEDA_S.ST_PAINEL_HUBS_IOD | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_IOD_ACUM) | TGT_SEDA_S.ST_PAINEL_HUBS_IOD_ACUM | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_IOD_ACUM_PREVIEW) | TGT_SEDA_S.ST_PAINEL_HUBS_IOD_ACUM_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_ON_TIME) | TGT_SEDA_S.ST_PAINEL_HUBS_ON_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_ON_TIME_ACUM) | TGT_SEDA_S.ST_PAINEL_HUBS_ON_TIME_ACUM | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PAINEL_HUBS_ON_TIME_ACUM_PREVIEW) | TGT_SEDA_S.ST_PAINEL_HUBS_ON_TIME_ACUM_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PGR_D2C) | TGT_SEDA_S.ST_PGR_D2C | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_PO_PER_DIV_AND_DAY) | TGT_SEDA_S.ST_PO_PER_DIV_AND_DAY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_REGION_CLUSTER) | TGT_SEDA_S.ST_REGION_CLUSTER | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_RESPONSIBLE_BY_OCC) | TGT_SEDA_S.ST_RESPONSIBLE_BY_OCC | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_STATUS_BY_OCC_CORREIOS) | TGT_SEDA_S.ST_STATUS_BY_OCC_CORREIOS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_STATUS_BY_OCC_PUP) | TGT_SEDA_S.ST_STATUS_BY_OCC_PUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_STATUS_BY_OCC_SDS_CORREIOS) | TGT_SEDA_S.ST_STATUS_BY_OCC_SDS_CORREIOS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_STATUS_BY_OCC_SIT) | TGT_SEDA_S.ST_STATUS_BY_OCC_SIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_TARIFAS_SIT_TEMP) | TGT_SEDA_S.ST_TARIFAS_SIT_TEMP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_TARIFAS_TEMPORARIA) | TGT_SEDA_S.ST_TARIFAS_TEMPORARIA | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_TIPO_DE_ATENDIMENTO_TOTAL_EXPRESS) | TGT_SEDA_S.ST_TIPO_DE_ATENDIMENTO_TOTAL_EXPRESS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_TOD40_ESHOP_ACUM) | TGT_SEDA_S.ST_TOD40_ESHOP_ACUM | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_TOTAL_OPERATION) | TGT_SEDA_S.ST_TOTAL_OPERATION | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_TOTAL_OPERATION2) | TGT_SEDA_S.ST_TOTAL_OPERATION2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_WGT_RANGE_2ND) | TGT_SEDA_S.ST_WGT_RANGE_2ND | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_WH_CAP_CONTROL) | TGT_SEDA_S.ST_WH_CAP_CONTROL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.ST_ZIP_CLUSTER) | TGT_SEDA_S.ST_ZIP_CLUSTER | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.TBL_CARRIERS) | TGT_SEDA_S.TBL_CARRIERS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.TBL_ENTREGAS) | TGT_SEDA_S.TBL_ENTREGAS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-09 | [7 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.TMP_D2C_LOGCOST_VIZ_AUX_CARRIER_CD) | TGT_SEDA_S.TMP_D2C_LOGCOST_VIZ_AUX_CARRIER_CD | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.TMP_D2C_LOGCOST_VIZ_RETAIL_D2C) | TGT_SEDA_S.TMP_D2C_LOGCOST_VIZ_RETAIL_D2C | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S.TMP_D2C_LOGCOST_VIZ_TRZONES) | TGT_SEDA_S.TMP_D2C_LOGCOST_VIZ_TRZONES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.CELLO_DELIVERY_WITH_1ST_BK) | TGT_SEDA_S.CELLO_DELIVERY_WITH_1ST_BK | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.CUSTO2024) | TGT_SEDA_S.CUSTO2024 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)]
|  | VIEW | (VIEW - TGT_SEDA_S.DIAS_UTEIS) | TGT_SEDA_S.DIAS_UTEIS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.INPUT_METRICS) | TGT_SEDA_S.INPUT_METRICS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.TESTE_IOD_ACUMULADO) | TGT_SEDA_S.TESTE_IOD_ACUMULADO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.TESTE_OSCAR) | TGT_SEDA_S.TESTE_OSCAR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ACTUAL_LT) | TGT_SEDA_S.VW_ACTUAL_LT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ACTUAL_LT_1STHUB) | TGT_SEDA_S.VW_ACTUAL_LT_1STHUB | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ACTUAL_VTEX_LT) | TGT_SEDA_S.VW_ACTUAL_VTEX_LT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ALE_HYPERCARE) | TGT_SEDA_S.VW_ALE_HYPERCARE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ALE_HYPERCARE_TRANSIT) | TGT_SEDA_S.VW_ALE_HYPERCARE_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ALERTA_IOD_PER_HOUR) | TGT_SEDA_S.VW_ALERTA_IOD_PER_HOUR | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - SYS.DUMMY),(SYNONYM - PUBLIC.DUMMY),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ALERTA_IOD_PER_HOUR_PREV_DAY) | TGT_SEDA_S.VW_ALERTA_IOD_PER_HOUR_PREV_DAY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ALL_TRK_UPLOAD_OCC) | TGT_SEDA_S.VW_ALL_TRK_UPLOAD_OCC | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ALL_TRK_UPLOAD_OCC_FINAL) | TGT_SEDA_S.VW_ALL_TRK_UPLOAD_OCC_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ALL_TRK_UPLOAD_OCC_PREVIEW) | TGT_SEDA_S.VW_ALL_TRK_UPLOAD_OCC_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ALL_TRK_UPLOAD_OCC_PREVIEW_5) | TGT_SEDA_S.VW_ALL_TRK_UPLOAD_OCC_PREVIEW_5 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-12 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ALL_TRK_UPLOAD_OCC_PREVIEW_6) | TGT_SEDA_S.VW_ALL_TRK_UPLOAD_OCC_PREVIEW_6 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ATTEMPT_DELIVERY) | TGT_SEDA_S.VW_ATTEMPT_DELIVERY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVAILABLE_PICKUP) | TGT_SEDA_S.VW_AVAILABLE_PICKUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_ACTUAL_LT) | TGT_SEDA_S.VW_AVG_ACTUAL_LT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_ACTUAL_LT_1STHUB) | TGT_SEDA_S.VW_AVG_ACTUAL_LT_1STHUB | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_ACTUAL_MODE_LT) | TGT_SEDA_S.VW_AVG_ACTUAL_MODE_LT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_AR_LOGISTICS_VAR) | TGT_SEDA_S.VW_AVG_AR_LOGISTICS_VAR | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_IOD_PER_HOUR) | TGT_SEDA_S.VW_AVG_IOD_PER_HOUR | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_LT_HUBS_AGROUP) | TGT_SEDA_S.VW_AVG_LT_HUBS_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_LT_HUBS_DELAYED_AGROUP) | TGT_SEDA_S.VW_AVG_LT_HUBS_DELAYED_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_LT_HUBS_DELAYED_DETAIL) | TGT_SEDA_S.VW_AVG_LT_HUBS_DELAYED_DETAIL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_LT_HUBS_IOD_AGROUP) | TGT_SEDA_S.VW_AVG_LT_HUBS_IOD_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_AGROUP) | TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_AGROUP_FINAL) | TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_AGROUP_PT1) | TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-13 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP) | TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP_FINAL) | TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP_PT1) | TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD40_DELAYED_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD50_AGROUP) | TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD50_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD50_AGROUP_FINAL) | TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD50_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD50_AGROUP_PT1) | TGT_SEDA_S.VW_AVG_RANGE_DATE_TOD50_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_AVG_VTEX_LT) | TGT_SEDA_S.VW_AVG_VTEX_LT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_3DAYS) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_3DAYS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_DELAYED) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_DELAYED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_TESTE) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_FINAL_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_PREVIEW) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_PREVIEW_TESTE) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_PREVIEW_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_TESTE) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_NEW_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_TESTE) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREDICT_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-14 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_0_TOD40) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_0_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_0_TOD40_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_0_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_0_TOD50) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_0_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_0_TOD50_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_0_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_1_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_1_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP_FINAL) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_TOD40) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_TOD40_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_TOD50) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_TOD50_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_TRANSIT) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_1_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-15 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_1_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_1_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_2) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_3DAYS) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_3DAYS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP_FINAL) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD10) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD10 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD10_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD10_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD40) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD40_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD50) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD50_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_2_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-16 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_1_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_1_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD40) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD40_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD50) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD50_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_2_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_TOD40) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_TOD40_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_TOD50) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_TOD50_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_3_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP_FINAL) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_DELAY) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_DELAY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_DELAY_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_DELAY_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-19 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_IOD_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT_ML) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT_ML | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT_TESTE) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_ALL_TRK_TRANSIT_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_2) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_2_TESTE) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_2_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_3) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_3 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_3_TESTE) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_3_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_TESTE) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PREDICT_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD10) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD10 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD40) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP_FINAL) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD40_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP_FINAL) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-20 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TOD50_AGROUP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT_2) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT_2_TESTE) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT_2_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT_TESTE) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PREVIEW_TRANSIT_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD10) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD10 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD10_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD10_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD10_TREINO) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD10_TREINO | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_DELAYED) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_DELAYED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_FINAL) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_FINAL_DELAYED) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_FINAL_DELAYED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_FINAL_DELAYED_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_FINAL_DELAYED_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_FINAL_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_FINAL_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_TREINO) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD40_TREINO | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-21 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD50) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD50_DELAYED) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD50_DELAYED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD50_FINAL) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD50_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD50_FINAL_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD50_FINAL_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD50_PT1) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TRANSIT) | TGT_SEDA_S.VW_BASE_MACHINE_LEARNING_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_BETA_CAP_WH) | TGT_SEDA_S.VW_BETA_CAP_WH | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_MD.DIM_CALENDAR),(VIEW - TGT_SEDA_S_SCM.VW_WH_MONTHLY_CAPA),(TABLE - OW_SEDA_S.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - TGT_SEDA_S_SCM.DIM_WH_CAPA_UPDATE),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.CELLO_SHIPMENT),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM),(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CALC_QTY_PCS_HOUR) | TGT_SEDA_S.VW_CALC_QTY_PCS_HOUR | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CD_HOUR) | TGT_SEDA_S.VW_CD_HOUR | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CELLO_DELIVERY_WITH_1ST_BK) | TGT_SEDA_S.VW_CELLO_DELIVERY_WITH_1ST_BK | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CELLO_FUTHER_PROC_TRATADA) | TGT_SEDA_S.VW_CELLO_FUTHER_PROC_TRATADA | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CELLO_TK_HUBS_TRATADA) | TGT_SEDA_S.VW_CELLO_TK_HUBS_TRATADA | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CELLO_TK_HUBS_TRATADA_PREVIEW) | TGT_SEDA_S.VW_CELLO_TK_HUBS_TRATADA_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CELLO_TK_HUBS_TRATADA_PREVIEW_TOD50) | TGT_SEDA_S.VW_CELLO_TK_HUBS_TRATADA_PREVIEW_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CELLO_TRK_DECISION_TREE) | TGT_SEDA_S.VW_CELLO_TRK_DECISION_TREE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-22 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CFP_HOUR) | TGT_SEDA_S.VW_CFP_HOUR | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CM_HOUR) | TGT_SEDA_S.VW_CM_HOUR | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_COCKPIT) | TGT_SEDA_S.VW_COCKPIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_CT_HOUR) | TGT_SEDA_S.VW_CT_HOUR | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_1ST_BOOKING) | TGT_SEDA_S.VW_D2C_1ST_BOOKING | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_2025) | TGT_SEDA_S.VW_D2C_2025 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_AR_LOGISTICS) | TGT_SEDA_S.VW_D2C_AR_LOGISTICS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_AR_LOGISTICS_2) | TGT_SEDA_S.VW_D2C_AR_LOGISTICS_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_AR_LOGISTICS_NEW_PROJECTED) | TGT_SEDA_S.VW_D2C_AR_LOGISTICS_NEW_PROJECTED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_AS_IS_FPC_RANKING) | TGT_SEDA_S.VW_D2C_AS_IS_FPC_RANKING | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_CATEGORY_TRANSIT_ML) | TGT_SEDA_S.VW_D2C_CATEGORY_TRANSIT_ML | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_GI_CONTROL) | TGT_SEDA_S.VW_D2C_GI_CONTROL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_IN_TRANSIT_RDD) | TGT_SEDA_S.VW_D2C_IN_TRANSIT_RDD | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_KPIS) | TGT_SEDA_S.VW_D2C_KPIS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_KPIS_INSERT_MONTH) | TGT_SEDA_S.VW_D2C_KPIS_INSERT_MONTH | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-23 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_KPIS_ML) | TGT_SEDA_S.VW_D2C_KPIS_ML | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_LOG_NEW_BID_FPC_RANKING) | TGT_SEDA_S.VW_D2C_LOG_NEW_BID_FPC_RANKING | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_LOGCOST_HIGHEST_CWGT_CATEGORY) | TGT_SEDA_S.VW_D2C_LOGCOST_HIGHEST_CWGT_CATEGORY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_LOGCOST_MGTM_SUBCARRIER_CELLO) | TGT_SEDA_S.VW_D2C_LOGCOST_MGTM_SUBCARRIER_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_NEW_BID_FPC_RANKING) | TGT_SEDA_S.VW_D2C_NEW_BID_FPC_RANKING | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_NEW_BID_LTC_RANKING) | TGT_SEDA_S.VW_D2C_NEW_BID_LTC_RANKING | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_RETURN_NEW_BID_FPC_RANKING) | TGT_SEDA_S.VW_D2C_RETURN_NEW_BID_FPC_RANKING | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_D2C_SIT_NEW_BID_FPC_RANKING) | TGT_SEDA_S.VW_D2C_SIT_NEW_BID_FPC_RANKING | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_DAYS_1STBK_IOD) | TGT_SEDA_S.VW_DAYS_1STBK_IOD | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_DELIVERY_FAIL) | TGT_SEDA_S.VW_DELIVERY_FAIL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_DELTA_T_LAST_MILE) | TGT_SEDA_S.VW_DELTA_T_LAST_MILE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_DEPARTURE_FOR_CUSTOMER) | TGT_SEDA_S.VW_DEPARTURE_FOR_CUSTOMER | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_DM_D2C_LOGCOST_MANAGEMENT) | TGT_SEDA_S.VW_DM_D2C_LOGCOST_MANAGEMENT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_DM_D2C_LOGCOST_MANAGEMENT_MX) | TGT_SEDA_S.VW_DM_D2C_LOGCOST_MANAGEMENT_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_DOS_DELAYED_EVENTS) | TGT_SEDA_S.VW_DOS_DELAYED_EVENTS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-26 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_FINAL_PAINEL_HUBS_TESTE) | TGT_SEDA_S.VW_FINAL_PAINEL_HUBS_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_FORECAST) | TGT_SEDA_S.VW_FORECAST | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_FORECAST2) | TGT_SEDA_S.VW_FORECAST2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_FORECAST3) | TGT_SEDA_S.VW_FORECAST3 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_FREIGHT_TEST) | TGT_SEDA_S.VW_FREIGHT_TEST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_GI_DATE) | TGT_SEDA_S.VW_GI_DATE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_HC) | TGT_SEDA_S.VW_HC | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_HC_ALE) | TGT_SEDA_S.VW_HC_ALE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_IN_TRANSIT_EVENTS) | TGT_SEDA_S.VW_IN_TRANSIT_EVENTS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_IN_TRANSIT_HUBS_TESTE) | TGT_SEDA_S.VW_IN_TRANSIT_HUBS_TESTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_IN_TRANSIT_REPORT) | TGT_SEDA_S.VW_IN_TRANSIT_REPORT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_IN_TRANSIT_REPORT_PREVIEW) | TGT_SEDA_S.VW_IN_TRANSIT_REPORT_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_IOD_LAST_MILE_PREDICTED) | TGT_SEDA_S.VW_IOD_LAST_MILE_PREDICTED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_IOD_POD_INBOUND) | TGT_SEDA_S.VW_IOD_POD_INBOUND | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_POD)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_IOD_PREDCTION) | TGT_SEDA_S.VW_IOD_PREDCTION | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_IOD_SAME_DAY) | TGT_SEDA_S.VW_IOD_SAME_DAY | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_IOD_SAME_DAY2) | TGT_SEDA_S.VW_IOD_SAME_DAY2 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ITTP_INBOUND) | TGT_SEDA_S.VW_ITTP_INBOUND | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-27 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND),(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_LAST_UPDATED_TABLES) | TGT_SEDA_S.VW_LAST_UPDATED_TABLES | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - SYS.DUMMY),(SYNONYM - PUBLIC.DUMMY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_LONG_TERM_SIT) | TGT_SEDA_S.VW_LONG_TERM_SIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MACHINE_LEARNING_ALL_TRK) | TGT_SEDA_S.VW_MACHINE_LEARNING_ALL_TRK | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MACHINE_LEARNING_ALL_TRK_PT1) | TGT_SEDA_S.VW_MACHINE_LEARNING_ALL_TRK_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_FP) | TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_FP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_FP_PT1) | TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_FP_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_GI) | TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_GI | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_GI_PT1) | TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_GI_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_TRK) | TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_TRK | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_TRK_PT1) | TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_TRK_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_TRK_TOD50) | TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_TRK_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_TRK_TOD50_PT1) | TGT_SEDA_S.VW_MACHINE_LEARNING_CELLO_TRK_TOD50_PT1 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_MEDIA_SIGMA) | TGT_SEDA_S.VW_MEDIA_SIGMA | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_NEW_ETA_CALCULATED) | TGT_SEDA_S.VW_NEW_ETA_CALCULATED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_OCCURRENCE_RETURNS) | TGT_SEDA_S.VW_OCCURRENCE_RETURNS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-28 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_OPEN_RETURN_NERP) | TGT_SEDA_S.VW_OPEN_RETURN_NERP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN),(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_OPEN_SO) | TGT_SEDA_S.VW_OPEN_SO | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ORDER_LIFE) | TGT_SEDA_S.VW_ORDER_LIFE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_SHIPMENT),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ORIGIN_PLANT_STORAGE) | TGT_SEDA_S.VW_ORIGIN_PLANT_STORAGE | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_FINAL_HUBS) | TGT_SEDA_S.VW_PAINEL_FINAL_HUBS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_DELAYED) | TGT_SEDA_S.VW_PAINEL_HUBS_DELAYED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_FINAL) | TGT_SEDA_S.VW_PAINEL_HUBS_FINAL | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_IN_TRANSIT) | TGT_SEDA_S.VW_PAINEL_HUBS_IN_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_IN_TRANSIT_ALL_TRK) | TGT_SEDA_S.VW_PAINEL_HUBS_IN_TRANSIT_ALL_TRK | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_IN_TRANSIT_ATRASADOS) | TGT_SEDA_S.VW_PAINEL_HUBS_IN_TRANSIT_ATRASADOS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_IN_TRANSIT_DELAYED) | TGT_SEDA_S.VW_PAINEL_HUBS_IN_TRANSIT_DELAYED | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_IOD) | TGT_SEDA_S.VW_PAINEL_HUBS_IOD | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_IOD_ACUM) | TGT_SEDA_S.VW_PAINEL_HUBS_IOD_ACUM | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_IOD_ACUM_PREVIEW) | TGT_SEDA_S.VW_PAINEL_HUBS_IOD_ACUM_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_ON_TIME) | TGT_SEDA_S.VW_PAINEL_HUBS_ON_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-29 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_ON_TIME_ACUM) | TGT_SEDA_S.VW_PAINEL_HUBS_ON_TIME_ACUM | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_ON_TIME_ACUM_PREVIEW) | TGT_SEDA_S.VW_PAINEL_HUBS_ON_TIME_ACUM_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_PREVIEW) | TGT_SEDA_S.VW_PAINEL_HUBS_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PAINEL_HUBS_PREVIEW_NEW) | TGT_SEDA_S.VW_PAINEL_HUBS_PREVIEW_NEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_PEDIDOS_MX_ZIP) | TGT_SEDA_S.VW_PEDIDOS_MX_ZIP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_REDESPACHO) | TGT_SEDA_S.VW_REDESPACHO | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_RETURN_CLAIM_OCCR) | TGT_SEDA_S.VW_RETURN_CLAIM_OCCR | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_RETURN_OCCURRENCES) | TGT_SEDA_S.VW_RETURN_OCCURRENCES | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_RETURN_REPORT) | TGT_SEDA_S.VW_RETURN_REPORT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_REVERSAO_ATRASOS) | TGT_SEDA_S.VW_REVERSAO_ATRASOS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ST_GORDURA_VTEX) | TGT_SEDA_S.VW_ST_GORDURA_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ST_GORDURA_VTEX_PREVIEW) | TGT_SEDA_S.VW_ST_GORDURA_VTEX_PREVIEW | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ST_MONTH_AVG_GI) | TGT_SEDA_S.VW_ST_MONTH_AVG_GI | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_STO_STATUS) | TGT_SEDA_S.VW_STO_STATUS | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_TESTE_SUBVIEW_1) | TGT_SEDA_S.VW_TESTE_SUBVIEW_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_TESTE_SUBVIEW_2) | TGT_SEDA_S.VW_TESTE_SUBVIEW_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_TOD50) | TGT_SEDA_S.VW_TOD50 | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-01-30 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_TOD50_CFP) | TGT_SEDA_S.VW_TOD50_CFP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-02 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_TRK_TEAM_IN_TRANSIT) | TGT_SEDA_S.VW_TRK_TEAM_IN_TRANSIT | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-02 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_TRK_TEAM_OCC) | TGT_SEDA_S.VW_TRK_TEAM_OCC | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_TRK_TEAM_OCC_OTD) | TGT_SEDA_S.VW_TRK_TEAM_OCC_OTD | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-02 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S.VW_UNION_D2C_MASTER) | TGT_SEDA_S.VW_UNION_D2C_MASTER | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-02 | [7 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S.VW_ZIP_TOP) | TGT_SEDA_S.VW_ZIP_TOP | SEDA-S - Logistics | gabriel.mp |  |  |  | To be migrated |  | 2026-02-02 | [7 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - CON_SEDA_S_SCM.VW_D2C_CELLO_WH_PGI_REPORT) | CON_SEDA_S_SCM.VW_D2C_CELLO_WH_PGI_REPORT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_MD.DIM_CALENDAR),(VIEW - TGT_SEDA_S_SCM.VW_WH_MONTHLY_CAPA),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - TGT_SEDA_S_SCM.DIM_WH_CAPA_UPDATE),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | VIEW | (VIEW - CON_SEDA_S_SCM.VW_WH_CARRIER_CAPA_MONITOR_V2) | CON_SEDA_S_SCM.VW_WH_CARRIER_CAPA_MONITOR_V2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_MD.DIM_CALENDAR),(VIEW - TGT_SEDA_S_SCM.VW_WH_MONTHLY_CAPA),(TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOGCOST_VIZ_AUX_CARRIER_CD),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE),(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM),(TABLE - OW_SEDA_S.CELLO_SHIPMENT),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM),(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM),(TABLE - TGT_SEDA_S_SCM.DIM_WH_CAPA_UPDATE),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | PROCEDURE | (PROCEDURE - CON_SEDA_S_SCM.PRC_AVG_LT_WORKDAYS) | CON_SEDA_S_SCM.PRC_AVG_LT_WORKDAYS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(VIEW - TGT_SEDA_S_SCM.VW_D2C_LOGCOST_MGTM_SUBCARRIER_CELLO),(TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOGCOST_VIZ_AUX_CARRIER_CD),(TABLE - OW_SEDA_S.CELLO_SHIPMENT),(TABLE - TGT_SEDA_S_SCM.DIM_TP_HOLIDAYS_CALENDAR),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_DELIVERY),(TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOGCOST_VIZ_TRZONES)]
|  | PROCEDURE | (PROCEDURE - CON_SEDA_S_SCM.PRC_D2CLOG_DO_PROJECTION_LT) | CON_SEDA_S_SCM.PRC_D2CLOG_DO_PROJECTION_LT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(VIEW - TGT_SEDA_S_SCM.VW_D2C_LOGCOST_MGTM_SUBCARRIER_CELLO),(TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOGCOST_VIZ_AUX_CARRIER_CD),(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER),(TABLE - OW_SEDA_S.CELLO_SHIPMENT),(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING),(TABLE - TGT_SEDA_S_SCM.DIM_TP_HOLIDAYS_CALENDAR),(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM),(TABLE - OW_SEDA_S.CELLO_MANIFEST),(TABLE - OW_SEDA_S.CELLO_TRACKING),(TABLE - OW_SEDA_S.CELLO_DELIVERY)]
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.CT_LOG) | TGT_SEDA_S_SCM.CT_LOG | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_B2C_ALERT_SEQ90) | TGT_SEDA_S_SCM.DIM_B2C_ALERT_SEQ90 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_B2C_OVBOOK_MATERIAL_TO_CATEGORY) | TGT_SEDA_S_SCM.DIM_B2C_OVBOOK_MATERIAL_TO_CATEGORY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_B2C_OVBOOK_SHIP_TO_AP1_CE) | TGT_SEDA_S_SCM.DIM_B2C_OVBOOK_SHIP_TO_AP1_CE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_B2C_OVBOOK_SHIP_TO_AP1_MX) | TGT_SEDA_S_SCM.DIM_B2C_OVBOOK_SHIP_TO_AP1_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_CT_STATUS_DE_PARA_MKP) | TGT_SEDA_S_SCM.DIM_CT_STATUS_DE_PARA_MKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_TP_CUTOFF_TIME) | TGT_SEDA_S_SCM.DIM_TP_CUTOFF_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_TP_HOLIDAYS_CALENDAR) | TGT_SEDA_S_SCM.DIM_TP_HOLIDAYS_CALENDAR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_TP_LAST_EVENT) | TGT_SEDA_S_SCM.DIM_TP_LAST_EVENT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_TP_LEADTIME_AZUL) | TGT_SEDA_S_SCM.DIM_TP_LEADTIME_AZUL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_TP_NEW_REALEASE) | TGT_SEDA_S_SCM.DIM_TP_NEW_REALEASE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_TP_OCCURRENCES) | TGT_SEDA_S_SCM.DIM_TP_OCCURRENCES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_TP_UF_TO_REGION) | TGT_SEDA_S_SCM.DIM_TP_UF_TO_REGION | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_TP_WORKDAYS_CALENDAR) | TGT_SEDA_S_SCM.DIM_TP_WORKDAYS_CALENDAR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.DIM_WH_CAPA_UPDATE) | TGT_SEDA_S_SCM.DIM_WH_CAPA_UPDATE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT1_B2B_LOGCOST_ACCRUAL) | TGT_SEDA_S_SCM.FT1_B2B_LOGCOST_ACCRUAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT1_D2C_LOGCOST_MGTM) | TGT_SEDA_S_SCM.FT1_D2C_LOGCOST_MGTM | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT1_D2C_LOGCOST_MGTM_ALL) | TGT_SEDA_S_SCM.FT1_D2C_LOGCOST_MGTM_ALL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT1_D2C_LOGCOST_MGTM_MX) | TGT_SEDA_S_SCM.FT1_D2C_LOGCOST_MGTM_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT2_B2B_LOGCOST_ACCRUAL) | TGT_SEDA_S_SCM.FT2_B2B_LOGCOST_ACCRUAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT2_D2C_LOGCOST_MGTM) | TGT_SEDA_S_SCM.FT2_D2C_LOGCOST_MGTM | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT2_D2C_LOGCOST_MGTM_ALL) | TGT_SEDA_S_SCM.FT2_D2C_LOGCOST_MGTM_ALL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT2_D2C_LOGCOST_MGTM_MX) | TGT_SEDA_S_SCM.FT2_D2C_LOGCOST_MGTM_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT2_D2C_LOGCOST_MGTM_MX_BKP) | TGT_SEDA_S_SCM.FT2_D2C_LOGCOST_MGTM_MX_BKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT3_D2C_LOGCOST_MGTM) | TGT_SEDA_S_SCM.FT3_D2C_LOGCOST_MGTM | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_CT2_PLUGG) | TGT_SEDA_S_SCM.FT_CT2_PLUGG | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_CT_CELLO_OCCURRENCES) | TGT_SEDA_S_SCM.FT_CT_CELLO_OCCURRENCES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_CT_CELLO_TRACKING_CODES) | TGT_SEDA_S_SCM.FT_CT_CELLO_TRACKING_CODES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_CT_OCCURRENCES) | TGT_SEDA_S_SCM.FT_CT_OCCURRENCES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_CT_VTEX_V2) | TGT_SEDA_S_SCM.FT_CT_VTEX_V2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_CLAIM_VISIBILITY) | TGT_SEDA_S_SCM.FT_D2C_CLAIM_VISIBILITY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_FPC_RANKING_VTEX_RANGES) | TGT_SEDA_S_SCM.FT_D2C_FPC_RANKING_VTEX_RANGES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_2023_FULLDATA) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_2023_FULLDATA | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_COPQ) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_COPQ | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_COPQ_MX) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_COPQ_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_FPC_RANK_BY_ROUTE) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_FPC_RANK_BY_ROUTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM_FPC_2023) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM_FPC_2023 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM_SIMULATION) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM_SIMULATION_ALL) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM_SIMULATION_ALL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM_SIMULATION_MX) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM_SIMULATION_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM_TARIFFS_2023) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_MGTM_TARIFFS_2023 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_UNIT_COST) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_UNIT_COST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGCOST_UNIT_COST_MX) | TGT_SEDA_S_SCM.FT_D2C_LOGCOST_UNIT_COST_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGISTICS_NEW_TARIFF_DB) | TGT_SEDA_S_SCM.FT_D2C_LOGISTICS_NEW_TARIFF_DB | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGISTICS_NEW_TARIFF_DB4_SIMULATION) | TGT_SEDA_S_SCM.FT_D2C_LOGISTICS_NEW_TARIFF_DB4_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGISTICS_NEW_TARIFF_DB_BACKUP) | TGT_SEDA_S_SCM.FT_D2C_LOGISTICS_NEW_TARIFF_DB_BACKUP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGISTICS_NEW_TARIFF_M2) | TGT_SEDA_S_SCM.FT_D2C_LOGISTICS_NEW_TARIFF_M2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOGISTICS_NEW_TARIFF_M2_TRZONE) | TGT_SEDA_S_SCM.FT_D2C_LOGISTICS_NEW_TARIFF_M2_TRZONE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOG_FPC_RATIO_BY_ROUTE) | TGT_SEDA_S_SCM.FT_D2C_LOG_FPC_RATIO_BY_ROUTE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOG_OLD_TARIFF_FPC_RANKING) | TGT_SEDA_S_SCM.FT_D2C_LOG_OLD_TARIFF_FPC_RANKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOG_UNIT_COST_SIMULATION) | TGT_SEDA_S_SCM.FT_D2C_LOG_UNIT_COST_SIMULATION | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_LOG_UNIT_COST_SIMULATION_MX) | TGT_SEDA_S_SCM.FT_D2C_LOG_UNIT_COST_SIMULATION_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_D2C_TEX_REDESPACHO_ZONES) | TGT_SEDA_S_SCM.FT_D2C_TEX_REDESPACHO_ZONES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_WH_CUTOFF_TIME) | TGT_SEDA_S_SCM.FT_WH_CUTOFF_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_WH_HANDLING_TARIFF_VD) | TGT_SEDA_S_SCM.FT_WH_HANDLING_TARIFF_VD | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.FT_WH_HANDLING_TEC_WORKAROUND) | TGT_SEDA_S_SCM.FT_WH_HANDLING_TEC_WORKAROUND | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.IMPORT_CEP_SP) | TGT_SEDA_S_SCM.IMPORT_CEP_SP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.INTERFACE_UPDATES) | TGT_SEDA_S_SCM.INTERFACE_UPDATES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.MASTER_LT_VTEX_CELLO) | TGT_SEDA_S_SCM.MASTER_LT_VTEX_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.MATERIAL_MASTER) | TGT_SEDA_S_SCM.MATERIAL_MASTER | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.PLUGG_FT_MANUAL_HISTORY) | TGT_SEDA_S_SCM.PLUGG_FT_MANUAL_HISTORY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.RAW_D2C_LOGCOST_MGTM_TARIFFS_2023) | TGT_SEDA_S_SCM.RAW_D2C_LOGCOST_MGTM_TARIFFS_2023 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.RAW_PREDIZE_TICKETS) | TGT_SEDA_S_SCM.RAW_PREDIZE_TICKETS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.RAW_PREDIZE_TICKETS_ORDER) | TGT_SEDA_S_SCM.RAW_PREDIZE_TICKETS_ORDER | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.REF_VTEX_PRODUCT_NAMES) | TGT_SEDA_S_SCM.REF_VTEX_PRODUCT_NAMES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TMP2_D2C_LOGISTICS_NEW_TARIFF_DB_INGESTION) | TGT_SEDA_S_SCM.TMP2_D2C_LOGISTICS_NEW_TARIFF_DB_INGESTION | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOGCOST_VIZ_AUX_CARRIER_CD) | TGT_SEDA_S_SCM.TMP_D2C_LOGCOST_VIZ_AUX_CARRIER_CD | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOGCOST_VIZ_RETAIL_D2C) | TGT_SEDA_S_SCM.TMP_D2C_LOGCOST_VIZ_RETAIL_D2C | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOGCOST_VIZ_TRZONES) | TGT_SEDA_S_SCM.TMP_D2C_LOGCOST_VIZ_TRZONES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOGISTICS_NEW_TARIFF_DB) | TGT_SEDA_S_SCM.TMP_D2C_LOGISTICS_NEW_TARIFF_DB | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOGISTICS_NEW_TARIFF_DB_INGESTION) | TGT_SEDA_S_SCM.TMP_D2C_LOGISTICS_NEW_TARIFF_DB_INGESTION | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOG_TOTAL_DIALOGO_ZIP_RANGES) | TGT_SEDA_S_SCM.TMP_D2C_LOG_TOTAL_DIALOGO_ZIP_RANGES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TMP_D2C_LOG_VTEX_ZIP_RANGES) | TGT_SEDA_S_SCM.TMP_D2C_LOG_VTEX_ZIP_RANGES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TMP_IOD_SAME_DAY) | TGT_SEDA_S_SCM.TMP_IOD_SAME_DAY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TMP_SKU_NAMES_VTEX) | TGT_SEDA_S_SCM.TMP_SKU_NAMES_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TRACKING_DIM_TP_CARRIER_NAME) | TGT_SEDA_S_SCM.TRACKING_DIM_TP_CARRIER_NAME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TRACKING_DIVISION_MAPPING) | TGT_SEDA_S_SCM.TRACKING_DIVISION_MAPPING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TRACKING_FT_ITT_HIST_DATA) | TGT_SEDA_S_SCM.TRACKING_FT_ITT_HIST_DATA | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TRACKING_ITT_OTD) | TGT_SEDA_S_SCM.TRACKING_ITT_OTD | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TRK_CODE_NM_REVIEWED) | TGT_SEDA_S_SCM.TRK_CODE_NM_REVIEWED | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TSP_RETAIL_TARIFF) | TGT_SEDA_S_SCM.TSP_RETAIL_TARIFF | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.TSP_RETAIL_TARIFF_COMP_COST) | TGT_SEDA_S_SCM.TSP_RETAIL_TARIFF_COMP_COST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | TABLE | (TABLE - TGT_SEDA_S_SCM.WH_HANDLING_TARIFF) | TGT_SEDA_S_SCM.WH_HANDLING_TARIFF | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.AR_FBL5N_ANALYSIS) | TGT_SEDA_S_SCM.AR_FBL5N_ANALYSIS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.DM_D2C_LOGCOST_VISIBILITY) | TGT_SEDA_S_SCM.DM_D2C_LOGCOST_VISIBILITY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_AR_JOIN) | TGT_SEDA_S_SCM.FT_AR_JOIN | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBREPP2), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_AR_VTEX) | TGT_SEDA_S_SCM.FT_AR_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_ASSIGNMENT_CLEANED) | TGT_SEDA_S_SCM.FT_ASSIGNMENT_CLEANED | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_ASSIGNMENT_CLEANED_FOUND) | TGT_SEDA_S_SCM.FT_ASSIGNMENT_CLEANED_FOUND | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_CELLO_IOD_TOTAL) | TGT_SEDA_S_SCM.FT_CELLO_IOD_TOTAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_FBL5N_ARRAY) | TGT_SEDA_S_SCM.FT_FBL5N_ARRAY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_FBL5N_BASE) | TGT_SEDA_S_SCM.FT_FBL5N_BASE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_FBL5N_DELAYED) | TGT_SEDA_S_SCM.FT_FBL5N_DELAYED | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_FBL5N_FORMAT) | TGT_SEDA_S_SCM.FT_FBL5N_FORMAT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_JOIN_OPEN_ITEMS) | TGT_SEDA_S_SCM.FT_JOIN_OPEN_ITEMS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_MISSING_ASSIGNMENT) | TGT_SEDA_S_SCM.FT_MISSING_ASSIGNMENT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_OPEN_ITEMS) | TGT_SEDA_S_SCM.FT_OPEN_ITEMS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL), (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO), (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_EXCLUDED_DO), (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST), (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBREPP2), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (VIEW - OW_SEDA_S.VW_STATUS_MAPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_SO_DO_AMT) | TGT_SEDA_S_SCM.FT_SO_DO_AMT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_UNION_TSS_CELLO) | TGT_SEDA_S_SCM.FT_UNION_TSS_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO), (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST), (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_VOUCHER) | TGT_SEDA_S_SCM.FT_VOUCHER | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_VTEX) | TGT_SEDA_S_SCM.FT_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_VTEX_ORDER_FOUND) | TGT_SEDA_S_SCM.FT_VTEX_ORDER_FOUND | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_VTEX_SEARCH) | TGT_SEDA_S_SCM.FT_VTEX_SEARCH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.FT_VTEX_SHIP) | TGT_SEDA_S_SCM.FT_VTEX_SHIP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.LOGCOST_ENTRY_DATE_DB) | TGT_SEDA_S_SCM.LOGCOST_ENTRY_DATE_DB | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.LOGCOST_VW_CLOSING_REPORT) | TGT_SEDA_S_SCM.LOGCOST_VW_CLOSING_REPORT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.LOGCOST_VW_DATABASE) | TGT_SEDA_S_SCM.LOGCOST_VW_DATABASE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.LOG_AC_BALANCE_VW_RAWDATA) | TGT_SEDA_S_SCM.LOG_AC_BALANCE_VW_RAWDATA | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.MKP_ISSUE_LIST) | TGT_SEDA_S_SCM.MKP_ISSUE_LIST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS) | TGT_SEDA_S_SCM.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST_EXTRACT) | TGT_SEDA_S_SCM.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST_EXTRACT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST_LAST) | TGT_SEDA_S_SCM.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST_LAST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST_LAST1) | TGT_SEDA_S_SCM.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST_LAST1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.PLUGG_LOG_HISTORY) | TGT_SEDA_S_SCM.PLUGG_LOG_HISTORY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.PLUGG_LOG_HISTORY_Migrar ph 2) | TGT_SEDA_S_SCM.PLUGG_LOG_HISTORY_Migrarph2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY_Migrar ph 2)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.PLUGG_STATUS_HISTORY) | TGT_SEDA_S_SCM.PLUGG_STATUS_HISTORY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.RAW_FBL5N_INPUT) | TGT_SEDA_S_SCM.RAW_FBL5N_INPUT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.RETURNS_PORTION_VW_ANALYSIS) | TGT_SEDA_S_SCM.RETURNS_PORTION_VW_ANALYSIS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.RETURNS_VW_ANALYSIS_2024) | TGT_SEDA_S_SCM.RETURNS_VW_ANALYSIS_2024 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.M_CODE_CELLO)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.RETURN_CORR_VW_OCCURRENCES) | TGT_SEDA_S_SCM.RETURN_CORR_VW_OCCURRENCES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TMP_CELLO_UNION_PO_DO_SKU_STATUS) | TGT_SEDA_S_SCM.TMP_CELLO_UNION_PO_DO_SKU_STATUS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO), (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TMP_TEST_LIST_REGEX) | TGT_SEDA_S_SCM.TMP_TEST_LIST_REGEX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(SYNONYM - PUBLIC.DUMMY), (TABLE - SYS.DUMMY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TMP_YAMI_JOIN_VTEX_CELLO) | TGT_SEDA_S_SCM.TMP_YAMI_JOIN_VTEX_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO), (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TRACKING_ITT_VW_SHIPPING_ESTIMATE_DATE) | TGT_SEDA_S_SCM.TRACKING_ITT_VW_SHIPPING_ESTIMATE_DATE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TRACKING_VW_ITT_CALENDAR) | TGT_SEDA_S_SCM.TRACKING_VW_ITT_CALENDAR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TRACKING_VW_ITT_DASH) | TGT_SEDA_S_SCM.TRACKING_VW_ITT_DASH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TRACKING_VW_ITT_DATABASE_2023H1) | TGT_SEDA_S_SCM.TRACKING_VW_ITT_DATABASE_2023H1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TRACKING_VW_ITT_DATABASE_2023H2) | TGT_SEDA_S_SCM.TRACKING_VW_ITT_DATABASE_2023H2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TRACKING_VW_ITT_DATABASE_2024Q1) | TGT_SEDA_S_SCM.TRACKING_VW_ITT_DATABASE_2024Q1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TRACKING_VW_ITT_DATABASE_D180) | TGT_SEDA_S_SCM.TRACKING_VW_ITT_DATABASE_D180 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TRACKING_VW_ITT_FP) | TGT_SEDA_S_SCM.TRACKING_VW_ITT_FP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TRACKING_VW_ITT_HIST) | TGT_SEDA_S_SCM.TRACKING_VW_ITT_HIST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.TRACKING_VW_ITT_HIST_DATA) | TGT_SEDA_S_SCM.TRACKING_VW_ITT_HIST_DATA | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VIEW_B2C_ALERT_CALENDAR) | TGT_SEDA_S_SCM.VIEW_B2C_ALERT_CALENDAR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_AR_CLEARED) | TGT_SEDA_S_SCM.VW_AR_CLEARED | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_AR_FBL5N_ANALYSIS) | TGT_SEDA_S_SCM.VW_AR_FBL5N_ANALYSIS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_AR_KPI) | TGT_SEDA_S_SCM.VW_AR_KPI | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_AR_KPI_CLEARED) | TGT_SEDA_S_SCM.VW_AR_KPI_CLEARED | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_AR_KPI_NEW) | TGT_SEDA_S_SCM.VW_AR_KPI_NEW | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_AR_OPEN) | TGT_SEDA_S_SCM.VW_AR_OPEN | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_AR_OPEN_KPI) | TGT_SEDA_S_SCM.VW_AR_OPEN_KPI | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_B2B_CELLO_MANIFEST_DATA) | TGT_SEDA_S_SCM.VW_B2B_CELLO_MANIFEST_DATA | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_B2B_FOB_INCOTERMS) | TGT_SEDA_S_SCM.VW_B2B_FOB_INCOTERMS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_B2C_ALERTS_OVERDUE_BOOKING) | TGT_SEDA_S_SCM.VW_B2C_ALERTS_OVERDUE_BOOKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (SYNONYM - PUBLIC.DUMMY), (TABLE - SYS.DUMMY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_B2C_ALERTS_OVERDUE_BOOKING_V0) | TGT_SEDA_S_SCM.VW_B2C_ALERTS_OVERDUE_BOOKING_V0 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (SYNONYM - PUBLIC.DUMMY), (TABLE - SYS.DUMMY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_B2C_ALERTS_PENDING_BOOKING) | TGT_SEDA_S_SCM.VW_B2C_ALERTS_PENDING_BOOKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_B2C_ALERTS_PENDING_BOOKING_V0) | TGT_SEDA_S_SCM.VW_B2C_ALERTS_PENDING_BOOKING_V0 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_B2C_ALERTS_PENDING_BOOKING_V1) | TGT_SEDA_S_SCM.VW_B2C_ALERTS_PENDING_BOOKING_V1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_B2C_ALERT_IOD_RISK) | TGT_SEDA_S_SCM.VW_B2C_ALERT_IOD_RISK | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_B2C_SCM_GI_DATABASE) | TGT_SEDA_S_SCM.VW_B2C_SCM_GI_DATABASE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CELLO_RETURN_TRACKING) | TGT_SEDA_S_SCM.VW_CELLO_RETURN_TRACKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CELLO_TRACKING_EVENT) | TGT_SEDA_S_SCM.VW_CELLO_TRACKING_EVENT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CELLO_TRACKING_EVENT_V2) | TGT_SEDA_S_SCM.VW_CELLO_TRACKING_EVENT_V2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_AR_OPEN_SEMANAL) | TGT_SEDA_S_SCM.VW_CT2_AR_OPEN_SEMANAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_AR_OVERDUE_ANALYSIS) | TGT_SEDA_S_SCM.VW_CT2_AR_OVERDUE_ANALYSIS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_AR_PREP_SEMANAL) | TGT_SEDA_S_SCM.VW_CT2_AR_PREP_SEMANAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_AR_UNION_SEMANAL) | TGT_SEDA_S_SCM.VW_CT2_AR_UNION_SEMANAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_CELLO) | TGT_SEDA_S_SCM.VW_CT2_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_CELLO_AR) | TGT_SEDA_S_SCM.VW_CT2_CELLO_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_CELLO_DELIVERY_AR) | TGT_SEDA_S_SCM.VW_CT2_CELLO_DELIVERY_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_CELLO_V2) | TGT_SEDA_S_SCM.VW_CT2_CELLO_V2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_FEED) | TGT_SEDA_S_SCM.VW_CT2_FEED | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_SHIPMENTS), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_NERP_090) | TGT_SEDA_S_SCM.VW_CT2_NERP_090 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_NERP_120) | TGT_SEDA_S_SCM.VW_CT2_NERP_120 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_PLUGG) | TGT_SEDA_S_SCM.VW_CT2_PLUGG | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_SHIPMENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_PLUGG_T) | TGT_SEDA_S_SCM.VW_CT2_PLUGG_T | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_SHIPMENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_SEARCH) | TGT_SEDA_S_SCM.VW_CT2_SEARCH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_SEARCH_AR) | TGT_SEDA_S_SCM.VW_CT2_SEARCH_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT2_VTEX) | TGT_SEDA_S_SCM.VW_CT2_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_BALANCE) | TGT_SEDA_S_SCM.VW_CT_AR_BALANCE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_BALANCE_REAL_TIME) | TGT_SEDA_S_SCM.VW_CT_AR_BALANCE_REAL_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_ENTRIES) | TGT_SEDA_S_SCM.VW_CT_AR_ENTRIES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_ENTRIES_EST) | TGT_SEDA_S_SCM.VW_CT_AR_ENTRIES_EST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_ENTRIES_MKP) | TGT_SEDA_S_SCM.VW_CT_AR_ENTRIES_MKP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_ENTRIES_REAL_TIME) | TGT_SEDA_S_SCM.VW_CT_AR_ENTRIES_REAL_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_MAPPING) | TGT_SEDA_S_SCM.VW_CT_AR_MAPPING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_MAPPING_REAL_TIME) | TGT_SEDA_S_SCM.VW_CT_AR_MAPPING_REAL_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_OPEN) | TGT_SEDA_S_SCM.VW_CT_AR_OPEN | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_OPEN_REAL_TIME) | TGT_SEDA_S_SCM.VW_CT_AR_OPEN_REAL_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_OPEN_SEMANAL) | TGT_SEDA_S_SCM.VW_CT_AR_OPEN_SEMANAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_PREP) | TGT_SEDA_S_SCM.VW_CT_AR_PREP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_PREP_REAL_TIME) | TGT_SEDA_S_SCM.VW_CT_AR_PREP_REAL_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_PREP_SEMANAL) | TGT_SEDA_S_SCM.VW_CT_AR_PREP_SEMANAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_UNION) | TGT_SEDA_S_SCM.VW_CT_AR_UNION | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_UNION_REAL_TIME) | TGT_SEDA_S_SCM.VW_CT_AR_UNION_REAL_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_AR_UNION_SEMANAL) | TGT_SEDA_S_SCM.VW_CT_AR_UNION_SEMANAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CANCELED_WITH_IOD) | TGT_SEDA_S_SCM.VW_CT_CANCELED_WITH_IOD | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO) | TGT_SEDA_S_SCM.VW_CT_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_COUNT) | TGT_SEDA_S_SCM.VW_CT_CELLO_COUNT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_DELIVERY) | TGT_SEDA_S_SCM.VW_CT_CELLO_DELIVERY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_DELIVERY_NO_RDO) | TGT_SEDA_S_SCM.VW_CT_CELLO_DELIVERY_NO_RDO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_DELIVERY_NO_RDO_DEV) | TGT_SEDA_S_SCM.VW_CT_CELLO_DELIVERY_NO_RDO_DEV | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_DELIVERY_NO_RDO_V2) | TGT_SEDA_S_SCM.VW_CT_CELLO_DELIVERY_NO_RDO_V2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_DELIVERY_OST_D2C_AR) | TGT_SEDA_S_SCM.VW_CT_CELLO_DELIVERY_OST_D2C_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_FUTHER_PROCESSING) | TGT_SEDA_S_SCM.VW_CT_CELLO_FUTHER_PROCESSING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_INCR) | TGT_SEDA_S_SCM.VW_CT_CELLO_INCR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL) | TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_INCR) | TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_INCR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_OST_D2C_AR) | TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_OST_D2C_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (VIEW - OW_SEDA_S.VW_STATUS_MAPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_PRE1) | TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_PRE1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_PRE1_INCR) | TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_PRE1_INCR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (VIEW - OW_SEDA_S.VW_STATUS_MAPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_PRE2) | TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_PRE2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_PRE2_INCR) | TGT_SEDA_S_SCM.VW_CT_CELLO_IOD_TOTAL_PRE2_INCR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_NEW) | TGT_SEDA_S_SCM.VW_CT_CELLO_NEW | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_OST_D2C_AR) | TGT_SEDA_S_SCM.VW_CT_CELLO_OST_D2C_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_RETURN) | TGT_SEDA_S_SCM.VW_CT_CELLO_RETURN | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_RETURN_OST_D2C_AR) | TGT_SEDA_S_SCM.VW_CT_CELLO_RETURN_OST_D2C_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_TRACKING), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_RETURN_SHIPCOND) | TGT_SEDA_S_SCM.VW_CT_CELLO_RETURN_SHIPCOND | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_RETURN_TRACKING) | TGT_SEDA_S_SCM.VW_CT_CELLO_RETURN_TRACKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_RETURN_TRACKING_OST_D2C_AR) | TGT_SEDA_S_SCM.VW_CT_CELLO_RETURN_TRACKING_OST_D2C_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_CELLO_TRACKING) | TGT_SEDA_S_SCM.VW_CT_CELLO_TRACKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_D2C_PLUGG_CANCEL) | TGT_SEDA_S_SCM.VW_CT_D2C_PLUGG_CANCEL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_D2C_PLUGG_STATUS) | TGT_SEDA_S_SCM.VW_CT_D2C_PLUGG_STATUS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_D2C_PLUGG_STATUS_ALL) | TGT_SEDA_S_SCM.VW_CT_D2C_PLUGG_STATUS_ALL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_DATA_MART) | TGT_SEDA_S_SCM.VW_CT_DATA_MART | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_DM_CS_RETURN) | TGT_SEDA_S_SCM.VW_CT_DM_CS_RETURN | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_DM_CS_RETURN_PAINEL_GERAL) | TGT_SEDA_S_SCM.VW_CT_DM_CS_RETURN_PAINEL_GERAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRSHOP), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_DM_OST_D2C_AR_OVERDUE_ANALYSIS_REAL_TIME) | TGT_SEDA_S_SCM.VW_CT_DM_OST_D2C_AR_OVERDUE_ANALYSIS_REAL_TIME | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_DM_OST_D2C_AR__OVERDUE_ANALYSIS) | TGT_SEDA_S_SCM.VW_CT_DM_OST_D2C_AR__OVERDUE_ANALYSIS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_MARKETPLACE) | TGT_SEDA_S_SCM.VW_CT_MARKETPLACE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.ODS_MKP_D2C_LEROY), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_MARKETPLACE_ORDER) | TGT_SEDA_S_SCM.VW_CT_MARKETPLACE_ORDER | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.ODS_MKP_D2C_LEROY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_MARKETPLACE_ORDER_2) | TGT_SEDA_S_SCM.VW_CT_MARKETPLACE_ORDER_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.ODS_MKP_D2C_LEROY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_PLUGG) | TGT_SEDA_S_SCM.VW_CT_PLUGG | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SALES_FORCE) | TGT_SEDA_S_SCM.VW_CT_SALES_FORCE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH) | TGT_SEDA_S_SCM.VW_CT_SEARCH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_1) | TGT_SEDA_S_SCM.VW_CT_SEARCH_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_2) | TGT_SEDA_S_SCM.VW_CT_SEARCH_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_2_RETURN_OST_D2C_AR) | TGT_SEDA_S_SCM.VW_CT_SEARCH_2_RETURN_OST_D2C_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_3) | TGT_SEDA_S_SCM.VW_CT_SEARCH_3 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_3_RETURN_OST_D2C_AR) | TGT_SEDA_S_SCM.VW_CT_SEARCH_3_RETURN_OST_D2C_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_4) | TGT_SEDA_S_SCM.VW_CT_SEARCH_4 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_DESENV) | TGT_SEDA_S_SCM.VW_CT_SEARCH_DESENV | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_DEV) | TGT_SEDA_S_SCM.VW_CT_SEARCH_DEV | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_EXCLUDED_DO), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (VIEW - OW_SEDA_S.VW_STATUS_MAPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_NEW_1) | TGT_SEDA_S_SCM.VW_CT_SEARCH_NEW_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_NEW_2) | TGT_SEDA_S_SCM.VW_CT_SEARCH_NEW_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_SEARCH_OST_D2C_AR_OVERDUE_ANALYSIS) | TGT_SEDA_S_SCM.VW_CT_SEARCH_OST_D2C_AR_OVERDUE_ANALYSIS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRSHOP), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (VIEW - OW_SEDA_S.VW_STATUS_MAPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO) | TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO_INCR) | TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO_INCR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO_OST_D2C_AR) | TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO_OST_D2C_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (VIEW - OW_SEDA_S.VW_STATUS_MAPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO_PHOTO) | TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO_PHOTO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO_PHOTO_INCR) | TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO_PHOTO_INCR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO_PHOTO_OST_D2C_AR) | TGT_SEDA_S_SCM.VW_CT_UNION_TSS_CELLO_PHOTO_OST_D2C_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (VIEW - OW_SEDA_S.VW_STATUS_MAPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX) | TGT_SEDA_S_SCM.VW_CT_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_BR) | TGT_SEDA_S_SCM.VW_CT_VTEX_BR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_BRIDGE) | TGT_SEDA_S_SCM.VW_CT_VTEX_BRIDGE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_BRIDGE_STATUS) | TGT_SEDA_S_SCM.VW_CT_VTEX_BRIDGE_STATUS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_COUNT) | TGT_SEDA_S_SCM.VW_CT_VTEX_COUNT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_EPP2) | TGT_SEDA_S_SCM.VW_CT_VTEX_EPP2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_INCR) | TGT_SEDA_S_SCM.VW_CT_VTEX_INCR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_MAX_WAREHOUSE_ID_SALES_ORDER_SHIPPING) | TGT_SEDA_S_SCM.VW_CT_VTEX_MAX_WAREHOUSE_ID_SALES_ORDER_SHIPPING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_OST_D2C_AR) | TGT_SEDA_S_SCM.VW_CT_VTEX_OST_D2C_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_SEARCH) | TGT_SEDA_S_SCM.VW_CT_VTEX_SEARCH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_SHOP) | TGT_SEDA_S_SCM.VW_CT_VTEX_SHOP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | TGT_SEDA_S_SCM.VW_CT_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_XL_IOD) | TGT_SEDA_S_SCM.VW_CT_XL_IOD | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_XL_MELI_ORDERS) | TGT_SEDA_S_SCM.VW_CT_XL_MELI_ORDERS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_XL_OST_SEARCH) | TGT_SEDA_S_SCM.VW_CT_XL_OST_SEARCH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_SHIPMENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_XL_SEARCH) | TGT_SEDA_S_SCM.VW_CT_XL_SEARCH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_XL_SSG_CARE_PLUS) | TGT_SEDA_S_SCM.VW_CT_XL_SSG_CARE_PLUS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_XL_VTEX) | TGT_SEDA_S_SCM.VW_CT_XL_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_XL_VTEX_ALL) | TGT_SEDA_S_SCM.VW_CT_XL_VTEX_ALL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_CT_YAMI) | TGT_SEDA_S_SCM.VW_CT_YAMI | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRSHOP)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_ABNORMAL_REPORT) | TGT_SEDA_S_SCM.VW_D2C_ABNORMAL_REPORT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRSHOP), (TABLE - OW_SEDA_S.RAW_DATA_SNOWFLAKE_CS_SALES_FORCE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_ABNORMAL_RETURN) | TGT_SEDA_S_SCM.VW_D2C_ABNORMAL_RETURN | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRSHOP)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_ABNORMAL_YAMI_RETURN) | TGT_SEDA_S_SCM.VW_D2C_ABNORMAL_YAMI_RETURN | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRSHOP)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_ABNORMAL_YAMI_RETURN_V0) | TGT_SEDA_S_SCM.VW_D2C_ABNORMAL_YAMI_RETURN_V0 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRSHOP)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_CANCEL_IOD_HIST) | TGT_SEDA_S_SCM.VW_D2C_CANCEL_IOD_HIST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_CANCEL_IOD_LOG) | TGT_SEDA_S_SCM.VW_D2C_CANCEL_IOD_LOG | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_FPC_REGION_RANK_AUXILIAR) | TGT_SEDA_S_SCM.VW_D2C_FPC_REGION_RANK_AUXILIAR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_GI_MONITORING_FOR_BF) | TGT_SEDA_S_SCM.VW_D2C_GI_MONITORING_FOR_BF | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOGCOST_HIGHEST_CWGT_CATEGORY) | TGT_SEDA_S_SCM.VW_D2C_LOGCOST_HIGHEST_CWGT_CATEGORY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOGCOST_MGTM_SUBCARRIER_CELLO) | TGT_SEDA_S_SCM.VW_D2C_LOGCOST_MGTM_SUBCARRIER_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOGCOST_SOUTH_CARRIER_ALLOCATION_ANALYSIS) | TGT_SEDA_S_SCM.VW_D2C_LOGCOST_SOUTH_CARRIER_ALLOCATION_ANALYSIS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOGCOST_SUBCARRIER_CELLO) | TGT_SEDA_S_SCM.VW_D2C_LOGCOST_SUBCARRIER_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOGCOST_VIZ_DASH) | TGT_SEDA_S_SCM.VW_D2C_LOGCOST_VIZ_DASH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOGCOST_VIZ_PRIMARY_WH) | TGT_SEDA_S_SCM.VW_D2C_LOGCOST_VIZ_PRIMARY_WH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOGCOST_VIZ_SECONDARY_WH) | TGT_SEDA_S_SCM.VW_D2C_LOGCOST_VIZ_SECONDARY_WH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOG_NEW_BID_FPC_RANKING) | TGT_SEDA_S_SCM.VW_D2C_LOG_NEW_BID_FPC_RANKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOG_NEW_BID_FPC_RANKING_BACKUP) | TGT_SEDA_S_SCM.VW_D2C_LOG_NEW_BID_FPC_RANKING_BACKUP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOG_NEW_BID_FPC_REGION_WGT_RANK) | TGT_SEDA_S_SCM.VW_D2C_LOG_NEW_BID_FPC_REGION_WGT_RANK | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_LOG_SIMULATION_NEW_FPC) | TGT_SEDA_S_SCM.VW_D2C_LOG_SIMULATION_NEW_FPC | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_MKP_MONITORING_ISS) | TGT_SEDA_S_SCM.VW_D2C_MKP_MONITORING_ISS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_NEW_BID_FPC_GROUPED_RANKING) | TGT_SEDA_S_SCM.VW_D2C_NEW_BID_FPC_GROUPED_RANKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_NEW_BID_FPC_GROUPED_RANKING_VTEX) | TGT_SEDA_S_SCM.VW_D2C_NEW_BID_FPC_GROUPED_RANKING_VTEX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_VTEX_CANCEL_REASONS) | TGT_SEDA_S_SCM.VW_D2C_VTEX_CANCEL_REASONS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_D2C_WH_PGI_CONTROL_REPORT) | TGT_SEDA_S_SCM.VW_D2C_WH_PGI_CONTROL_REPORT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_MD.DIM_CALENDAR), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZSE16_DELETED_DO)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_DM_B2B_LOGCOST_MANAGEMENT_ALL) | TGT_SEDA_S_SCM.VW_DM_B2B_LOGCOST_MANAGEMENT_ALL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_DM_D2C_LOGCOST_MANAGEMENT) | TGT_SEDA_S_SCM.VW_DM_D2C_LOGCOST_MANAGEMENT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_DM_D2C_LOGCOST_MANAGEMENT_ALL) | TGT_SEDA_S_SCM.VW_DM_D2C_LOGCOST_MANAGEMENT_ALL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_DM_D2C_LOGCOST_MANAGEMENT_MX) | TGT_SEDA_S_SCM.VW_DM_D2C_LOGCOST_MANAGEMENT_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_DM_D2C_LOGCOST_VISIBILITY) | TGT_SEDA_S_SCM.VW_DM_D2C_LOGCOST_VISIBILITY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_FT_BI_CELLO_IOD_TOTAL) | TGT_SEDA_S_SCM.VW_FT_BI_CELLO_IOD_TOTAL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_FT_UNION_TSS_CELLO) | TGT_SEDA_S_SCM.VW_FT_UNION_TSS_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_EXCLUDED_DO)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_INTERFACE_UPDATES) | TGT_SEDA_S_SCM.VW_INTERFACE_UPDATES | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_MONTHLY), (TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_WEEKLY), (TABLE - OW_SEDA_S.ODS_GSCM_FCST_MGMT_AP1), (TABLE - OW_SEDA_S.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA), (TABLE - OW_SEDA_S.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO), (TABLE - OW_SEDA_S.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A080_SALES_ORDER_LIST), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRSHOP), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRSHOP), (TABLE - OW_SEDA_S.RAW_DATA_SNOWFLAKE_CS_SALES_FORCE), (SYNONYM - PUBLIC.DUMMY), (TABLE - SYS.DUMMY), (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_CARREFOUR), (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_LEROY), (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_MAGALU), (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_MELI), (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_VIA), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_EPP2), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_LOGISTICS_OUTBOUND_TRACKING) | TGT_SEDA_S_SCM.VW_LOGISTICS_OUTBOUND_TRACKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_LOG_RETURN_MISSING_RDO_MKP_20230502) | TGT_SEDA_S_SCM.VW_LOG_RETURN_MISSING_RDO_MKP_20230502 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_MARKETPLACE_CANCELED_WITH_IOD) | TGT_SEDA_S_SCM.VW_MARKETPLACE_CANCELED_WITH_IOD | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_MARKETPLACE_COMPARISON_CANCELED) | TGT_SEDA_S_SCM.VW_MARKETPLACE_COMPARISON_CANCELED | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_MARKETPLACE_COMPARISON_CANCELED_GI_DT) | TGT_SEDA_S_SCM.VW_MARKETPLACE_COMPARISON_CANCELED_GI_DT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_MARKETPLACE_COMPARISON_CANCELED_V1) | TGT_SEDA_S_SCM.VW_MARKETPLACE_COMPARISON_CANCELED_V1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_MARKETPLACE_COMPARISON_IOD) | TGT_SEDA_S_SCM.VW_MARKETPLACE_COMPARISON_IOD | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_MARKETPLACE_OPEN_PENDING) | TGT_SEDA_S_SCM.VW_MARKETPLACE_OPEN_PENDING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_MARKETPLACE_VTEX_CELLO) | TGT_SEDA_S_SCM.VW_MARKETPLACE_VTEX_CELLO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_OST_BRIDGE) | TGT_SEDA_S_SCM.VW_OST_BRIDGE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_OST_PO_NO_MELI) | TGT_SEDA_S_SCM.VW_OST_PO_NO_MELI | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_OUTBOUND_HANA_EXPORT) | TGT_SEDA_S_SCM.VW_OUTBOUND_HANA_EXPORT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_OUTBOUND_HANA_EXPORT_OLD) | TGT_SEDA_S_SCM.VW_OUTBOUND_HANA_EXPORT_OLD | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_PLUGG_UNION) | TGT_SEDA_S_SCM.VW_PLUGG_UNION | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_SALES_ORDER_OUTPUT) | TGT_SEDA_S_SCM.VW_SALES_ORDER_OUTPUT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_SCM_TRIGGER_IOD_RISK) | TGT_SEDA_S_SCM.VW_SCM_TRIGGER_IOD_RISK | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_SCM_TRIGGER_PENDING_BOOKING) | TGT_SEDA_S_SCM.VW_SCM_TRIGGER_PENDING_BOOKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_SCM_TRIGGER_REBOOKING) | TGT_SEDA_S_SCM.VW_SCM_TRIGGER_REBOOKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (SYNONYM - PUBLIC.DUMMY), (TABLE - SYS.DUMMY)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_STATUS_MAPPING_SCM) | TGT_SEDA_S_SCM.VW_STATUS_MAPPING_SCM | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_TMP_CELLO_RETURN_TRACKING) | TGT_SEDA_S_SCM.VW_TMP_CELLO_RETURN_TRACKING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_VTEX_ORDER_PAY) | TGT_SEDA_S_SCM.VW_VTEX_ORDER_PAY | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_WH_MONTHLY_CAPA) | TGT_SEDA_S_SCM.VW_WH_MONTHLY_CAPA | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_MD.DIM_CALENDAR)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_XL_VTEX_ITEM_PROMO) | TGT_SEDA_S_SCM.VW_XL_VTEX_ITEM_PROMO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_XL_VTEX_PAYMENT) | TGT_SEDA_S_SCM.VW_XL_VTEX_PAYMENT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]
|  | VIEW | (VIEW - TGT_SEDA_S_SCM.VW_XL_VTEX_PROMO) | TGT_SEDA_S_SCM.VW_XL_VTEX_PROMO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.DROPTBIFEX) | TGT_SEDA_S_SCM.DROPTBIFEX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT2_UPDATE) | TGT_SEDA_S_SCM.PRC_CT2_UPDATE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT2_UPDATE_OVERDUE_ANALYSIS) | TGT_SEDA_S_SCM.PRC_CT2_UPDATE_OVERDUE_ANALYSIS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_CELLO_OCC) | TGT_SEDA_S_SCM.PRC_CT_CELLO_OCC | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_TRACKING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_DATA_MART_UPDATE) | TGT_SEDA_S_SCM.PRC_CT_DATA_MART_UPDATE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRSHOP), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_DM_OST_UPDATE_OVERDUE_ANALYSIS) | TGT_SEDA_S_SCM.PRC_CT_DM_OST_UPDATE_OVERDUE_ANALYSIS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE) | TGT_SEDA_S_SCM.PRC_CT_UPDATE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRSHOP), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_AR) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_AR | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_DEV_LUIZ) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_DEV_LUIZ | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_0) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_0 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_POD), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_1) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_1_2) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_1_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_1_3) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_1_3 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_1_4) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_1_4 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_2) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRSHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_1) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_1 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_2) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_3) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_3 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_4) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_4 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_5) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_5 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_6) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_6 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_7) | TGT_SEDA_S_SCM.PRC_CT_UPDATE_PARTE_3_7 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_D2C_COST_MGTM) | TGT_SEDA_S_SCM.PRC_D2C_COST_MGTM | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_D2C_COST_MGTM_MX) | TGT_SEDA_S_SCM.PRC_D2C_COST_MGTM_MX | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_FUNCTION_TEST) | TGT_SEDA_S_SCM.PRC_FUNCTION_TEST | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(SYNONYM - PUBLIC.DUMMY), (TABLE - SYS.DUMMY)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_IOD_RISK_ALERT) | TGT_SEDA_S_SCM.PRC_IOD_RISK_ALERT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_LOGCOST_DATA_VIZ) | TGT_SEDA_S_SCM.PRC_LOGCOST_DATA_VIZ | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_LOOP_DEV) | TGT_SEDA_S_SCM.PRC_LOOP_DEV | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_PREDIZE_UPDATE) | TGT_SEDA_S_SCM.PRC_PREDIZE_UPDATE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER), (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_SHIPMENTS), (TABLE - U_PRJ_ECOM.ODS_PREDIZE_TICKET_ORDER), (TABLE - U_PRJ_ECOM.ODS_PREDIZE_TICKETS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_SCMLOG_UPDATE) | TGT_SEDA_S_SCM.PRC_SCMLOG_UPDATE | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(PROCEDURE - CON_SEDA_S_SCM.PRC_D2CLOG_DO_PROJECTION_LT), (VIEW - CON_SEDA_S_SCM.VW_WH_CARRIER_CAPA_MONITOR_V2), (TABLE - OW_MD.DIM_CALENDAR), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_TRACKING_ITT_THRESHOLD_STATS_V2) | TGT_SEDA_S_SCM.PRC_TRACKING_ITT_THRESHOLD_STATS_V2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_TRACKING_ITT_THRESHOLD_STATS_V2_VALIDACAO) | TGT_SEDA_S_SCM.PRC_TRACKING_ITT_THRESHOLD_STATS_V2_VALIDACAO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_TRACKING_PANEL) | TGT_SEDA_S_SCM.PRC_TRACKING_PANEL | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_TRACKING_PILOTO) | TGT_SEDA_S_SCM.PRC_TRACKING_PILOTO | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PRC_WH) | TGT_SEDA_S_SCM.PRC_WH | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PROC_CTM_REPORT) | TGT_SEDA_S_SCM.PROC_CTM_REPORT | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING), (TABLE - U_PRJ_ECOM.DIM_ECOM_CHANNEL), (TABLE - U_PRJ_ECOM.DIM_PRODUCT_CATEGORY_SEDA), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_KIT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.PROC_INTERFACE_UPDATE2) | TGT_SEDA_S_SCM.PROC_INTERFACE_UPDATE2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_MONTHLY), (TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_WEEKLY), (TABLE - OW_SEDA_S.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA), (TABLE - OW_SEDA_S.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO), (TABLE - OW_SEDA_S.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A080_SALES_ORDER_LIST), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_PRODUCT_DETAIL_SAMSUNGBREPP2), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBR), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBRB2B), (TABLE - OW_SEDA_S.ODS_YAMI_RETURN_LIST_SAMSUNGBREPP2), (SYNONYM - PUBLIC.DUMMY), (TABLE - SYS.DUMMY), (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_CARREFOUR), (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_LEROY), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.RETURN_CORR_PRC) | TGT_SEDA_S_SCM.RETURN_CORR_PRC | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND), (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.SAVE_PROCEDURE_METADATA) | TGT_SEDA_S_SCM.SAVE_PROCEDURE_METADATA | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(SYNONYM - PUBLIC.PROCEDURES), (TABLE - SYS.DUMMY), (VIEW - SYS.PROCEDURE_PARAMETER_COLUMNS), (VIEW - SYS.PROCEDURE_PARAMETERS), (VIEW - SYS.PROCEDURES)]
|  | FUNCTION | (FUNCTION - TGT_SEDA_S_SCM.SPLIT_STRING) | TGT_SEDA_S_SCM.SPLIT_STRING | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(SYNONYM - PUBLIC.DUMMY), (TABLE - SYS.DUMMY)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.TMP_PRC_SEARCH_400) | TGT_SEDA_S_SCM.TMP_PRC_SEARCH_400 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING), (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.TMP_PRC_TEST_LOOP) | TGT_SEDA_S_SCM.TMP_PRC_TEST_LOOP | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.TMP_PRC_TEST_LOOP_2) | TGT_SEDA_S_SCM.TMP_PRC_TEST_LOOP_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.TRACKING_PRC_ITT_THRESHOLD_STATS) | TGT_SEDA_S_SCM.TRACKING_PRC_ITT_THRESHOLD_STATS | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | PROCEDURE | (PROCEDURE - TGT_SEDA_S_SCM.TRACKING_PRC_ITT_THRESHOLD_STATS_2) | TGT_SEDA_S_SCM.TRACKING_PRC_ITT_THRESHOLD_STATS_2 | SEDA-S - Logistics | gabriel.mp |  |  |  | Not to be migrated | [9 empty] | Migrar ph2: end |  |  |  | [(TABLE - OW_SEDA_S.CELLO_BOOKING), (TABLE - OW_SEDA_S.CELLO_DELIVERY), (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM), (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING), (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST), (TABLE - OW_SEDA_S.CELLO_MANIFEST), (TABLE - OW_SEDA_S.CELLO_SHIPMENT), (TABLE - OW_SEDA_S.CELLO_TRACKING), (TABLE - OW_SEDA_S.CELLO_VESSEL), (TABLE - OW_SEDA_S.M_CODE_CELLO), (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM), (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION), (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS), (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT), (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT), (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE), (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]
|  | CALCULATION VIEW | (CALCULATION VIEW - sap.hrf.content.model.TIME_ZONE_VIEW) | sap.hrf.content.model.TIME_ZONE_VIEW |  | SYSTEM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - sap.hrf.resources.rule.model.RULES_PER_VOCAB_AND_OUTPUT) | sap.hrf.resources.rule.model.RULES_PER_VOCAB_AND_OUTPUT |  | SYSTEM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - sap.hrf.resources.rule.model.RULE_SERVICE_PER_VOCAB_AND_OUTPUT) | sap.hrf.resources.rule.model.RULE_SERVICE_PER_VOCAB_AND_OUTPUT |  | SYSTEM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_TEST_PARAMETER) | cdm.CV_TEST_PARAMETER |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_STATUS_GCIC_STG) | cdm.CV_STATUS_GCIC_STG |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_CUSTOMER_NO_INT_REC) | cdm.CV_CUSTOMER_NO_INT_REC |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_CUSTOMER_NO_INT) | cdm.CV_CUSTOMER_NO_INT |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_CAMPAIGNS_BY_CONTACT_SUBQ_V2) | cdm.CV_CAMPAIGNS_BY_CONTACT_SUBQ_V2 |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_CAMPAIGNS_BY_CONTACT_SUBQ) | cdm.CV_CAMPAIGNS_BY_CONTACT_SUBQ |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_OCCURRENCE_REPORT) | TSS.CV_TSS_IOD_OCCURRENCE_REPORT |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_STATUS_BK_CONF_NO_GI) | TSS.CV_TSS_IOD_STATUS_BK_CONF_NO_GI |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_STATUS_BK_PEND) | TSS.CV_TSS_IOD_STATUS_BK_PEND |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_STATUS_RBK_REQ_PEND) | TSS.CV_TSS_IOD_STATUS_RBK_REQ_PEND |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_CT_OPENS_CLICKS) | cdm.CV_CT_OPENS_CLICKS |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_CUSTOMER_RESPONSE) | cdm.CV_CUSTOMER_RESPONSE |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_TRACKING_ITEM) | TSS.CV_TSS_IOD_TRACKING_ITEM |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_PROD_RET) | cdm.CV_PROD_RET |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_TMP_IOD_STATUS_LIMPA) | LIMPEZA_BI_TRACKING.CV_TMP_IOD_STATUS_LIMPA |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_TMP_BI_TRACKING_LIMPA) | LIMPEZA_BI_TRACKING.CV_TMP_BI_TRACKING_LIMPA |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_TMP_IOD_STATUS_CLEAN) | LIMPEZA_BI_TRACKING.CV_TMP_IOD_STATUS_CLEAN |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_IOD_STATUS_CLEAN) | LIMPEZA_BI_TRACKING.CV_IOD_STATUS_CLEAN |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_TMP_BI_TRACKING_HIST_LIMPA) | LIMPEZA_BI_TRACKING.CV_TMP_BI_TRACKING_HIST_LIMPA |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST) | DLAKE_DMS.DMS_FCST |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_IOD_STATUS_CLEAN) | LIMPEZA_BI_TRACKING.CV_BI_IOD_STATUS_CLEAN |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_HIST) | DLAKE_DMS.DMS_HIST |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_W1) | DLAKE_DMS.DMS_FCST_W1 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_W2) | DLAKE_DMS.DMS_FCST_W2 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_W3) | DLAKE_DMS.DMS_FCST_W3 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_W4) | DLAKE_DMS.DMS_FCST_W4 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_W5) | DLAKE_DMS.DMS_FCST_W5 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_W6) | DLAKE_DMS.DMS_FCST_W6 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_W7) | DLAKE_DMS.DMS_FCST_W7 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_W8) | DLAKE_DMS.DMS_FCST_W8 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_W0) | DLAKE_DMS.DMS_FCST_W0 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_IOD_STATUS_CLEAN_2) | LIMPEZA_BI_TRACKING.CV_BI_IOD_STATUS_CLEAN_2 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_IOD_UNION) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_IOD_UNION |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_HIST_CLEAN) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_HIST_CLEAN |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_DELIVERIES_N_CT) | cdm.CV_DELIVERIES_N_CT |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_DELIVERIES_RESULT) | cdm.CV_DELIVERIES_RESULT |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_CONTACT_INFO_SUBQ) | cdm.CV_CONTACT_INFO_SUBQ |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_PUSH_RESULT) | cdm.CV_PUSH_RESULT |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_STATUS_GCIC) | cdm.CV_STATUS_GCIC |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_ORIGIN_COUNT) | cdm.CV_ORIGIN_COUNT |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_CK_NO_INTERACTION) | cdm.CV_CK_NO_INTERACTION |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_HIST_UNION) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_HIST_UNION |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_LEADS_VS_EMAILS) | cdm.CV_LEADS_VS_EMAILS |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_LEADS_RESULTS) | cdm.CV_LEADS_RESULTS |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_LEADS) | cdm.CV_LEADS |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_CONTACT_INFO) | cdm.CV_CONTACT_INFO |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_CAMPAIGNS_BY_CONTACT) | cdm.CV_CAMPAIGNS_BY_CONTACT |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_LEADS_VS_EMAILS_SUBQ) | cdm.CV_LEADS_VS_EMAILS_SUBQ |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_UNION) | TSS.CV_TSS_IOD_UNION |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_CLEAN) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_CLEAN |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - cdm.CV_ORIGIN_OPTIN) | cdm.CV_ORIGIN_OPTIN |  | TEST_CDM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_STATUS_TOTAL) | TSS.CV_TSS_IOD_STATUS_TOTAL |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_RETURN_TRACKING) | TSS.CV_TSS_IOD_RETURN_TRACKING |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_VW_BI_CAPACITY_TRACKING_SDI) | TSS.CV_VW_BI_CAPACITY_TRACKING_SDI |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_VW_BI_CAPACITY_TRACKING) | TSS.CV_VW_BI_CAPACITY_TRACKING |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_IOD_STAUS_CLEAN) | LIMPEZA_BI_TRACKING.CV_BI_IOD_STAUS_CLEAN |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_STATUS_TOTAL_SDI) | TSS.CV_TSS_IOD_STATUS_TOTAL_SDI |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_UNION_SDI) | TSS.CV_TSS_IOD_UNION_SDI |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_SUM_TMP) | DLAKE_DMS.DMS_FCST_SUM_TMP |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - DLAKE_DMS.DMS_FCST_SUM) | DLAKE_DMS.DMS_FCST_SUM |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_VW_BI_IOD_STATUS_MONITORING) | TSS.CV_VW_BI_IOD_STATUS_MONITORING |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - CELLO.CV_CELLO_TRACKING_IOD) | CELLO.CV_CELLO_TRACKING_IOD |  | G_NUNES |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - CELLO.CV_UNION_CELLO_TSS_TRACKING) | CELLO.CV_UNION_CELLO_TSS_TRACKING |  | U_A_DUEK |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - CELLO.CV_UNION_CELLO_TSS) | CELLO.CV_UNION_CELLO_TSS |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - UPC_SERVICE.UPC_PARTS_RETURN) | UPC_SERVICE.UPC_PARTS_RETURN |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_HIST_CLEAN_SDI) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_HIST_CLEAN_SDI |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_CLEAN_SDI) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_CLEAN_SDI |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.COPY_CV_BI_TRACKING_HIST_CLEAN_SDI) | LIMPEZA_BI_TRACKING.COPY_CV_BI_TRACKING_HIST_CLEAN_SDI |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.COPY_CV_BI_TRACKING_CLEAN_SDI) | LIMPEZA_BI_TRACKING.COPY_CV_BI_TRACKING_CLEAN_SDI |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_BI_AIR_CAPACITY_TRACKING) | TSS.CV_BI_AIR_CAPACITY_TRACKING |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - CELLO.CV_UNION_CELLO_TSS_3MONTHS) | CELLO.CV_UNION_CELLO_TSS_3MONTHS |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - CELLO.CV_UNION_CELLO_TSS_HIST) | CELLO.CV_UNION_CELLO_TSS_HIST |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_TRACKING_INBOUND_TC_ORDERS) | TSS.CV_TSS_IOD_TRACKING_INBOUND_TC_ORDERS |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_TRACKING_INBOUND) | TSS.CV_TSS_IOD_TRACKING_INBOUND |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_SDI_IOD_OCCURRENCE_REPORT) | TSS.CV_TSS_SDI_IOD_OCCURRENCE_REPORT |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_TRACKING_INBOUND_OD_INBOUND) | TSS.CV_TSS_IOD_TRACKING_INBOUND_OD_INBOUND |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_RETURN_TRACKING_SDI) | TSS.CV_TSS_IOD_RETURN_TRACKING_SDI |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_SDI_IOD_OCCURRENCE_REPORT_V2) | TSS.CV_TSS_SDI_IOD_OCCURRENCE_REPORT_V2 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_DAILY_SALES) | SDSLA_ECOM.CV_ECOM_DAILY_SALES |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_CATALOG_SSG_VTEX_SYNAPCOM) | SDSLA_ECOM.CV_ECOM_CATALOG_SSG_VTEX_SYNAPCOM |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_SEDA_RAW_DATA) | SDSLA_ECOM.CV_ECOM_SEDA_RAW_DATA |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_MGLU_ORDERS_CUSTOMERS_PRODUCTS) | SDSLA_ECOM.CV_ECOM_MGLU_ORDERS_CUSTOMERS_PRODUCTS |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_CATALOG_SSG_VTEX) | SDSLA_ECOM.CV_ECOM_CATALOG_SSG_VTEX |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_SYNAPCOM_FULL) | SDSLA_ECOM.CV_ECOM_ORDERS_SYNAPCOM_FULL |  | U_MV_SILVA |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - TSS.CV_TSS_IOD_RETURN_TRACKING_SDI_2014_OF_2016) | TSS.CV_TSS_IOD_RETURN_TRACKING_SDI_2014_OF_2016 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PAYMENT) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PAYMENT |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_EPP) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_EPP |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_OLD) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_OLD |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EPP_DATA) | SDSLA_ECOM.CV_ECOM_EPP_DATA |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_TEST) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_TEST |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_V4_VALID) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_V4_VALID |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_HQ_INTEGRATION_OLD) | SDSLA_ECOM.CV_HQ_INTEGRATION_OLD |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_AGG) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_AGG |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_V1) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_V1 |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_DEV) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_DEV |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_VTEST) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_VTEST |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EXCHANGE_PROD) | SDSLA_ECOM.CV_ECOM_EXCHANGE_PROD |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EXCHANGE_PAN) | SDSLA_ECOM.CV_ECOM_EXCHANGE_PAN |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EXCHANGE_ARG) | SDSLA_ECOM.CV_ECOM_EXCHANGE_ARG |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_RAW_DATA) | SDSLA_ECOM.CV_ECOM_ORDERS_RAW_DATA |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EXCHANGE_COL) | SDSLA_ECOM.CV_ECOM_EXCHANGE_COL |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EXCHANGE_CHL) | SDSLA_ECOM.CV_ECOM_EXCHANGE_CHL |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EXCHANGE_MEX) | SDSLA_ECOM.CV_ECOM_EXCHANGE_MEX |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EXCHANGE_PER) | SDSLA_ECOM.CV_ECOM_EXCHANGE_PER |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EXCHANGE_PRY) | SDSLA_ECOM.CV_ECOM_EXCHANGE_PRY |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EXCHANGE_URY) | SDSLA_ECOM.CV_ECOM_EXCHANGE_URY |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_RULES) | SDSLA_ECOM.CV_ECOM_RULES |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_FT_ECOM_ORDER_ALL) | SDSLA_ECOM.CV_FT_ECOM_ORDER_ALL |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EXCHANGE_ARG_EPP) | SDSLA_ECOM.CV_ECOM_EXCHANGE_ARG_EPP |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_TEST) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_TEST |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_SITE_EPP) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_SITE_EPP |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_EPP_SITE_TEST) | SDSLA_ECOM.CV_ECOM_EPP_SITE_TEST |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_SITE2) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_SITE2 |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_V3) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_V3 |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_SITE) | SDSLA_ECOM.CV_ECOM_HQ_INTEGRATION_SITE |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_RAW_DATA_V2) | SDSLA_ECOM.CV_ECOM_ORDERS_RAW_DATA_V2 |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_INVENTORY_HISTORY) | SDSLA_ECOM.CV_ECOM_INVENTORY_HISTORY |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2 |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PAYMENT_SYNAPCOM) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PAYMENT_SYNAPCOM |  | CON_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_HQ_EMAIL_HASH) | SDSLA_ECOM.CV_ECOM_HQ_EMAIL_HASH |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - sap.hana.uis.db.GET_NAVIGATION_TARGET_DATA) | sap.hana.uis.db.GET_NAVIGATION_TARGET_DATA |  | _SYS_REPO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_INVENTORY_HISTORY_NEW) | SDSLA_ECOM.CV_ECOM_INVENTORY_HISTORY_NEW |  | CON_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_INVENTORY_HISTORY_SELA) | SDSLA_ECOM.CV_ECOM_INVENTORY_HISTORY_SELA |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SAMSUNGBR) | SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SAMSUNGBR |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SYNAPCON_BRSHOP) | SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SYNAPCON_BRSHOP |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_RAW_DATA_SYNAPCON_BRSHOP_V3_BACKUP) | SDSLA_ECOM.CV_RAW_DATA_SYNAPCON_BRSHOP_V3_BACKUP |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_RAW_DATA_SAMSUNGBR_V3_BACKUP) | SDSLA_ECOM.CV_RAW_DATA_SAMSUNGBR_V3_BACKUP |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_PAYMENT_TYPE_SYNAPCOM) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_PAYMENT_TYPE_SYNAPCOM |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_PAYMENT_TYPE) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_PAYMENT_TYPE |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SYNAPCON_BRSHOP_SAMSUNGCARE) | SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SYNAPCON_BRSHOP_SAMSUNGCARE |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_CLEAN_CELLO_TSS_ORDER_OPERATION) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_CLEAN_CELLO_TSS_ORDER_OPERATION |  | U_BRUNO_MELLO |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_O2O) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_O2O |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_HQ_INTEGRATION_TST_PLAT_MOBILE) | SDSLA_ECOM.CV_HQ_INTEGRATION_TST_PLAT_MOBILE |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LAO.D2C_NERP_SALES_BY_CHANNEL_GP) | LAO.D2C_NERP_SALES_BY_CHANNEL_GP |  | U_L_MARIANI |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LAO.D2C_NERP_SALES_BY_CHANNEL) | LAO.D2C_NERP_SALES_BY_CHANNEL |  | U_L_MARIANI |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LAO.D2C_NERP_DAILY_SALES_KPI) | LAO.D2C_NERP_DAILY_SALES_KPI |  | U_L_MARIANI |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_VIEW_ECOM_ORDERS_CUBO_TST) | SDSLA_ECOM.CV_VIEW_ECOM_ORDERS_CUBO_TST |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_HQ_INTEGRATION_TST_MAPPING) | SDSLA_ECOM.CV_HQ_INTEGRATION_TST_MAPPING |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SAMSUNG_ORDERS) | SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SAMSUNG_ORDERS |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SYNAPCON_SAMSUNG_ORDERS) | SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SYNAPCON_SAMSUNG_ORDERS |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_RAW_ORDERS_ALL) | SDSLA_ECOM.CV_RAW_ORDERS_ALL |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_HQ_INTEGRATION_TST_MODEL) | SDSLA_ECOM.CV_HQ_INTEGRATION_TST_MODEL |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_SYNAPCOM_TRADE_IN) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_SYNAPCOM_TRADE_IN |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_HQ_INTEGRATION_TST_TRADEIN) | SDSLA_ECOM.CV_HQ_INTEGRATION_TST_TRADEIN |  | CON_SDSLA |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_HQ_INTEGRATION_TST_AJ_DISCOUNT) | SDSLA_ECOM.CV_HQ_INTEGRATION_TST_AJ_DISCOUNT |  | TGT_SDSLA_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_TRADEIN) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_TRADEIN |  | CON_SDSLA |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_HQ_INTEGRATION_TST) | SDSLA_ECOM.CV_HQ_INTEGRATION_TST |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_SYNAPCOM) | SDSLA_ECOM.CV_ECOM_ORDERS_CUSTOMERS_PRODUCTS_SYNAPCOM |  | CON_SDSLA |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_HQ_INTEGRATION_TST_TESTE01) | SDSLA_ECOM.CV_HQ_INTEGRATION_TST_TESTE01 |  | CON_SDSLA |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SAMSUNGBR_V3) | SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SAMSUNGBR_V3 |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SAMSUNGBR_V2) | SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SAMSUNGBR_V2 |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SYNAPCON_BRSHOP_V2) | SDSLA_ECOM.CV_PAYMENT_RAW_DATA_SYNAPCON_BRSHOP_V2 |  | U_PRJ_ECOM |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV
|  | CALCULATION VIEW | (CALCULATION VIEW - LIMPEZA_BI_TRACKING.CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2) | LIMPEZA_BI_TRACKING.CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2 |  | U_MV_SILVA |  |  |  | To be migrated | [9 empty] | Migrar ph2: CV

## CountMigrationObjects
Area | (Tudo) |  | Area | SEDA-S - Logistics |  | Area | LAO EStore
Objects | Quantity | Quantity (%) | Objects | Quantity | Quantity (%) | Objects | Quantity | Quantity (%)
FUNCTION | 14 | 0.347% | FUNCTION | 1 | 0.1056% | PROCEDURE | 157 | 24.92%
Not to be migrated | 1 | 7.143% | Not to be migrated | 1 | 100% | Done | 146 | 92.99%
To be migrated | 13 | 92.86% | PROCEDURE | 76 | 8.025% | Not found | 2 | 1.274%
PROCEDURE | 500 | 12.39% | Not to be migrated | 50 | 65.79% | Not to be migrated | 9 | 5.732%
Done | 405 | 81% | To be migrated | 26 | 34.21% | TABLE | 466 | 73.97%
Not found | 2 | 0.4% | TABLE | 384 | 40.55% | Done | 425 | 91.2%
Not to be migrated | 60 | 12% | Not to be migrated | 163 | 42.45% | Not to be migrated | 12 | 2.575%
To be migrated | 33 | 6.6% | To be migrated | 221 | 57.55% | To be migrated | 29 | 6.223%
TABLE | 2603 | 64.51% | VIEW | 486 | 51.32% | VIEW | 7 | 1.111%
Done | 2178 | 83.67% | Not to be migrated | 256 | 52.67% | Done | 7 | 100%
Not to be migrated | 175 | 6.723% | To be migrated | 230 | 47.33% | Total Geral | 630 | 100%
To be migrated | 250 | 9.604% | Total Geral | 947 | 100%
VIEW | 758 | 18.79%
Done | 72 | 9.499%
Not to be migrated | 256 | 33.77%
To be migrated | 430 | 56.73%
CALCULATION VIEW | 160 | 3.965%
To be migrated | 160 | 100%
Total Geral | 4035 | 100%
Area | (Tudo) |  | Area | (Tudo)
MIGRATION_CLASS | (Vários itens) |  | MIGRATION_CLASS | (Vários itens)
Objects | Quantity | Quantity (%) | Objects | Quantity | Quantity (%)
PROCEDURE | 286 | 20.74% | FUNCTION | 14 | 0.5275%
Done | 279 | 97.55% | Not to be migrated | 1 | 7.143%
Not to be migrated | 7 | 2.448% | To be migrated | 13 | 92.86%
TABLE | 965 | 69.98% | PROCEDURE | 212 | 7.988%
Done | 965 | 100% | Done | 124 | 58.49%
VIEW | 128 | 9.282% | Not found | 2 | 0.9434%
Done | 57 | 44.53% | Not to be migrated | 53 | 25%
To be migrated | 71 | 55.47% | To be migrated | 33 | 15.57%
Total Geral | 1379 | 100% | TABLE | 1638 | 61.72%
|  |  | Done | 1213 | 74.05%
|  |  | Not to be migrated | 175 | 10.68%
|  |  | To be migrated | 250 | 15.26%
|  |  | VIEW | 630 | 23.74%
|  |  | Done | 15 | 2.381%
|  |  | Not to be migrated | 256 | 40.63%
|  |  | To be migrated | 359 | 56.98%
|  |  | CALCULATION VIEW | 160 | 6.029%
|  |  | To be migrated | 160 | 100%
|  |  | Total Geral | 2654 | 100%

## LaoEStoreSumary
Area | LAO EStore
Contagem de Task Name Original | Rótulos de Coluna
Rótulos de Linha | PROCEDURE | TABLE | VIEW | Total Geral
Done | 146 | 425 | 7 | 578
Not found | 2 |  |  | 2
Not to be migrated | 9 | 12 |  | 21
To be migrated |  | 29 |  | 29
Total Geral | 157 | 466 | 7 | 630

## PlanProject (hidden)
Rótulos de Linha
FUNCTION
PROCEDURE
TABLE
VIEW
CALCULATION VIEW
Total Geral

## Ingestion (Old) (hidden)
Origin | Type | Task Name Original | Task Name | Area | PIC | Classificação | D2C | Priority | Status Migração | Otimizada | Level | Duration | Start | End | Dependencies | PRIORITY2 | MIGRATION_CLASS | DISK_GB | TABLE_TYPE | Qty Dependencies | Referenced | Qty Referenced | W35-2025 | W36-2025 | W37-2025 | W38-2025 | W39-2025 | W40-2025 | W41-2025 | W42-2025 | W43-2025 | W44-2025 | W45-2025 | W46-2025 | W47-2025 | W48-2025 | W49-2025 | W50-2025 | W51-2025 | W52-2025 | W01-2026 | W02-2026 | W03-2026 | W04-2026 | Remark
| INGESTION | (INGESTION - JOB.ODS_TARGETS_CAMPAIGN) | JOB.ODS_TARGETS_CAMPAIGN | [7 empty] | 2 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_TARGET_PRODUCTS_CURRENT_YEAR)'", "'(TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS)'", "'(TABLE - OW_LAO.TMP_TARGET_PRODUCTS_PREVIOUS_YEAR)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0008 | ODS | 6 |  | 0 |  |  | 10/09 - 10/09
| INGESTION | (INGESTION - JOB.TMP_CAMPAIGN_NAME) | JOB.TMP_CAMPAIGN_NAME | [7 empty] | 2 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME)'", "'(TABLE - OW_LAO.DIM_CAMPAIGN_NAME)'", "'(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_UPDATE_ID_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 7 |  | 0 |  |  | 10/09 - 10/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS) | JOB.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)]']"] | 1 | 1.1 Ingestion VTEX | 0.0002 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES) | JOB.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES)]']"] | 1 | 1.1 Ingestion VTEX | 1.7933 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX | 32.5656 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)]']"] | 1 | 1.1 Ingestion VTEX | 5.3735 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)]']"] | 1 | 1.1 Ingestion VTEX | 0.2317 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]']"] | 1 | 1.1 Ingestion VTEX | 0.9546 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX | 1.4594 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX | 1.0527 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA) | JOB.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 1 | 1.1 Ingestion VTEX | 0.0001 | TMP | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 0 | 1.1 Ingestion VTEX | 0.346 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)]']"] | 0 | 1.1 Ingestion VTEX | 1.3423 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)]']"] | 0 | 1.1 Ingestion VTEX | 0.0006 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]']"] | 0 | 1.1 Ingestion VTEX | 0.2095 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]']"] | 0 | 1.1 Ingestion VTEX | 0.2215 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 0 | 1.1 Ingestion VTEX | 0.1928 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS) | JOB.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_SEDA_S.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS)]']"] | 0 | 1.1 Ingestion VTEX | 0.0099 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_AR) | JOB.ODS_VTEX_FEED_SSG_AR | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR)]']"] | 0 | 1.1 Ingestion VTEX | 2.882 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_AR_SMB) | JOB.ODS_VTEX_FEED_SSG_AR_SMB | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0411 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_BR_B2B) | JOB.ODS_VTEX_FEED_SSG_BR_B2B | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_B2B)]']"] | 0 | 1.1 Ingestion VTEX | 0.3744 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_BR_EPP2) | JOB.ODS_VTEX_FEED_SSG_BR_EPP2 | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_EPP2)]']"] | 0 | 1.1 Ingestion VTEX | 4.1824 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_PY) | JOB.ODS_VTEX_FEED_SSG_PY | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_PY)]']"] | 0 | 1.1 Ingestion VTEX | 0.0022 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_UY) | JOB.ODS_VTEX_FEED_SSG_UY | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_UY)]']"] | 0 | 1.1 Ingestion VTEX | 0.0031 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA) | JOB.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA)]']"] | 0 | 1.1 Ingestion VTEX | 0.002 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_MASTER_DATA_CL) | JOB.ODS_VTEX_MASTER_DATA_CL | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)]']"] | 0 | 1.1 Ingestion VTEX | 0.0139 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_MASTER_DATA_DOMAIN) | JOB.ODS_VTEX_MASTER_DATA_DOMAIN | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_DOMAIN)]']"] | 0 | 1.1 Ingestion VTEX | 0.0412 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_PRICE_LIST) | JOB.ODS_VTEX_SSG_BR_PRICE_LIST | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PRICE_LIST)]']"] | 0 | 1.1 Ingestion VTEX | 0 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA) | JOB.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA)]']"] | 0 | 1.1 Ingestion VTEX | 0.0037 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST) | JOB.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST)]']"] | 0 | 1.1 Ingestion VTEX | 0 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX) | JOB.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX)]']"] | 0 | 1.1 Ingestion VTEX | 0.002 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA) | JOB.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA)]']"] | 0 | 1.1 Ingestion VTEX | 2.7504 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SEASA_MASTER_DATA_CL) | JOB.RAW_VTEX_SEASA_MASTER_DATA_CL | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.015 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SEASA_MASTER_DATA_EM) | JOB.RAW_VTEX_SEASA_MASTER_DATA_EM | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.0002 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SEASA_TRADEIN_FEED) | JOB.RAW_VTEX_SEASA_TRADEIN_FEED | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.002 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SEDA_MASTER_DATA_CL) | JOB.RAW_VTEX_SEDA_MASTER_DATA_CL | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.0672 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER) | JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0046 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM) | JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0012 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PACKAGE) | JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PACKAGE | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0003 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT) | JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0011 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING) | JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0032 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_TRADE_UP_SEASA_ORDER) | JOB.RAW_VTEX_TRADE_UP_SEASA_ORDER | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.021 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_TRADE_UP_SEDA_ORDER) | JOB.RAW_VTEX_TRADE_UP_SEDA_ORDER | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.0823 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA_TLD) | JOB.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA_TLD | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_PAYMENTS) | JOB.ODS_HYBRIS_PAYMENTS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)]']"] | 1 | 1.2 Ingestion HYBRIS | 0.2854 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_SALES) | JOB.ODS_HYBRIS_SALES | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS | 0.7395 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_CANCELLATIONS) | JOB.ODS_HYBRIS_CANCELLATIONS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_CANCELLATIONS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0221 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_OFFERS) | JOB.ODS_HYBRIS_OFFERS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_OFFERS)]']"] | 0 | 1.2 Ingestion HYBRIS | 2.0153 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_PREORDERS) | JOB.ODS_HYBRIS_PREORDERS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PREORDERS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0006 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_PRICING) | JOB.ODS_HYBRIS_PRICING | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PRICING)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_REFUNDS) | JOB.ODS_HYBRIS_REFUNDS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_REFUNDS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0186 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_RETURNS) | JOB.ODS_HYBRIS_RETURNS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_RETURNS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_REWARDS) | JOB.ODS_HYBRIS_REWARDS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_REWARDS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.1916 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS) | JOB.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.2573 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_TRADEIN) | JOB.ODS_HYBRIS_TRADEIN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_TRADEIN)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0083 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_CANCELLATIONS) | JOB.RAW_HYBRIS_CANCELLATIONS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0005 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_OFFERS) | JOB.RAW_HYBRIS_OFFERS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_PAYMENTS) | JOB.RAW_HYBRIS_PAYMENTS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_PREORDERS) | JOB.RAW_HYBRIS_PREORDERS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0001 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_PRICING) | JOB.RAW_HYBRIS_PRICING | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_REFUNDS) | JOB.RAW_HYBRIS_REFUNDS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0005 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_RETURNS) | JOB.RAW_HYBRIS_RETURNS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_REWARDS) | JOB.RAW_HYBRIS_REWARDS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0006 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_SALES) | JOB.RAW_HYBRIS_SALES | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0007 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_TRADEIN) | JOB.RAW_HYBRIS_TRADEIN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_OFFERS_DEDUP) | JOB.TMP_HYBRIS_OFFERS_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_PAYMENTS_DEDUP) | JOB.TMP_HYBRIS_PAYMENTS_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_PREORDERS_DEDUP) | JOB.TMP_HYBRIS_PREORDERS_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_REFUNDS_DEDUP) | JOB.TMP_HYBRIS_REFUNDS_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0002 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_REWARDS_DEDUP) | JOB.TMP_HYBRIS_REWARDS_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_SALES_AGG_DEDUP) | JOB.TMP_HYBRIS_SALES_AGG_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0003 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_SALES_DEDUP) | JOB.TMP_HYBRIS_SALES_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_SALES_VOUCHER_CODE_AGG) | JOB.TMP_HYBRIS_SALES_VOUCHER_CODE_AGG | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0006 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_MAGENTO) | JOB.ODS_SELA_API_MAGENTO | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0097 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP) | JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP_SUB) | JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP_SUB | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP_UPDATE) | JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP_UPDATE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_MAGENTO_UPDATE_TEMP) | JOB.ODS_SELA_API_MAGENTO_UPDATE_TEMP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_ODS_SELA_API_MAGENTO_SUB) | JOB.TMP_ODS_SELA_API_MAGENTO_SUB | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0002 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_ODS_SELA_API_MAGENTO_UPDATE) | JOB.TMP_ODS_SELA_API_MAGENTO_UPDATE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0002 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | JOB.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)]']"] | 1 | 1.4 Ingestion NERP | 0.1826 | ODS | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | JOB.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)]']"] | 1 | 1.4 Ingestion NERP | 1.4001 | ODS | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW) | JOB.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)]']"] | 1 | 1.4 Ingestion NERP | 0.4139 | ODS | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | JOB.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)]']"] | 1 | 1.4 Ingestion NERP | 0.2907 | RAW | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_MB51_GR_FOLDER) | JOB.ODS_NERP_MB51_GR_FOLDER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_MB51_GR_FOLDER)]']"] | 1 | 1.4 Ingestion NERP | 0.6549 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZLLEB57910_CLAIM_FOLDER) | JOB.ODS_NERP_ZLLEB57910_CLAIM_FOLDER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)]']"] | 1 | 1.4 Ingestion NERP | 0.004 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRCOS43400_TARGET_FOLDER) | JOB.ODS_NERP_ZRCOS43400_TARGET_FOLDER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER)]']"] | 1 | 1.4 Ingestion NERP | 0.0105 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_MB51_GR_FOLDER) | JOB.RAW_DATA_NERP_MB51_GR_FOLDER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_MB51_GR_FOLDER)]']"] | 1 | 1.4 Ingestion NERP | 0.6733 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_FOLDER) | JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_FOLDER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)]']"] | 1 | 1.4 Ingestion NERP | 0.0054 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_MAINTENANCE) | JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_MAINTENANCE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE)]']"] | 1 | 1.4 Ingestion NERP | 0.0072 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | JOB.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]']"] | 1 | 1.4 Ingestion NERP | 6.0427 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO) | JOB.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO)'", "'(TABLE - OW_LAO.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO)]']"] | 0 | 1.4 Ingestion NERP | 0.0343 | ODS | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS) | JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS)]']"] | 0 | 1.4 Ingestion NERP | 1.2433 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS) | JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]']"] | 0 | 1.4 Ingestion NERP | 0.0113 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE) | JOB.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE)]']"] | 0 | 1.4 Ingestion NERP | 0.0006 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRCOA20250_PA_ALLOC_RES) | JOB.ODS_NERP_ZRCOA20250_PA_ALLOC_RES | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRCOA20250_PA_ALLOC_RES)]']"] | 0 | 1.4 Ingestion NERP | 0.0064 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN) | JOB.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN)]']"] | 0 | 1.4 Ingestion NERP | 0.0094 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER) | JOB.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER)]']"] | 0 | 1.4 Ingestion NERP | 0.4483 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS) | JOB.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS)]']"] | 0 | 1.4 Ingestion NERP | 0.0016 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER) | JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER)]']"] | 0 | 1.4 Ingestion NERP | 0.0003 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER) | JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER)]']"] | 0 | 1.4 Ingestion NERP | 0.0003 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER) | JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER)]']"] | 0 | 1.4 Ingestion NERP | 0.0005 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZLMKF03006_CONDITION_CALC) | JOB.RAW_DATA_NERP_ZLMKF03006_CONDITION_CALC | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLMKF03006_CONDITION_CALC)]']"] | 0 | 1.4 Ingestion NERP | 0.0036 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | JOB.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 0 | 1.4 Ingestion NERP | 7.6947 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP_PREPARE) | JOB.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP_PREPARE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRCOA20250_FORECAST_SALES_DEDUP_PREPARE)]']"] | 0 | 1.4 Ingestion NERP | 0.0001 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.FT_ECOM_ORDER_ITEM) | JOB.FT_ECOM_ORDER_ITEM | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)]']"] | 1 | 2.1 Migrar ph1 | 0.5176 | FT | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.MAP_CANCELLATION_MESSAGE) | JOB.MAP_CANCELLATION_MESSAGE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 1 | 2.1 Migrar ph1 | 0.0001 | MAP | 1 |  | 0 |  |  | 12/09 - 12/09
Control Tower | INGESTION | (INGESTION - JOB.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING) | JOB.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)]']"] | 0 | 2.1 Migrar ph1 | 0 | DIM | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.DIM_EXCEL_TARGETS_CAMPAIGN) | JOB.DIM_EXCEL_TARGETS_CAMPAIGN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.DIM_EXCEL_TARGETS_CAMPAIGN)]']"] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.DIM_EXCHANGE_RATE) | JOB.DIM_EXCHANGE_RATE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.003 | DIM | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.DIM_MONITORING_BI_LAO_PROCCESS_ALERT) | JOB.DIM_MONITORING_BI_LAO_PROCCESS_ALERT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.DIM_MONITORING_BI_LAO_PROCCESS_ALERT)]']"] | 0 | 2.1 Migrar ph1 | 0.0003 | DIM | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.DIM_SELLER_INSTANCE) | JOB.DIM_SELLER_INSTANCE | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.DIM_SUBSIDIARY) | JOB.DIM_SUBSIDIARY | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0002 | DIM | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_ECOM_ORDER) | JOB.FT_ECOM_ORDER | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)]']"] | 0 | 2.1 Migrar ph1 | 1.3795 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_ECOM_ORDER_KIT_COMPONENT) | JOB.FT_ECOM_ORDER_KIT_COMPONENT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)]']"] | 0 | 2.1 Migrar ph1 | 0.0486 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_ECOM_ORDER_PAYMENT) | JOB.FT_ECOM_ORDER_PAYMENT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 0 | 2.1 Migrar ph1 | 0.8166 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_MAGENTO_ORDER) | JOB.FT_MAGENTO_ORDER | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0003 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_MAGENTO_ORDER_ITEM) | JOB.FT_MAGENTO_ORDER_ITEM | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0002 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_MAGENTO_ORDER_PAYMENT) | JOB.FT_MAGENTO_ORDER_PAYMENT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0001 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.TF_GLOBAL_BI_TRAFFIC_ALL) | JOB.TF_GLOBAL_BI_TRAFFIC_ALL | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0009 | TF | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.TF_GLOBAL_BI_TRAFFIC_DA) | JOB.TF_GLOBAL_BI_TRAFFIC_DA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0007 | TF | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.TF_GLOBAL_BI_TRAFFIC_MX) | JOB.TF_GLOBAL_BI_TRAFFIC_MX | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0008 | TF | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.TF_GLOBAL_BI_TRAFFIC_VD) | JOB.TF_GLOBAL_BI_TRAFFIC_VD | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0007 | TF | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_SALES) | JOB.ODS_GLOBAL_BI_SALES | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)]']"] | 1 | 3.1 Migrar ph1 | 1.6817 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_STOCKOUT) | JOB.ODS_GLOBAL_BI_STOCKOUT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT)]']"] | 1 | 3.1 Migrar ph1 | 0.8038 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_ALL) | JOB.ODS_GLOBAL_BI_TRAFFIC_ALL | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 3.1 Migrar ph1 | 0.0042 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_B2B) | JOB.RAW_DATA_API_AFTER_SALES_LIST_B2B | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 1 | 3.1 Migrar ph1 | 0.0012 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_BREA) | JOB.RAW_DATA_API_AFTER_SALES_LIST_BREA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 1 | 3.1 Migrar ph1 | 0 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_EPP2) | JOB.RAW_DATA_API_AFTER_SALES_LIST_EPP2 | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 1 | 3.1 Migrar ph1 | 0.0011 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_CAMPAIGN_TARGET_CHANNELS) | JOB.ODS_CAMPAIGN_TARGET_CHANNELS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS)'", "'(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_CHANNELS)]']"] | 0 | 3.1 Migrar ph1 | 0.002 | ODS | 2 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.TMP_TARGETS_CAMPAIGN) | JOB.TMP_TARGETS_CAMPAIGN | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.TMP_TARGETS_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 | 0.0016 | TMP | 2 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_APPSFLYER_IN_APP_EVENTS) | JOB.ODS_APPSFLYER_IN_APP_EVENTS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_APPSFLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 | 0.1138 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_CAMPAIGN_TARGET_PRODUCTS) | JOB.ODS_CAMPAIGN_TARGET_PRODUCTS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS)]']"] | 0 | 3.1 Migrar ph1 | 0.0012 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_DA) | JOB.ODS_GLOBAL_BI_TRAFFIC_DA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_DA)]']"] | 0 | 3.1 Migrar ph1 | 0.0034 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_MX) | JOB.ODS_GLOBAL_BI_TRAFFIC_MX | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_MX)]']"] | 0 | 3.1 Migrar ph1 | 0.004 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_VD) | JOB.ODS_GLOBAL_BI_TRAFFIC_VD | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_VD)]']"] | 0 | 3.1 Migrar ph1 | 0.0037 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS) | JOB.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT) | JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT)]']"] | 0 | 3.1 Migrar ph1 | 0.0009 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Control Tower | INGESTION | (INGESTION - JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM) | JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM)]']"] | 0 | 3.1 Migrar ph1 | 0.0007 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_ORDERS_VISUAR) | JOB.ODS_ORDERS_VISUAR | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_ORDERS_VISUAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0021 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_PAYMENT_FUNNEL) | JOB.ODS_PAYMENT_FUNNEL | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 3.1 Migrar ph1 | 0.3013 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_SALES_CAMPAIGN) | JOB.ODS_SALES_CAMPAIGN | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 | 0.2956 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_STATUS_MAP) | JOB.ODS_SELA_API_STATUS_MAP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.ODS_SELA_API_STATUS_MAP)]']"] | 0 | 3.1 Migrar ph1 | 0 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_APPLYER_IN_APP_EVENTS) | JOB.RAW_APPLYER_IN_APP_EVENTS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_APPSFLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 | 6.625 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_B2B) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_B2B | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0004 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_BREA) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_BREA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0046 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_EPP2) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_EPP2 | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0004 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_EST) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_EST | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0007 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_MEMBERS) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_MEMBERS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0005 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_MKP) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_MKP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0074 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_PARC) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_PARC | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0004 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_RESID) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_RESID | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0002 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP) | JOB.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0253 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_EST) | JOB.RAW_DATA_API_AFTER_SALES_LIST_EST | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0029 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_MEMBERS) | JOB.RAW_DATA_API_AFTER_SALES_LIST_MEMBERS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0009 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_MKP) | JOB.RAW_DATA_API_AFTER_SALES_LIST_MKP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0547 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_PARC) | JOB.RAW_DATA_API_AFTER_SALES_LIST_PARC | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0015 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_RESID) | JOB.RAW_DATA_API_AFTER_SALES_LIST_RESID | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED) | JOB.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.017 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_PRODUCT_TRADEIN) | JOB.RAW_ECOM_PRODUCT_TRADEIN | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_PRODUCT_TRADEIN_SEASA) | JOB.RAW_ECOM_PRODUCT_TRADEIN_SEASA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_PRODUCT_TRADEUP) | JOB.RAW_ECOM_PRODUCT_TRADEUP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_PRODUCT_TRADEUP_SEASA) | JOB.RAW_ECOM_PRODUCT_TRADEUP_SEASA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_SKU) | JOB.RAW_ECOM_SKU | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0019 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_SKU_SAMSUNG_CARE_PLUS) | JOB.RAW_ECOM_SKU_SAMSUNG_CARE_PLUS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0002 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS) | JOB.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ORDERS_VISUAR) | JOB.RAW_ORDERS_VISUAR | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_ORDERS_VISUAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0135 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR) | JOB.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS) | JOB.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS)]']"] | 0 | 3.1 Migrar ph1 | 0.0002 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR) | JOB.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0014 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR) | JOB.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0012 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | JOB.TMP_ECOM_HQ_ORDERS_PRODUCTS_COMBO | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
Global D2C BI | INGESTION | (INGESTION - JOB.TMP_GLOBAL_BI_SALES) | JOB.TMP_GLOBAL_BI_SALES | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_SALES)]']"] | 0 | 3.1 Migrar ph1 | 0.09 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_MONITORING_BI_LAO_PROCCESS_ALERT) | JOB.TMP_MONITORING_BI_LAO_PROCCESS_ALERT | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ALERT)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_ODS_ECOM_SKU_ENABLES) | JOB.TMP_ODS_ECOM_SKU_ENABLES | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN) | JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID) | JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID_SEASA) | JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID_SEASA | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_RAW_ECOM_SKU_SAMSUNG_CARE_PLUS) | JOB.TMP_RAW_ECOM_SKU_SAMSUNG_CARE_PLUS | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_SALES_CAMPAIGN) | JOB.TMP_SALES_CAMPAIGN | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 | 0.2806 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_UPDATE_CAMPAIGN_NAME) | JOB.TMP_UPDATE_CAMPAIGN_NAME | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_UPDATE_ID_CAMPAIGN) | JOB.TMP_UPDATE_ID_CAMPAIGN | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_UPDATE_ID_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_VL_SALES_CHANNEL_TABLE_BIZTYPE_CHANNEL_NULL) | JOB.TMP_VL_SALES_CHANNEL_TABLE_BIZTYPE_CHANNEL_NULL | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | INGESTION | (INGESTION - JOB.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STATUS_NULL) | JOB.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STATUS_NULL | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.ODS_LAO_MEDALLIA_EXPRESS_REPORT) | JOB.ODS_LAO_MEDALLIA_EXPRESS_REPORT | [7 empty] | 2 | 1 | 46007 | 46007 | ["['[(TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT)]']"] | 1 | Check | 0.688 | ODS | 1 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.STG_CT_TRADEIN_SEASA) | JOB.STG_CT_TRADEIN_SEASA | [7 empty] | 2 | 1 | 46007 | 46007 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 1 | Check | 0.0001 | OTHER | 1 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS) | JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS | [7 empty] | 2 | 1 | 46007 | 46007 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | Check | 0.0004 | OTHER | 1 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS_TOTALS_TEMP) | JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS_TOTALS_TEMP | [7 empty] | 2 | 1 | 46007 | 46007 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | Check | 0.0001 | OTHER | 1 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS_UPDATE_TEMP) | JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS_UPDATE_TEMP | [7 empty] | 2 | 1 | 46007 | 46007 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | Check | 0.0001 | OTHER | 1 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.ETL_PANAMA_ECOMMERCE_ORDERS) | JOB.ETL_PANAMA_ECOMMERCE_ORDERS | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | Check | 0.0002 | OTHER | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ETL_PANAMA_ECOMMERCE_ORDERS_UPDATE_TEMP) | JOB.ETL_PANAMA_ECOMMERCE_ORDERS_UPDATE_TEMP | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | Check | 0 | OTHER | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_DIRECTSHIP_RAWDATA_GPL) | JOB.ODS_DIRECTSHIP_RAWDATA_GPL | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_SEDA_S.ODS_DIRECTSHIP_RAWDATA_GPL)]']"] | 0 | Check | 0.0249 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_ECOM_SKU_ENABLES) | JOB.ODS_ECOM_SKU_ENABLES | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES)]']"] | 0 | Check | 0.0005 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_MD_MAPPING_PROMOTION_PRODUCT) | JOB.ODS_MD_MAPPING_PROMOTION_PRODUCT | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_MD.ODS_MD_MAPPING_PROMOTION_PRODUCT)]']"] | 0 | Check | 0.0001 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_MKP_D2C_FASTSHOP) | JOB.ODS_MKP_D2C_FASTSHOP | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - U_PRJ_ECOM.ODS_MKP_D2C_FASTSHOP)]']"] | 0 | Check | 0.0325 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_ONTIMEGI_RAWDATA_GPL) | JOB.ODS_ONTIMEGI_RAWDATA_GPL | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_SEDA_S.ODS_ONTIMEGI_RAWDATA_GPL)]']"] | 0 | Check | 0.0413 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_ONTIMEGR_RAWDATA_GPL) | JOB.ODS_ONTIMEGR_RAWDATA_GPL | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_SEDA_S.ODS_ONTIMEGR_RAWDATA_GPL)]']"] | 0 | Check | 0.027 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_RP_DOA_INSPECTION_RESULT) | JOB.ODS_RP_DOA_INSPECTION_RESULT | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_SEDA_S.ODS_RP_DOA_INSPECTION_RESULT)]']"] | 0 | Check | 0.1115 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_RP_DOA_TRACKING_BY_SERIAL) | JOB.ODS_RP_DOA_TRACKING_BY_SERIAL | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_SEDA_S.ODS_RP_DOA_TRACKING_BY_SERIAL)]']"] | 0 | Check | 0.0802 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM) | JOB.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM)]']"] | 0 | Check | 0.0093 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_ESCOLTA) | JOB.ODS_SM_PORTAL_ANGELIRA_ESCOLTA | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA)]']"] | 0 | Check | 0.0049 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_NC) | JOB.ODS_SM_PORTAL_ANGELIRA_NC | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_NC)]']"] | 0 | Check | 0.0051 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_CHECKLIST) | JOB.ODS_SM_PORTAL_ANGELIRA_RM_CHECKLIST | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_CHECKLIST)]']"] | 0 | Check | 0.0011 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA) | JOB.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA)]']"] | 0 | Check | 0.0007 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS) | JOB.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS)]']"] | 0 | Check | 0.0005 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SURICATO_HR) | JOB.ODS_SURICATO_HR | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SURICATO_HR)]']"] | 0 | Check | 0.0038 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SURSIS_DELIVERY_DATA) | JOB.ODS_SURSIS_DELIVERY_DATA | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA)]']"] | 0 | Check | 0.011 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SURSIS_ESCORT) | JOB.ODS_SURSIS_ESCORT | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SURSIS_ESCORT)]']"] | 0 | Check | 0.0065 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SURSIS_NC) | JOB.ODS_SURSIS_NC | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SURSIS_NC)]']"] | 0 | Check | 0.0052 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT) | JOB.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_SEDA_S.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT)]']"] | 0 | Check | 0.2136 | ODS | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.RAW_DATA_LAO_MEDALLIA_EXPRESS_REPORT) | JOB.RAW_DATA_LAO_MEDALLIA_EXPRESS_REPORT | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT)]']"] | 0 | Check | 0.0734 | RAW | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS) | JOB.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | Check | 0.0001 | OTHER | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_CANCELLATIONS_DEDUP) | JOB.TMP_HYBRIS_CANCELLATIONS_DEDUP | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | Check | 0.0002 | TMP | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_TRADEIN_DEDUP) | JOB.TMP_HYBRIS_TRADEIN_DEDUP | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | Check | 0.0004 | TMP | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.TMP_ODS_GENERIC_INPUT) | JOB.TMP_ODS_GENERIC_INPUT | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_SEDA_S.TMP_ODS_GENERIC_INPUT)]']"] | 0 | Check | 0.0141 | TMP | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_AP1_ACCURACY) | JOB.ODS_GSCM_AP1_ACCURACY | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY)]']"] | 1 | Migrar ph2 | 0.0173 | ODS | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_FCST_MGMT_D2C) | JOB.ODS_GSCM_FCST_MGMT_D2C | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.ODS_GSCM_FCST_MGMT_D2C)]']"] | 1 | Migrar ph2 | 3.995 | ODS | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER) | JOB.ODS_PLUGG_MARKETPLACE_ORDER | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | Migrar ph2 | 0.2784 | ODS | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.ODS_WMS_ABNORMAL_INVENTORY) | JOB.ODS_WMS_ABNORMAL_INVENTORY | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_ABNORMAL_INVENTORY)]']"] | 1 | Migrar ph2 | 0.3011 | ODS | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD) | JOB.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD)]']"] | 1 | Migrar ph2 | 0.0159 | ODS | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.ODS_WMS_GATE_DOCK_IN_MAO) | JOB.ODS_WMS_GATE_DOCK_IN_MAO | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_MAO)]']"] | 1 | Migrar ph2 | 0.1685 | ODS | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD) | JOB.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD)]']"] | 1 | Migrar ph2 | 0.015 | ODS | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.ODS_WMS_PICKING_PACKING) | JOB.ODS_WMS_PICKING_PACKING | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_PICKING_PACKING)]']"] | 1 | Migrar ph2 | 0.0925 | ODS | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.ODS_WMS_YMS_GATE_DOCK_IN_CAJ) | JOB.ODS_WMS_YMS_GATE_DOCK_IN_CAJ | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_YMS_GATE_DOCK_IN_CAJ)]']"] | 1 | Migrar ph2 | 0.0262 | ODS | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.RAW_DATA_GSCM_ACTUAL_ON_HAND) | JOB.RAW_DATA_GSCM_ACTUAL_ON_HAND | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)]']"] | 1 | Migrar ph2 | 0.3142 | RAW | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.RAW_GSCM_CE_SELL_OUT) | JOB.RAW_GSCM_CE_SELL_OUT | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_LAO.ODS_GSCM_CE_SELL_OUT)]']"] | 1 | Migrar ph2 | 0.2705 | RAW | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.RAW_GSCM_MX_SELL_OUT) | JOB.RAW_GSCM_MX_SELL_OUT | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_LAO.ODS_GSCM_MX_SELL_OUT)]']"] | 1 | Migrar ph2 | 0.4139 | RAW | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.FT_CE_SELL_IN_FCST) | JOB.FT_CE_SELL_IN_FCST | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.FT_CE_SELL_IN_FCST)]']"] | 0 | Migrar ph2 | 0.0024 | FT | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.MAP_CE_ASP_RANGE) | JOB.MAP_CE_ASP_RANGE | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.MAP_CE_ASP_RANGE)]']"] | 0 | Migrar ph2 | 0.0029 | MAP | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.MAP_CE_ASP_RANGE_TABLE) | JOB.MAP_CE_ASP_RANGE_TABLE | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_ASP_RANGE_TABLE)]']"] | 0 | Migrar ph2 | 0.0001 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_DISTRIBUTION_QUALITY_TRACKER) | JOB.MAP_CE_DISTRIBUTION_QUALITY_TRACKER | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_QUALITY_TRACKER)]']"] | 0 | Migrar ph2 | 0.0409 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE) | JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE)]']"] | 0 | Migrar ph2 | 0.012 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA) | JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA)]']"] | 0 | Migrar ph2 | 0.0066 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT) | JOB.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT)]']"] | 0 | Migrar ph2 | 0.008 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_JOURNEY) | JOB.MAP_CE_JOURNEY | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)]']"] | 0 | Migrar ph2 | 0.0117 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_PRODUCTS) | JOB.MAP_CE_PRODUCTS | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 | 0.0114 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_PROMOTER_TARGET) | JOB.MAP_CE_PROMOTER_TARGET | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PROMOTER_TARGET)]']"] | 0 | Migrar ph2 | 0.0083 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_SALES_DEDUCTION) | JOB.MAP_CE_SALES_DEDUCTION | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 | 0.0004 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_ACTUAL_SALES) | JOB.ODS_GSCM_ACTUAL_SALES | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_ACTUAL_SALES)]']"] | 0 | Migrar ph2 | 0.0407 | ODS | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_CE_SELL_OUT) | JOB.ODS_GSCM_CE_SELL_OUT | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_LAO.ODS_GSCM_CE_SELL_OUT)]']"] | 0 | Migrar ph2 | 0.0079 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION) | JOB.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION)]']"] | 0 | Migrar ph2 | 0.0001 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_FCST_MGMT_AP1) | JOB.ODS_GSCM_FCST_MGMT_AP1 | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_FCST_MGMT_AP1)]']"] | 0 | Migrar ph2 | 0.1936 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_MX_SELL_OUT) | JOB.ODS_GSCM_MX_SELL_OUT | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_LAO.ODS_GSCM_MX_SELL_OUT)]']"] | 0 | Migrar ph2 | 0.0145 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_PROMOTION_PLAN_RAW) | JOB.ODS_GSCM_PROMOTION_PLAN_RAW | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_PROMOTION_PLAN_RAW)]']"] | 0 | Migrar ph2 | 0.0196 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SELL_OUT_ACCOUNT) | JOB.ODS_GSCM_SELL_OUT_ACCOUNT | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SELL_OUT_ACCOUNT)]']"] | 0 | Migrar ph2 | 0.0154 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SI_FCST_DA) | JOB.ODS_GSCM_SI_FCST_DA | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_DA)]']"] | 0 | Migrar ph2 | 0.0849 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SI_FCST_MX) | JOB.ODS_GSCM_SI_FCST_MX | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_MX)]']"] | 0 | Migrar ph2 | 0.1837 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SI_FCST_VD) | JOB.ODS_GSCM_SI_FCST_VD | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_VD)]']"] | 0 | Migrar ph2 | 0.0798 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SO_FCST_DA) | JOB.ODS_GSCM_SO_FCST_DA | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_DA)]']"] | 0 | Migrar ph2 | 0.0862 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SO_FCST_HHP) | JOB.ODS_GSCM_SO_FCST_HHP | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_HHP)]']"] | 0 | Migrar ph2 | 0.1631 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SO_FCST_OTHERS) | JOB.ODS_GSCM_SO_FCST_OTHERS | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_OTHERS)]']"] | 0 | Migrar ph2 | 0.077 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SO_FCST_VD) | JOB.ODS_GSCM_SO_FCST_VD | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_VD)]']"] | 0 | Migrar ph2 | 0.0597 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC) | JOB.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC)]']"] | 0 | Migrar ph2 | 0.0001 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION) | JOB.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION)]']"] | 0 | Migrar ph2 | 0 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_NERP_ZLMKF03006_CONDITION_CALC) | JOB.ODS_NERP_ZLMKF03006_CONDITION_CALC | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLMKF03006_CONDITION_CALC)]']"] | 0 | Migrar ph2 | 0.0003 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY) | JOB.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY)]']"] | 0 | Migrar ph2 | 0.5782 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY) | JOB.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY)]']"] | 0 | Migrar ph2 | 0.655 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW) | JOB.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW)]']"] | 0 | Migrar ph2 | 0.0667 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION) | JOB.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION)]']"] | 0 | Migrar ph2 | 0 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION) | JOB.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION)]']"] | 0 | Migrar ph2 | 0 | ODS | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION) | JOB.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION)]']"] | 0 | Migrar ph2 | 0 | ODS | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.ODS_WEBPRICE_TRACKING_DAILY_MX) | JOB.ODS_WEBPRICE_TRACKING_DAILY_MX | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX)]']"] | 0 | Migrar ph2 | 0.2357 | ODS | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.ODS_WEBPRICE_TRACKING_DAILY_TV) | JOB.ODS_WEBPRICE_TRACKING_DAILY_TV | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_TV)]']"] | 0 | Migrar ph2 | 0.7171 | ODS | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.RAW_GSCM_PRODUCT_LIST) | JOB.RAW_GSCM_PRODUCT_LIST | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | Migrar ph2 | 0.0003 | RAW | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.TMP_CE_FORMAT) | JOB.TMP_CE_FORMAT | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.TMP_CE_FORMAT)]']"] | 0 | Migrar ph2 | 0.0942 | TMP | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.TMP_ODS_GSCM_PROMOTION_PLAN) | JOB.TMP_ODS_GSCM_PROMOTION_PLAN | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.TMP_ODS_GSCM_PROMOTION_PLAN)]']"] | 0 | Migrar ph2 | 0.0085 | TMP | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION) | JOB.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 | 0.0026 | TMP | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.FT_CE_DAILY_PIVOT) | JOB.FT_CE_DAILY_PIVOT | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)]']"] | 0 | Migrar ph2 SEDA RM | 0.7634 | FT | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.FT_CE_DB_FCST) | JOB.FT_CE_DB_FCST | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.FT_CE_DB_FCST)]']"] | 0 | Migrar ph2 SEDA RM | 0.0538 | FT | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.FT_CE_READY) | JOB.FT_CE_READY | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)]']"] | 0 | Migrar ph2 SEDA RM | 0.6369 | FT | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.MAP_CE_STORES) | JOB.MAP_CE_STORES | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM | 0.0884 | MAP | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.ODS_CONTROLLING_FORMAT_ACTUAL) | JOB.ODS_CONTROLLING_FORMAT_ACTUAL | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)]']"] | 0 | Migrar ph2: Controlling | 1.1336 | ODS | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.ODS_CONTROLLING_PL) | JOB.ODS_CONTROLLING_PL | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)]']"] | 0 | Migrar ph2: Controlling | 0.0721 | ODS | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.RAW_IBGE_POPULACAO) | JOB.RAW_IBGE_POPULACAO | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | Migrar ph2: SEDA MI& Big Data | 0.0002 | RAW | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.ODS_RP_ETR_LOGISTICS_TRACKING) | JOB.ODS_RP_ETR_LOGISTICS_TRACKING | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.ODS_RP_ETR_LOGISTICS_TRACKING)]']"] | 0 | check | 0.1935 | ODS | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG) | JOB.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG)]']"] | 0 | check | 0 | ODS | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.RAW_ANATEL_ACESSOS_TELEFONIA_MOVEL) | JOB.RAW_ANATEL_ACESSOS_TELEFONIA_MOVEL | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | check | 1.7213 | RAW | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.RAW_MX_TMV_INDEX) | JOB.RAW_MX_TMV_INDEX | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX)]']"] | 0 | check | 0.0002 | RAW | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.RAW_TECH_INSIGHTS) | JOB.RAW_TECH_INSIGHTS | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | check | 0.0005 | RAW | 1 |  | 0 | [18 empty] | 29/12 - 29/12

## OldStructure (hidden)
Origin | Type | Task Name Original | Task Name | Area | PIC | Classificação | D2C | Priority | Status Migração | Otimizada | Level | Duration | Start | End | Dependencies | PRIORITY2 | MIGRATION_CLASS | DISK_GB | TABLE_TYPE | Qty Dependencies | Referenced | Qty Referenced | W35-2025 | W36-2025 | W37-2025 | W38-2025 | W39-2025 | W40-2025 | W41-2025 | W42-2025 | W43-2025 | W44-2025 | W45-2025 | W46-2025 | W47-2025 | W48-2025 | W49-2025 | W50-2025 | W51-2025 | W52-2025 | W01-2026 | W02-2026 | W03-2026 | W04-2026 | Remark
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 32.5656 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_TESTE_),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_MD.PROC_DIM_VTEX_ORDER_STATUS),(PROCEDURE - OW_LAO.PROC_TESTE),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE),(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.RAW_VTEX_PAYMENTS_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN),(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN)] | 75 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.4564 | RAW | 0 | [(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_TESTE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5)] | 47 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 5.3735 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING)] | 47 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 1.0527 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 46 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.2317 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT)] | 43 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0002 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP)] | 41 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.7697 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD),(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT)] | 33 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.7722 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VW_SDU_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX)] | 31 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 1.4594 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.RAW_VTEX_PAYMENTS_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION)] | 22 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.217 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA),(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_TESTE),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION)] | 18 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.1202 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_RAW_VTEX_SSG_BR_B2B_SALES_ORDER_MONITORING_DATASOURCE),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_TESTE)] | 11 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.2296 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS),(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION)] | 9 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0107 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711)] | 7 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.1855 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION),(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD)] | 7 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0006 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0002 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0047 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0004 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0282 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0002 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0377 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0019 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0198 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI)] | 4 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 1.7933 | ODS | 0 | [(VIEW - OW_MD.VW_PRICE_MONITORING_AUDIT_PROCESS),(INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU)] | 3 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0735 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU),(VIEW - OW_MD.VW_PRICE_MONITORING_AUDIT_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU)] | 3 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 1.1093 | RAW | 0 | [(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING)] | 3 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 32.5656 | RAW | 0 | [(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER),(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 5.3735 | RAW | 0 | [(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM),(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.2317 | RAW | 0 | [(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS),(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.9546 | RAW | 0 | [(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE),(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 1.4594 | RAW | 0 | [(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT),(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 1.0527 | RAW | 0 | [(INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING),(INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.1612 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU)] | 1 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.9546 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)] | 1 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBR_PROMOCARD) | U_PRJ_ECOM.RAW_VTEX_SSGBR_PROMOCARD | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0272 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBR_PROMOCARD_ID) | U_PRJ_ECOM.RAW_VTEX_SSGBR_PROMOCARD_ID | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0303 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.002 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0027 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0638 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0298 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_CLIENT_PROFILE_DATA) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_CLIENT_PROFILE_DATA | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ID) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ID | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.1056 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_KIT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_KIT | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0064 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_EPP_DETAIL_HIST_TALEND_PRL_2024) | U_PRJ_ECOM.RAW_VTEX_SSG_EPP_DETAIL_HIST_TALEND_PRL_2024 | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.5438 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_EPP_DETAIL_TALEND) | U_PRJ_ECOM.RAW_VTEX_SSG_EPP_DETAIL_TALEND | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA) | U_PRJ_ECOM.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VIEW_VTEX_BR_SHOP_MASTER) | U_PRJ_ECOM.TMP_VIEW_VTEX_BR_SHOP_MASTER | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_EPP2) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_EPP2 | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_19) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_19 | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_9) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_9 | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_TALEND_01) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_TALEND_01 | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_TALEND) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_TALEND | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_EPP_TALEND) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_EPP_TALEND | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0329 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_INV_SEM_INT) | U_PRJ_ECOM.TMP_VTEX_INV_SEM_INT | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0021 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.TMP_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED) | U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.002 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST_ADJ),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MAT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_PROD),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 23 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.3629 | RAW | 0 | [(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 12 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0046 | RAW | 0 | [(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS)] | 9 | 25/08 - 25/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2 | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0148 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT)] | 7 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.RAW_VTEX_PAYMENTS) | OW_LAO.RAW_VTEX_PAYMENTS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 1.8895 | RAW | 0 | [(VIEW - OW_LAO.RAW_VTEX_PAYMENTS_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_GENERATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS)] | 6 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0411 | RAW | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_AR_SMB),(INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PACKAGE),(INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM),(INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT),(INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)] | 6 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL) | U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0139 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL),(INGESTION - JOB.ODS_VTEX_MASTER_DATA_CL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5)] | 6 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0504 | RAW | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER)] | 6 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0613 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG)] | 6 | 25/08 - 25/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0022 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP)] | 5 | 25/08 - 25/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0022 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.1709 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.4119 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER)] | 4 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI) | OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI | LAO EStore | r.bojart |  | yes | 4 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0067 | ODS | 0 | [(PROCEDURE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_GENERATE),(PROCEDURE - OW_LAO.PROC_ODS_STOCKOUT_VTEX_GLOBALBI),(PROCEDURE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_SEDA_GENERATE)] | 3 | 25/08 - 25/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER)] | 3 | 25/08 - 25/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG)] | 3 | 25/08 - 25/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER)] | 3 | 25/08 - 25/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER)] | 3 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0012 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)] | 3 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0011 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 3 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0032 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 3 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.RAW_VTEX_PAYMENTS_FILES) | OW_LAO.RAW_VTEX_PAYMENTS_FILES | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0006 | RAW | 0 | [(PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_FILES_GET),(PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_FILES_DEDUP)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP) | OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(VIEW - OW_LAO.VW_TMP_VTEX_CONCAT),(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_PRODUCT_SKU) | U_PRJ_ECOM.ODS_VTEX_PRODUCT_SKU | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0507 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_PRODUCT),(PROCEDURE - OW_MD.PROC_FT_PRODUCT_STATUS)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_STATUS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_STATUS | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0011 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_AUDIT_VTEX) | U_PRJ_ECOM.RAW_AUDIT_VTEX | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0007 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_OK),(VIEW - U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_NOK)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_CL) | U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_CL | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.015 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_SEDA_VTEX_KIT_COMPONENTS_REGISTRATION) | OW_LAO.ODS_SEDA_VTEX_KIT_COMPONENTS_REGISTRATION | [5 empty] | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 | [(VIEW - OW_LAO.VW_PMS_TESTE)] | 1 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS) | OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS)] | 1 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_SALES) | OW_LAO.ODS_HYBRIS_SALES | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.2 Ingestion HYBRIS | 0.7395 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(INGESTION - JOB.ODS_HYBRIS_SALES),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS)] | 22 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS) | OW_LAO.ODS_HYBRIS_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.2 Ingestion HYBRIS | 0.2854 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS),(INGESTION - JOB.ODS_HYBRIS_PAYMENTS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PAYMENTS),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING)] | 5 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_COMBO) | OW_LAO.ODS_HYBRIS_COMBO | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0003 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 3 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_CANCELLATIONS) | OW_LAO.ODS_HYBRIS_CANCELLATIONS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0221 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_CANCELLATIONS),(INGESTION - JOB.ODS_HYBRIS_CANCELLATIONS)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_OFFERS) | OW_LAO.ODS_HYBRIS_OFFERS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 2.0153 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_OFFERS),(INGESTION - JOB.ODS_HYBRIS_OFFERS)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_PREORDERS) | OW_LAO.ODS_HYBRIS_PREORDERS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0006 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PREORDERS),(INGESTION - JOB.ODS_HYBRIS_PREORDERS)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_REFUNDS) | OW_LAO.ODS_HYBRIS_REFUNDS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0186 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REFUNDS),(INGESTION - JOB.ODS_HYBRIS_REFUNDS)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_RETURNS) | OW_LAO.ODS_HYBRIS_RETURNS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_RETURNS),(INGESTION - JOB.ODS_HYBRIS_RETURNS)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_REWARDS) | OW_LAO.ODS_HYBRIS_REWARDS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.1916 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REWARDS),(INGESTION - JOB.ODS_HYBRIS_REWARDS)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_INSERT) | U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_INSERT | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 1 | 1.3 Ingestion MAGENTO | 0.0002 | TMP | 0 |  | 0 | 25/08 - 25/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO) | U_PRJ_ECOM.ODS_SELA_API_MAGENTO | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45894 | 45894 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0.0097 | ODS | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO),(INGESTION - JOB.ODS_SELA_API_MAGENTO)] | 2 | 25/08 - 25/08
| TABLE | (TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS_HOMOLOG) | OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS) | OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS_HOMOLOG) | OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0015 | TMP | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_VTEX_PROFILE) | OW_LAO.TMP_VTEX_PROFILE | [5 empty] | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - OW_SEDA_S.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS) | OW_SEDA_S.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0099 | ODS | 0 | [(INGESTION - JOB.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 2.882 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_AR)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_B2B) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_B2B | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.3744 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_BR_B2B)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_EPP2) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_EPP2 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 4.1824 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_BR_EPP2)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_PY) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_PY | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0022 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_PY)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_UY) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_UY | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0031 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_FEED_SSG_UY)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.002 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_DOMAIN) | U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_DOMAIN | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0412 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_MASTER_DATA_DOMAIN)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_BY_SKU) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_BY_SKU | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0008 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PRICE_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_PRICE_LIST | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_SSG_BR_PRICE_LIST)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0037 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0809 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0008 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.002 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 2.7504 | ODS | 0 | [(INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_BY_REF_ID) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_BY_REF_ID | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0012 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_CT_TRADEIN) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_CT_TRADEIN | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_CT_TRADEIN) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_CT_TRADEIN | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_COLLECTION) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_COLLECTION | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.353 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_INTEGRATION_RAW_VTEX_SALES_COLLECTION)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0057 | RAW | 0 | [(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 4.4249 | RAW | 0 | [(VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0671 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_2020) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_2020 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_INTEGRATION_RAW_VTEX_SALES_COLLECTION)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 | [(VIEW - U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN)] | 1 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_SEASA_VTEX_CANCEL) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_SEASA_VTEX_CANCEL | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0804 | ODS | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.ODS_SEDA_SOLD_NERP_VS_CHANNEL_VTEX) | OW_LAO.ODS_SEDA_SOLD_NERP_VS_CHANNEL_VTEX | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO_HOMOLOG) | OW_LAO.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO_HOMOLOG | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0018 | ODS | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_ACCESS_CODE_PARTNER_LEVEL_VTEX) | OW_LAO.TMP_ACCESS_CODE_PARTNER_LEVEL_VTEX | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_ACCESS_CODE_PARTNER_LEVEL_VTEX_SELA) | OW_LAO.TMP_ACCESS_CODE_PARTNER_LEVEL_VTEX_SELA | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER_SKU_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER_AGG | LAO EStore | r.bojart |  | yes | 1 | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SKU_AGG | LAO EStore | r.bojart |  | yes | 1 | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_2) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_2 | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0012 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_AGG_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_AGG_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0009 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_DISCOUNT) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_DISCOUNT | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0036 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_ITEM) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0044 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0011 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS_HOMOLOG_2) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_PAYMENTS_HOMOLOG_2 | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0043 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_RATEIO) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_RATEIO | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_SKU_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_SKU_AGG_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_SKU_AGG_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0011 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_TOTAL) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_TOTAL | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0105 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_TOTAL_ITEM) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_TOTAL_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0126 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER_AGG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER_SKU_AGG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_PAYMENTS | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER_AGG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER_SKU_AGG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_PAYMENTS | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_FT_D2C_VTEX_PROMOTION_PROM_NAME_REFERENCE) | OW_LAO.TMP_FT_D2C_VTEX_PROMOTION_PROM_NAME_REFERENCE | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0092 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_FT_D2C_VTEX_PROMOTION_PROM_NAME_REFERENCE_FIX_NULL) | OW_LAO.TMP_FT_D2C_VTEX_PROMOTION_PROM_NAME_REFERENCE_FIX_NULL | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0091 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_PROMOTION_01) | OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_PROMOTION_01 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_PROMOTION_TMP) | OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_PROMOTION_TMP | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_TEMP_20250711) | OW_LAO.TMP_ITEM_COMPONENTS_PO_VTEX_TEMP_20250711 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_ORDER_ITEM_TO_COMPONENTS_PO_VTEX_TEMP_20250711) | OW_LAO.TMP_ORDER_ITEM_TO_COMPONENTS_PO_VTEX_TEMP_20250711 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_PARAMETER_PO_VTEX_TEMP_20250711) | OW_LAO.TMP_PARAMETER_PO_VTEX_TEMP_20250711 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_PAYMENT_VTEX_NERP_SALES_TEMP_20250711) | OW_LAO.TMP_PAYMENT_VTEX_NERP_SALES_TEMP_20250711 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_PROMOTION_01) | OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_PROMOTION_01 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP_20250711) | OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP_20250711 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_PO_VTEX_PROMOTION) | OW_LAO.TMP_PO_VTEX_PROMOTION | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_PROMOTION_VTEX_NERP_SALES_TEMP_20250711) | OW_LAO.TMP_PROMOTION_VTEX_NERP_SALES_TEMP_20250711 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_RP_VTEX_2024_06_01_AND_2025_01_29) | OW_LAO.TMP_RP_VTEX_2024_06_01_AND_2025_01_29 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.105 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_SHIPPING_VTEX_TEMP_20250711) | OW_LAO.TMP_SHIPPING_VTEX_TEMP_20250711 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_VTEX_PAYMENTS_2024_06_01_AND_2025_01_29) | OW_LAO.TMP_VTEX_PAYMENTS_2024_06_01_AND_2025_01_29 | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.028 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.TMP_VTEX_PAYMENT_SKU_FINAL) | OW_LAO.TMP_VTEX_PAYMENT_SKU_FINAL | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0027 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_SEDA_S.ODS_ELASTIC_VTEX_NERP_INTERFACE) | OW_SEDA_S.ODS_ELASTIC_VTEX_NERP_INTERFACE | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0005 | ODS | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_SEDA_S.TMP_ELASTIC_VTEX_NERP_INTERFACE) | OW_SEDA_S.TMP_ELASTIC_VTEX_NERP_INTERFACE | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_SEDA_S.TMP_LINKAPI_VTEX_NERP_INTERFACE_ERRORS) | OW_SEDA_S.TMP_LINKAPI_VTEX_NERP_INTERFACE_ERRORS | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_SEDA_S.TMP_OST_PLUGG_STATUS_COM_VTEX) | OW_SEDA_S.TMP_OST_PLUGG_STATUS_COM_VTEX | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0623 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_SEDA_S.TMP_OST_PLUGG_VTEX) | OW_SEDA_S.TMP_OST_PLUGG_VTEX | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.064 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_SEDA_S.TMP_OST_PLUGG_VTEX_BASE) | OW_SEDA_S.TMP_OST_PLUGG_VTEX_BASE | [5 empty] | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0433 | TMP | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS) | OW_LAO.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.2573 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS),(INGESTION - JOB.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS)] | 2 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_TRADEIN) | OW_LAO.ODS_HYBRIS_TRADEIN | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0083 | ODS | 0 | [(INGESTION - JOB.ODS_HYBRIS_TRADEIN),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_TRADEIN)] | 2 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_PRICING) | OW_LAO.ODS_HYBRIS_PRICING | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | ODS | 0 | [(INGESTION - JOB.ODS_HYBRIS_PRICING)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_CANCELLATIONS) | OW_LAO.RAW_HYBRIS_CANCELLATIONS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0005 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_CANCELLATIONS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_COMBO) | OW_LAO.RAW_HYBRIS_COMBO | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0002 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_OFFERS) | OW_LAO.RAW_HYBRIS_OFFERS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_OFFERS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_PAYMENTS) | OW_LAO.RAW_HYBRIS_PAYMENTS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PAYMENTS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_PREORDERS) | OW_LAO.RAW_HYBRIS_PREORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PREORDERS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_REFUNDS) | OW_LAO.RAW_HYBRIS_REFUNDS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0005 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REFUNDS)] | 1 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP) | U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP_SUB) | U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP_SUB | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45895 | 45895 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 0 |  | 0 | 26/08 - 26/08
| TABLE | (TABLE - OW_SEDA_S.TMP_VTEX_BR_SHOP_MASTER) | OW_SEDA_S.TMP_VTEX_BR_SHOP_MASTER | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0018 | TMP | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_ACCOUNT_TOKEN) | U_PRJ_ECOM.ODS_VTEX_ACCOUNT_TOKEN | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_MARCOM_SPV) | U_PRJ_ECOM.ODS_VTEX_FEED_MARCOM_SPV | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 1.6868 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0069 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 2.9009 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP_LEO) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP_LEO | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP_SALES_ORDER_LIST) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_SHOP_SALES_ORDER_LIST | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.4138 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_TALEND) | U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_TALEND | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO) | U_PRJ_ECOM.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0018 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO_AGG) | U_PRJ_ECOM.ODS_VTEX_NERP_SALES_ORDER_TRACKING_LAO_AGG | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0045 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_PRODUCT_SKU) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_PRODUCT_SKU | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0016 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_COUPON) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_COUPON | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.2916 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP2_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP2_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0128 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0073 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_PRODUCT_SKU) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_PRODUCT_SKU | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0034 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_COUPON) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_COUPON | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.1145 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0763 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ID) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ID | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0268 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ITEMS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ITEMS | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.2596 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_TRANSACTION) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_TRANSACTION | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.045 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_PRODUCT_SKU) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_PRODUCT_SKU | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0199 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_COUPON) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_COUPON | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.5751 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM_HMLG_FIELDS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM_HMLG_FIELDS | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_ID_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_ID_LIST | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_TRANSACTION_INTERACTIONS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_TRANSACTION_INTERACTIONS | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_WAREHOUSE_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_WAREHOUSE_LIST | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_ID_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_ID_LIST | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_TRANSACTION_INTERACTIONS) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_TRANSACTION_INTERACTIONS | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_WAREHOUSE_LIST) | U_PRJ_ECOM.ODS_VTEX_SSG_BR_WAREHOUSE_LIST | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_BRIDGE_COMPLIENCE_RATE) | U_PRJ_ECOM.RAW_VTEX_BRIDGE_COMPLIENCE_RATE | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0009 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_FEED_B2B_INFORMATION) | U_PRJ_ECOM.RAW_VTEX_FEED_B2B_INFORMATION | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_FEED_EPP2_INFORMATION) | U_PRJ_ECOM.RAW_VTEX_FEED_EPP2_INFORMATION | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_FEED_INFORMATION) | U_PRJ_ECOM.RAW_VTEX_FEED_INFORMATION | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.2456 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0067 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0073 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_MARCOM_SPV_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0052 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_PROMOTION) | U_PRJ_ECOM.RAW_VTEX_PROMOTION | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_EM) | U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_EM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SEDA_MASTER_DATA_CL) | U_PRJ_ECOM.RAW_VTEX_SEDA_MASTER_DATA_CL | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0672 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBREPP2_PROMOCARD) | U_PRJ_ECOM.RAW_VTEX_SSGBREPP2_PROMOCARD | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0019 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBREPP2_PROMOCARD_ID) | U_PRJ_ECOM.RAW_VTEX_SSGBREPP2_PROMOCARD_ID | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0018 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT) | U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_KIT | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.003 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_PROMOCARD) | U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_PROMOCARD | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0196 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_PROMOCARD_ID) | U_PRJ_ECOM.RAW_VTEX_SSGBRSHOP_PROMOCARD_ID | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0195 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_CT_COMPANY_DOMAIN) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_CT_COMPANY_DOMAIN | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM_COMPONENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0333 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PACKAGE | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0286 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM_COMPONENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PACKAGE | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_B2B_DETAIL_HIST_TALEND_PRL_2024) | U_PRJ_ECOM.RAW_VTEX_SSG_B2B_DETAIL_HIST_TALEND_PRL_2024 | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0523 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_2023) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_2023 | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 2.9745 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_DETAIL_TALEND) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_DETAIL_TALEND | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0882 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST_AT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST_AT | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0691 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0813 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP_PROMOTION_TAX) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP_PROMOTION_TAX | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_INVENTORY) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_INVENTORY | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_PROMOTION_TAX) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_PROMOTION_TAX | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_CLIENT_PROFILE_DATA) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_CLIENT_PROFILE_DATA | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_LIST) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_LIST | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.2204 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_VAGNER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_VAGNER | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_CDM_REPORT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_CDM_REPORT | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0109 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_CPF) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_CPF | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0013 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0086 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_TALEND) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_DETAIL_TALEND | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0758 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_INVENTORY) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_INVENTORY | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0395 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER2) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER2 | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0005 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0013 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0026 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_ITEM_ATTACHMENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_ITEM_ATTACHMENTS | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_LIST) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_LIST | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0008 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_BR_TROCA_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0053 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_EPP2_DETAIL_HIST_TALEND_PRL_2022) | U_PRJ_ECOM.RAW_VTEX_SSG_EPP2_DETAIL_HIST_TALEND_PRL_2022 | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.1153 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_TRADE_UP_SEASA_ORDER) | U_PRJ_ECOM.RAW_VTEX_TRADE_UP_SEASA_ORDER | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.021 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_TRADE_UP_SEDA_ORDER) | U_PRJ_ECOM.RAW_VTEX_TRADE_UP_SEDA_ORDER | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0823 | RAW | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_RETURNS) | OW_LAO.RAW_HYBRIS_RETURNS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_RETURNS)] | 1 | 27/08 - 27/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_REWARDS) | OW_LAO.RAW_HYBRIS_REWARDS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0006 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REWARDS)] | 1 | 27/08 - 27/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_SALES) | OW_LAO.RAW_HYBRIS_SALES | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0007 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES)] | 1 | 27/08 - 27/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_SALES_HOMOLOG) | OW_LAO.RAW_HYBRIS_SALES_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_ITEMS_DISCOUNTS)] | 1 | 27/08 - 27/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_SALES_MONITORING) | OW_LAO.RAW_HYBRIS_SALES_MONITORING | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0005 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES)] | 1 | 27/08 - 27/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_TRADEIN) | OW_LAO.RAW_HYBRIS_TRADEIN | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_TRADEIN)] | 1 | 27/08 - 27/08
| TABLE | (TABLE - OW_LAO.TMP_ODS_HYBRIS_COMBO) | OW_LAO.TMP_ODS_HYBRIS_COMBO | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO)] | 1 | 27/08 - 27/08
| TABLE | (TABLE - OW_LAO.ODS_HYBRIS_COMBO_VALID) | OW_LAO.ODS_HYBRIS_COMBO_VALID | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
Control Tower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_COMBO_HYBRIS_HOMOLOG) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_COMBO_HYBRIS_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0544 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP_UPDATE) | U_PRJ_ECOM.ODS_SELA_API_MAGENTO_TOTALS_TEMP_UPDATE | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO_UPDATE_TEMP) | U_PRJ_ECOM.ODS_SELA_API_MAGENTO_UPDATE_TEMP | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45896 | 45896 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 0 |  | 0 | 27/08 - 27/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.TMP_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_LINKAPI_VTEX_NERP_INTERFACE_ERRORS) | U_PRJ_ECOM.TMP_LINKAPI_VTEX_NERP_INTERFACE_ERRORS | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_FEED_SSG_BR_SHOP_SALES_ORDER_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_FEED_SSG_BR_SHOP_SALES_ORDER_LIST | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA_TLD) | U_PRJ_ECOM.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA_TLD | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_ORDER_DATA_SBB) | U_PRJ_ECOM.TMP_ODS_VTEX_ORDER_DATA_SBB | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_PRODUCT_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_PRODUCT_SKU | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0011 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_ID | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU_ID | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU_ID_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_CAMPAIGN_AUDIENCE_SKU_ID_LIST | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_ID | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU_ID | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU_ID_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_CAMPAIGN_AUDIENCE_SKU_ID_LIST | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_ID | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_INVENTORY_BY_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_INVENTORY_BY_SKU | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0005 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_ID | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU_ID) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU_ID | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU_ID_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_CAMPAIGN_AUDIENCE_SKU_ID_LIST | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0005 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_SKU_ID_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SHOP_SKU_ID_LIST | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SKU_ID_LIST) | U_PRJ_ECOM.TMP_ODS_VTEX_SSG_BR_SKU_ID_LIST | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_BRSHOP_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_BRSHOP_LIST | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0007 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.TMP_RAW_VTEX_MARCOM_SPV_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SEASA_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SEASA_LIST | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSGBREPP2_PROMOCARD) | U_PRJ_ECOM.TMP_RAW_VTEX_SSGBREPP2_PROMOCARD | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSGBREPP2_PROMOCARD_ID) | U_PRJ_ECOM.TMP_RAW_VTEX_SSGBREPP2_PROMOCARD_ID | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSGBRSHOP_PROMOCARD) | U_PRJ_ECOM.TMP_RAW_VTEX_SSGBRSHOP_PROMOCARD | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0019 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSGBRSHOP_PROMOCARD_ID) | U_PRJ_ECOM.TMP_RAW_VTEX_SSGBRSHOP_PROMOCARD_ID | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0022 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0207 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_01) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_01 | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0784 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_02) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_02 | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_2024) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_2024 | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_AUX) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_AUX | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_AUX_TEMP) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_AUX_TEMP | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_ERROR_2022) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_HIST_TALEND_PRL_ERROR_2022 | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_TALEND) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_DETAIL_TALEND | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0009 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0005 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST__FALSE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_LIST__FALSE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0006 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0005 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_LIST_FALSE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_LIST_FALSE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_LIST_TRUE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_LIST_TRUE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_01) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_01 | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_TALEND) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_TALEND | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0034 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER2 | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_2 | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0011 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_2 | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0005 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0005 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS_2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS_2 | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_UNIQUEID_NULL) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_UNIQUEID_NULL | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_UNIQUE_ID_NULL_CLEAN) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_UNIQUE_ID_NULL_CLEAN | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST__) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST__ | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE_T) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE_T | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT_2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT_2 | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [5 empty] | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - OW_LAO.RAW_HYBRIS_PRICING) | OW_LAO.RAW_HYBRIS_PRICING | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | RAW | 0 |  | 0 | 28/08 - 28/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | TMP | 0 |  | 0 | 28/08 - 28/08
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_OFFERS_DEDUP) | OW_LAO.TMP_HYBRIS_OFFERS_DEDUP | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_PAYMENTS_DEDUP) | OW_LAO.TMP_HYBRIS_PAYMENTS_DEDUP | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_PREORDERS_DEDUP) | OW_LAO.TMP_HYBRIS_PREORDERS_DEDUP | LAO EStore | r.bojart |  | yes | 1 | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_REFUNDS_DEDUP) | OW_LAO.TMP_HYBRIS_REFUNDS_DEDUP | LAO EStore | r.bojart |  | yes | 1 | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_REWARDS_DEDUP) | OW_LAO.TMP_HYBRIS_REWARDS_DEDUP | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_GTM) | U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_GTM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0.0012 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_SUB) | U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_SUB | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45897 | 45897 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0.0002 | TMP | 0 |  | 0 | 28/08 - 28/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING_2) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING_2 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SKU_ID_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_SKU_ID_LIST | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_WAREHOUSE_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_WAREHOUSE_LIST | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SKU_ID_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SKU_ID_LIST | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_WAREHOUSE_LIST) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_WAREHOUSE_LIST | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_EPP_DETAIL_HIST_TALEND) | U_PRJ_ECOM.TMP_RAW_VTEX_SSG_EPP_DETAIL_HIST_TALEND | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0227 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_MARCOM_SPV) | U_PRJ_ECOM.TMP_VTEX_FEED_MARCOM_SPV | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_B2B_TALEND) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_B2B_TALEND | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0005 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_1) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_1 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_10) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_10 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_11) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_11 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_12) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_12 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_13) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_13 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_14) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_14 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_15) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_15 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_16) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_16 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_17) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_17 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_18) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_18 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_2) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_2 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_20) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_20 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0007 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_21) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_21 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_22) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_22 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_23) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_23 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_3) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_3 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_4) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_4 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_5) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_5 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_6) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_6 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_7) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_7 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_8) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_8 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV1) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV1 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV2) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV2 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV3) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV3 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV4) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV4 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV5) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV5 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV6) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV6 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV7) | U_PRJ_ECOM.TMP_VTEX_FEED_SSG_BR_SHOP_DEV7 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD) | U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_ID) | U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_ID | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_ID_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_ID_STATUS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBREPP2_PROMOCARD_STATUS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD) | U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_1) | U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_1 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_2) | U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_2 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0017 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_ID_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_ID_STATUS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0019 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBRSHOP_PROMOCARD_STATUS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_2) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_2 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0152 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_2) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_2 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0039 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_3) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_3 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0026 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_ID_STATUS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_STATUS) | U_PRJ_ECOM.TMP_VTEX_SSGBR_PROMOCARD_STATUS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_AR_CT_ORDER_DOMAIN) | U_PRJ_ECOM.TMP_VTEX_SSG_AR_CT_ORDER_DOMAIN | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_B2B_PROMOTION_ITEM) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_B2B_PROMOTION_ITEM | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP2_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP2_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ID) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ID | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ITEMS) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_EMPLOYEE_LIMIT_LIST_ITEMS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_PROMOTION_ITEM) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_EPP_PROMOTION_ITEM | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_PAYMENT_TRANSACTION) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_PAYMENT_TRANSACTION | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0003 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_PRICE_LIST) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_PRICE_LIST | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_PROMOTION_ITEM) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_PROMOTION_ITEM | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0002 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_FEED_QTD_JSON) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_FEED_QTD_JSON | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_FIXED_PRICES) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_FIXED_PRICES | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0035 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_INTERACTIONS) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_INTERACTIONS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.1125 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PRICE_LIST) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PRICE_LIST | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_ITEM) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_ITEM | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0004 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_T1) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_T1 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_T2) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_T2 | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0008 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0841 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_TRANSACTION_INTERACTIONS) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_TRANSACTION_INTERACTIONS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SKU_BY_REF_ID) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_SKU_BY_REF_ID | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0181 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_TRANSACTION_INTERACTIONS) | U_PRJ_ECOM.TMP_VTEX_SSG_BR_TRANSACTION_INTERACTIONS | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_VTEX_VIRTUAL_INV) | U_PRJ_ECOM.TMP_VTEX_VIRTUAL_INV | [5 empty] | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.1 Ingestion VTEX | 0.0021 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_SALES_AGG_DEDUP) | OW_LAO.TMP_HYBRIS_SALES_AGG_DEDUP | LAO EStore | r.bojart |  | yes | 1 | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0003 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_SALES_DEDUP) | OW_LAO.TMP_HYBRIS_SALES_DEDUP | LAO EStore | r.bojart |  | yes | 1 | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_SALES_DELETE_IDS) | OW_LAO.TMP_HYBRIS_SALES_DELETE_IDS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_SALES_VOUCHER_CODE_AGG) | OW_LAO.TMP_HYBRIS_SALES_VOUCHER_CODE_AGG | LAO EStore | r.bojart |  | yes | 1 | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0.0006 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - OW_LAO.TMP_VL_ODS_HYBRIS_SALES_ALERT) | OW_LAO.TMP_VL_ODS_HYBRIS_SALES_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_UPDATE) | U_PRJ_ECOM.TMP_ODS_SELA_API_MAGENTO_UPDATE | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45898 | 45898 | ['[]'] | 0 | 1.3 Ingestion MAGENTO | 0.0002 | TMP | 0 |  | 0 | 29/08 - 29/08
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 1.3264 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.PROC_D2C_DIM_SOLD_TO),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(VIEW - OW_LAO.VW_PMS_TESTE),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_TESTE_),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING),(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE),(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(VIEW - OW_LAO.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG)] | 37 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 1.6432 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_OUTBOUND_UPDATE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME),(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(PROCEDURE - OW_LAO.PROC_D2C_DIM_SOLD_TO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_OUTBOUND_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION)] | 19 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST) | OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 18.4249 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_FORECAST_OST),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT)] | 6 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER) | OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.0054 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING),(INGESTION - JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_FOLDER),(INGESTION - JOB.ODS_NERP_ZLLEB57910_CLAIM_FOLDER),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | 5 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.1826 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN),(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(INGESTION - JOB.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS),(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 1.4001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(INGESTION - JOB.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN),(INGESTION - JOB.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER) | OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.0105 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZRCOS43400_TARGET_FOLDER),(VIEW - OW_LAO.VIEW_NERP_ZRCOS43400_TARGET),(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW) | OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.4139 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_INVENTORY),(INGESTION - JOB.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS),(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_MB51_GR_FOLDER) | OW_LAO.ODS_NERP_MB51_GR_FOLDER | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.6733 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI),(INGESTION - JOB.RAW_DATA_NERP_MB51_GR_FOLDER),(INGESTION - JOB.ODS_NERP_MB51_GR_FOLDER)] | 3 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 6.0427 | RAW | 0 | [(INGESTION - JOB.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING),(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING)] | 3 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES) | OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.2042 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] | 2 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE) | OW_SEDA_S.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.0072 | RAW | 0 | [(INGESTION - JOB.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE),(INGESTION - JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_MAINTENANCE)] | 2 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.2907 | RAW | 0 | [(INGESTION - JOB.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN),(INGESTION - JOB.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)] | 2 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT) | OW_LAO.ODS_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.1437 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.3371 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_MB51_GR_FOLDER) | OW_LAO.RAW_DATA_NERP_MB51_GR_FOLDER | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.6733 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLLEB57910_CLAIM_FOLDER) | OW_LAO.RAW_DATA_NERP_ZLLEB57910_CLAIM_FOLDER | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.0054 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | OW_LAO.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.0049 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM) | U_PRJ_ECOM.FT_ECOM_ORDER_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.5176 | FT | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(INGESTION - JOB.FT_ECOM_ORDER_ITEM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_REFERENCE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX)] | 48 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_SALES) | OW_LAO.TF_D2C_NERP_SALES | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 2.9117 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_COUPON_KPI),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_MD.PROC_INGESTION_DIM_PRODUCT_GLOBAL),(VIEW - OW_LAO.VW_PMS_TESTE),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(PROCEDURE - OW_LAO.PROC_INSERT_SALES_CANCELLED_FROM_ODS),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI),(PROCEDURE - OW_MD.PROC_INGESTION_DIM_PRODUCT_ESTORE),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PO_TARGET_LAUNCH_S25),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_REWARDS_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_SELLOUT_PLATFORM_KPI),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_TESTE),(PROCEDURE - OW_LAO.PROC_TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_LAO.PROC_INSERT_SALES_FROM_ODS),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_FT_D2C_VTEX_O2O_SALES_KPI),(VIEW - OW_LAO.VW_TAB1_PMS_DW),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_O2O_SALES_KPI),(VIEW - OW_SEDA_S.VW_SEDA_PREORDER),(PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_MD.PROC_DIM_PRODUCT_ESTORE_GLOBAL)] | 37 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN) | OW_LAO.TF_D2C_PO_VTEX_TRADE_IN | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0206 | TF | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_TST),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_SELLOUT_PLATFORM_KPI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST_ADJ),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MAT),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_PROD),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX)] | 29 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION) | OW_LAO.FT_D2C_VTEX_PROMOTION | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 3.3047 | FT | 0 | [(VIEW - OW_LAO.VW_PMS_TESTE),(PROCEDURE - OW_LAO.PROC_TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES),(VIEW - OW_LAO.VW_TAB2_PMS_DW),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES)] | 11 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_MD.DIM_SALES_CHANNEL) | OW_MD.DIM_SALES_CHANNEL | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI)] | 9 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TF_NERP_GROSS_MARGIN) | OW_LAO.TF_NERP_GROSS_MARGIN | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.2184 | TF | 0 | [(VIEW - OW_LAO.VW_TAB3_PMS_DW),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_DIM_TAX_GROSS_MARGIN),(PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA),(PROCEDURE - OW_LAO.PROC_TF_NERP_GROSS_MARGIN_MONITORING_DATASOURCE),(VIEW - OW_LAO.VW_PMS_TESTE),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES)] | 7 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO) | OW_LAO.DIM_PRODUCT_MAPPING_LAO | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.016 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIM_PRODUCT_MAPPING_LAO_UPDATE),(PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO),(PROCEDURE - OW_MD.PROC_DIM_PRODUCT_ESTORE_GLOBAL),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU) | OW_LAO.TF_D2C_PAYMENT_ITAU | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0384 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_TESTE),(PROCEDURE - OW_LAO.PROC_INSERT_SALES_CANCELLED_FROM_ODS),(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU),(PROCEDURE - OW_LAO.PROC_INSERT_SALES_FROM_ODS)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_ORDER_STATUS) | OW_MD.DIM_VTEX_ORDER_STATUS | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.001 | DIM | 0 | [(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_MD.PROC_DIM_VTEX_ORDER_STATUS),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS) | OW_MD.DIM_VTEX_PAYMENT_STATUS | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0009 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER) | OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0007 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN) | OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0008 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION) | OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0954 | DIM | 0 | [(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TF_D2C_VTEX_PAYMENT_SKU) | OW_LAO.TF_D2C_VTEX_PAYMENT_SKU | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.606 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_LAO.VIEW_VTEX_PAYMENTS)] | 3 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_AR_TABLE_MONTH) | OW_LAO.FT_D2C_AR_TABLE_MONTH | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.5402 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT2),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1)] | 2 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_AR_TABLE_WEEK) | OW_LAO.FT_D2C_AR_TABLE_WEEK | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.5743 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT2)] | 2 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TF_D2C_PO_VTEX_RDD) | OW_LAO.TF_D2C_PO_VTEX_RDD | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.1459 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS)] | 2 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_AR_ONE_VIEW_TABLE) | OW_LAO.FT_D2C_AR_ONE_VIEW_TABLE | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0227 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_GSCM_INVENTORY) | OW_LAO.FT_D2C_GSCM_INVENTORY | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.1656 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_GSCM_INVENTORY)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_DELIVERY_PENDING) | OW_LAO.FT_D2C_NERP_DELIVERY_PENDING | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0013 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_GSCM_PSI) | OW_LAO.FT_D2C_NERP_GSCM_PSI | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.2972 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_INVENTORY) | OW_LAO.FT_D2C_NERP_INVENTORY | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.314 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_INVENTORY)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_LEAD_TIME) | OW_LAO.FT_D2C_NERP_LEAD_TIME | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0641 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_ORDER_PENDING) | OW_LAO.FT_D2C_NERP_ORDER_PENDING | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0037 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_ORDER_PENDING_OVERVIEW) | OW_LAO.FT_D2C_NERP_ORDER_PENDING_OVERVIEW | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.2444 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_TO_STOCK_OVERVIEW_BY_PLANT) | OW_LAO.FT_D2C_NERP_TO_STOCK_OVERVIEW_BY_PLANT | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0063 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_WH_OPERATION_PENDING) | OW_LAO.FT_D2C_NERP_WH_OPERATION_PENDING | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.001 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.FT_D2C_WOS) | OW_LAO.FT_D2C_WOS | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0091 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_01) | OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_01 | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0218 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_02) | OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_02 | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.022 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TF_D2C_GSCM_TO_WOS) | OW_LAO.TF_D2C_GSCM_TO_WOS | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0035 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS)] | 1 |  | 01/09 - 01/09
Global D2C BI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_SALES) | OW_LAO.ODS_GLOBAL_BI_SALES | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 1.6817 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS),(VIEW - OW_LAO.VIEW_ODS_GLOBAL_BI_SALES),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW),(INGESTION - JOB.ODS_GLOBAL_BI_SALES),(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(VIEW - OW_LAO.VIEW_ECOM_ODS_GLOBAL_BI_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_GLOBALBI_UPDATE),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2),(PROCEDURE - OW_LAO.PROC_ODS_GLOBAL_BI_SALES_EMPTY_DIMENSIONS_ALERT),(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_GLOBALBI_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS)] | 13 |  | 01/09 - 01/09
Global D2C BI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL) | OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0042 | ODS | 0 | [(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_ALL),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2),(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_ALL)] | 5 |  | 01/09 - 01/09
| TABLE | (TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS) | U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0019 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT)] | 5 |  | 01/09 - 01/09
Global D2C BI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT) | OW_LAO.ODS_GLOBAL_BI_STOCKOUT | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.8038 | ODS | 0 | [(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(INGESTION - JOB.ODS_GLOBAL_BI_STOCKOUT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PBI),(PROCEDURE - OW_LAO.PROC_D2C_FT_STOCKOUT)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2) | OW_LAO.ODS_AFTER_SALES_REFUND_EPP2 | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0004 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREPP2)] | 3 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST) | OW_LAO.ODS_AFTER_SALES_REFUND_EST | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0004 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2ESTUDANTES),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP)] | 3 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_RESID) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_RESID | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0024 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND)] | 2 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_D2C_AR_TABLE_MONTH) | OW_LAO.TMP_D2C_AR_TABLE_MONTH | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.4415 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT2),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1)] | 2 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_D2C_AR_TABLE_WEEK) | OW_LAO.TMP_D2C_AR_TABLE_WEEK | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.5614 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1),(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT2)] | 2 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_MD.ODS_MP_ESTORE) | OW_MD.ODS_MP_ESTORE | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0007 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI),(PROCEDURE - OW_MD.PROC_INGESTION_ODS_MP_ESTORE)] | 2 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_MONTH) | OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_MONTH | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_WEEK) | OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_WEEK | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH) | OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_WEEK) | OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_WEEK | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)] | 1 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_CONSOLIDATED) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_CONSOLIDATED | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0129 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | 1 |  | 01/09 - 01/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE_DISCOUNT) | OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE_DISCOUNT | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0075 | TMP | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_ODS_SALES_LISTINGS) | OW_LAO.TMP_ODS_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_BRSHOP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_BRSHOP | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0005 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_B2B) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_B2B | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0389 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_BREA) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_BREA | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_BRSHOP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_BRSHOP | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.4324 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_B2B) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_B2B | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0012 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BREA) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BREA | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_EPP2) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_EPP2 | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0011 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_MKP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_MKP | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.001 | RAW | 0 |  | 0 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_PARC) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_PARC | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 1 | 3.1 Migrar ph1 | 0.0002 | RAW | 0 |  | 0 |  | 01/09 - 01/09
Control Tower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 3.679 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_NAME_AJUSTE),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_ODS_SELA_CUSTOM_ORDERS_ITEMS_UPDATE),(PROCEDURE - OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_OUTBOUND_UPDATE),(PROCEDURE - OW_LAO.PROC_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - U_PRJ_ECOM.PROC_RAW_ECOM_HQ_ORDERS_TRADEIN_FEED),(VIEW - OW_LAO.VW_APPSFLYER_IN_APP_EVENTS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS_NERP),(PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_MONITORING_DATASOURCE),(PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_STATUS_CANCELED),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_EMPTY_DIMENSIONS_ALERT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MAT),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW),(PROCEDURE - U_PRJ_ECOM.PROC_ECOM_HQ_ORDERS_PRODUCTS_COMBO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI),(PROCEDURE - OW_LAO.PROC_DIVISION_NERP_CONTROL_TOWER_STATUS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_TAXES_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ),(PROCEDURE - OW_LAO.PROC_BLACK_FRIDAY_PBI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_CHECK_DATASOURCE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_CHECK_DATASOURCE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_TF_PO_COUPON_ID_CONTROL_TOWER_LIST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PBI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_PROD),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_DEPARA),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_TST),(VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIM_PRODUCT_MAPPING_LAO_UPDATE),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_GLOBALBI_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ_BKP10032025),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_ITEMS_EXCLUSIVES_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE),(PROCEDURE - OW_LAO.PROC_CHECK_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PREMIUM_MODELS_UPDATE),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS)] | 89 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_PAYMENT_FUNNEL) | OW_LAO.ODS_PAYMENT_FUNNEL | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.3013 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP),(INGESTION - JOB.ODS_PAYMENT_FUNNEL),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP),(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS)] | 10 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_SALES_CAMPAIGN) | OW_LAO.ODS_SALES_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.2956 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V2),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V3),(INGESTION - JOB.TMP_CAMPAIGN_NAME),(INGESTION - JOB.ODS_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_NAME_AJUSTE),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_DAILY_CHECK),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN)] | 10 |  | 01/09 - 01/09
| TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA) | U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0476 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL)] | 8 |  | 01/09 - 01/09
| TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA) | U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.2827 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX)] | 8 |  | 01/09 - 01/09
| TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA) | U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0482 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX)] | 8 |  | 01/09 - 01/09
| TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA) | U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.2811 | ODS | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023)] | 8 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_ORDERS_VISUAR) | OW_LAO.ODS_ORDERS_VISUAR | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0135 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR),(INGESTION - JOB.ODS_ORDERS_VISUAR),(INGESTION - JOB.RAW_ORDERS_VISUAR),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_ODS_ORDERS_VISUAR)] | 7 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS) | OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS),(INGESTION - JOB.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS),(INGESTION - JOB.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS),(INGESTION - JOB.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS),(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_ITEMS_EXCLUSIVES_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 6 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES) | OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0284 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL)] | 6 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS) | OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.098 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL)] | 6 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS) | OW_LAO.RAW_APPLYER_IN_APP_EVENTS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 6.625 | RAW | 0 | [(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEDA),(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEM),(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEPR),(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SECH),(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SAMCOL),(VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEASA)] | 6 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES) | OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0272 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA)] | 6 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS) | OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.4029 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL),(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY)] | 6 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_SALES_CAMPAIGN) | OW_LAO.TMP_SALES_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.2806 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN),(INGESTION - JOB.TMP_CAMPAIGN_NAME),(INGESTION - JOB.TMP_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_NAME_AJUSTE),(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME)] | 6 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS) | OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0516 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PREMIUM_MODELS_UPDATE),(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS),(PROCEDURE - OW_LAO.PROC_ODS_LAO_PREMIUM_PRODUCTS_TABLE_FROM_GSCM_UPDATE)] | 5 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS) | OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0191 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS_VALIDATION),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_ODS_SELA_CUSTOM_ORDERS_ITEMS_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS)] | 5 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.021 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2RESIDENCIAL),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2PARCERIAS)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC) | OW_LAO.ODS_AFTER_SALES_REFUND_PARC | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0003 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2PARCERIAS),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2RESIDENCIAL)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE) | OW_LAO.ODS_ERP_EXCHANGE_RATE | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0154 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE),(PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE_BKP),(PROCEDURE - OW_LAO.PROC_ODS_EXCHANGE_RATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_FT_AP2_EXCHANGE_RATE_HOMOLOG)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN) | OW_LAO.ODS_TARGETS_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0016 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.ODS_TARGETS_CAMPAIGN),(INGESTION - JOB.TMP_TARGETS_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_DIM_TARGETS_CAMPAIGN_CADASTRA_UPDATE)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR) | OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN),(INGESTION - JOB.TMP_CAMPAIGN_NAME),(INGESTION - JOB.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN)] | 4 |  | 01/09 - 01/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0158 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_GLOBALBI_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_OUTBOUND_UPDATE_HOMOLOG)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME) | OW_LAO.TMP_UPDATE_CAMPAIGN_NAME | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME),(INGESTION - JOB.TMP_UPDATE_CAMPAIGN_NAME),(INGESTION - JOB.TMP_CAMPAIGN_NAME),(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN)] | 4 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND) | OW_LAO.ODS_AFTER_SALES_REFUND | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0028 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND)] | 3 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B) | OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B | [5 empty] | Done |  | 1 | 1 | 45901 | 45901 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0003 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRB2B),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP)] | 3 |  | 01/09 - 01/09
| TABLE | (TABLE - OW_LAO.TMP_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI) | OW_LAO.TMP_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.0008 | TMP | 0 |  | 0 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_NERP_ZRCOS43400_TARGET_FOLDER) | OW_LAO.TMP_NERP_ZRCOS43400_TARGET_FOLDER | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.0005 | TMP | 0 |  | 0 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_NERP_ZLLEB57910_CLAIM_MAINTENANCE) | OW_SEDA_S.RAW_DATA_NERP_ZLLEB57910_CLAIM_MAINTENANCE | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.0072 | RAW | 0 |  | 0 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | OW_SEDA_S.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.2907 | RAW | 0 |  | 0 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN) | OW_SEDA_S.TMP_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 1.4 Ingestion NERP | 0.0005 | TMP | 0 |  | 0 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 7.6947 | RAW | 0 | [(VIEW - OW_LAO.VW_SDU_RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING),(INGESTION - JOB.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN) | OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0094 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_TF_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI_UNPIVOT),(PROCEDURE - OW_LAO.PROC_TF_NERP_ZRCOS43400_SALES_PROGRESS_KPI_UNPIVOT_AGG_DIVISION_GROUP),(INGESTION - JOB.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER) | OW_SEDA_S.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.4483 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER),(INGESTION - JOB.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER),(VIEW - OW_MD.VW_PRICE_MONITORING_AUDIT_PROCESS)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZLMKF03006_CONDITION_CALC) | OW_LAO.ODS_NERP_ZLMKF03006_CONDITION_CALC | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0036 | RAW | 0 | [(INGESTION - JOB.RAW_DATA_NERP_ZLMKF03006_CONDITION_CALC),(INGESTION - JOB.ODS_NERP_ZLMKF03006_CONDITION_CALC)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS) | OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 1.2433 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_AR_CLEARED),(INGESTION - JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.2099 | ODS | 0 | [(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO) | OW_LAO.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0224 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM) | OW_LAO.ODS_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.003 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_LAO.RAW_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 1.9029 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER) | OW_LAO.RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.3892 | RAW | 0 | [(VIEW - OW_LAO.VW_SDU_RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER)] | 1 |  | 02/09 - 02/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0007 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.TMP_NERP_ZLLEJ50090_OUTBOUND_TRACKING | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0031 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS) | OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0113 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_MELI_COLETAS) | OW_LAO.TF_D2C_MELI_COLETAS | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0013 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_DAILY_SALES_KPI) | OW_LAO.TF_D2C_NERP_DAILY_SALES_KPI | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0553 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME) | OW_LAO.TF_D2C_NERP_LEAD_TIME | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.3019 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_01) | OW_LAO.TF_D2C_NERP_LEAD_TIME_01 | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.2866 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_02) | OW_LAO.TF_D2C_NERP_LEAD_TIME_02 | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.3125 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_03) | OW_LAO.TF_D2C_NERP_LEAD_TIME_03 | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.334 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_01) | OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_01 | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.1579 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_02) | OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_02 | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.2431 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_SALES_BY_CHANNEL_KPI) | OW_LAO.TF_D2C_NERP_SALES_BY_CHANNEL_KPI | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0081 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_SALES_BY_HOUR_KPI) | OW_LAO.TF_D2C_NERP_SALES_BY_HOUR_KPI | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.2828 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_TO_STOCK_OVERVIEW) | OW_LAO.TF_D2C_NERP_TO_STOCK_OVERVIEW | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0068 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_TO_WOS) | OW_LAO.TF_D2C_NERP_TO_WOS | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0077 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_WEEKLY_SALES_KPI) | OW_LAO.TF_D2C_NERP_WEEKLY_SALES_KPI | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.1895 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TF_WAREHOUSE_OPERATION) | OW_LAO.TF_WAREHOUSE_OPERATION | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.2893 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOCK) | OW_MD.DIM_VTEX_PURCHASE_ORDER_DOCK | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.FT_NERP_SALES_PROGRESS_KPI) | OW_LAO.FT_NERP_SALES_PROGRESS_KPI | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0006 | FT | 0 |  | 0 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.FT_VTEX_BR_SHOP_TMP) | OW_LAO.FT_VTEX_BR_SHOP_TMP | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0751 | FT | 0 |  | 0 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.FT_VTEX_EPP_TMP) | OW_LAO.FT_VTEX_EPP_TMP | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0084 | FT | 0 |  | 0 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_SEDA_S.FT_VTEX_BR_SHOP_MASTER) | OW_SEDA_S.FT_VTEX_BR_SHOP_MASTER | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.5447 | FT | 0 |  | 0 |  | 02/09 - 02/09
| TABLE | (TABLE - U_PRJ_ECOM.MAP_CANCELLATION_MESSAGE) | U_PRJ_ECOM.MAP_CANCELLATION_MESSAGE | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 1 | 2.1 Migrar ph1 | 0.0001 | MAP | 0 |  | 0 |  | 02/09 - 02/09
| TABLE | (TABLE - U_PRJ_ECOM.FT_ECOM_ORDER) | U_PRJ_ECOM.FT_ECOM_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 1.3795 | FT | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP05052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_RETROATIVO_TST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(INGESTION - JOB.FT_ECOM_ORDER),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_BI),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_PLATFORM_SEDA),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_REFERENCE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADEIN_PAYMENT),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_SL),(VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_bkp26052022),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_SYNAPCON),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_EPP_STATUS_NEW_RULE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP15062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1)] | 74 |  | 02/09 - 02/09
| TABLE | (TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY) | U_PRJ_ECOM.DIM_SUBSIDIARY | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0002 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - OW_LAO.VIEW_ECOM_EXCHANGE_RATE),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(PROCEDURE - U_PRJ_ECOM.PROC_DIM_EXCHANGE_RATE_RAWDATA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG),(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(PROCEDURE - OW_LAO.PROC_CHECK_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02)] | 63 |  | 02/09 - 02/09
| TABLE | (TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE) | U_PRJ_ECOM.DIM_EXCHANGE_RATE | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.003 | DIM | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP05052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_EPP_STATUS_NEW_RULE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_PLATFORM_SEDA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP15062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_RETROATIVO_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_bkp26052022),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707),(VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_SL),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT)] | 50 |  | 02/09 - 02/09
| TABLE | (TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT) | U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.8166 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(INGESTION - JOB.FT_ECOM_ORDER_PAYMENT),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_SYNAPCON),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADEIN_PAYMENT)] | 43 |  | 02/09 - 02/09
| TABLE | (TABLE - U_PRJ_ECOM.DIM_CUSTOMER) | U_PRJ_ECOM.DIM_CUSTOMER | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.6124 | DIM | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST),(VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023),(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707)] | 37 |  | 02/09 - 02/09
Control Tower | TABLE | (TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING) | OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(INGESTION - JOB.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS),(VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG)] | 30 |  | 02/09 - 02/09
| TABLE | (TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT) | U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0486 | FT | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(INGESTION - JOB.FT_ECOM_ORDER_KIT_COMPONENT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_REFERENCE),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023)] | 11 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING) | OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP_HOMOLOG)] | 6 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME) | OW_LAO.DIM_LAO_CRP_CS_STORENAME | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_STORENAME_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING)] | 5 |  | 02/09 - 02/09
Control Tower | TABLE | (TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER) | OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_DELIVERY_MODE_DIM_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 5 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING) | OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS)] | 5 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA) | OW_LAO.ODS_AFTER_SALES_REFUND_BREA | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREA)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL) | OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.005 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOPMKTPL),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.1295 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOP)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0677 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRB2B)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREA),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.4111 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOPMKTPL),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2 | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0162 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREPP2)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0238 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2ESTUDANTES)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS) | OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0103 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2MEMBERS)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS) | OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0003 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2MEMBERS)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_APPSFLYER_IN_APP_EVENTS) | OW_LAO.ODS_APPSFLYER_IN_APP_EVENTS | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 6.625 | RAW | 0 | [(VIEW - OW_LAO.VW_APPSFLYER_IN_APP_EVENTS),(INGESTION - JOB.RAW_APPLYER_IN_APP_EVENTS),(INGESTION - JOB.ODS_APPSFLYER_IN_APP_EVENTS)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS) | OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0012 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.ODS_TARGETS_CAMPAIGN),(INGESTION - JOB.ODS_CAMPAIGN_TARGET_PRODUCTS)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS) | OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_FEED_SEND_ESTORE) | OW_LAO.RAW_FEED_SEND_ESTORE | LAO EStore | r.bojart |  | yes | 4 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 1.6842 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ_BKP10032025),(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ),(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_SAMPLE_HQ)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS) | OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0238 | RAW | 0 | [(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS) | OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.4467 | RAW | 0 | [(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_CUT) | OW_LAO.TMP_CAMPAIGN_CUT | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V3),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V2),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_NAME) | OW_LAO.TMP_CAMPAIGN_NAME | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME),(INGESTION - JOB.TMP_CAMPAIGN_NAME)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS) | OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.002 | TMP | 0 | [(INGESTION - JOB.ODS_CAMPAIGN_TARGET_CHANNELS),(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR) | OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0014 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.ODS_TARGETS_CAMPAIGN),(INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR) | OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0012 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.ODS_TARGETS_CAMPAIGN),(INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR)] | 3 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_RESID) | OW_LAO.ODS_AFTER_SALES_REFUND_RESID | [5 empty] | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND),(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_CHANNELS) | OW_LAO.ODS_CAMPAIGN_TARGET_CHANNELS | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.002 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.ODS_CAMPAIGN_TARGET_CHANNELS)] | 2 |  | 02/09 - 02/09
Global D2C BI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_DA) | OW_LAO.ODS_GLOBAL_BI_TRAFFIC_DA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0034 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_DA),(INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_DA)] | 2 |  | 02/09 - 02/09
Global D2C BI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_MX) | OW_LAO.ODS_GLOBAL_BI_TRAFFIC_MX | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.004 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_MX),(INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_MX)] | 2 |  | 02/09 - 02/09
Global D2C BI | TABLE | (TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_VD) | OW_LAO.ODS_GLOBAL_BI_TRAFFIC_VD | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0037 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_VD),(INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_VD)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT) | OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0009 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(INGESTION - JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT)] | 2 |  | 02/09 - 02/09
Control Tower | TABLE | (TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM) | OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0007 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(INGESTION - JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM)] | 2 |  | 02/09 - 02/09
Control Tower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0618 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG)] | 2 |  | 02/09 - 02/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0022 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ALERT) | OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(INGESTION - JOB.TMP_MONITORING_BI_LAO_PROCCESS_ALERT),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT)] | 2 |  | 02/09 - 02/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE) | OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0906 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_PAYMENT_PAYMENT_TYPE) | OW_LAO.TMP_PAYMENT_PAYMENT_TYPE | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP_HOMOLOG)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_PAYMENT_PAY_GATEWAY) | OW_LAO.TMP_PAYMENT_PAY_GATEWAY | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_TARGETS_CAMPAIGN) | OW_LAO.TMP_TARGETS_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0016 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.TMP_TARGETS_CAMPAIGN)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_UPDATE_ID_CAMPAIGN) | OW_LAO.TMP_UPDATE_ID_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 | [(INGESTION - JOB.TMP_CAMPAIGN_NAME),(INGESTION - JOB.TMP_UPDATE_ID_CAMPAIGN)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_PRODUCTS_COMBO | LAO EStore | r.bojart |  | yes | 4 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0082 | RAW | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - U_PRJ_ECOM.PROC_ECOM_HQ_ORDERS_PRODUCTS_COMBO)] | 2 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS) | OW_LAO.ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.003 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO) | OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0005 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS) | OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY) | OW_LAO.ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0003 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_SELA_SALES_COUPONS) | OW_LAO.ODS_SELA_SALES_COUPONS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0009 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_SALES_COUPONS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.ODS_SELA_SALES_COUPONS_ITEMS) | OW_LAO.ODS_SELA_SALES_COUPONS_ITEMS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0004 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SELA_SALES_COUPONS_ITEMS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_FILES_MINIO) | OW_LAO.RAW_FILES_MINIO | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.027 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_LAO_CRP_CS_STORENAME) | OW_LAO.RAW_LAO_CRP_CS_STORENAME | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_STORENAME_UPDATE)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_LAO_CRP_CS_VOUCHER_COUPON) | OW_LAO.RAW_LAO_CRP_CS_VOUCHER_COUPON | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_VOUCHER_COUPON_UPDATE)] | 1 |  | 02/09 - 02/09
Control Tower | TABLE | (TABLE - OW_LAO.RAW_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER) | OW_LAO.RAW_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_DELIVERY_MODE_DIM_UPDATE)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_LAO_DIM_PRODUCT_MAPPING_APOIO) | OW_LAO.RAW_LAO_DIM_PRODUCT_MAPPING_APOIO | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0004 | INPUT | 0 | [(PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS) | OW_LAO.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_LAO_PRODUCT_PREMIUM_ITEMS) | OW_LAO.RAW_LAO_PRODUCT_PREMIUM_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.RAW_ORDERS_VISUAR) | OW_LAO.RAW_ORDERS_VISUAR | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0135 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_ORDERS_VISUAR)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS) | OW_LAO.TMP_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45902 | 45902 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)] | 1 |  | 02/09 - 02/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_SEDA_S.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0053 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRCOA20250_PA_ALLOC_RES) | OW_SEDA_S.ODS_NERP_ZRCOA20250_PA_ALLOC_RES | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0064 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZRCOA20250_PA_ALLOC_RES)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO) | OW_SEDA_S.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0343 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW) | OW_SEDA_S.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0333 | ODS | 0 | [(INGESTION - JOB.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS) | OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0016 | ODS | 0 | [(INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER) | OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0003 | ODS | 0 | [(INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER) | OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0003 | ODS | 0 | [(INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER) | OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0005 | ODS | 0 | [(INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM) | OW_SEDA_S.TMP_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0014 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_SELLIN_2022) | OW_LAO.ODS_NERP_SELLIN_2022 | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0033 | ODS | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_SELLIN_2022_TMP) | OW_LAO.ODS_NERP_SELLIN_2022_TMP | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0038 | ODS | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZLLEB57970_CLAIM_ANALISYS) | OW_LAO.ODS_NERP_ZLLEB57970_CLAIM_ANALISYS | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0008 | ODS | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA) | OW_LAO.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.01 | ODS | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.ODS_SEDA_CURRENT_PRICE_NERP) | OW_LAO.ODS_SEDA_CURRENT_PRICE_NERP | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.001 | ODS | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLMKF03006_CONDITION_CALC) | OW_LAO.RAW_DATA_NERP_ZLMKF03006_CONDITION_CALC | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0036 | RAW | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT) | OW_LAO.RAW_DATA_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0 | RAW | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM) | OW_LAO.RAW_DATA_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.2327 | RAW | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_TMP) | OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_TMP | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0396 | RAW | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING) | OW_LAO.DIM_PAYMENT_TYPE_MAPPING | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP)] | 5 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING) | OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.7779 | FT | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] | 5 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_AFFILIATE) | OW_MD.DIM_VTEX_AFFILIATE | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0012 | DIM | 0 | [(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE)] | 4 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP) | OW_MD.DIM_VTEX_PAYMENT_GROUP | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0002 | DIM | 0 | [(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP),(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE)] | 4 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN) | OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0005 | DIM | 0 | [(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING)] | 4 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON) | OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_VOUCHER_COUPON_UPDATE),(PROCEDURE - OW_LAO.PROC_TF_PO_COUPON_ID_CONTROL_TOWER_LIST),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES)] | 3 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE) | OW_LAO.DIM_PAYMENT_GATEWAY_CODE | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI),(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP)] | 3 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE) | OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0008 | DIM | 0 | [(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)] | 3 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT) | OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.2606 | FT | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] | 3 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM) | OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.3961 | FT | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM)] | 3 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.DIM_ECOM_PARTNER_LEVEL) | OW_LAO.DIM_ECOM_PARTNER_LEVEL | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0018 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 2 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.DIM_EXCEL_TARGETS_CAMPAIGN) | OW_LAO.DIM_EXCEL_TARGETS_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS),(INGESTION - JOB.DIM_EXCEL_TARGETS_CAMPAIGN)] | 2 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.DIM_MONITORING_BI_LAO_PROCCESS_ALERT) | OW_LAO.DIM_MONITORING_BI_LAO_PROCCESS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0003 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT),(INGESTION - JOB.DIM_MONITORING_BI_LAO_PROCCESS_ALERT)] | 2 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_PAYMENT_TYPE) | OW_LAO.DIM_PAYMENT_PAYMENT_TYPE | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP)] | 2 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY) | OW_LAO.DIM_PAYMENT_PAY_GATEWAY | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP)] | 2 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.FT_D2C_ONE_VIEW_TABLE) | OW_LAO.FT_D2C_ONE_VIEW_TABLE | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.2208 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA),(VIEW - OW_LAO.VW_TAB3_PMS_DW)] | 2 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_SKU) | OW_MD.DIM_VTEX_SSG_BR_INVENTORY_SKU | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0095 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU),(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY)] | 2 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE) | OW_MD.DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY),(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)] | 2 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU) | OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0045 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU),(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY)] | 2 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE) | OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE),(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY)] | 2 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.DIM_UNIQUE_ID) | OW_LAO.DIM_UNIQUE_ID | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.9954 | DIM | 0 | [(PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID)] | 1 |  | 03/09 - 03/09
Global D2C BI | TABLE | (TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_ALL) | OW_LAO.TF_GLOBAL_BI_TRAFFIC_ALL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0009 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_ALL)] | 1 |  | 03/09 - 03/09
Global D2C BI | TABLE | (TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_DA) | OW_LAO.TF_GLOBAL_BI_TRAFFIC_DA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0007 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_DA)] | 1 |  | 03/09 - 03/09
Global D2C BI | TABLE | (TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_MX) | OW_LAO.TF_GLOBAL_BI_TRAFFIC_MX | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0008 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_MX)] | 1 |  | 03/09 - 03/09
Global D2C BI | TABLE | (TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_VD) | OW_LAO.TF_GLOBAL_BI_TRAFFIC_VD | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0007 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_VD)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.FT_VTEX_SSG_BR_INVENTORY) | OW_MD.FT_VTEX_SSG_BR_INVENTORY | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0005 | FT | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.FT_VTEX_SSG_BR_SHOP_INVENTORY) | OW_MD.FT_VTEX_SSG_BR_SHOP_INVENTORY | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0049 | FT | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.TF_VTEX_AFFILIATE_01) | OW_MD.TF_VTEX_AFFILIATE_01 | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.TF_VTEX_AFFILIATE_02) | OW_MD.TF_VTEX_AFFILIATE_02 | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0002 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.TF_VTEX_AFFILIATE_03) | OW_MD.TF_VTEX_AFFILIATE_03 | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.TF_VTEX_ORDER_STATUS_01) | OW_MD.TF_VTEX_ORDER_STATUS_01 | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_ORDER_STATUS)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_UNIQUE_ID) | OW_LAO.TMP_DIM_UNIQUE_ID | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.3248 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID)] | 1 |  | 03/09 - 03/09
Global D2C BI | TABLE | (TABLE - OW_LAO.TMP_GLOBAL_BI_SALES) | OW_LAO.TMP_GLOBAL_BI_SALES | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.09 | TMP | 0 | [(INGESTION - JOB.TMP_GLOBAL_BI_SALES)] | 1 |  | 03/09 - 03/09
Global D2C BI | TABLE | (TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_ALL) | OW_LAO.TMP_GLOBAL_BI_TRAFFIC_ALL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.003 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_ALL)] | 1 |  | 03/09 - 03/09
Global D2C BI | TABLE | (TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_DA) | OW_LAO.TMP_GLOBAL_BI_TRAFFIC_DA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0031 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_DA)] | 1 |  | 03/09 - 03/09
Global D2C BI | TABLE | (TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_MX) | OW_LAO.TMP_GLOBAL_BI_TRAFFIC_MX | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0029 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_MX)] | 1 |  | 03/09 - 03/09
Global D2C BI | TABLE | (TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_VD) | OW_LAO.TMP_GLOBAL_BI_TRAFFIC_VD | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0026 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_VD)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ID) | OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ID | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_PAYMENT_FUNNEL_STATUS) | OW_LAO.TMP_PAYMENT_FUNNEL_STATUS | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO) | OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 | [(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_BRASIL) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0006 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_CHILE) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0005 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_COLOMBIA) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0005 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_MEXICO) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0005 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_PERU) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0006 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_URUGUAY) | OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_URUGUAY | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0005 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_BRASIL) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0656 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_CHILE) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.007 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_COLOMBIA) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0046 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_MEXICO) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.04 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_PERU) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0014 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_URUGUAY) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_URUGUAY | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0028 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_SALES_PAYMENTS_GRAFANA_DETAILS) | OW_LAO.TMP_SALES_PAYMENTS_GRAFANA_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0003 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.INPUT_SALES_CHANNELS) | OW_MD.INPUT_SALES_CHANNELS | LAO EStore | r.bojart |  | yes |  | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | INPUT | 0 | [(PROCEDURE - OW_MD.PROC_ODS_SALES_CHANNELS)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.ODS_SALES_CHANNELS) | OW_MD.ODS_SALES_CHANNELS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_ODS_SALES_CHANNELS)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.RAW_MP_ESTORE) | OW_MD.RAW_MP_ESTORE | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0007 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_INGESTION_ODS_MP_ESTORE)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.TMP_SALES_CHANNEL_LAO) | OW_MD.TMP_SALES_CHANNEL_LAO | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | TMP | 0 | [(PROCEDURE - OW_MD.PROC_DIM_SALES_CHANNEL)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_MD.TMP_SALES_CHANNEL_SEDA) | OW_MD.TMP_SALES_CHANNEL_SEDA | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | TMP | 0 | [(PROCEDURE - OW_MD.PROC_DIM_SALES_CHANNEL)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_SEDA_S.ODS_ONLINE_SELL_IN) | OW_SEDA_S.ODS_ONLINE_SELL_IN | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_ONLINE_SELL_IN)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - U_PRJ_ECOM.ODS_SELA_API_STATUS_MAP) | U_PRJ_ECOM.ODS_SELA_API_STATUS_MAP | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | ODS | 0 | [(INGESTION - JOB.ODS_SELA_API_STATUS_MAP)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED) | U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED | LAO EStore | r.bojart |  | yes | 4 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.017 | RAW | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_RAW_ECOM_HQ_ORDERS_TRADEIN_FEED)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_DIGGIT_ECOM_ORDERS) | U_PRJ_ECOM.TMP_DIGGIT_ECOM_ORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0015 | TMP | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS_HIST_HOMOLG)] | 1 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.ODS_AFTER_SALES_CANCELATION) | OW_LAO.ODS_AFTER_SALES_CANCELATION | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0015 | ODS | 0 |  | 0 |  | 03/09 - 03/09
Control Tower | TABLE | (TABLE - OW_LAO.ODS_LAO_CONTROL_TOWER_ORIGIN_PROCESS_LAST_UPDATE) | OW_LAO.ODS_LAO_CONTROL_TOWER_ORIGIN_PROCESS_LAST_UPDATE | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | ODS | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.ODS_SALES_CAMPAIGN_UPDATE) | OW_LAO.ODS_SALES_CAMPAIGN_UPDATE | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0101 | ODS | 0 |  | 0 |  | 03/09 - 03/09
Control Tower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_VISUAR) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_VISUAR | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0012 | ODS | 0 |  | 0 |  | 03/09 - 03/09
Control Tower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_SEASA_MIGRATION) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_SEASA_MIGRATION | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0033 | ODS | 0 |  | 0 |  | 03/09 - 03/09
Control Tower | TABLE | (TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_SEDA_HOMOLOG) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_SEDA_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0079 | ODS | 0 |  | 0 |  | 03/09 - 03/09
Control Tower | TABLE | (TABLE - OW_LAO.ODS_TABLE_CHECK_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE) | OW_LAO.ODS_TABLE_CHECK_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | ODS | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.RAW_NUBIMETRICS_CATEGORYIDS) | OW_LAO.RAW_NUBIMETRICS_CATEGORYIDS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.RAW_SALES_LISTINGS) | OW_LAO.RAW_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0061 | RAW | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP2_SOT_SALES_PROGRESS_KPI) | OW_LAO.TMP2_SOT_SALES_PROGRESS_KPI | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0773 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_NAME_OLDYEAR) | OW_LAO.TMP_CAMPAIGN_NAME_OLDYEAR | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_D2C_AR_ONE_VIEW_TABLE_01) | OW_LAO.TMP_D2C_AR_ONE_VIEW_TABLE_01 | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_D2C_PO_SALES) | OW_LAO.TMP_D2C_PO_SALES | [5 empty] | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0706 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_ECOM_PARTNER_LEVEL) | OW_LAO.TMP_DIM_ECOM_PARTNER_LEVEL | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_ECOM_PARTNER_LEVEL_INSERT) | OW_LAO.TMP_DIM_ECOM_PARTNER_LEVEL_INSERT | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_GSCM) | OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_GSCM | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0037 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_PRODUCT_CATEGORY) | OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_PRODUCT_CATEGORY | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0123 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_PRODUCT_CATEGORY_AJ) | OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_PRODUCT_CATEGORY_AJ | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0004 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_SALES) | OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_SALES | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_SALES_DEDUP) | OW_LAO.TMP_DIM_PRODUCT_MAPPING_LAO_SALES_DEDUP | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0003 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_ORDERING) | OW_LAO.TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_ORDERING | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45903 | 45903 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0076 | TMP | 0 |  | 0 |  | 03/09 - 03/09
| TABLE | (TABLE - OW_LAO.RAW_ECOM_NERP_HIST_LAO) | OW_LAO.RAW_ECOM_NERP_HIST_LAO | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.2355 | RAW | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.RAW_LAO_NERP_SELL_IN_ONLINE) | OW_LAO.RAW_LAO_NERP_SELL_IN_ONLINE | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0887 | RAW | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.RAW_LAO_NERP_SELL_IN_ONLINE_HOMOLOG) | OW_LAO.RAW_LAO_NERP_SELL_IN_ONLINE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.014 | RAW | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.RAW_LAO_NERP_SELL_IN_SET_TOTAL) | OW_LAO.RAW_LAO_NERP_SELL_IN_SET_TOTAL | LAO EStore | r.bojart |  |  | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0132 | RAW | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP) | OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0004 | RAW | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP_PREPARE) | OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP_PREPARE | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0001 | RAW | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_DATA_NERP_MB51_GR_FOLDER) | OW_LAO.TMP_DATA_NERP_MB51_GR_FOLDER | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES) | OW_LAO.TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0166 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_FILTER) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_FILTER | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NERP_DISPLAY_CLOSING_REPORT_NOT_IN_ZKE) | OW_LAO.TMP_NERP_DISPLAY_CLOSING_REPORT_NOT_IN_ZKE | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0007 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NERP_DISPLAY_CLOSING_REPORT_NOT_IN_ZKE_COMPLETE) | OW_LAO.TMP_NERP_DISPLAY_CLOSING_REPORT_NOT_IN_ZKE_COMPLETE | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0007 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NERP_MB51_GR_FOLDER) | OW_LAO.TMP_NERP_MB51_GR_FOLDER | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0012 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_LAO.TMP_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0021 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NERP_ZLLEB57910_CLAIM_FOLDER) | OW_LAO.TMP_NERP_ZLLEB57910_CLAIM_FOLDER | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0005 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NERP_ZLLEE50090) | OW_LAO.TMP_NERP_ZLLEE50090 | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0089 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_LAO_NERP_SELL_IN_ONLINE) | OW_LAO.TMP_RAW_LAO_NERP_SELL_IN_ONLINE | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0023 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_LAO_NERP_SELL_IN_SET_TOTAL) | OW_LAO.TMP_RAW_LAO_NERP_SELL_IN_SET_TOTAL | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0028 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TMP_MAP_NERP_GSCM) | OW_MD.TMP_MAP_NERP_GSCM | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PAYMENT_GROUP_01) | OW_MD.TF_VTEX_PAYMENT_GROUP_01 | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PAYMENT_STATUS_01) | OW_MD.TF_VTEX_PAYMENT_STATUS_01 | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_COURIER) | OW_MD.TF_VTEX_PURCHASE_ORDER_COURIER | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_DOCK) | OW_MD.TF_VTEX_PURCHASE_ORDER_DOCK | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_DOMAIN) | OW_MD.TF_VTEX_PURCHASE_ORDER_DOMAIN | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_01) | OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_01 | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.1257 | TF | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_02) | OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_02 | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0386 | TF | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_03) | OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_03 | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0433 | TF | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_04) | OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_04 | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0816 | TF | 0 | [(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_REGION) | OW_MD.TF_VTEX_PURCHASE_ORDER_REGION | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0077 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_TRACKING_01) | OW_MD.TF_VTEX_PURCHASE_ORDER_TRACKING_01 | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.6232 | TF | 0 | [(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_TRADE_IN) | OW_MD.TF_VTEX_PURCHASE_ORDER_TRADE_IN | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_WAREHOUSE) | OW_MD.TF_VTEX_PURCHASE_ORDER_WAREHOUSE | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_SSG_BR_INVENTORY_SKU) | OW_MD.TF_VTEX_SSG_BR_INVENTORY_SKU | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_SSG_BR_INVENTORY_WAREHOUSE) | OW_MD.TF_VTEX_SSG_BR_INVENTORY_WAREHOUSE | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_SKU) | OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_SKU | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0004 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU)] | 1 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE) | OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | TF | 0 | [(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)] | 1 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.DIM_CONTROL_TOWER_TABLE_PO_COUPON) | OW_LAO.DIM_CONTROL_TOWER_TABLE_PO_COUPON | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_LAO_TARGETS_CAMPAIGN_CADASTRA) | OW_LAO.DIM_LAO_TARGETS_CAMPAIGN_CADASTRA | LAO EStore | r.bojart |  | yes | 5 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0011 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_NUBIMETRICS_CATEGORYID) | OW_LAO.DIM_NUBIMETRICS_CATEGORYID | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_NUBIMETRICS_CATEGORYID_BRAZIL) | OW_LAO.DIM_NUBIMETRICS_CATEGORYID_BRAZIL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_NUBIMETRICS_TOKEN) | OW_LAO.DIM_NUBIMETRICS_TOKEN | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_PARADIGM_SKU) | OW_LAO.DIM_PARADIGM_SKU | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_AUXILIARY_PBI_MEASURES_CURRENCY) | OW_LAO.DIM_PAYMENT_AUXILIARY_PBI_MEASURES_CURRENCY | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_AUXILIARY_PBI_MEASURES_KPI) | OW_LAO.DIM_PAYMENT_AUXILIARY_PBI_MEASURES_KPI | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_CALCULATION_STATUS_FUNNEL) | OW_LAO.DIM_PAYMENT_CALCULATION_STATUS_FUNNEL | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_CALCULATION_STATUS_FUNNEL_2) | OW_LAO.DIM_PAYMENT_CALCULATION_STATUS_FUNNEL_2 | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_MANUAL_INPUT) | OW_LAO.DIM_PAYMENT_MANUAL_INPUT | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_MANUAL_INPUT_HOMOLOG) | OW_LAO.DIM_PAYMENT_MANUAL_INPUT_HOMOLOG | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_PAYMENT_MAP_FUNNEL_STATUS) | OW_LAO.DIM_PAYMENT_MAP_FUNNEL_STATUS | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.DIM_SUBSIDIARY_ALERT_TIMESTAMP_DEFAULT) | OW_LAO.DIM_SUBSIDIARY_ALERT_TIMESTAMP_DEFAULT | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0052 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_SELA_STATUS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_SELA_STATUS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0003 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_DISCOUNT) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_DISCOUNT | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_PAYMENTS) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0004 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_SKU_AGG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_SKU_AGG | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0005 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_EPP_PROMOTION) | OW_LAO.TMP_EPP_PROMOTION | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0226 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_FT_PO_ORDER_ID) | OW_LAO.TMP_FT_PO_ORDER_ID | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0181 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_GROSS_MARGIN_DCR_) | OW_LAO.TMP_GROSS_MARGIN_DCR_ | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0274 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_GROSS_MARGIN_ZKE_) | OW_LAO.TMP_GROSS_MARGIN_ZKE_ | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.055 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING) | OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_SALES_RULE_1) | OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_SALES_RULE_1 | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_SALES_RULE_GSCM) | OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_SALES_RULE_GSCM | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_TABLE_MINIO_2) | OW_LAO.TMP_LAO_DIM_PRODUCT_MAPPING_TABLE_MINIO_2 | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_HOUR) | OW_LAO.TMP_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_HOUR | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS) | OW_LAO.TMP_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_BRASIL) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_CHILE) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_COLOMBIA) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_MEXICO) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_PERU) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_CATEGORIES_URUGUAI) | OW_LAO.TMP_NUBIMETRICS_CATEGORIES_URUGUAI | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_SALES_LISTINGS) | OW_LAO.TMP_NUBIMETRICS_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_BRASIL) | OW_LAO.TMP_NUBIMETRICS_TOKEN_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_BRASIL_API) | OW_LAO.TMP_NUBIMETRICS_TOKEN_BRASIL_API | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_CHILE) | OW_LAO.TMP_NUBIMETRICS_TOKEN_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_COLOMBIA) | OW_LAO.TMP_NUBIMETRICS_TOKEN_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_MEXICO) | OW_LAO.TMP_NUBIMETRICS_TOKEN_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_PERU) | OW_LAO.TMP_NUBIMETRICS_TOKEN_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_NUBIMETRICS_TOKEN_URUGUAY) | OW_LAO.TMP_NUBIMETRICS_TOKEN_URUGUAY | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Global D2C BI | TABLE | (TABLE - OW_LAO.TMP_ODS_GLOBAL_BI_SALES_KIT) | OW_LAO.TMP_ODS_GLOBAL_BI_SALES_KIT | LAO EStore | r.bojart |  | yes | 4 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_ODS_LAO_PRODUCT_PREMIUM_ITEMS_GSCM_PREMIUM_MODELS) | OW_LAO.TMP_ODS_LAO_PRODUCT_PREMIUM_ITEMS_GSCM_PREMIUM_MODELS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_PARTNER_LEVEL_SMB_SEASA) | OW_LAO.TMP_PARTNER_LEVEL_SMB_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAYMENT_TYPE_NULL) | OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAYMENT_TYPE_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAY_GATEWAY_NULL) | OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAY_GATEWAY_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAY_STATUS_NULL) | OW_LAO.TMP_PAYMENTS_FUNNEL_TABLE_PAY_STATUS_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO_HOMOLOG) | OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO_HOMOLOG | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_FEED_SEND_ESTORE) | OW_LAO.TMP_RAW_FEED_SEND_ESTORE | LAO EStore | r.bojart |  | yes | 4 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0004 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_LAO_DIM_PRODUCT_MAPPING_APOIO) | OW_LAO.TMP_RAW_LAO_DIM_PRODUCT_MAPPING_APOIO | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS) | OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0204 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_SALES_CAMPAIGN_UPDATE) | OW_LAO.TMP_SALES_CAMPAIGN_UPDATE | LAO EStore | r.bojart |  | yes | 5 | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0101 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_SELA_CUSTON_ORDERS) | OW_LAO.TMP_SELA_CUSTON_ORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_SELA_CUSTON_ORDERS_ITEMS) | OW_LAO.TMP_SELA_CUSTON_ORDERS_ITEMS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_SOT_SALES_PROGRESS_KPI) | OW_LAO.TMP_SOT_SALES_PROGRESS_KPI | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.1589 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_LAO.TMP_VL_SALES_CHANNEL_TABLE_BIZTYPE_CHANNEL_NULL) | OW_LAO.TMP_VL_SALES_CHANNEL_TABLE_BIZTYPE_CHANNEL_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STATUS_NULL) | OW_LAO.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STATUS_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
Control Tower | TABLE | (TABLE - OW_LAO.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STORENAME_NULL) | OW_LAO.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STORENAME_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_MD.TMP_DIM_SALES_CHANNELS_PROMOTIONS_GENERATE) | OW_MD.TMP_DIM_SALES_CHANNELS_PROMOTIONS_GENERATE | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_SEDA_S.ODS_AFTER_SALES_ACCOUNT_TOKEN) | OW_SEDA_S.ODS_AFTER_SALES_ACCOUNT_TOKEN | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | ODS | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_SEDA_S.ODS_OST_CANCELLATION) | OW_SEDA_S.ODS_OST_CANCELLATION | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | ODS | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0006 | RAW | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_B2B) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_B2B | [5 empty] | Done |  | 1 | 1 | 45904 | 45904 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 |  | 0 |  | 04/09 - 04/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_PRICES) | OW_SEDA_S.ODS_NERP_PRICES | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0008 | ODS | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA) | OW_SEDA_S.ODS_NERP_ZLSDR79100_DISPLAY_RETURN_DATA | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0473 | ODS | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRFIZFX00007_EXCHANGE_RATE) | OW_SEDA_S.ODS_NERP_ZRFIZFX00007_EXCHANGE_RATE | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0007 | ODS | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A080_SALES_ORDER_LIST) | OW_SEDA_S.ODS_NERP_ZRSDD6A080_SALES_ORDER_LIST | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.4251 | ODS | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDK65000_BILLING_LIST) | OW_SEDA_S.ODS_NERP_ZRSDK65000_BILLING_LIST | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0128 | ODS | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZSE16_DELETED_DO) | OW_SEDA_S.ODS_NERP_ZSE16_DELETED_DO | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0144 | ODS | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_NERP_ZSE16_DELETED_DO) | OW_SEDA_S.RAW_NERP_ZSE16_DELETED_DO | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.6686 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS) | OW_SEDA_S.TMP_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0117 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST) | OW_SEDA_S.TMP_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0109 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_SEDA_S.TMP_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0001 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZLLEB57910_CLAIM_MAINTENANCE) | OW_SEDA_S.TMP_NERP_ZLLEB57910_CLAIM_MAINTENANCE | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0006 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZLLEB57910_CLAIM_MAINTENANCE_OLD) | OW_SEDA_S.TMP_NERP_ZLLEB57910_CLAIM_MAINTENANCE_OLD | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_NERP_ZSE16_DELETED_DO) | OW_SEDA_S.TMP_NERP_ZSE16_DELETED_DO | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.001 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS) | OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0004 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER) | OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0003 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER) | OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0003 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER) | OW_SEDA_S.TMP_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 1.4 Ingestion NERP | 0.0005 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.DIM_VTEX_SELLER_ORDER_LIST) | OW_LAO.DIM_VTEX_SELLER_ORDER_LIST | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0002 | DIM | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.FT_D2C_FORECAST_OST) | OW_LAO.FT_D2C_FORECAST_OST | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | FT | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_LEAD_TIME_ORDER_IOD_KPI) | OW_LAO.FT_D2C_NERP_LEAD_TIME_ORDER_IOD_KPI | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0066 | FT | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.FT_D2C_VTEX_NERP_WEEKLY_SALES) | OW_LAO.FT_D2C_VTEX_NERP_WEEKLY_SALES | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0372 | FT | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.FT_D2C_VTEX_O2O_SALES_KPI) | OW_LAO.FT_D2C_VTEX_O2O_SALES_KPI | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0838 | FT | 0 |  | 0 |  | 05/09 - 05/09
Control Tower | TABLE | (TABLE - OW_LAO.FT_SALES_CONTROL_TOWER_SELA_CHECK_SALES) | OW_LAO.FT_SALES_CONTROL_TOWER_SELA_CHECK_SALES | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.1091 | FT | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.FT_VTEX_SSG_BR_TMP) | OW_LAO.FT_VTEX_SSG_BR_TMP | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | FT | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_DB_SALES_ORDER_TRACKING) | OW_LAO.TF_D2C_NERP_DB_SALES_ORDER_TRACKING | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0111 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_SALES_COUPON_KPI) | OW_LAO.TF_D2C_NERP_SALES_COUPON_KPI | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0875 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_SALES_REWARDS_KPI) | OW_LAO.TF_D2C_NERP_SALES_REWARDS_KPI | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.2029 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.TF_D2C_NERP_TRADEIN_SALES_KPI) | OW_LAO.TF_D2C_NERP_TRADEIN_SALES_KPI | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0028 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.TF_D2C_PO_VTEX_SALES_KPI) | OW_LAO.TF_D2C_PO_VTEX_SALES_KPI | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0944 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.TF_D2C_VTEX_PO_TARGET_LAUNCH_S25) | OW_LAO.TF_D2C_VTEX_PO_TARGET_LAUNCH_S25 | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0059 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.TF_D2C_VTEX_PROMOTION_KPI) | OW_LAO.TF_D2C_VTEX_PROMOTION_KPI | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.4388 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.TF_D2C_VTEX_SELLOUT_PLATFORM_KPI) | OW_LAO.TF_D2C_VTEX_SELLOUT_PLATFORM_KPI | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0637 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.TF_NERP_SALES_PROGRESS_KPI) | OW_LAO.TF_NERP_SALES_PROGRESS_KPI | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0003 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_LAO.TF_VTEX_MONITORING_SKU) | OW_LAO.TF_VTEX_MONITORING_SKU | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.006 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_MD.DIM_MAPPING_VTEX_POLICIES_PRODUCT) | OW_MD.DIM_MAPPING_VTEX_POLICIES_PRODUCT | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.DIM_VTEX_AFFILIATE) | OW_SEDA_S.DIM_VTEX_AFFILIATE | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0002 | DIM | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.DIM_SELA_API_PARAMETERS) | U_PRJ_ECOM.DIM_SELA_API_PARAMETERS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.DIM_SELA_API_PARAMETERS_QTD) | U_PRJ_ECOM.DIM_SELA_API_PARAMETERS_QTD | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | DIM | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.DIM_SELLER_INSTANCE) | U_PRJ_ECOM.DIM_SELLER_INSTANCE | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.FT_MAGENTO_ORDER) | U_PRJ_ECOM.FT_MAGENTO_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0003 | FT | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.FT_MAGENTO_ORDER_ITEM) | U_PRJ_ECOM.FT_MAGENTO_ORDER_ITEM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0002 | FT | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.FT_MAGENTO_ORDER_PAYMENT) | U_PRJ_ECOM.FT_MAGENTO_ORDER_PAYMENT | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.0001 | FT | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TF_D2C_NERP_WEEKLY_SALES_KPI) | U_PRJ_ECOM.TF_D2C_NERP_WEEKLY_SALES_KPI | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TF_D2C_NERP_WEEKLY_SALES_KPI_SAMPLE) | U_PRJ_ECOM.TF_D2C_NERP_WEEKLY_SALES_KPI_SAMPLE | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 2.1 Migrar ph1 | 0.2122 | TF | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_EPP2) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_EPP2 | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.019 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_EST) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_EST | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0554 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_MEMBERS) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_MEMBERS | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0136 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_MKP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_MKP | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.6605 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_PARC) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_PARC | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0282 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_RESID) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_COLLECTION_DETAIL_RESID | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0006 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_B2B) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_B2B | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0004 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BREA) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BREA | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0046 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP_VL) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP_VL | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_EPP2) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_EPP2 | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0004 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_EST) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_EST | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0007 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_MEMBERS) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_MEMBERS | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0005 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_MKP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_MKP | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0074 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_PARC) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_PARC | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0004 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_RESID) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_RESID | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_EPP2) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_EPP2 | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_EST) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_EST | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0253 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP_VL) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP_VL | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0075 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_EST) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_EST | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0029 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_MEMBERS) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_MEMBERS | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0009 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_MKP) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_MKP | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0547 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_PARC) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_PARC | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0015 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_RESID) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST_RESID | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_MEMBERS) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_MEMBERS | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - OW_SEDA_S.TMP_NUBI_SALES_REPORT) | OW_SEDA_S.TMP_NUBI_SALES_REPORT | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0003 | TMP | 0 |  | 0 |  | 05/09 - 05/09
Global D2C BI | TABLE | (TABLE - U_PRJ_ECOM.ODS_GLOBAL_BI_STOCKOUT_HISTORY) | U_PRJ_ECOM.ODS_GLOBAL_BI_STOCKOUT_HISTORY | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0049 | ODS | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.ODS_OST_SEDA_CANCELLATION_HMLG) | U_PRJ_ECOM.ODS_OST_SEDA_CANCELLATION_HMLG | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.018 | ODS | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEIN) | U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEIN | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEIN_SEASA) | U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEIN_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEUP) | U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEUP | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEUP_SEASA) | U_PRJ_ECOM.RAW_ECOM_PRODUCT_TRADEUP_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_SKU) | U_PRJ_ECOM.RAW_ECOM_SKU | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0019 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.RAW_ECOM_SKU_SAMSUNG_CARE_PLUS) | U_PRJ_ECOM.RAW_ECOM_SKU_SAMSUNG_CARE_PLUS | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | RAW | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_DIM_PRODUCT_CATEGORY_SEDA) | U_PRJ_ECOM.TMP_DIM_PRODUCT_CATEGORY_SEDA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_PRODUCTS_COMBO | LAO EStore | r.bojart |  | yes | 4 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_TRADEIN_FEED) | U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_TRADEIN_FEED | LAO EStore | r.bojart |  | yes | 4 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0005 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_TRADEIN_FEED_SEND) | U_PRJ_ECOM.TMP_ECOM_HQ_ORDERS_TRADEIN_FEED_SEND | LAO EStore | r.bojart |  | yes | 4 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0002 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_ECOM_SKU_ENABLES) | U_PRJ_ECOM.TMP_ODS_ECOM_SKU_ENABLES | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN) | U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID) | U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID_SEASA) | U_PRJ_ECOM.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID_SEASA | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_ECOM_SKU_SAMSUNG_CARE_PLUS) | U_PRJ_ECOM.TMP_RAW_ECOM_SKU_SAMSUNG_CARE_PLUS | [5 empty] | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_FEED_SEND_ESTORE_SAMPLE) | U_PRJ_ECOM.TMP_RAW_FEED_SEND_ESTORE_SAMPLE | LAO EStore | r.bojart |  | yes | 7 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0343 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_PAYMENTS) | U_PRJ_ECOM.TMP_RAW_PAYMENTS | LAO EStore | r.bojart |  | yes | 6 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_SELA_API_PARAMETERS) | U_PRJ_ECOM.TMP_SELA_API_PARAMETERS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_SELA_API_PARAMETERS_QTD_DIM) | U_PRJ_ECOM.TMP_SELA_API_PARAMETERS_QTD_DIM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| TABLE | (TABLE - U_PRJ_ECOM.TMP_SELA_API_PARAMETERS_QTD_GTM) | U_PRJ_ECOM.TMP_SELA_API_PARAMETERS_QTD_GTM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45905 | 45905 | ['[]'] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 0 |  | 0 |  | 05/09 - 05/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT) | U_PRJ_ECOM.VIEW_ECOM_ENDLESS_AISLE_REPORT | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION) | U_PRJ_ECOM.VIEW_VTEX_PROMOTION | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM) | U_PRJ_ECOM.VIEW_VTEX_PROMOTION_ITEM | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - OW_LAO.RAW_VTEX_PAYMENTS_HOMOLOG) | OW_LAO.RAW_VTEX_PAYMENTS_HOMOLOG | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM) | OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM | [7 empty] | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM) | OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM | [7 empty] | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_DOMAIN)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - OW_LAO.VW_TMP_VTEX_CONCAT) | OW_LAO.VW_TMP_VTEX_CONCAT | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER) | OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER | [7 empty] | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.VTEX_SSG_AR_RATES_AND_BENEFITS_DATA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  | 08/09 - 08/09
Control Tower | VIEW | (VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE) | OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
Control Tower | VIEW | (VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MAT) | OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MAT | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
Control Tower | VIEW | (VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_PROD) | OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_PROD | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
Control Tower | VIEW | (VIEW - OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_TST) | OW_LAO.VIEW_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_TST | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION) | OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION | [7 empty] | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_COURIER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_DOCK)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOCK)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED) | U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED | LAO EStore | r.bojart |  | yes | 4 | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG) | U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS) | OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS | [7 empty] | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS) | OW_LAO.VIEW_DISTINCT_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS | [7 empty] | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS) | OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS | LAO EStore | r.bojart |  |  |  | Not to be migrated |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS_HOMOLOG)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  | 08/09 - 08/09 | [19 empty] | Confirmed by r.bojart via knox on 21/11
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU) | OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_MD.TF_VTEX_SSG_BR_INVENTORY_SKU)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_BY_REF_ID)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_SKU)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE) | OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_BY_SKU)'", "'(TABLE - OW_MD.TF_VTEX_SSG_BR_INVENTORY_WAREHOUSE)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE) | OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done | SIM | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.DIM_ECOM_PARTNER_LEVEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT) | OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION) | OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION |  |  |  | yes |  | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.TF_WAREHOUSE_OPERATION)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.ODS_WMS_PICKING_PACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING) | OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING |  |  |  | yes |  | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.FT_D2C_NERP_WH_OPERATION_PENDING)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING |  |  |  | yes |  | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.TMP_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE | LAO EStore | r.bojart |  | yes | 1 | Done | SIM | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - OW_MD.VW_PRICE_MONITORING_AUDIT_PROCESS) | OW_MD.VW_PRICE_MONITORING_AUDIT_PROCESS | [7 empty] | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI) | OW_LAO.PROC_D2C_NERP_GSCM_PSI |  |  |  | yes |  |  |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_MB51_GR_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_D2C_NERP_GSCM_PSI)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI) | OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI | [7 empty] | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES)'", "'(TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - OW_LAO.VIEW_VTEX_PAYMENTS_OLD) | OW_LAO.VIEW_VTEX_PAYMENTS_OLD | [5 empty] | Done |  | 3 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU) | OW_LAO.PROC_D2C_PAYMENT_ITAU |  |  |  | yes | yes | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_TESTE) | OW_LAO.PROC_TESTE | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES) | OW_LAO.PROC_D2C_PO_HYBRIS_SALES |  |  |  | yes |  | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI) | OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI |  |  |  | yes | yes | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES_BY_HOUR_KPI)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - OW_LAO.VW_PMS_TESTE) | OW_LAO.VW_PMS_TESTE | [7 empty] | 3 | 1 | 45908 | 45908 | ["['[(TABLE - OW_MD.COGS)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.ODS_SEDA_VTEX_KIT_COMPONENTS_REGISTRATION)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION) | OW_LAO.PROC_D2C_VTEX_PROMOTION |  |  |  | yes | yes | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI) | OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI |  |  |  | yes | yes | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS) | OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP) | OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1) | OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1 |  |  |  | yes |  | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_AR_TABLE_WEEK)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_D2C_AR_TABLE_WEEK)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING) | OW_LAO.PROC_D2C_NERP_ORDER_PENDING |  |  |  | yes |  | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.FT_D2C_NERP_ORDER_PENDING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU) | OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU |  |  |  | yes | yes | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TF_D2C_VTEX_PAYMENT_SKU)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 7 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_ORDER_STATUS) | OW_MD.PROC_DIM_VTEX_ORDER_STATUS | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_MD.TF_VTEX_ORDER_STATUS_01)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS) | OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS | [5 empty] | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.TF_VTEX_PAYMENT_STATUS_01)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING) | OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING |  |  |  | yes |  | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.FT_D2C_NERP_DELIVERY_PENDING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_INVENTORY) | OW_LAO.PROC_D2C_NERP_INVENTORY |  |  |  | yes |  | Done |  | 4 | 1 | 45908 | 45908 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.FT_D2C_NERP_INVENTORY)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP01112023 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP20230707 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_1 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_TRADEIN_FEED_ADJ | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST) | U_PRJ_ECOM.VIEW_ECOM_ORD_TST | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 7 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO) | U_PRJ_ECOM.VIEW_ECOM_ORDERS_CUBO | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN) | U_PRJ_ECOM.VIEW_RAW_VTEX_SSG_CT_TRADEIN | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_CT_TRADEIN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_CT_TRADEIN)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO_TST | [5 empty] | Done |  | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_EPP | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_2 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A01 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_A02 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_AGO | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_DEV | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A2 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_A3 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_EPP_ARG | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SELA | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP01112023 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP19052023 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP20230707 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP21062023 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP27042023 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_USA | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp02032023 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_bkp´180522 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - OW_LAO.VIEW_ECOM_PRODUCT_VTEX) | OW_LAO.VIEW_ECOM_PRODUCT_VTEX | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_REFERENCE) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_REFERENCE | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)]']"] | 1 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME) | OW_LAO.PROC_D2C_NERP_LEAD_TIME |  |  |  | yes |  | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_03)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME)'", "'(TABLE - OW_LAO.FT_D2C_NERP_LEAD_TIME)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_01)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_02)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW) | OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW |  |  |  | yes |  | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_D2C_NERP_ORDER_PENDING_OVERVIEW)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_01)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_02)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO) | OW_LAO.PROC_ODS_HYBRIS_COMBO | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_COMBO)'", "'(TABLE - OW_LAO.RAW_HYBRIS_COMBO)'", "'(TABLE - OW_LAO.TMP_ODS_HYBRIS_COMBO)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 5 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO) | U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO)]']"] | 1 | 1.3 Ingestion MAGENTO |  |  | 5 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP) | OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP | LAO EStore | r.bojart |  | yes | 6 | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM) | OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM | [5 empty] | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE | [5 empty] | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA) | OW_LAO.PROC_PMS_DW_UNIFICADA | [5 empty] | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.FT_D2C_ONE_VIEW_TABLE)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING) | OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING) | OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING | [5 empty] | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_TRACKING_01)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 12 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT) | OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT | [5 empty] | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_01)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_02)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_03)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_04)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE) | OW_MD.PROC_DIM_VTEX_AFFILIATE | [5 empty] | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_AFFILIATE_01)'", "'(TABLE - OW_MD.TF_VTEX_AFFILIATE_02)'", "'(TABLE - OW_MD.TF_VTEX_AFFILIATE_03)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP) | OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP | [7 empty] | 4 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.TF_VTEX_PAYMENT_GROUP_01)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN) | OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN | [5 empty] | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU) | OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU | [7 empty] | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU)'", "'(TABLE - OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_SKU)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY) | OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY | [5 empty] | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_SKU)'", "'(TABLE - OW_MD.FT_VTEX_SSG_BR_INVENTORY)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY) | OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY | [5 empty] | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU)'", "'(TABLE - OW_MD.FT_VTEX_SSG_BR_SHOP_INVENTORY)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH) | OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH |  |  |  | yes |  | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_MONTH)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_WEEK)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_WEEK)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 11 |  | 0 |  |  | 09/09 - 09/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1) | OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1 |  |  |  | yes |  | Done |  | 4 | 1 | 45909 | 45909 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_D2C_AR_TABLE_MONTH)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.FT_D2C_AR_TABLE_MONTH)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5) | U_PRJ_ECOM.VIEW_ECOM_ORDERS_B5Q5 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ) | U_PRJ_ECOM.VIEW_ECOM_FEED_HIST_HQ | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP06062024 | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO) | OW_LAO.VIEW_ORDERS_GOVERNANCE_LAO | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO) | OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS) | OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_RECORD_HOURS | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR) | OW_LAO.VIEW_GOVERNANCE_SUBSIDIARY_HOUR | [7 empty] | 3 | 1 | 45909 | 45909 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  | 09/09 - 09/09
| VIEW | (VIEW - OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW) | OW_LAO.VIEW_GOVERNANCE_ORDERS_LAO_NEW | [7 empty] | 3 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 5 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI) | OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI | LAO EStore | r.bojart |  | yes | 3 | Done | SIM | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID) | OW_LAO.PROC_DIM_UNIQUE_ID | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_VTEX_PROFILE)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_UNIQUE_ID)'", "'(TABLE - OW_LAO.TMP_DIM_UNIQUE_ID)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO) | OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)'", "'(TABLE - OW_LAO.RAW_LAO_DIM_PRODUCT_MAPPING_APOIO)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS) | OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS | [7 empty] | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)]']"] | 0 | 2.1 Migrar ph1 |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS) | OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN) | OW_LAO.PROC_SALES_CAMPAIGN | LAO EStore | r.bojart |  | yes | 5 | Done | SIM | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR)]']"] | 0 | 3.1 Migrar ph1 |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_NAME_AJUSTE) | OW_LAO.PROC_NAME_AJUSTE | [5 empty] | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_BRASIL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_CHILE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_COLOMBIA)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_MEXICO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_PERU)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_BRASIL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_CHILE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_COLOMBIA)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_MEXICO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_PERU)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_URUGUAY)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY) | OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_URUGUAY)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| INGESTION | (INGESTION - JOB.ODS_TARGETS_CAMPAIGN) | JOB.ODS_TARGETS_CAMPAIGN | [7 empty] | 2 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_TARGET_PRODUCTS_CURRENT_YEAR)'", "'(TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS)'", "'(TABLE - OW_LAO.TMP_TARGET_PRODUCTS_PREVIOUS_YEAR)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0008 | ODS | 6 |  | 0 |  |  | 10/09 - 10/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG) | OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS) | OW_LAO.PROC_SALES_CAMPAIGN_TARGETS | LAO EStore | r.bojart |  | yes | 5 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_TARGETS_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_CHANNELS)'", "'(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR)'", "'(TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN)'", "'(TABLE - OW_LAO.DIM_EXCEL_TARGETS_CAMPAIGN)]']"] | 0 | 2.1 Migrar ph1 |  |  | 9 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND) | OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND | [7 empty] | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA)]']"] | 1 | 3.1 Migrar ph1 |  |  | 18 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP | [5 empty] | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA)]']"] | 1 | 3.1 Migrar ph1 |  |  | 18 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN) | OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME)'", "'(TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME)]']"] | 0 | 3.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME) | OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME | [5 empty] | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME)'", "'(TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| INGESTION | (INGESTION - JOB.TMP_CAMPAIGN_NAME) | JOB.TMP_CAMPAIGN_NAME | [7 empty] | 2 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME)'", "'(TABLE - OW_LAO.DIM_CAMPAIGN_NAME)'", "'(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_UPDATE_ID_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 7 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP) | OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP | LAO EStore | r.bojart |  | yes | 6 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.TMP_PAYMENT_PAYMENT_TYPE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP) | OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP | LAO EStore | r.bojart |  | yes | 6 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.TMP_PAYMENT_FUNNEL_STATUS)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU) | OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU |  |  |  | yes |  | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES)'", "'(TABLE - OW_MD.MASTER_TRADE_POLICIES)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_SALES_CHANNEL) | OW_MD.PROC_DIM_SALES_CHANNEL | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_MD.TMP_SALES_CHANNEL_LAO)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_MD.TMP_SALES_CHANNEL_SEDA)]']"] | 1 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 11 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 5 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 |  | 0 |  |  | 10/09 - 10/09
| VIEW | (VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX) | OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX | [7 empty] | 3 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 24 |  | 0 |  |  | 10/09 - 10/09
| VIEW | (VIEW - OW_LAO.VW_ECOM_SKUS_VTEX) | OW_LAO.VW_ECOM_SKUS_VTEX | [7 empty] | 3 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 24 |  | 0 |  |  | 10/09 - 10/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT | [7 empty] | 3 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  | 0 |  |  | 10/09 - 10/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023 | [7 empty] | 3 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  | 0 |  |  | 10/09 - 10/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201 | [7 empty] | 3 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  | 0 |  |  | 10/09 - 10/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023 | [7 empty] | 3 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 13 |  | 0 |  |  | 10/09 - 10/09
| VIEW | (VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE) | OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE | [7 empty] | 3 | 1 | 45910 | 45910 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 12 |  | 0 |  |  | 10/09 - 10/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL) | U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL | [7 empty] | 3 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)]']"] | 1 | 2.1 Migrar ph1 |  |  | 9 |  | 0 |  |  | 10/09 - 10/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST) | U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST | [7 empty] | 3 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEDA)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)'", "'(TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_SAMSUNG_CARE_PLUS_SEASA)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_TRADEIN_AND_TRADEUP_SEASA)]']"] | 1 | 2.1 Migrar ph1 |  |  | 9 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES) | OW_LAO.PROC_ODS_HYBRIS_SALES | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.RAW_HYBRIS_SALES_MONITORING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES)'", "'(TABLE - OW_LAO.RAW_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 6 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM) | OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM | [7 empty] | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 13 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT)'", "'(TABLE - OW_LAO.DIM_MONITORING_BI_LAO_PROCCESS_ALERT)'", "'(TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ID)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.RAW_FILES_MINIO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ALERT)'", "'(TABLE - OW_LAO.TIME_DEFINITION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS) | OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS)'", "'(TABLE - OW_LAO.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS) | OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.STG_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.RAW_LAO_PRODUCT_PREMIUM_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA) | U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_CUSTOMER_ID_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES) | OW_LAO.PROC_D2C_PO_VTEX_SALES |  |  |  | yes | yes | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 21 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP) | OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP | [5 empty] | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 21 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711) | OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711 | [7 empty] | 4 | 1 | 45910 | 45910 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 20 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS) | OW_LAO.PROC_D2C_MELI_COLETAS |  |  |  | yes | yes | Done |  | 4 | 1 | 45910 | 45910 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_LAO.TF_D2C_MELI_COLETAS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_RDD)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 |  | 0 |  |  | 10/09 - 10/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN) | OW_LAO.PROC_D2C_NERP_GROSS_MARGIN |  |  |  | yes | yes | Done | SIM | 4 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_MD.REBATE)'", "'(TABLE - OW_LAO.ODS_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_MD.SOLD_TO_CHANNEL)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  | 0 |  |  | 11/09 - 11/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI) | OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI |  |  |  | yes |  | Done |  | 4 | 1 | 45911 | 45911 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  | 0 |  |  | 11/09 - 11/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW) | OW_LAO.PROC_FT_D2C_BIZOVERVIEW |  |  |  | yes |  | Done |  | 4 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY)'", "'(TABLE - OW_MD.ODS_MEDALIA_TARGET_NPS)'", "'(TABLE - OW_LAO.ODS_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 3.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 11/09 - 11/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2) | OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2 |  |  |  | yes |  | Done |  | 4 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY)'", "'(TABLE - OW_MD.ODS_MEDALIA_TARGET_NPS)'", "'(TABLE - OW_LAO.ODS_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 3.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 11/09 - 11/09
| VIEW | (VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW) | OW_LAO.VW_D2C_ORDER_ONE_VIEW | [5 empty] | Done |  | 3 | 1 | 45911 | 45911 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)'", "'(TABLE - OW_SEDA_S.ODS_WMS_PICKING_PACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 7 |  | 0 |  |  | 11/09 - 11/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI) | OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI |  |  |  | yes | yes | Done | SIM | 4 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.RAW_GSCM_CE_SELL_OUT)'", "'(TABLE - OW_MD.ODS_MP_ESTORE)'", "'(TABLE - OW_LAO.ODS_TARGET_STRETCH)'", "'(TABLE - OW_LAO.RAW_GSCM_MX_SELL_OUT)'", "'(TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES)'", "'(TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_WEEKLY_SALES_KPI)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 10 |  | 0 |  |  | 11/09 - 11/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS) | OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS |  |  |  | yes |  |  |  | 4 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.TF_D2C_NERP_TO_WOS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_TO_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.FT_D2C_NERP_TO_STOCK_OVERVIEW_BY_PLANT)'", "'(TABLE - OW_LAO.TF_D2C_GSCM_TO_WOS)'", "'(TABLE - OW_LAO.ODS_GSCM_FCST_MGMT_D2C)'", "'(TABLE - OW_LAO.FT_D2C_WOS)]']"] | 1 | 1.4 Ingestion NERP |  |  | 7 |  | 0 |  |  | 11/09 - 11/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO) | OW_SEDA_S.PROC_FT_OST_PLUGGTO | [5 empty] | Done |  | 4 | 1 | 45911 | 45911 | ["['[(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  | 11/09 - 11/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM) | OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM | [5 empty] | Done |  | 4 | 1 | 45911 | 45911 | ["['[(TABLE - OW_SEDA_S.RAW_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)'", "'(TABLE - OW_SEDA_S.TMP_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]']"] | 0 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 11/09 - 11/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_PRODUCT) | OW_MD.PROC_DIM_PRODUCT | [5 empty] | Done |  | 4 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_GSCM_PRODUCT_LIST)'", "'(TABLE - OW_MD.ODS_TDF_MARA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_PRODUCT_SKU)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS) | JOB.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)]']"] | 1 | 1.1 Ingestion VTEX | 0.0002 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES) | JOB.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES)]']"] | 1 | 1.1 Ingestion VTEX | 1.7933 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX | 32.5656 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)]']"] | 1 | 1.1 Ingestion VTEX | 5.3735 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)]']"] | 1 | 1.1 Ingestion VTEX | 0.2317 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]']"] | 1 | 1.1 Ingestion VTEX | 0.9546 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX | 1.4594 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | JOB.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX | 1.0527 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA) | JOB.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 1 | 1.1 Ingestion VTEX | 0.0001 | TMP | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 0 | 1.1 Ingestion VTEX | 0.346 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)]']"] | 0 | 1.1 Ingestion VTEX | 1.3423 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)]']"] | 0 | 1.1 Ingestion VTEX | 0.0006 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)]']"] | 0 | 1.1 Ingestion VTEX | 0.2095 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]']"] | 0 | 1.1 Ingestion VTEX | 0.2215 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING) | JOB.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_FEED_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 0 | 1.1 Ingestion VTEX | 0.1928 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS) | JOB.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_SEDA_S.ODS_LINKAPI_VTEX_NERP_INTERFACE_ERRORS)]']"] | 0 | 1.1 Ingestion VTEX | 0.0099 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_AR) | JOB.ODS_VTEX_FEED_SSG_AR | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR)]']"] | 0 | 1.1 Ingestion VTEX | 2.882 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_AR_SMB) | JOB.ODS_VTEX_FEED_SSG_AR_SMB | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0411 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_BR_B2B) | JOB.ODS_VTEX_FEED_SSG_BR_B2B | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_B2B)]']"] | 0 | 1.1 Ingestion VTEX | 0.3744 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_BR_EPP2) | JOB.ODS_VTEX_FEED_SSG_BR_EPP2 | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_BR_EPP2)]']"] | 0 | 1.1 Ingestion VTEX | 4.1824 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_PY) | JOB.ODS_VTEX_FEED_SSG_PY | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_PY)]']"] | 0 | 1.1 Ingestion VTEX | 0.0022 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_FEED_SSG_UY) | JOB.ODS_VTEX_FEED_SSG_UY | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_UY)]']"] | 0 | 1.1 Ingestion VTEX | 0.0031 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA) | JOB.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_MARCOM_SPV_RATES_AND_BENEFITS_DATA)]']"] | 0 | 1.1 Ingestion VTEX | 0.002 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_MASTER_DATA_CL) | JOB.ODS_VTEX_MASTER_DATA_CL | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)]']"] | 0 | 1.1 Ingestion VTEX | 0.0139 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_MASTER_DATA_DOMAIN) | JOB.ODS_VTEX_MASTER_DATA_DOMAIN | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_DOMAIN)]']"] | 0 | 1.1 Ingestion VTEX | 0.0412 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_PRICE_LIST) | JOB.ODS_VTEX_SSG_BR_PRICE_LIST | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PRICE_LIST)]']"] | 0 | 1.1 Ingestion VTEX | 0 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA) | JOB.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_RATES_AND_BENEFITS_DATA)]']"] | 0 | 1.1 Ingestion VTEX | 0.0037 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST) | JOB.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PRICE_LIST)]']"] | 0 | 1.1 Ingestion VTEX | 0 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX) | JOB.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_TAX)]']"] | 0 | 1.1 Ingestion VTEX | 0.002 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA) | JOB.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA)]']"] | 0 | 1.1 Ingestion VTEX | 2.7504 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SEASA_MASTER_DATA_CL) | JOB.RAW_VTEX_SEASA_MASTER_DATA_CL | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.015 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SEASA_MASTER_DATA_EM) | JOB.RAW_VTEX_SEASA_MASTER_DATA_EM | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.0002 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SEASA_TRADEIN_FEED) | JOB.RAW_VTEX_SEASA_TRADEIN_FEED | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.002 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SEDA_MASTER_DATA_CL) | JOB.RAW_VTEX_SEDA_MASTER_DATA_CL | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.0672 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER) | JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0046 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM) | JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0012 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PACKAGE) | JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PACKAGE | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0003 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT) | JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0011 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING) | JOB.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_FEED_SSG_AR_SMB)]']"] | 0 | 1.1 Ingestion VTEX | 0.0032 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_TRADE_UP_SEASA_ORDER) | JOB.RAW_VTEX_TRADE_UP_SEASA_ORDER | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.021 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.RAW_VTEX_TRADE_UP_SEDA_ORDER) | JOB.RAW_VTEX_TRADE_UP_SEDA_ORDER | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.0823 | RAW | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA_TLD) | JOB.TMP_ODS_VTEX_MASTER_DATA_CL_SEDA_TLD | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.1 Ingestion VTEX | 0.0001 | TMP | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_PAYMENTS) | JOB.ODS_HYBRIS_PAYMENTS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)]']"] | 1 | 1.2 Ingestion HYBRIS | 0.2854 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_SALES) | JOB.ODS_HYBRIS_SALES | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS | 0.7395 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_CANCELLATIONS) | JOB.ODS_HYBRIS_CANCELLATIONS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_CANCELLATIONS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0221 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_OFFERS) | JOB.ODS_HYBRIS_OFFERS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_OFFERS)]']"] | 0 | 1.2 Ingestion HYBRIS | 2.0153 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_PREORDERS) | JOB.ODS_HYBRIS_PREORDERS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PREORDERS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0006 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_PRICING) | JOB.ODS_HYBRIS_PRICING | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PRICING)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_REFUNDS) | JOB.ODS_HYBRIS_REFUNDS | [7 empty] | 2 | 1 | 45911 | 45911 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_REFUNDS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0186 | ODS | 1 |  | 0 |  |  | 11/09 - 11/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_RETURNS) | JOB.ODS_HYBRIS_RETURNS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_RETURNS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_REWARDS) | JOB.ODS_HYBRIS_REWARDS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_REWARDS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.1916 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS) | JOB.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.2573 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_HYBRIS_TRADEIN) | JOB.ODS_HYBRIS_TRADEIN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_TRADEIN)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0083 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_CANCELLATIONS) | JOB.RAW_HYBRIS_CANCELLATIONS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0005 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_OFFERS) | JOB.RAW_HYBRIS_OFFERS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_PAYMENTS) | JOB.RAW_HYBRIS_PAYMENTS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_PREORDERS) | JOB.RAW_HYBRIS_PREORDERS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0001 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_PRICING) | JOB.RAW_HYBRIS_PRICING | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_REFUNDS) | JOB.RAW_HYBRIS_REFUNDS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0005 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_RETURNS) | JOB.RAW_HYBRIS_RETURNS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_REWARDS) | JOB.RAW_HYBRIS_REWARDS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0006 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_SALES) | JOB.RAW_HYBRIS_SALES | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0007 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_HYBRIS_TRADEIN) | JOB.RAW_HYBRIS_TRADEIN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_OFFERS_DEDUP) | JOB.TMP_HYBRIS_OFFERS_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_PAYMENTS_DEDUP) | JOB.TMP_HYBRIS_PAYMENTS_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_PREORDERS_DEDUP) | JOB.TMP_HYBRIS_PREORDERS_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_REFUNDS_DEDUP) | JOB.TMP_HYBRIS_REFUNDS_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0002 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_REWARDS_DEDUP) | JOB.TMP_HYBRIS_REWARDS_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_SALES_AGG_DEDUP) | JOB.TMP_HYBRIS_SALES_AGG_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0003 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_SALES_DEDUP) | JOB.TMP_HYBRIS_SALES_DEDUP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0004 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_SALES_VOUCHER_CODE_AGG) | JOB.TMP_HYBRIS_SALES_VOUCHER_CODE_AGG | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 1.2 Ingestion HYBRIS | 0.0006 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_MAGENTO) | JOB.ODS_SELA_API_MAGENTO | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0097 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP) | JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP_SUB) | JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP_SUB | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP_UPDATE) | JOB.ODS_SELA_API_MAGENTO_TOTALS_TEMP_UPDATE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_MAGENTO_UPDATE_TEMP) | JOB.ODS_SELA_API_MAGENTO_UPDATE_TEMP | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0001 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_ODS_SELA_API_MAGENTO_SUB) | JOB.TMP_ODS_SELA_API_MAGENTO_SUB | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0002 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.TMP_ODS_SELA_API_MAGENTO_UPDATE) | JOB.TMP_ODS_SELA_API_MAGENTO_UPDATE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 1.3 Ingestion MAGENTO | 0.0002 | TMP | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | JOB.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)]']"] | 1 | 1.4 Ingestion NERP | 0.1826 | ODS | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | JOB.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)]']"] | 1 | 1.4 Ingestion NERP | 1.4001 | ODS | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW) | JOB.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)]']"] | 1 | 1.4 Ingestion NERP | 0.4139 | ODS | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN) | JOB.RAW_DATA_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)]']"] | 1 | 1.4 Ingestion NERP | 0.2907 | RAW | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_MB51_GR_FOLDER) | JOB.ODS_NERP_MB51_GR_FOLDER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_MB51_GR_FOLDER)]']"] | 1 | 1.4 Ingestion NERP | 0.6549 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZLLEB57910_CLAIM_FOLDER) | JOB.ODS_NERP_ZLLEB57910_CLAIM_FOLDER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)]']"] | 1 | 1.4 Ingestion NERP | 0.004 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRCOS43400_TARGET_FOLDER) | JOB.ODS_NERP_ZRCOS43400_TARGET_FOLDER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER)]']"] | 1 | 1.4 Ingestion NERP | 0.0105 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_MB51_GR_FOLDER) | JOB.RAW_DATA_NERP_MB51_GR_FOLDER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_MB51_GR_FOLDER)]']"] | 1 | 1.4 Ingestion NERP | 0.6733 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_FOLDER) | JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_FOLDER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)]']"] | 1 | 1.4 Ingestion NERP | 0.0054 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_MAINTENANCE) | JOB.RAW_DATA_NERP_ZLLEB57910_CLAIM_MAINTENANCE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE)]']"] | 1 | 1.4 Ingestion NERP | 0.0072 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | JOB.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]']"] | 1 | 1.4 Ingestion NERP | 6.0427 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO) | JOB.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO)'", "'(TABLE - OW_LAO.ODS_NERP_ZRLEJ56150_DEVOLUCAO_SIT_BAIXO)]']"] | 0 | 1.4 Ingestion NERP | 0.0343 | ODS | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS) | JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS)]']"] | 0 | 1.4 Ingestion NERP | 1.2433 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS) | JOB.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS)]']"] | 0 | 1.4 Ingestion NERP | 0.0113 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE) | JOB.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZLLEB57910_CLAIM_MAINTENANCE)]']"] | 0 | 1.4 Ingestion NERP | 0.0006 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRCOA20250_PA_ALLOC_RES) | JOB.ODS_NERP_ZRCOA20250_PA_ALLOC_RES | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRCOA20250_PA_ALLOC_RES)]']"] | 0 | 1.4 Ingestion NERP | 0.0064 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN) | JOB.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN)]']"] | 0 | 1.4 Ingestion NERP | 0.0094 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER) | JOB.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER)]']"] | 0 | 1.4 Ingestion NERP | 0.4483 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS) | JOB.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZRSDE61020_DISPLAY_SAMPLE_INVENTORY_STATUS)]']"] | 0 | 1.4 Ingestion NERP | 0.0016 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER) | JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S110_DATA_BROWSER)]']"] | 0 | 1.4 Ingestion NERP | 0.0003 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER) | JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S120_DATA_BROWSER)]']"] | 0 | 1.4 Ingestion NERP | 0.0003 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER) | JOB.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_SEDA_S.ODS_SEDA_S_NERP_SAMPLE_ZTSDE6S130_DATA_BROWSER)]']"] | 0 | 1.4 Ingestion NERP | 0.0005 | ODS | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZLMKF03006_CONDITION_CALC) | JOB.RAW_DATA_NERP_ZLMKF03006_CONDITION_CALC | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLMKF03006_CONDITION_CALC)]']"] | 0 | 1.4 Ingestion NERP | 0.0036 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | JOB.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 0 | 1.4 Ingestion NERP | 7.6947 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP_PREPARE) | JOB.RAW_NERP_ZRCOA20250_FORECAST_SALES_DEDUP_PREPARE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRCOA20250_FORECAST_SALES_DEDUP_PREPARE)]']"] | 0 | 1.4 Ingestion NERP | 0.0001 | RAW | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.FT_ECOM_ORDER_ITEM) | JOB.FT_ECOM_ORDER_ITEM | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)]']"] | 1 | 2.1 Migrar ph1 | 0.5176 | FT | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.MAP_CANCELLATION_MESSAGE) | JOB.MAP_CANCELLATION_MESSAGE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 1 | 2.1 Migrar ph1 | 0.0001 | MAP | 1 |  | 0 |  |  | 12/09 - 12/09
Control Tower | INGESTION | (INGESTION - JOB.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING) | JOB.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.\\xa0)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)]']"] | 0 | 2.1 Migrar ph1 | 0 | DIM | 2 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.DIM_EXCEL_TARGETS_CAMPAIGN) | JOB.DIM_EXCEL_TARGETS_CAMPAIGN | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - OW_LAO.DIM_EXCEL_TARGETS_CAMPAIGN)]']"] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.DIM_EXCHANGE_RATE) | JOB.DIM_EXCHANGE_RATE | [7 empty] | 2 | 1 | 45912 | 45912 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.003 | DIM | 1 |  | 0 |  |  | 12/09 - 12/09
| INGESTION | (INGESTION - JOB.DIM_MONITORING_BI_LAO_PROCCESS_ALERT) | JOB.DIM_MONITORING_BI_LAO_PROCCESS_ALERT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.DIM_MONITORING_BI_LAO_PROCCESS_ALERT)]']"] | 0 | 2.1 Migrar ph1 | 0.0003 | DIM | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.DIM_SELLER_INSTANCE) | JOB.DIM_SELLER_INSTANCE | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0001 | DIM | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.DIM_SUBSIDIARY) | JOB.DIM_SUBSIDIARY | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0002 | DIM | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_ECOM_ORDER) | JOB.FT_ECOM_ORDER | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)]']"] | 0 | 2.1 Migrar ph1 | 1.3795 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_ECOM_ORDER_KIT_COMPONENT) | JOB.FT_ECOM_ORDER_KIT_COMPONENT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_KIT_COMPONENT)]']"] | 0 | 2.1 Migrar ph1 | 0.0486 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_ECOM_ORDER_PAYMENT) | JOB.FT_ECOM_ORDER_PAYMENT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 0 | 2.1 Migrar ph1 | 0.8166 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_MAGENTO_ORDER) | JOB.FT_MAGENTO_ORDER | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0003 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_MAGENTO_ORDER_ITEM) | JOB.FT_MAGENTO_ORDER_ITEM | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0002 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.FT_MAGENTO_ORDER_PAYMENT) | JOB.FT_MAGENTO_ORDER_PAYMENT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0001 | FT | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.TF_GLOBAL_BI_TRAFFIC_ALL) | JOB.TF_GLOBAL_BI_TRAFFIC_ALL | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0009 | TF | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.TF_GLOBAL_BI_TRAFFIC_DA) | JOB.TF_GLOBAL_BI_TRAFFIC_DA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0007 | TF | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.TF_GLOBAL_BI_TRAFFIC_MX) | JOB.TF_GLOBAL_BI_TRAFFIC_MX | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0008 | TF | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.TF_GLOBAL_BI_TRAFFIC_VD) | JOB.TF_GLOBAL_BI_TRAFFIC_VD | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 2.1 Migrar ph1 | 0.0007 | TF | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_SALES) | JOB.ODS_GLOBAL_BI_SALES | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)]']"] | 1 | 3.1 Migrar ph1 | 1.6817 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_STOCKOUT) | JOB.ODS_GLOBAL_BI_STOCKOUT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT)]']"] | 1 | 3.1 Migrar ph1 | 0.8038 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_ALL) | JOB.ODS_GLOBAL_BI_TRAFFIC_ALL | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 3.1 Migrar ph1 | 0.0042 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_B2B) | JOB.RAW_DATA_API_AFTER_SALES_LIST_B2B | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 1 | 3.1 Migrar ph1 | 0.0012 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_BREA) | JOB.RAW_DATA_API_AFTER_SALES_LIST_BREA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 1 | 3.1 Migrar ph1 | 0 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_EPP2) | JOB.RAW_DATA_API_AFTER_SALES_LIST_EPP2 | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 1 | 3.1 Migrar ph1 | 0.0011 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_CAMPAIGN_TARGET_CHANNELS) | JOB.ODS_CAMPAIGN_TARGET_CHANNELS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS)'", "'(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_CHANNELS)]']"] | 0 | 3.1 Migrar ph1 | 0.002 | ODS | 2 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.TMP_TARGETS_CAMPAIGN) | JOB.TMP_TARGETS_CAMPAIGN | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.TMP_TARGETS_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 | 0.0016 | TMP | 2 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_APPSFLYER_IN_APP_EVENTS) | JOB.ODS_APPSFLYER_IN_APP_EVENTS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_APPSFLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 | 0.1138 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_CAMPAIGN_TARGET_PRODUCTS) | JOB.ODS_CAMPAIGN_TARGET_PRODUCTS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS)]']"] | 0 | 3.1 Migrar ph1 | 0.0012 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_DA) | JOB.ODS_GLOBAL_BI_TRAFFIC_DA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_DA)]']"] | 0 | 3.1 Migrar ph1 | 0.0034 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_MX) | JOB.ODS_GLOBAL_BI_TRAFFIC_MX | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_MX)]']"] | 0 | 3.1 Migrar ph1 | 0.004 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Global D2C BI | INGESTION | (INGESTION - JOB.ODS_GLOBAL_BI_TRAFFIC_VD) | JOB.ODS_GLOBAL_BI_TRAFFIC_VD | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_VD)]']"] | 0 | 3.1 Migrar ph1 | 0.0037 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS) | JOB.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT) | JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT)]']"] | 0 | 3.1 Migrar ph1 | 0.0009 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
Control Tower | INGESTION | (INGESTION - JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM) | JOB.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM)]']"] | 0 | 3.1 Migrar ph1 | 0.0007 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_ORDERS_VISUAR) | JOB.ODS_ORDERS_VISUAR | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_ORDERS_VISUAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0021 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_PAYMENT_FUNNEL) | JOB.ODS_PAYMENT_FUNNEL | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 3.1 Migrar ph1 | 0.3013 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_SALES_CAMPAIGN) | JOB.ODS_SALES_CAMPAIGN | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 | 0.2956 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.ODS_SELA_API_STATUS_MAP) | JOB.ODS_SELA_API_STATUS_MAP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.ODS_SELA_API_STATUS_MAP)]']"] | 0 | 3.1 Migrar ph1 | 0 | ODS | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_APPLYER_IN_APP_EVENTS) | JOB.RAW_APPLYER_IN_APP_EVENTS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_APPSFLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 | 6.625 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_B2B) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_B2B | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0004 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_BREA) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_BREA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_BRSHOP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0046 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_EPP2) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_EPP2 | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0004 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_EST) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_EST | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0007 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_MEMBERS) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_MEMBERS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0005 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_MKP) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_MKP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0074 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_PARC) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_PARC | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0004 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_DETAIL_RESID) | JOB.RAW_DATA_API_AFTER_SALES_DETAIL_RESID | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0002 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP) | JOB.RAW_DATA_API_AFTER_SALES_LIST_BRSHOP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0253 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_EST) | JOB.RAW_DATA_API_AFTER_SALES_LIST_EST | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0029 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_MEMBERS) | JOB.RAW_DATA_API_AFTER_SALES_LIST_MEMBERS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0009 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_MKP) | JOB.RAW_DATA_API_AFTER_SALES_LIST_MKP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0547 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_PARC) | JOB.RAW_DATA_API_AFTER_SALES_LIST_PARC | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0015 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_DATA_API_AFTER_SALES_LIST_RESID) | JOB.RAW_DATA_API_AFTER_SALES_LIST_RESID | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED) | JOB.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.017 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_PRODUCT_TRADEIN) | JOB.RAW_ECOM_PRODUCT_TRADEIN | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_PRODUCT_TRADEIN_SEASA) | JOB.RAW_ECOM_PRODUCT_TRADEIN_SEASA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_PRODUCT_TRADEUP) | JOB.RAW_ECOM_PRODUCT_TRADEUP | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_PRODUCT_TRADEUP_SEASA) | JOB.RAW_ECOM_PRODUCT_TRADEUP_SEASA | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_SKU) | JOB.RAW_ECOM_SKU | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0019 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ECOM_SKU_SAMSUNG_CARE_PLUS) | JOB.RAW_ECOM_SKU_SAMSUNG_CARE_PLUS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0002 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS) | JOB.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.RAW_ORDERS_VISUAR) | JOB.RAW_ORDERS_VISUAR | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.ODS_ORDERS_VISUAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0135 | RAW | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR) | JOB.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR | [7 empty] | 2 | 1 | 45915 | 45915 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 1 |  | 0 |  |  |  | 15/09 - 15/09
| INGESTION | (INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS) | JOB.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS)]']"] | 0 | 3.1 Migrar ph1 | 0.0002 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR) | JOB.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0014 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR) | JOB.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR)]']"] | 0 | 3.1 Migrar ph1 | 0.0012 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | JOB.TMP_ECOM_HQ_ORDERS_PRODUCTS_COMBO | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
Global D2C BI | INGESTION | (INGESTION - JOB.TMP_GLOBAL_BI_SALES) | JOB.TMP_GLOBAL_BI_SALES | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_SALES)]']"] | 0 | 3.1 Migrar ph1 | 0.09 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_MONITORING_BI_LAO_PROCCESS_ALERT) | JOB.TMP_MONITORING_BI_LAO_PROCCESS_ALERT | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ALERT)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_ODS_ECOM_SKU_ENABLES) | JOB.TMP_ODS_ECOM_SKU_ENABLES | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN) | JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID) | JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID_SEASA) | JOB.TMP_RAW_ECOM_PRODUCT_TRADEIN_ID_SEASA | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_RAW_ECOM_SKU_SAMSUNG_CARE_PLUS) | JOB.TMP_RAW_ECOM_SKU_SAMSUNG_CARE_PLUS | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0.0001 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_SALES_CAMPAIGN) | JOB.TMP_SALES_CAMPAIGN | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 | 0.2806 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_UPDATE_CAMPAIGN_NAME) | JOB.TMP_UPDATE_CAMPAIGN_NAME | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_UPDATE_ID_CAMPAIGN) | JOB.TMP_UPDATE_ID_CAMPAIGN | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_UPDATE_ID_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| INGESTION | (INGESTION - JOB.TMP_VL_SALES_CHANNEL_TABLE_BIZTYPE_CHANNEL_NULL) | JOB.TMP_VL_SALES_CHANNEL_TABLE_BIZTYPE_CHANNEL_NULL | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | INGESTION | (INGESTION - JOB.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STATUS_NULL) | JOB.TMP_VL_SALES_CONTROL_TOWER_TABLE_PO_STATUS_NULL | [7 empty] | 2 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | 3.1 Migrar ph1 | 0 | TMP | 1 |  | 0 |  |  |  | 16/09 - 16/09
| VIEW | (VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX) | OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX | [7 empty] | 3 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  | 0 |  |  |  | 16/09 - 16/09
| VIEW | (VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS) | OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS | [5 empty] | Done |  | 3 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 7 |  | 0 |  |  |  | 16/09 - 16/09
| VIEW | (VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW) | OW_LAO.VIEW_RAW_BIZ_OVERVIEW | [7 empty] | 3 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 1.4 Ingestion NERP |  |  | 7 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM)'", "'(TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE)'", "'(TABLE - OW_LAO.ODS_HYBRIS_COMBO)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.DIM_ECOM_PARTNER_LEVEL)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 56 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 30 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE) | OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE |  |  |  | yes |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_CONSOLIDATED)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_LAO.FT_D2C_AR_ONE_VIEW_TABLE)'", "'(TABLE - OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_01)'", "'(TABLE - OW_LAO.TF_D2C_VTEX_PAYMENT_SKU)'", "'(TABLE - OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_02)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 28 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE) | OW_LAO.PROC_D2C_ONE_VIEW_TABLE |  |  |  | yes |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5) | OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5 | LAO EStore | r.bojart |  |  |  | TBC |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG | [7 empty] | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP | LAO EStore | r.bojart |  | yes | 1 | Done | SIM | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 16 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 16 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN) | OW_LAO.PROC_D2C_NERP_SALES_TRADEIN |  |  |  | yes | yes | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 14 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI) | OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI |  |  |  | yes | yes | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 14 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD) | OW_LAO.PROC_D2C_PO_VTEX_RDD |  |  |  | yes | yes |  |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_RDD)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2 | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2 | LAO EStore | r.bojart |  |  |  | Not to be migrated |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  |  | 16/09 - 16/09 | [18 empty] | Confirmed by r.bojart via knox on 21/11
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3 | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done | SIM | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS) | OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS) | OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS | LAO EStore | r.bojart |  | yes | 6 | To be migrated |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES) | OW_LAO.PROC_D2C_NERP_DAILY_SALES |  |  |  | yes | yes | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.TF_D2C_NERP_DAILY_SALES_KPI)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL) | OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL |  |  |  | yes | yes | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES_BY_CHANNEL_KPI)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS) | OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS_HOMOLOG)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS) | OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS | LAO EStore | r.bojart |  | yes | 6 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_GRAFANA_DETAILS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 12 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES | LAO EStore | r.bojart |  | yes | 1 | Done | SIM | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)'", "'(TABLE - OW_LAO.ODS_HYBRIS_COMBO)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 10 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS) | OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS | LAO EStore | r.bojart |  |  |  | Not to be migrated |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 7 |  | 0 |  |  |  | 16/09 - 16/09 | [18 empty] | Confirmed by r.bojart via knox on 21/11
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS) | OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS |  |  |  | No |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_04)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM)'", "'(TABLE - OW_LAO.ODS_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT)'", "'(TABLE - OW_MD.MAP_INCENTIVE_TYPE_MAPPING)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_05)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP_HISTORICO)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE_HISTORICO)'", "'(TABLE - OW_MD.MAP_CUSTOMER_EXCEPTION)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE)'", "'(TABLE - OW_LAO.ODS_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_01)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO_CONSOLIDADO)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_02)'", "'(TABLE - OW_LAO.ODS_GSSC_REPORT_TO_SR)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_03)]']"] | 1 | 1.4 Ingestion NERP |  |  | 19 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION) | OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION |  |  |  | yes |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_LAO.FT_D2C_CELLO_NERP_RETURN_OPERATION)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_WEEKLY)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | 1.4 Ingestion NERP |  |  | 14 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES) | OW_LAO.PROC_D2C_NERP_SALES |  |  |  | yes | yes | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING) | OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING |  |  |  | yes |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)'", "'(TABLE - OW_LAO.FT_D2C_CELLO_NERP_RETURN_PENDING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM | LAO EStore | r.bojart |  | yes | 1 | Done | SIM | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 2.1 Migrar ph1 |  |  | 14 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP) | OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAYMENT_TYPE)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 8 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP) | OW_LAO.PROC_FUNNEL_PAYMENTS_MAP | LAO EStore | r.bojart |  | yes | 6 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAYMENT_TYPE)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 7 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  |  | 16/09 - 16/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI) | OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI | LAO EStore | r.bojart |  | yes | 6 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 |  | 0 |  |  |  | 16/09 - 16/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45916 | 45916 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 |  | 0 |  |  |  | 16/09 - 16/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST_ADJ) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN_TST_ADJ | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VW_SDU_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM) | U_PRJ_ECOM.VW_SDU_RAW_VTEX_SSG_BR_SALES_ORDER_ITEM | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN) | U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_MD.RAW_DATA_MD_MAPPING_PROMOTION_PRODUCT)'", "'(TABLE - U_PRJ_ECOM.TMP_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_NOK) | U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_NOK | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.RAW_AUDIT_VTEX)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_OK) | U_PRJ_ECOM.VW_AUDIT_VTEX_EXCEL_OK | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.RAW_AUDIT_VTEX)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX) | U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VIEW_NERP_ZRCOS43400_TARGET) | OW_LAO.VIEW_NERP_ZRCOS43400_TARGET | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_LAO.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VW_SDU_RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_LAO.VW_SDU_RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VW_SDU_RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER) | OW_LAO.VW_SDU_RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_SEDA_S.VW_AR_CLEARED) | OW_SEDA_S.VW_AR_CLEARED | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_CLEARED_ITEMS)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER) | OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRSDB64000_EXTRACT_PRICE_MASTER)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VIEW_ECOM_EXCHANGE_RATE) | OW_LAO.VIEW_ECOM_EXCHANGE_RATE | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VW_TAB3_PMS_DW) | OW_LAO.VW_TAB3_PMS_DW | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.FT_D2C_ONE_VIEW_TABLE)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VIEW_VTEX_PAYMENTS) | OW_LAO.VIEW_VTEX_PAYMENTS | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.TF_D2C_VTEX_PAYMENT_SKU)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VW_TAB1_PMS_DW) | OW_LAO.VW_TAB1_PMS_DW | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VW_TAB2_PMS_DW) | OW_LAO.VW_TAB2_PMS_DW | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_SEDA_S.VW_SEDA_PREORDER) | OW_SEDA_S.VW_SEDA_PREORDER | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_EPP_STATUS_NEW_RULE) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_EPP_STATUS_NEW_RULE | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_RETROATIVO_TST) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_RETROATIVO_TST | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP05052023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP05052023 | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP15062023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP15062023 | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP21062023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP21062023 | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP27042023) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP27042023 | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_PLATFORM_SEDA) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_PLATFORM_SEDA | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_SL) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_SL | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_bkp26052022) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_bkp26052022 | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADEIN_PAYMENT) | U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADEIN_PAYMENT | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_PAYMENT) | U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_PAYMENT | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_SYNAPCON) | U_PRJ_ECOM.VIEW_ECOM_ORDERS_TRADE_IN_SYNAPCON | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PAYMENT) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PAYMENT | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)]']"] | 0 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
Global D2C BI | VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_BI) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_GLOBAL_BI | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)]']"] | 0 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_2) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_2 | [7 empty] | 3 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 0 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
Global D2C BI | VIEW | (VIEW - OW_LAO.VIEW_ECOM_ODS_GLOBAL_BI_SALES) | OW_LAO.VIEW_ECOM_ODS_GLOBAL_BI_SALES | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)]']"] | 1 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
Global D2C BI | VIEW | (VIEW - OW_LAO.VIEW_ODS_GLOBAL_BI_SALES) | OW_LAO.VIEW_ODS_GLOBAL_BI_SALES | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)]']"] | 1 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VW_APPSFLYER_IN_APP_EVENTS) | OW_LAO.VW_APPSFLYER_IN_APP_EVENTS | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_APPSFLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_SEDA_S.VW_ONLINE_SELL_IN) | OW_SEDA_S.VW_ONLINE_SELL_IN | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)'", "'(TABLE - OW_SEDA_S.ODS_ONLINE_SELL_IN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SAMCOL) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SAMCOL | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEASA) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEASA | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SECH) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SECH | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEDA) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEDA | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEM) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEM | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEPR) | OW_LAO.VIEW_LAO_APPLYER_IN_APP_EVENTS_SEPR | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_APPLYER_IN_APP_EVENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| VIEW | (VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_COMBO | [5 empty] | Done |  | 3 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_TESTE_) | OW_LAO.PROC_TESTE_ | [5 empty] | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN) | U_PRJ_ECOM.PROC_ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN | LAO EStore | r.bojart |  | yes | 4 | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_RAW_VTEX_SSG_BR_B2B_SALES_ORDER_MONITORING_DATASOURCE) | OW_LAO.PROC_RAW_VTEX_SSG_BR_B2B_SALES_ORDER_MONITORING_DATASOURCE | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_INTEGRATION_RAW_VTEX_SALES_COLLECTION) | OW_LAO.PROC_INTEGRATION_RAW_VTEX_SALES_COLLECTION | [7 empty] | 4 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_COLLECTION)'", "'(TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_2020)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_GENERATE) | OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_GENERATE | LAO EStore | r.bojart |  | yes | 4 | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_SEDA_GENERATE) | OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_SEDA_GENERATE | LAO EStore | r.bojart |  | yes | 4 | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_STOCKOUT_VTEX_GLOBALBI) | OW_LAO.PROC_ODS_STOCKOUT_VTEX_GLOBALBI | LAO EStore | r.bojart |  | yes | 4 | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_FILES_DEDUP) | OW_LAO.RAW_VTEX_PAYMENTS_FILES_DEDUP | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS_FILES)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_FILES_GET) | OW_LAO.RAW_VTEX_PAYMENTS_FILES_GET | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS_FILES)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_GENERATE) | OW_LAO.RAW_VTEX_PAYMENTS_GENERATE | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_FT_PRODUCT_STATUS) | OW_MD.PROC_FT_PRODUCT_STATUS | [5 empty] | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_PRODUCT_SKU)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PAYMENTS) | OW_LAO.PROC_ODS_HYBRIS_PAYMENTS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45917 | 45917 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_PAYMENTS)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_CANCELLATIONS) | OW_LAO.PROC_ODS_HYBRIS_CANCELLATIONS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_CANCELLATIONS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_CANCELLATIONS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_OFFERS) | OW_LAO.PROC_ODS_HYBRIS_OFFERS | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_OFFERS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_OFFERS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PREORDERS) | OW_LAO.PROC_ODS_HYBRIS_PREORDERS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PREORDERS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_PREORDERS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REFUNDS) | OW_LAO.PROC_ODS_HYBRIS_REFUNDS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_REFUNDS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_REFUNDS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_RETURNS) | OW_LAO.PROC_ODS_HYBRIS_RETURNS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_RETURNS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_RETURNS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REWARDS) | OW_LAO.PROC_ODS_HYBRIS_REWARDS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_REWARDS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_REWARDS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS) | OW_LAO.PROC_ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS | LAO EStore | r.bojart |  | yes | 1 | Done | SIM | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS)'", "'(TABLE - OW_LAO.STG_HYBRIS_SALES_PRODUCTS_DISCOUNTS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_TRADEIN) | OW_LAO.PROC_ODS_HYBRIS_TRADEIN | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_TRADEIN)'", "'(TABLE - OW_LAO.RAW_HYBRIS_TRADEIN)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_ITEMS_DISCOUNTS) | OW_LAO.PROC_ODS_HYBRIS_SALES_ITEMS_DISCOUNTS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.RAW_HYBRIS_SALES_HOMOLOG)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_DIM_SOLD_TO) | OW_LAO.PROC_D2C_DIM_SOLD_TO |  |  |  | yes | yes | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_FORECAST_OST) | OW_LAO.PROC_D2C_FORECAST_OST |  |  |  | yes |  | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - OW_LAO.RAW_REPASSES_D2C_2022_2024)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | OW_LAO.PROC_INGESTION_ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.RAW_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_OUTBOUND_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_OUTBOUND_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_OUTBOUND_UPDATE_HOMOLOG) | OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_OUTBOUND_UPDATE_HOMOLOG | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_TF_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI_UNPIVOT) | OW_LAO.PROC_TF_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI_UNPIVOT | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_TF_NERP_ZRCOS43400_SALES_PROGRESS_KPI_UNPIVOT_AGG_DIVISION_GROUP) | OW_LAO.PROC_TF_NERP_ZRCOS43400_SALES_PROGRESS_KPI_UNPIVOT_AGG_DIVISION_GROUP | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT2) | OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT2 |  |  |  | yes |  | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TMP_D2C_AR_TABLE_MONTH)'", "'(TABLE - OW_LAO.FT_D2C_AR_TABLE_MONTH)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT2) | OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT2 |  |  |  | yes |  | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.FT_D2C_AR_TABLE_WEEK)'", "'(TABLE - OW_LAO.TMP_D2C_AR_TABLE_WEEK)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_GSCM_INVENTORY) | OW_LAO.PROC_D2C_GSCM_INVENTORY |  |  |  | yes |  | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.FT_D2C_GSCM_INVENTORY)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_KPI) | OW_LAO.PROC_D2C_PO_VTEX_SALES_KPI |  |  |  | yes |  | Done | SIM | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_SELLOUT_PLATFORM_KPI) | OW_LAO.PROC_D2C_VTEX_SELLOUT_PLATFORM_KPI |  |  |  | yes |  | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_INSERT_SALES_CANCELLED_FROM_ODS) | OW_LAO.PROC_INSERT_SALES_CANCELLED_FROM_ODS | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_INSERT_SALES_FROM_ODS) | OW_LAO.PROC_INSERT_SALES_FROM_ODS | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_ALL) | OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_ALL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_ALL)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIM_PRODUCT_MAPPING_LAO_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIM_PRODUCT_MAPPING_LAO_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES) | OW_LAO.PROC_TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_PRODUCT_ESTORE_GLOBAL) | OW_MD.PROC_DIM_PRODUCT_ESTORE_GLOBAL | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_DIM_EXCHANGE_RATE_RAWDATA) | U_PRJ_ECOM.PROC_DIM_EXCHANGE_RATE_RAWDATA | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_COUPON_KPI) | OW_LAO.PROC_D2C_NERP_SALES_COUPON_KPI |  |  |  | yes | yes | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_REWARDS_KPI) | OW_LAO.PROC_D2C_NERP_SALES_REWARDS_KPI |  |  |  | yes | yes | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_O2O_SALES_KPI) | OW_LAO.PROC_D2C_VTEX_O2O_SALES_KPI |  |  |  | yes | yes | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_VTEX_PO_TARGET_LAUNCH_S25) | OW_LAO.PROC_D2C_VTEX_PO_TARGET_LAUNCH_S25 |  |  |  | yes | yes | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_DIM_TAX_GROSS_MARGIN) | OW_LAO.PROC_DIM_TAX_GROSS_MARGIN | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_D2C_VTEX_O2O_SALES_KPI) | OW_LAO.PROC_FT_D2C_VTEX_O2O_SALES_KPI |  |  |  | yes | yes | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_TF_NERP_GROSS_MARGIN_MONITORING_DATASOURCE) | OW_LAO.PROC_TF_NERP_GROSS_MARGIN_MONITORING_DATASOURCE | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_INGESTION_DIM_PRODUCT_ESTORE) | OW_MD.PROC_INGESTION_DIM_PRODUCT_ESTORE | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_INGESTION_DIM_PRODUCT_GLOBAL) | OW_MD.PROC_INGESTION_DIM_PRODUCT_GLOBAL | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_CHECK_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE) | OW_LAO.PROC_CHECK_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_STORENAME_UPDATE) | OW_LAO.PROC_LAO_CRP_CS_STORENAME_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_LAO.RAW_LAO_CRP_CS_STORENAME)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_VOUCHER_COUPON_UPDATE) | OW_LAO.PROC_LAO_CRP_CS_VOUCHER_COUPON_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON)'", "'(TABLE - OW_LAO.RAW_LAO_CRP_CS_VOUCHER_COUPON)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_DELIVERY_MODE_DIM_UPDATE) | OW_LAO.PROC_LAO_DELIVERY_MODE_DIM_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - OW_LAO.RAW_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_DA) | OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_DA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_DA)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_DA)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_MX) | OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_MX | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_MX)'", "'(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_MX)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_VD) | OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_VD | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_VD)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_VD)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP_HOMOLOG) | OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TF_PO_COUPON_ID_CONTROL_TOWER_LIST) | OW_LAO.PROC_TF_PO_COUPON_ID_CONTROL_TOWER_LIST | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE) | OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE_BKP) | OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE_BKP | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_LAO_PREMIUM_PRODUCTS_TABLE_FROM_GSCM_UPDATE) | OW_LAO.PROC_ODS_LAO_PREMIUM_PRODUCTS_TABLE_FROM_GSCM_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_GLOBALBI_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_GLOBALBI_UPDATE | LAO EStore | r.bojart |  | yes | 4 | Done | SIM | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PBI) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PBI | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_GLOBALBI_UPDATE_HOMOLOG) | OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_GLOBALBI_UPDATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_INGESTION_ODS_MP_ESTORE) | OW_MD.PROC_INGESTION_ODS_MP_ESTORE | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_MD.RAW_MP_ESTORE)'", "'(TABLE - OW_MD.ODS_MP_ESTORE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREPP2) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREPP2 | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2ESTUDANTES) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2ESTUDANTES | [5 empty] | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS) | U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - U_PRJ_ECOM.STG_DIGGIT_ECOM_ORDERS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_D2C_FT_STOCKOUT) | OW_LAO.PROC_D2C_FT_STOCKOUT | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT)]']"] | 1 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_GLOBAL_BI_SALES_EMPTY_DIMENSIONS_ALERT) | OW_LAO.PROC_ODS_GLOBAL_BI_SALES_EMPTY_DIMENSIONS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)]']"] | 1 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_ODS_SELA_CUSTOM_ORDERS_ITEMS_UPDATE) | OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_ODS_SELA_CUSTOM_ORDERS_ITEMS_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45918 | 45918 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_DEPARA) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_DEPARA | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS_NERP) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS_NERP | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_ITEMS_EXCLUSIVES_UPDATE) | OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_ITEMS_EXCLUSIVES_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS) | OW_LAO.PROC_ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)'", "'(TABLE - OW_LAO.TMP_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_ORDERS_VISUAR) | OW_LAO.PROC_ODS_ORDERS_VISUAR | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.RAW_ORDERS_VISUAR)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PREMIUM_MODELS_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PREMIUM_MODELS_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_TAXES_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_TAXES_UPDATE | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ) | OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ | LAO EStore | r.bojart |  | yes | 4 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_FEED_SEND_ESTORE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ_BKP10032025) | OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ_BKP10032025 | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_FEED_SEND_ESTORE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI) | OW_LAO.PROC_SALES_CAMPAIGN_PBI | LAO EStore | r.bojart |  | yes | 5 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_CUT)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V2) | OW_LAO.PROC_SALES_CAMPAIGN_PBI_V2 | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_CUT)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V3) | OW_LAO.PROC_SALES_CAMPAIGN_PBI_V3 | LAO EStore | r.bojart |  |  | 0 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_CUT)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_MD.PROC_ODS_SALES_CHANNELS) | OW_MD.PROC_ODS_SALES_CHANNELS | [5 empty] | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_MD.INPUT_SALES_CHANNELS)'", "'(TABLE - OW_MD.ODS_SALES_CHANNELS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRB2B) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRB2B | [7 empty] | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREA) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREA | [7 empty] | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOP) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOP | [7 empty] | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOPMKTPL) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOPMKTPL | [7 empty] | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2MEMBERS) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2MEMBERS | [7 empty] | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2PARCERIAS) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2PARCERIAS | [7 empty] | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2RESIDENCIAL) | OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2RESIDENCIAL | [7 empty] | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | U_PRJ_ECOM.PROC_ECOM_HQ_ORDERS_PRODUCTS_COMBO | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_PRODUCTS_COMBO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP) | U_PRJ_ECOM.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP | LAO EStore | r.bojart |  | yes | 1 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_PRODUCTS_COMBO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_RAW_ECOM_HQ_ORDERS_TRADEIN_FEED) | U_PRJ_ECOM.PROC_RAW_ECOM_HQ_ORDERS_TRADEIN_FEED | LAO EStore | r.bojart |  | yes | 4 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_BLACK_FRIDAY_PBI) | OW_LAO.PROC_BLACK_FRIDAY_PBI | [5 empty] | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_DIM_TARGETS_CAMPAIGN_CADASTRA_UPDATE) | OW_LAO.PROC_DIM_TARGETS_CAMPAIGN_CADASTRA_UPDATE | LAO EStore | r.bojart |  | yes | 5 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_DIVISION_NERP_CONTROL_TOWER_STATUS) | OW_LAO.PROC_DIVISION_NERP_CONTROL_TOWER_STATUS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_FT_AP2_EXCHANGE_RATE_HOMOLOG) | OW_LAO.PROC_FT_AP2_EXCHANGE_RATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_ALL) | OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_ALL | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_ALL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_DA) | OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_DA | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_DA)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_MX) | OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_MX | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_MX)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Global D2C BI | PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_VD) | OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_VD | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_VD)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS) | OW_LAO.PROC_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_EXCHANGE_RATE_HOMOLOG) | OW_LAO.PROC_ODS_EXCHANGE_RATE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Not to be migrated |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09 | [18 empty] | Confirmed by r.bojart via knox on 21/11
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_CHECK_DATASOURCE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_CHECK_DATASOURCE | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_CHECK_DATASOURCE_HOMOLOG) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_CHECK_DATASOURCE_HOMOLOG | LAO EStore | r.bojart |  |  |  | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_MONITORING_DATASOURCE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_MONITORING_DATASOURCE | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_EMPTY_DIMENSIONS_ALERT) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_EMPTY_DIMENSIONS_ALERT | LAO EStore | r.bojart |  | yes | 3 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_STATUS_CANCELED) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_STATUS_CANCELED | LAO EStore | r.bojart |  | yes | 2 | Done | SIM | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS) | OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS) | OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS_VALIDATION) | OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS_VALIDATION | LAO EStore | r.bojart |  | yes | 2 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO) | OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS) | OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY) | OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_SALES_COUPONS) | OW_LAO.PROC_ODS_SELA_SALES_COUPONS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SELA_SALES_COUPONS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_SALES_COUPONS_ITEMS) | OW_LAO.PROC_ODS_SELA_SALES_COUPONS_ITEMS | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SELA_SALES_COUPONS_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP_HOMOLOG) | OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Not to be migrated |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_PAYMENT_TYPE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09 | [18 empty] | Confirmed by r.bojart via knox on 21/11
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_SAMPLE_HQ) | OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_SAMPLE_HQ | LAO EStore | r.bojart |  | yes | 7 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.RAW_FEED_SEND_ESTORE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_DAILY_CHECK) | OW_LAO.PROC_SALES_CAMPAIGN_DAILY_CHECK | LAO EStore | r.bojart |  | yes | 5 | Done |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| PROCEDURE | (PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS_HIST_HOMOLG) | U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS_HIST_HOMOLG | LAO EStore | r.bojart |  |  |  | To be migrated |  | 4 | 1 | 45919 | 45919 | ["['[(TABLE - U_PRJ_ECOM.TMP_DIGGIT_ECOM_ORDERS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
| TABLE | (TABLE - OW_MD.SALES_CHANNEL) | OW_MD.SALES_CHANNEL | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0002 | OTHER | 0 | [(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_MD.PROC_DIM_SALES_CHANNEL),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT)] | 28 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S.M_CODE_CELLO) | OW_SEDA_S.M_CODE_CELLO | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0004 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING_AUX),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5)] | 27 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT) | OW_SEDA_S.TF_CELLO_TRACKING_EVENT | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.748 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | 9 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_MD.COGS) | OW_MD.COGS | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0007 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN),(VIEW - OW_LAO.VW_PMS_TESTE),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711)] | 5 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT) | OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.688 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2),(INGESTION - JOB.RAW_DATA_LAO_MEDALLIA_EXPRESS_REPORT),(INGESTION - JOB.ODS_LAO_MEDALLIA_EXPRESS_REPORT),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW)] | 4 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_MD.ODS_MEDALIA_TARGET_NPS) | OW_MD.ODS_MEDALIA_TARGET_NPS | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW),(PROCEDURE - OW_MD.PROC_INGESTION_ODS_MEDALIA_TARGET_NPS)] | 3 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE) | OW_LAO.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS),(PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI)] | 2 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.ODS_MEDALLIA_EXPRESS_REPORT) | OW_LAO.ODS_MEDALLIA_EXPRESS_REPORT | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0048 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2)] | 2 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S.GSCM_TMP) | OW_SEDA_S.GSCM_TMP | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0004 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_API_GSCM_TO_ASM),(VIEW - OW_SEDA_S.VW_API_GSCM_TO_ASM_2)] | 2 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.ODS_TARGET_STRETCH) | OW_LAO.ODS_TARGET_STRETCH | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] | 1 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.RAW_REPASSES_D2C_2022_2024) | OW_LAO.RAW_REPASSES_D2C_2022_2024 | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0001 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_FORECAST_OST)] | 1 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_MD.MASTER_TRADE_POLICIES) | OW_MD.MASTER_TRADE_POLICIES | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU)] | 1 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_MD.REBATE) | OW_MD.REBATE | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0016 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN)] | 1 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_MD.SOLD_TO_CHANNEL) | OW_MD.SOLD_TO_CHANNEL | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN)] | 1 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_WEEKLY) | OW_SEDA_S.ODS_GLP_RETURN_RATIO_WEEKLY | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0799 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION)] | 1 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SELA.STAGE2_FACT_STOCK_SALES) | OW_SELA.STAGE2_FACT_STOCK_SALES | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0002 | OTHER | 0 | [(PROCEDURE - OW_SELA.ProcMergeDMSDataV2)] | 1 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - U_PRJ_ECOM.VTEX_SSG_AR_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.VTEX_SSG_AR_RATES_AND_BENEFITS_DATA | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.3925 | OTHER | 0 | [(VIEW - OW_LAO.VW_RAW_VTEX_SSG_LAO_SALES_ORDER)] | 1 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_CUSTOMER_RESTRICTION) | OW_APL_POALLOCATION.ODS_CUSTOMER_RESTRICTION | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_CUSTOMER_SOLDS_AND_SHIPS) | OW_APL_POALLOCATION.ODS_CUSTOMER_SOLDS_AND_SHIPS | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0042 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_VALIDATION_OPTIMIZATION) | OW_APL_POALLOCATION.ODS_VALIDATION_OPTIMIZATION | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_VALIDATION_OPTIMIZATION_LOG) | OW_APL_POALLOCATION.ODS_VALIDATION_OPTIMIZATION_LOG | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0034 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_WOS) | OW_APL_POALLOCATION.ODS_WOS | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0049 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_WOS_WEEK) | OW_APL_POALLOCATION.ODS_WOS_WEEK | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0101 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.PRODUCT_COMMENTS) | OW_LAO.PRODUCT_COMMENTS | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.RAW_DATA_LINKAPI_REPORT) | OW_LAO.RAW_DATA_LINKAPI_REPORT | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0 | RAW | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.RAW_DATA_MKP_REPORT_VIA_VAREJO) | OW_LAO.RAW_DATA_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.038 | RAW | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_MD.SOLD_TO_CHANNEL_TMP) | OW_MD.SOLD_TO_CHANNEL_TMP | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S.GSCM_PSI_SALES_DEDUCTION) | OW_SEDA_S.GSCM_PSI_SALES_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0003 | OTHER | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S.GSCM_TMP_2) | OW_SEDA_S.GSCM_TMP_2 | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0004 | OTHER | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_LIST | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0 | RAW | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_RESID) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_RESID | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0 | RAW | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_MKP_REPORT_VIA_VAREJO) | OW_SEDA_S.RAW_DATA_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0501 | RAW | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_CUSTO_SAMSUNG_AEREO_CST) | OW_SEDA_S_COMEX.ODS_CMX_CUSTO_SAMSUNG_AEREO_CST | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_CUSTO_SAMSUNG_MARITIMO_CST) | OW_SEDA_S_COMEX.ODS_CMX_CUSTO_SAMSUNG_MARITIMO_CST | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_DEMURRAGE_CST) | OW_SEDA_S_COMEX.ODS_CMX_DEMURRAGE_CST | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0001 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_ENTREGAS_IMPORTADOS_SVC_CST) | OW_SEDA_S_COMEX.ODS_CMX_ENTREGAS_IMPORTADOS_SVC_CST | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0005 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_MAPA_IMPORTACAO_SVC_HEADER) | OW_SEDA_S_COMEX.ODS_CMX_MAPA_IMPORTACAO_SVC_HEADER | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.001 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_PROCESSOS_LIBERADOS_SVC_CST) | OW_SEDA_S_COMEX.ODS_CMX_PROCESSOS_LIBERADOS_SVC_CST | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0002 | ODS | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_CHANNEL_GROUPING_DAY) | U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_CHANNEL_GROUPING_DAY | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0 | RAW | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_DEVICE) | U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_DEVICE | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0001 | RAW | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - U_PRJ_ECOM.STG_CT_TRADEIN_SEASA) | U_PRJ_ECOM.STG_CT_TRADEIN_SEASA | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 1 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING) | OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 0 | Check | 0.0092 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HISTORICO),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HISTORICO),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_DUEK),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HIST),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_V2),(PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING_1_0),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_DUEK),(PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HIST)] | 13 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS) | OW_LAO.MONITORING_BI_LAO_PROCCESS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 0 | Check | 0.4748 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS_NERP),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_DEPARA),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS)] | 11 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER) | U_PRJ_ECOM.RAW_PRODUCT_SEASA_ORDER | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 0 | Check | 0.0482 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023)] | 8 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER) | U_PRJ_ECOM.RAW_PRODUCT_SEDA_ORDER | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 0 | Check | 0.2788 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP14112023),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL_TST),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_BKP_20240201),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_SYNAPCOM_TST_AJ_DISCOUNT),(VIEW - OW_LAO.VW_ECOM_SKUS_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_VTEX_ORDERS_MODEL),(VIEW - OW_LAO.VIEW_ECOM_SKUS_ELIGIBLE_VTEX),(VIEW - U_PRJ_ECOM.VIEW_ECOM_HQ_ORDERS_PRODUCTS_PAYMENT_TST_BKP14112023)] | 8 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE) | OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_V2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_DUEK),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HIST),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HISTORICO),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2)] | 6 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM) | OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM)] | 6 | [9 empty] | 27/10 - 27/10
Control Tower | TABLE | (TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES) | OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES | [5 empty] | Done |  | 1 | 1 | 45957 | 45957 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_TAXES_UPDATE)] | 5 | [9 empty] | 27/10 - 27/10
| TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS) | OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2)] | 5 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1) | OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1 | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0243 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_2),(PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_1),(PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_5),(PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_4),(PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_3)] | 5 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING) | OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WERABLES_SITE_MAPPING_MERGE_AUTOMATIC),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC),(VIEW - OW_LAO.VW_CRAWLING_AP1_NPC_SEGMENT)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING) | OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1_V2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1),(VIEW - OW_LAO.VW_CRAWLING_AP1_REF_SEGMENT),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_SITE_MAPPING_MERGE_AUTOMATIC)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING) | OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0 | OTHER | 0 | [(VIEW - OW_LAO.VW_CRAWLING_AP1_TV_SEGMENT),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_SITE_MAPPING_MERGE_AUTOMATIC),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1_V2)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING) | OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1_V2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_SITE_MAPPING_MERGE_AUTOMATIC),(VIEW - OW_LAO.VW_CRAWLING_AP1_WM_SEGMENT)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_MD.OLD_DIM_PRODUCT) | OW_MD.OLD_DIM_PRODUCT | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0284 | OTHER | 0 | [(VIEW - OW_MD.VW_VTEX_PURCHASE_ORDER_ESTORE),(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM),(PROCEDURE - OW_MD.PROC_DIM_PRODUCT)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0093 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA),(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM),(VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA_VIAGEM_ESCOLTA),(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0049 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA_VIAGEM_ESCOLTA),(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA),(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_ESCOLTA),(VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA) | OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.011 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA),(VIEW - OW_SEDA_S.TF_PORTAL_SM_SURSIS_JOIN_1),(INGESTION - JOB.ODS_SURSIS_DELIVERY_DATA),(VIEW - OW_SEDA_S.VW_PORTAL_SM_SURSIS)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_SURSIS_ESCORT) | OW_SEDA_S.ODS_SURSIS_ESCORT | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0065 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_PORTAL_SM_SURSIS),(INGESTION - JOB.ODS_SURSIS_ESCORT),(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA),(VIEW - OW_SEDA_S.TF_PORTAL_SM_SURSIS_JOIN_1)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SELA.DIM_PRODUCT) | OW_SELA.DIM_PRODUCT | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0021 | DIM | 0 | [(VIEW - OW_SELA.MISSINGSEGMENT),(PROCEDURE - OW_SELA.ProcMergeDMSDataV2),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(VIEW - OW_SELA.MISSING_MKTNAME)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SELA.FACT_STOCK_SALES) | OW_SELA.FACT_STOCK_SALES | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.2849 | OTHER | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(VIEW - OW_SELA.MISSING_MKTNAME),(VIEW - OW_SELA.CURRENTWEEK),(PROCEDURE - OW_SELA.ProcMergeDMSDataV2)] | 4 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES) | OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.018 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION),(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS)] | 3 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING_KEY) | OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING_KEY | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.3527 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2),(PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING_1_0)] | 3 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_NC) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_NC | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0051 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA),(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA),(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_NC)] | 3 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_SURSIS_NC) | OW_SEDA_S.ODS_SURSIS_NC | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0052 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_PORTAL_SM_SURSIS),(INGESTION - JOB.ODS_SURSIS_NC),(VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA)] | 3 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SELA.DIM_MN_SEGMENT) | OW_SELA.DIM_MN_SEGMENT | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0001 | DIM | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD),(VIEW - OW_SELA.MISSINGSEGMENT),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | 3 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SELA.DIM_WEEK) | OW_SELA.DIM_WEEK | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0001 | DIM | 0 | [(VIEW - OW_SELA.CURRENTWEEK),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD)] | 3 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES) | U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0005 | ODS | 0 | [(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(VIEW - U_PRJ_ECOM.VIEW_ECOM_ORD_TST),(INGESTION - JOB.ODS_ECOM_SKU_ENABLES)] | 3 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.CRAWLER_PROCESS_LIST) | OW_LAO.CRAWLER_PROCESS_LIST | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0027 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_RETRY_PRODUCTS),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_CRAWLER_STATUS)] | 2 | [9 empty] | 28/10 - 28/10
Control Tower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE)] | 2 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT) | OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0018 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT)] | 2 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT_FLOORING) | OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT_FLOORING | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0006 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_FLOORING),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE)] | 2 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SELA.DIM_DC) | OW_SELA.DIM_DC | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0001 | DIM | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD)] | 2 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SELA.FCST_SNAPSHOT) | OW_SELA.FCST_SNAPSHOT | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.011 | OTHER | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | 2 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SELA.TMP_DLAKE_HIST) | OW_SELA.TMP_DLAKE_HIST | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.3991 | TMP | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | 2 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SELA.TMP_DLAKE_W3) | OW_SELA.TMP_DLAKE_W3 | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.004 | TMP | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD)] | 2 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SELA.TMP_DLAKE_W8) | OW_SELA.TMP_DLAKE_W8 | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0002 | TMP | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST),(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD)] | 2 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS) | OW_LAO.AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0006 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.AUX_YAMI_PRODUCT_DETAIL_STATUS) | OW_LAO.AUX_YAMI_PRODUCT_DETAIL_STATUS | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.CRAWLER_STATUS) | OW_LAO.CRAWLER_STATUS | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0673 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_CRAWLER_STATUS)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.STG_HYBRIS_SALES_PRODUCTS_DISCOUNTS) | OW_LAO.STG_HYBRIS_SALES_PRODUCTS_DISCOUNTS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0006 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS) | OW_LAO.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.STG_LAO_PRODUCT_PREMIUM_ITEMS) | OW_LAO.STG_LAO_PRODUCT_PREMIUM_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.TIME_DEFINITION) | OW_LAO.TIME_DEFINITION | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_LAO.TMP_MAP_ESTORE_URL_SKU) | OW_LAO.TMP_MAP_ESTORE_URL_SKU | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0006 | TMP | 0 | [(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_ESTORE_URL_SKU)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_MD.ODS_MD_MAPPING_PROMOTION_PRODUCT) | OW_MD.ODS_MD_MAPPING_PROMOTION_PRODUCT | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 | [(INGESTION - JOB.ODS_MD_MAPPING_PROMOTION_PRODUCT)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_MD.RAW_DATA_MD_MAPPING_PROMOTION_PRODUCT) | OW_MD.RAW_DATA_MD_MAPPING_PROMOTION_PRODUCT | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0001 | RAW | 0 | [(VIEW - U_PRJ_ECOM.VW_RAW_VTEX_SSG_BR_SHOP_PROMOTION_TAX_OPEN)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_MD.RAW_MEDALIA_TARGET_NPS) | OW_MD.RAW_MEDALIA_TARGET_NPS | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0001 | RAW | 0 | [(PROCEDURE - OW_MD.PROC_INGESTION_ODS_MEDALIA_TARGET_NPS)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ACCOUNT_MANAGEMENT_FLOORSHRE_TT) | OW_SEDA_S.ACCOUNT_MANAGEMENT_FLOORSHRE_TT | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_DIRECTSHIP_RAWDATA_GPL) | OW_SEDA_S.ODS_DIRECTSHIP_RAWDATA_GPL | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0249 | ODS | 0 | [(INGESTION - JOB.ODS_DIRECTSHIP_RAWDATA_GPL)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_ONTIMEGI_RAWDATA_GPL) | OW_SEDA_S.ODS_ONTIMEGI_RAWDATA_GPL | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0413 | ODS | 0 | [(INGESTION - JOB.ODS_ONTIMEGI_RAWDATA_GPL)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_ONTIMEGR_RAWDATA_GPL) | OW_SEDA_S.ODS_ONTIMEGR_RAWDATA_GPL | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.027 | ODS | 0 | [(INGESTION - JOB.ODS_ONTIMEGR_RAWDATA_GPL)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_RP_DOA_INSPECTION_RESULT) | OW_SEDA_S.ODS_RP_DOA_INSPECTION_RESULT | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.1115 | ODS | 0 | [(INGESTION - JOB.ODS_RP_DOA_INSPECTION_RESULT)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_RP_DOA_TRACKING_BY_SERIAL) | OW_SEDA_S.ODS_RP_DOA_TRACKING_BY_SERIAL | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0802 | ODS | 0 | [(INGESTION - JOB.ODS_RP_DOA_TRACKING_BY_SERIAL)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_CHECKLIST) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_CHECKLIST | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0011 | ODS | 0 | [(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_CHECKLIST)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA | [5 empty] | Done |  | 1 | 1 | 45958 | 45958 | ['[]'] | 0 | Check | 0.0007 | ODS | 0 | [(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA)] | 1 | [9 empty] | 28/10 - 28/10
| TABLE | (TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS) | OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0005 | ODS | 0 | [(INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_SEDA_S.ODS_SURICATO_HR) | OW_SEDA_S.ODS_SURICATO_HR | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0038 | ODS | 0 | [(INGESTION - JOB.ODS_SURICATO_HR)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_SEDA_S.ODS_TV_WEEKLY_GFK) | OW_SEDA_S.ODS_TV_WEEKLY_GFK | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.004 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_SEDA_S.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT) | OW_SEDA_S.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.2136 | ODS | 0 | [(INGESTION - JOB.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MKP) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MKP | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0356 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MKP)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_SEDA_S.TMP_ODS_GENERIC_INPUT) | OW_SEDA_S.TMP_ODS_GENERIC_INPUT | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0141 | TMP | 0 | [(INGESTION - JOB.TMP_ODS_GENERIC_INPUT)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_SEDA_S.VW_MX_FOTA_AND_GFK) | OW_SEDA_S.VW_MX_FOTA_AND_GFK | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0021 | OTHER | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_SELA.DIM_COUNTRY) | OW_SELA.DIM_COUNTRY | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0001 | DIM | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_SELA.DIM_COUNTRY_BRANCH) | OW_SELA.DIM_COUNTRY_BRANCH | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0004 | DIM | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_SELA.DIM_GROWTH) | OW_SELA.DIM_GROWTH | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0001 | DIM | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_SELA.WOS_PARAMETERS) | OW_SELA.WOS_PARAMETERS | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 | [(PROCEDURE - OW_SELA.PROCSNAPSHOTFCST)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_FASTSHOP) | U_PRJ_ECOM.ODS_MKP_D2C_FASTSHOP | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0325 | ODS | 0 | [(INGESTION - JOB.ODS_MKP_D2C_FASTSHOP)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - U_PRJ_ECOM.RAW_CUSTOMER_ID_SEDA) | U_PRJ_ECOM.RAW_CUSTOMER_ID_SEDA | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0059 | RAW | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - U_PRJ_ECOM.STG_DIGGIT_ECOM_ORDERS) | U_PRJ_ECOM.STG_DIGGIT_ECOM_ORDERS | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 | [(PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS)] | 1 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.OAUTH_ACCESS_TOKEN) | OW_APL_POALLOCATION.OAUTH_ACCESS_TOKEN | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0012 | OTHER | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.OAUTH_REFRESH_TOKEN) | OW_APL_POALLOCATION.OAUTH_REFRESH_TOKEN | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0034 | OTHER | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_AIR_CAPACITY) | OW_APL_POALLOCATION.ODS_AIR_CAPACITY | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0005 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_ALIGNMENT_CRITERIA) | OW_APL_POALLOCATION.ODS_ALIGNMENT_CRITERIA | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_ALIGNMENT_CRITERIA_WEEK) | OW_APL_POALLOCATION.ODS_ALIGNMENT_CRITERIA_WEEK | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT) | OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.007 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT_STOCK) | OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT_STOCK | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.003 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT_WEEKLY) | OW_APL_POALLOCATION.ODS_ALIGNMENT_RESULT_WEEKLY | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0259 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_AP1) | OW_APL_POALLOCATION.ODS_AP1 | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0021 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_AP1_WEEK) | OW_APL_POALLOCATION.ODS_AP1_WEEK | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0057 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_APPLICATION_CLIENT) | OW_APL_POALLOCATION.ODS_APPLICATION_CLIENT | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_APPLICATION_CLIENT_GRANT) | OW_APL_POALLOCATION.ODS_APPLICATION_CLIENT_GRANT | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_APPLICATION_SCOPE) | OW_APL_POALLOCATION.ODS_APPLICATION_SCOPE | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_AVAILABLE_CARS) | OW_APL_POALLOCATION.ODS_AVAILABLE_CARS | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_AVERAGE_DIVISION_WEIGHT) | OW_APL_POALLOCATION.ODS_AVERAGE_DIVISION_WEIGHT | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_CALENDAR_SAMSUNG) | OW_APL_POALLOCATION.ODS_CALENDAR_SAMSUNG | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_CONFIGURATION) | OW_APL_POALLOCATION.ODS_CONFIGURATION | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_DIVISION_COMPATIBILITY) | OW_APL_POALLOCATION.ODS_DIVISION_COMPATIBILITY | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_DIVISION_MAP) | OW_APL_POALLOCATION.ODS_DIVISION_MAP | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_DO_NOT_ALIGN_SO) | OW_APL_POALLOCATION.ODS_DO_NOT_ALIGN_SO | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_EXECUTION_OPTIMIZATION) | OW_APL_POALLOCATION.ODS_EXECUTION_OPTIMIZATION | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_EXECUTION_OPTIMIZATION_LOG) | OW_APL_POALLOCATION.ODS_EXECUTION_OPTIMIZATION_LOG | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_FILES) | OW_APL_POALLOCATION.ODS_FILES | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0005 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_FILES_COLUMNS_DATA_BIND) | OW_APL_POALLOCATION.ODS_FILES_COLUMNS_DATA_BIND | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_HOLIDAY) | OW_APL_POALLOCATION.ODS_HOLIDAY | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0005 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_HUB_LOG) | OW_APL_POALLOCATION.ODS_HUB_LOG | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_INVOICE_RESTRICTION) | OW_APL_POALLOCATION.ODS_INVOICE_RESTRICTION | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_KEEP_ALIGNMENT) | OW_APL_POALLOCATION.ODS_KEEP_ALIGNMENT | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_LEAD_TIME) | OW_APL_POALLOCATION.ODS_LEAD_TIME | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0005 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_MULTIPLES) | OW_APL_POALLOCATION.ODS_MULTIPLES | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0006 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_OPTIMIZATION_RESULT) | OW_APL_POALLOCATION.ODS_OPTIMIZATION_RESULT | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0309 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_OUTBOUND) | OW_APL_POALLOCATION.ODS_OUTBOUND | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.009 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PLANT_SOURCE_MAP) | OW_APL_POALLOCATION.ODS_PLANT_SOURCE_MAP | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PRODUCT) | OW_APL_POALLOCATION.ODS_PRODUCT | [5 empty] | Done |  | 1 | 1 | 45959 | 45959 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 29/10 - 29/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PRODUCTION_PLAN) | OW_APL_POALLOCATION.ODS_PRODUCTION_PLAN | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PRODUCTION_PLAN_MONTH_DAY) | OW_APL_POALLOCATION.ODS_PRODUCTION_PLAN_MONTH_DAY | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0014 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PRODUCT_KIT) | OW_APL_POALLOCATION.ODS_PRODUCT_KIT | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PRODUCT_RTF_WEEK) | OW_APL_POALLOCATION.ODS_PRODUCT_RTF_WEEK | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0045 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_PROJECTED_STOCK) | OW_APL_POALLOCATION.ODS_PROJECTED_STOCK | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0109 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_RDD_HORIZON) | OW_APL_POALLOCATION.ODS_RDD_HORIZON | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0006 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALABLE_STORAGE_LOCATION) | OW_APL_POALLOCATION.ODS_SALABLE_STORAGE_LOCATION | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALES_MAPPING) | OW_APL_POALLOCATION.ODS_SALES_MAPPING | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0009 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALES_ORDER) | OW_APL_POALLOCATION.ODS_SALES_ORDER | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0111 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_CANCEL) | OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_CANCEL | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0106 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_CREATE) | OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_CREATE | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0289 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_EDIT) | OW_APL_POALLOCATION.ODS_SALES_ORDER_TO_EDIT | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SHIP_COMPATIBILITY) | OW_APL_POALLOCATION.ODS_SHIP_COMPATIBILITY | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_SKU_CUBAGE_VOLUME) | OW_APL_POALLOCATION.ODS_SKU_CUBAGE_VOLUME | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0051 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_STOCK) | OW_APL_POALLOCATION.ODS_STOCK | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0005 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_USER) | OW_APL_POALLOCATION.ODS_USER | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_USER_LAST_PASSWORD) | OW_APL_POALLOCATION.ODS_USER_LAST_PASSWORD | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_USER_PROFILE_ROLE) | OW_APL_POALLOCATION.ODS_USER_PROFILE_ROLE | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_USER_RESTRICT_ACCOUNTS) | OW_APL_POALLOCATION.ODS_USER_RESTRICT_ACCOUNTS | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_USER_RESTRICT_PROD_GROUPS) | OW_APL_POALLOCATION.ODS_USER_RESTRICT_PROD_GROUPS | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_VEHICLE_CAPACITY) | OW_APL_POALLOCATION.ODS_VEHICLE_CAPACITY | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_WAREHOUSE_CAPACITY) | OW_APL_POALLOCATION.ODS_WAREHOUSE_CAPACITY | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_POALLOCATION.ODS_YOUR_REFERENCE_DATA) | OW_APL_POALLOCATION.ODS_YOUR_REFERENCE_DATA | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_ALLOWED_EMAIL) | OW_APL_TRUSTED_AUTH.TB_ALLOWED_EMAIL | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_EMAIL_TOKEN) | OW_APL_TRUSTED_AUTH.TB_EMAIL_TOKEN | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_EMAIL_VIEW_PATH) | OW_APL_TRUSTED_AUTH.TB_EMAIL_VIEW_PATH | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_SYSTEM_CONFIG) | OW_APL_TRUSTED_AUTH.TB_SYSTEM_CONFIG | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_SYSTEM_LOG) | OW_APL_TRUSTED_AUTH.TB_SYSTEM_LOG | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_USER) | OW_APL_TRUSTED_AUTH.TB_USER | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0003 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_APL_TRUSTED_AUTH.TB_USER_WRONG_PASSWORD_ENTRY) | OW_APL_TRUSTED_AUTH.TB_USER_WRONG_PASSWORD_ENTRY | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.ADJ_RAW_NERP_ZRSDD6A310_DISPLAY_ESTORE_E2E_MONITORING_INFO) | OW_LAO.ADJ_RAW_NERP_ZRSDD6A310_DISPLAY_ESTORE_E2E_MONITORING_INFO | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.089 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.ARIMA_RESULTS) | OW_LAO.ARIMA_RESULTS | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.AUX_NERP_ZRCOA20250_FORECAST_SALES_B2C_FILTER) | OW_LAO.AUX_NERP_ZRCOA20250_FORECAST_SALES_B2C_FILTER | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.AUX_ODS_CRAWLING_AP1_REF_PRODUCT_DETAIL_DAILY) | OW_LAO.AUX_ODS_CRAWLING_AP1_REF_PRODUCT_DETAIL_DAILY | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.BASE64) | OW_LAO.BASE64 | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.BIZ_AREA_TESTE_TALEND) | OW_LAO.BIZ_AREA_TESTE_TALEND | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.BIZ_AREA_TESTE_TALEND_V2) | OW_LAO.BIZ_AREA_TESTE_TALEND_V2 | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CONTROLE_JOB_SALES_ORDER_TRACKING) | OW_LAO.CONTROLE_JOB_SALES_ORDER_TRACKING | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CONTROLE_JOB_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.CONTROLE_JOB_ZLLEJ50090_OUTBOUND_TRACKING | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CRAWLER_BANNER_STEPS) | OW_LAO.CRAWLER_BANNER_STEPS | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CRAWLER_COMMENT_STEPS) | OW_LAO.CRAWLER_COMMENT_STEPS | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0003 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CRAWLER_NEWS_DATA) | OW_LAO.CRAWLER_NEWS_DATA | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CRAWLER_NEWS_STEPS) | OW_LAO.CRAWLER_NEWS_STEPS | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CRAWLER_NEWS_URLS) | OW_LAO.CRAWLER_NEWS_URLS | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CRAWLER_PARAMETER_SCHEDULE) | OW_LAO.CRAWLER_PARAMETER_SCHEDULE | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CRAWLER_PRODUCT_PRICE_STEPS) | OW_LAO.CRAWLER_PRODUCT_PRICE_STEPS | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0005 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CRAWLER_PRODUCT_SPECS_STEPS) | OW_LAO.CRAWLER_PRODUCT_SPECS_STEPS | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0003 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.CRAWLER_SCHEDULE) | OW_LAO.CRAWLER_SCHEDULE | [5 empty] | Done |  | 1 | 1 | 45960 | 45960 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [9 empty] | 30/10 - 30/10
| TABLE | (TABLE - OW_LAO.DELETE_TO_REF) | OW_LAO.DELETE_TO_REF | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0103 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.DELETE_TO_TV) | OW_LAO.DELETE_TO_TV | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0102 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.DELETE_TO_WM) | OW_LAO.DELETE_TO_WM | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0093 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.LAO_FT_ORDER_OPERATION_LEAD_TIME) | OW_LAO.LAO_FT_ORDER_OPERATION_LEAD_TIME | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0013 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.LAO_ONLINE_PRICE_LOG) | OW_LAO.LAO_ONLINE_PRICE_LOG | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0149 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.LAO_ONLINE_PRICE_STORE_REF) | OW_LAO.LAO_ONLINE_PRICE_STORE_REF | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0003 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.LAO_SALES_DEDUCTION_WEEK_REPORT_DATA) | OW_LAO.LAO_SALES_DEDUCTION_WEEK_REPORT_DATA | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.LAO_SALES_DEDUCTION_WEEK_REPORT_DATA_TESTE_PENTAHO) | OW_LAO.LAO_SALES_DEDUCTION_WEEK_REPORT_DATA_TESTE_PENTAHO | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.MP_COUNTRY) | OW_LAO.MP_COUNTRY | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.MP_EMAIL) | OW_LAO.MP_EMAIL | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.MP_ESTORE) | OW_LAO.MP_ESTORE | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.MP_EVENTS) | OW_LAO.MP_EVENTS | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.MP_MEDIA) | OW_LAO.MP_MEDIA | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0006 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.MP_MEDIA_SCRAPING) | OW_LAO.MP_MEDIA_SCRAPING | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.MP_NEWSROOM) | OW_LAO.MP_NEWSROOM | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0022 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.MP_SNS) | OW_LAO.MP_SNS | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.MP_VALIDATION_CRAWLING_AP1_PRODUCT_DAILY_PRICE) | OW_LAO.MP_VALIDATION_CRAWLING_AP1_PRODUCT_DAILY_PRICE | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.ODS_ITAU_BALLOON_REFUND_INFO) | OW_LAO.ODS_ITAU_BALLOON_REFUND_INFO | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0008 | ODS | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.ODS_LINKAPI_REPORT) | OW_LAO.ODS_LINKAPI_REPORT | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0057 | ODS | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.ODS_LINKAPI_REVERSE_REFUND_TRACKING) | OW_LAO.ODS_LINKAPI_REVERSE_REFUND_TRACKING | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0038 | ODS | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.ODS_MKP_REPORT_VIA_VAREJO) | OW_LAO.ODS_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0127 | ODS | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.ODS_PMS_PRICE_SIMULATION) | OW_LAO.ODS_PMS_PRICE_SIMULATION | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0203 | ODS | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.ODS_PMS_PROMOTION) | OW_LAO.ODS_PMS_PROMOTION | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0296 | ODS | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.ODS_SNS_DL) | OW_LAO.ODS_SNS_DL | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.1026 | ODS | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.PAL_ARIMA_DATA_TBL) | OW_LAO.PAL_ARIMA_DATA_TBL | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.RAW_DATA_LAO_MEDALLIA_EXPRESS_REPORT) | OW_LAO.RAW_DATA_LAO_MEDALLIA_EXPRESS_REPORT | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0734 | RAW | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.RAW_DATA_VOUCHER) | OW_LAO.RAW_DATA_VOUCHER | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0038 | RAW | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT) | OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.9447 | RAW | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT_CLEAN) | OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT_CLEAN | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.6855 | RAW | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT_PIVOT) | OW_LAO.RAW_LAO_MEDALLIA_EXPRESS_REPORT_PIVOT | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0052 | RAW | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.RAW_TALEND_GUIDE_DATA) | OW_LAO.RAW_TALEND_GUIDE_DATA | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0001 | RAW | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.RAW_TALEND_GUIDE_FILE_REGISTRATION) | OW_LAO.RAW_TALEND_GUIDE_FILE_REGISTRATION | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0001 | RAW | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.STG_ORDERS_VISUAR) | OW_LAO.STG_ORDERS_VISUAR | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TEMPLATETABLE) | OW_LAO.TEMPLATETABLE | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0004 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TEMP_ACCESS_CODE_PARTNER_LEVEL_SMB_1) | OW_LAO.TEMP_ACCESS_CODE_PARTNER_LEVEL_SMB_1 | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0004 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TEMP_DIM_MAPPING) | OW_LAO.TEMP_DIM_MAPPING | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST) | OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.1322 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST_SSGBR) | OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST_SSGBR | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.1274 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST_V1) | OW_LAO.TEMP_FEED_SEND_ESTORE_GB_HIST_V1 | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.1322 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
Control Tower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MX) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_ELIGIBLE_MX | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0003 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
Control Tower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_1) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_1 | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0003 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
Control Tower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_FILTER_1) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_FILTER_1 | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0005 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TEMP_PARTNER_LEVEL_SMB_SEASA_1) | OW_LAO.TEMP_PARTNER_LEVEL_SMB_SEASA_1 | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TEMP_PRD_NERP) | OW_LAO.TEMP_PRD_NERP | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.001 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TEMP_PRD_NERP_1) | OW_LAO.TEMP_PRD_NERP_1 | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0011 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TESTE_TMP_VALIDATION_IM_PT2) | OW_LAO.TESTE_TMP_VALIDATION_IM_PT2 | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0128 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TESTE_TMP_VALIDATION_IM_PT3) | OW_LAO.TESTE_TMP_VALIDATION_IM_PT3 | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0.0156 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TIME_SERIES_DATA) | OW_LAO.TIME_SERIES_DATA | [5 empty] | Done |  | 1 | 1 | 45961 | 45961 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [9 empty] | 31/10 - 31/10
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_CANCELLATIONS_DEDUP) | OW_LAO.TMP_HYBRIS_CANCELLATIONS_DEDUP | [5 empty] | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | TMP | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_LAO.TMP_HYBRIS_TRADEIN_DEDUP) | OW_LAO.TMP_HYBRIS_TRADEIN_DEDUP | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0004 | TMP | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_LAO.TMP_LINKAPI_REVERSE_REFUND_TRACKING) | OW_LAO.TMP_LINKAPI_REVERSE_REFUND_TRACKING | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0 | TMP | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_LAO.TMP_MEDALLIA_EXPRESS_REPORT) | OW_LAO.TMP_MEDALLIA_EXPRESS_REPORT | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0014 | TMP | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_LAO.TMP_MKP_REPORT_VIA_VAREJO) | OW_LAO.TMP_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0009 | TMP | 0 |  | 0 | [10 empty] | 03/11 - 03/11
Control Tower | TABLE | (TABLE - OW_LAO.TMP_PO_QTY_CONTROL_TOWER) | OW_LAO.TMP_PO_QTY_CONTROL_TOWER | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0001 | TMP | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_LAO.TMP_PROC_ODS_ORDERS_VISUAR) | OW_LAO.TMP_PROC_ODS_ORDERS_VISUAR | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0016 | TMP | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_LAO_SSC_HR.TB_LABOR_COST) | OW_LAO_SSC_HR.TB_LABOR_COST | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_LAO_SSC_HR.TB_LABOR_COST_teste2) | OW_LAO_SSC_HR.TB_LABOR_COST_teste2 | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_MD.COGS_TMP) | OW_MD.COGS_TMP | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_MD.MASTER_TRADE_POLICIES_TMP) | OW_MD.MASTER_TRADE_POLICIES_TMP | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_MD.ODS_ERP_MD_CUSTOMER) | OW_MD.ODS_ERP_MD_CUSTOMER | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0713 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_MD.RAW_JENKINS_API_REST_PROJECTS) | OW_MD.RAW_JENKINS_API_REST_PROJECTS | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0001 | RAW | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_MD.REBATE_TMP) | OW_MD.REBATE_TMP | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_MD.TARGET_LAUNCH) | OW_MD.TARGET_LAUNCH | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_MD.TEMP_INPUT_SALES_CHANNELS_DEDUP) | OW_MD.TEMP_INPUT_SALES_CHANNELS_DEDUP | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.LOG_SDSLA_APAGA_ARQUIVOS) | OW_SDSLA.LOG_SDSLA_APAGA_ARQUIVOS | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0102 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.ODS_CATALOG_TABLE_COLUMNS_INFO) | OW_SDSLA.ODS_CATALOG_TABLE_COLUMNS_INFO | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0007 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.ODS_CATALOG_TABLE_INFO) | OW_SDSLA.ODS_CATALOG_TABLE_INFO | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0019 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.ODS_CATALOG_VIEW_INFO) | OW_SDSLA.ODS_CATALOG_VIEW_INFO | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.ODS_LISTA_DESLIGADOS) | OW_SDSLA.ODS_LISTA_DESLIGADOS | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_BI_ITVOC_MONTHY_REPORT) | OW_SDSLA.ODS_SDSLA_BI_ITVOC_MONTHY_REPORT | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ACCESS_PER_PROJECT) | OW_SDSLA.ODS_SDSLA_TABLE_ACCESS_PER_PROJECT | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.003 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_PROJECTS) | OW_SDSLA.ODS_SDSLA_TABLE_ALL_PROJECTS | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLE_HIST_ACCESS_VIEW) | OW_SDSLA.ODS_SDSLA_TABLE_HIST_ACCESS_VIEW | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0033 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLE_WORKBOOKS_TO_COMPARE) | OW_SDSLA.ODS_SDSLA_TABLE_WORKBOOKS_TO_COMPARE | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SDSLA.RAW_DATA_SDSLA_BI_ITVOC_MONTHY_REPORT) | OW_SDSLA.RAW_DATA_SDSLA_BI_ITVOC_MONTHY_REPORT | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | RAW | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.API_GSCM_PSI) | OW_SEDA_S.API_GSCM_PSI | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.BI_TRACKING) | OW_SEDA_S.BI_TRACKING | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0642 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.DSM_EDI_TEMP) | OW_SEDA_S.DSM_EDI_TEMP | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0373 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.DS_CE_MBO) | OW_SEDA_S.DS_CE_MBO | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.NPC_CHANNEL_PSI) | OW_SEDA_S.NPC_CHANNEL_PSI | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0059 | OTHER | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ALIANCA_TIMETABLE) | OW_SEDA_S.ODS_ALIANCA_TIMETABLE | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_B2W_REALTIME_IMEI) | OW_SEDA_S.ODS_B2W_REALTIME_IMEI | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_B2W_REALTIME_SALES) | OW_SEDA_S.ODS_B2W_REALTIME_SALES | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_B2W_REALTIME_STOCK) | OW_SEDA_S.ODS_B2W_REALTIME_STOCK | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ESTORE_VISIBILITY_KPI_ORDER_OPERATION_LEAD_TIME) | OW_SEDA_S.ODS_ESTORE_VISIBILITY_KPI_ORDER_OPERATION_LEAD_TIME | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0012 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GERPAM_WFCHANGE_SOREPORT) | OW_SEDA_S.ODS_GERPAM_WFCHANGE_SOREPORT | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0328 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GLP_PL) | OW_SEDA_S.ODS_GLP_PL | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0073 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_MONTHLY) | OW_SEDA_S.ODS_GLP_RETURN_RATIO_MONTHLY | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0367 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSPN_PARTS_RETURN_UPC_GR_PERFORMANCE) | OW_SEDA_S.ODS_GSPN_PARTS_RETURN_UPC_GR_PERFORMANCE | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.1035 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSPN_PARTS_RETURN_UPC_STOCK_TRANSFER) | OW_SEDA_S.ODS_GSPN_PARTS_RETURN_UPC_STOCK_TRANSFER | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0088 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_HR_COMPLETE_BASE_RPA) | OW_SEDA_S.ODS_HR_COMPLETE_BASE_RPA | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.001 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_INCENTIVES_POINT_REFERENCE) | OW_SEDA_S.ODS_INCENTIVES_POINT_REFERENCE | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_INVENTORY_CONSISTENCY) | OW_SEDA_S.ODS_INVENTORY_CONSISTENCY | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE) | OW_SEDA_S.ODS_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0112 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_MKP_REPORT_VIA_VAREJO) | OW_SEDA_S.ODS_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0155 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ONTIMEDELIVERY_RAWDATA_GLP) | OW_SEDA_S.ODS_ONTIMEDELIVERY_RAWDATA_GLP | [5 empty] | Done |  | 1 | 1 | 45964 | 45964 | ['[]'] | 0 | Check | 0.0321 | ODS | 0 |  | 0 | [10 empty] | 03/11 - 03/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ONTIMEGR_INBOUND_GLP) | OW_SEDA_S.ODS_ONTIMEGR_INBOUND_GLP | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0005 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ONTIMEGR_INBOUND_GLP_NEW) | OW_SEDA_S.ODS_ONTIMEGR_INBOUND_GLP_NEW | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_PRODUCT_TECHNICAL_INFO) | OW_SEDA_S.ODS_PRODUCT_TECHNICAL_INFO | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ROBBERY_REPORT) | OW_SEDA_S.ODS_ROBBERY_REPORT | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.001 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_RP_DOA_AEN_NF_CHECK) | OW_SEDA_S.ODS_RP_DOA_AEN_NF_CHECK | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0877 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_RP_DOA_RDO_CREATE_STATUS) | OW_SEDA_S.ODS_RP_DOA_RDO_CREATE_STATUS | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.1065 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_RP_ETR_ASC_MASTER) | OW_SEDA_S.ODS_RP_ETR_ASC_MASTER | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0023 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_SAMPLE_MANAGEMENT_BASE_VPS) | OW_SEDA_S.ODS_SAMPLE_MANAGEMENT_BASE_VPS | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_SAMPLE_MANAGEMENT_WH_CODE_DE_PARA) | OW_SEDA_S.ODS_SAMPLE_MANAGEMENT_WH_CODE_DE_PARA | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_API_OMNITRACKING_AUX) | OW_SEDA_S.ODS_SEDA_API_OMNITRACKING_AUX | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_SEDA_API_OMNITRACKING_AUX_REPROCESS) | OW_SEDA_S.ODS_SEDA_API_OMNITRACKING_AUX_REPROCESS | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WH_UNLOADING_YMS) | OW_SEDA_S.ODS_WH_UNLOADING_YMS | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0114 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.PDI_LOG_INFO) | OW_SEDA_S.PDI_LOG_INFO | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0179 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.RAW_AGNES_ADJ_BRSHOP_VIA_ADMIN_15_07_2024) | OW_SEDA_S.RAW_AGNES_ADJ_BRSHOP_VIA_ADMIN_15_07_2024 | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0 | RAW | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_BREA) | OW_SEDA_S.RAW_DATA_API_AFTER_SALES_BREA | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0 | RAW | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.RAW_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE) | OW_SEDA_S.RAW_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0013 | RAW | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.RAW_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE_PIVOT) | OW_SEDA_S.RAW_MANUAL_INPUT_PROMOTERS_STORE_TARGET_CE_PIVOT | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0033 | RAW | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.SALES_DEDUCTION_SERVICE_VALIDATION) | OW_SEDA_S.SALES_DEDUCTION_SERVICE_VALIDATION | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0005 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.ST_SDI_CELLO_STAGE) | OW_SEDA_S.ST_SDI_CELLO_STAGE | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0072 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TF_BI_CELLO_IOD_TOTAL_PRE1) | OW_SEDA_S.TF_BI_CELLO_IOD_TOTAL_PRE1 | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.5947 | TF | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TF_BI_CELLO_IOD_TOTAL_PRE2) | OW_SEDA_S.TF_BI_CELLO_IOD_TOTAL_PRE2 | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.6088 | TF | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_BI_CELLO_IOD_TOTAL) | OW_SEDA_S.TMP_BI_CELLO_IOD_TOTAL | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0544 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_MKP) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_MKP | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0066 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MKP_REPORT_VIA_VAREJO) | OW_SEDA_S.TMP_MKP_REPORT_VIA_VAREJO | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0002 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_ODS_GENERIC_INPUT_2) | OW_SEDA_S.TMP_ODS_GENERIC_INPUT_2 | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0507 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_ODS_GENERIC_INPUT_R) | OW_SEDA_S.TMP_ODS_GENERIC_INPUT_R | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0034 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_ODS_GENERIC_INPUT_R2) | OW_SEDA_S.TMP_ODS_GENERIC_INPUT_R2 | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0006 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_RP_ETR_ASC_MASTER) | OW_SEDA_S.TMP_RP_ETR_ASC_MASTER | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0022 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_API_AFTER_SALES_MKP) | OW_SEDA_S.TMP_SEDA_API_AFTER_SALES_MKP | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.001 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_API_OMNITRACKING) | OW_SEDA_S.TMP_SEDA_API_OMNITRACKING | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0002 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SURSIS_DELIVERY_DATA) | OW_SEDA_S.TMP_SURSIS_DELIVERY_DATA | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.011 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SURSIS_ESCORT) | OW_SEDA_S.TMP_SURSIS_ESCORT | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0066 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SURSIS_NC) | OW_SEDA_S.TMP_SURSIS_NC | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0052 | TMP | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.TR1_ORDER_OPERATION_OUTBOUND) | OW_SEDA_S.TR1_ORDER_OPERATION_OUTBOUND | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0206 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S.VW_TT_AVARIAS_MARCO_ZERO_VM) | OW_SEDA_S.VW_TT_AVARIAS_MARCO_ZERO_VM | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0004 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_MAPA_IMPORTACAO_SVC_ITEM) | OW_SEDA_S_COMEX.ODS_CMX_MAPA_IMPORTACAO_SVC_ITEM | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.001 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_RELATORIO_DARE_CST) | OW_SEDA_S_COMEX.ODS_CMX_RELATORIO_DARE_CST | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0004 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_VARIACAO_PRECO_CST) | OW_SEDA_S_COMEX.ODS_CMX_VARIACAO_PRECO_CST | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SEDA_S_COMEX.ODS_CMX_VOLUME_IMPORTADO_CST) | OW_SEDA_S_COMEX.ODS_CMX_VOLUME_IMPORTADO_CST | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0003 | ODS | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SELA.DIM_CALENDAR) | OW_SELA.DIM_CALENDAR | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0005 | DIM | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SELA.DIM_MN) | OW_SELA.DIM_MN | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0001 | DIM | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SELA.DIM_RESELLER) | OW_SELA.DIM_RESELLER | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0002 | DIM | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - OW_SELA.STAGE_FACT_STOCK_SALES) | OW_SELA.STAGE_FACT_STOCK_SALES | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - U_PRJ_ECOM.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE) | U_PRJ_ECOM.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - U_PRJ_ECOM.AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS) | U_PRJ_ECOM.AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0004 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - U_PRJ_ECOM.AUX_YAMI_PRODUCT_DETAIL_STATUS) | U_PRJ_ECOM.AUX_YAMI_PRODUCT_DETAIL_STATUS | [5 empty] | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_JOB_HISTORY) | U_PRJ_ECOM.BI_ECOM_JOB_HISTORY | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - U_PRJ_ECOM.CV_EPP_CONTROL) | U_PRJ_ECOM.CV_EPP_CONTROL | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45965 | 45965 | ['[]'] | 0 | Check | 0.0039 | OTHER | 0 |  | 0 | [10 empty] | 04/11 - 04/11
| TABLE | (TABLE - U_PRJ_ECOM.CV_WOS_AND_STOCKOUT) | U_PRJ_ECOM.CV_WOS_AND_STOCKOUT | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0064 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.DATE_DIM) | U_PRJ_ECOM.DATE_DIM | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS) | U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0004 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS_TOTALS_TEMP) | U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS_TOTALS_TEMP | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS_UPDATE_TEMP) | U_PRJ_ECOM.ETL_GUATEMALA_ECOMMERCE_ORDERS_UPDATE_TEMP | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ETL_PANAMA_ECOMMERCE_ORDERS) | U_PRJ_ECOM.ETL_PANAMA_ECOMMERCE_ORDERS | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0002 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ETL_PANAMA_ECOMMERCE_ORDERS_UPDATE_TEMP) | U_PRJ_ECOM.ETL_PANAMA_ECOMMERCE_ORDERS_UPDATE_TEMP | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ITEM_COMPONENT_TESTE) | U_PRJ_ECOM.ITEM_COMPONENT_TESTE | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0396 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.LOG_PROCESSCONTROL_HMLG) | U_PRJ_ECOM.LOG_PROCESSCONTROL_HMLG | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.MONGO_VALIDATION) | U_PRJ_ECOM.MONGO_VALIDATION | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.1007 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_ASSERTH_CANCELLATION) | U_PRJ_ECOM.ODS_ASSERTH_CANCELLATION | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.002 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_D2C_ENTITY_ENDLESS_STORE_SSG_BR) | U_PRJ_ECOM.ODS_D2C_ENTITY_ENDLESS_STORE_SSG_BR | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_D2C_ENTITY_ENDLESS_STORE_SSG_BR_SHOP) | U_PRJ_ECOM.ODS_D2C_ENTITY_ENDLESS_STORE_SSG_BR_SHOP | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0002 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_CARREFOUR) | U_PRJ_ECOM.ODS_MKP_D2C_CARREFOUR | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0037 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_CARREFOUR_LSPOSITO) | U_PRJ_ECOM.ODS_MKP_D2C_CARREFOUR_LSPOSITO | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0001 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_FASTSHOP_QUEUE) | U_PRJ_ECOM.ODS_MKP_D2C_FASTSHOP_QUEUE | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_LEROY) | U_PRJ_ECOM.ODS_MKP_D2C_LEROY | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.001 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_MAGALU) | U_PRJ_ECOM.ODS_MKP_D2C_MAGALU | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0171 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_MELI) | U_PRJ_ECOM.ODS_MKP_D2C_MELI | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.001 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_MELI_2) | U_PRJ_ECOM.ODS_MKP_D2C_MELI_2 | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_MKP_D2C_VIA) | U_PRJ_ECOM.ODS_MKP_D2C_VIA | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0236 | ODS | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.ORDERS_MISSING) | U_PRJ_ECOM.ORDERS_MISSING | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.PACKAGE_TESTE) | U_PRJ_ECOM.PACKAGE_TESTE | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.2108 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RATES_AND_BENEFITS_TESTE) | U_PRJ_ECOM.RATES_AND_BENEFITS_TESTE | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0327 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_CTV_SSG) | U_PRJ_ECOM.RAW_CTV_SSG | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | RAW | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_CHANNEL_GROUPING) | U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_CHANNEL_GROUPING | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0002 | RAW | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_CHANNEL_GROUPING_DAY) | U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_CHANNEL_GROUPING_DAY | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | RAW | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_DEVICE) | U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_DEVICE | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0001 | RAW | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_DEVICE_DAY) | U_PRJ_ECOM.RAW_GA_SAMSUNGSHOP_SESSION_DEVICE_DAY | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | RAW | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_CHANNEL_GROUPING) | U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_CHANNEL_GROUPING | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0002 | RAW | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_DEVICE_DAY) | U_PRJ_ECOM.RAW_GA_SAMSUNG_SESSION_DEVICE_DAY | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | RAW | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_SAMSUNGBRSHOP_PAYMENT) | U_PRJ_ECOM.RAW_SAMSUNGBRSHOP_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.3675 | RAW | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_SAMSUNGBR_PAYMENT) | U_PRJ_ECOM.RAW_SAMSUNGBR_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.1036 | RAW | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_SAP_SSG_ECOM_ZRMMB34070) | U_PRJ_ECOM.RAW_SAP_SSG_ECOM_ZRMMB34070 | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0027 | RAW | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.SEASA_ORDERS_GAP) | U_PRJ_ECOM.SEASA_ORDERS_GAP | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.SHIPPING_TESTE) | U_PRJ_ECOM.SHIPPING_TESTE | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.2462 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.STG_CT_O2O_SEASA) | U_PRJ_ECOM.STG_CT_O2O_SEASA | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.STG_MGLU_ORDER_ITEM) | U_PRJ_ECOM.STG_MGLU_ORDER_ITEM | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0042 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.STG_MGLU_ORDER_PAYMENT) | U_PRJ_ECOM.STG_MGLU_ORDER_PAYMENT | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.002 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.TABELA_DETALHES) | U_PRJ_ECOM.TABELA_DETALHES | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.TEMP_DIM_UNIQUE_ID) | U_PRJ_ECOM.TEMP_DIM_UNIQUE_ID | LAO EStore | r.bojart |  | yes | 2 | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0133 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.TEMP_ORDERS_CODE_FEED) | U_PRJ_ECOM.TEMP_ORDERS_CODE_FEED | LAO EStore | r.bojart |  | yes | 4 | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0506 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.TEMP_SO) | U_PRJ_ECOM.TEMP_SO | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.TMP_MKP_D2C_CARREFOUR) | U_PRJ_ECOM.TMP_MKP_D2C_CARREFOUR | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0023 | TMP | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.TMP_MKP_D2C_MAGALU) | U_PRJ_ECOM.TMP_MKP_D2C_MAGALU | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0171 | TMP | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.TMP_MKP_D2C_VIA) | U_PRJ_ECOM.TMP_MKP_D2C_VIA | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0002 | TMP | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_MKP_D2C_LEROY) | U_PRJ_ECOM.TMP_ODS_MKP_D2C_LEROY | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0011 | TMP | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ODS_MKP_D2C_MELI) | U_PRJ_ECOM.TMP_ODS_MKP_D2C_MELI | [5 empty] | Done |  | 1 | 1 | 45966 | 45966 | ['[]'] | 0 | Check | 0.0002 | TMP | 0 |  | 0 | [10 empty] | 05/11 - 05/11
| TABLE | (TABLE - U_PRJ_ECOM.TMP_ORDER_ALERT_ORDER_ID_LINKAPI) | U_PRJ_ECOM.TMP_ORDER_ALERT_ORDER_ID_LINKAPI | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 0 | Check | 0 | TMP | 0 |  | 0 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - U_PRJ_ECOM.TST_SEASA_LIST) | U_PRJ_ECOM.TST_SEASA_LIST | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 0 | Check | 0.0004 | OTHER | 0 |  | 0 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - U_PRJ_ECOM.TST_SEDA_LIST) | U_PRJ_ECOM.TST_SEDA_LIST | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 0 | Check | 0.0021 | OTHER | 0 |  | 0 | [10 empty] | 06/11 - 06/11
Control Tower | TABLE | (TABLE - U_PRJ_ECOM.VALID_SEND_CONTROL_TOWER) | U_PRJ_ECOM.VALID_SEND_CONTROL_TOWER | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 0 | Check | 0.0468 | OTHER | 0 |  | 0 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - U_PRJ_ECOM.VTEX_SSG_AR_SMB_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.VTEX_SSG_AR_SMB_RATES_AND_BENEFITS_DATA | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 0 | Check | 0.0001 | OTHER | 0 |  | 0 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - U_PRJ_ECOM.VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.VTEX_SSG_BR_SHOP_RATES_AND_BENEFITS_DATA | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 0 | Check | 0 | OTHER | 0 |  | 0 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_TRACKING) | OW_SEDA_S.CELLO_TRACKING | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 6.1647 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(FUNCTION - OW_SEDA_S.FN_GET_CELLO_EVENT),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING_AUX),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING)] | 29 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY) | OW_SEDA_S.CELLO_DELIVERY | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 1.1931 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP_TEST),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_STATUS_MAPPING_AUX),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD)] | 28 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND) | OW_SEDA_S.CELLO_DELIVERY_INBOUND | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.1417 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING)] | 28 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM) | OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.091 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING)] | 25 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM) | OW_SEDA_S.CELLO_DELIVERY_ITEM | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.5672 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228)] | 25 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING) | OW_SEDA_S.CELLO_FUTHER_PROCESSING | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0986 | OTHER | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING)] | 25 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS) | OW_LAO.ODS_GSCM_PREMIUM_MODELS | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0455 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_ODS_LAO_PREMIUM_PRODUCTS_TABLE_FROM_GSCM_UPDATE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI),(PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_KPI)] | 14 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND) | OW_SEDA_S.CELLO_MANIFEST_INBOUND | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0514 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228)] | 9 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND) | OW_SEDA_S.CELLO_SHIPMENT_INBOUND | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0559 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION)] | 9 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL) | OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 1.2948 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING),(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | 9 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS) | OW_SEDA_S.SDI_TSS_TC_ORDERS | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.4706 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | 8 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W) | OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0125 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W)] | 5 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND) | OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.3142 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_GSCM_INVENTORY),(INGESTION - JOB.RAW_DATA_GSCM_ACTUAL_ON_HAND),(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI),(PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO),(PROCEDURE - OW_LAO.PROC_D2C_NERP_INVENTORY)] | 5 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA) | OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0013 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W)] | 4 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO) | OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 3.1078 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W)] | 4 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING) | OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0002 | FT | 0 | [(PROCEDURE - OW_LAO.UPDATE_SALES_WEEKLY_MONITORING),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_MONITORING_STATUS),(VIEW - OW_LAO.VW_LAO_SALES_DEDUCTION_DAILY_MONITORING_MAPPING_STATUS),(PROCEDURE - OW_LAO.PROC_ATU_LAO_SALES_DEDUCTION_MONITORING_STATUS_HIST)] | 4 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY) | OW_LAO.ODS_GSCM_AP1_ACCURACY | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0173 | ODS | 0 | [(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(INGESTION - JOB.ODS_GSCM_AP1_ACCURACY),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2),(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW)] | 4 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER) | OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.2784 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO),(INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE)] | 4 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY) | OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0123 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY)] | 3 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_PICKING_PACKING) | OW_SEDA_S.ODS_WMS_PICKING_PACKING | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0925 | ODS | 0 | [(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(INGESTION - JOB.ODS_WMS_PICKING_PACKING),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION)] | 3 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_EXCEPTION) | OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0001 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION)] | 2 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_CE_SELL_OUT) | OW_LAO.ODS_GSCM_CE_SELL_OUT | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.2705 | RAW | 0 | [(INGESTION - JOB.RAW_GSCM_CE_SELL_OUT),(INGESTION - JOB.ODS_GSCM_CE_SELL_OUT)] | 2 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_FCST_MGMT_D2C) | OW_LAO.ODS_GSCM_FCST_MGMT_D2C | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 3.995 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS),(INGESTION - JOB.ODS_GSCM_FCST_MGMT_D2C)] | 2 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_MX_SELL_OUT) | OW_LAO.ODS_GSCM_MX_SELL_OUT | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.4139 | RAW | 0 | [(INGESTION - JOB.RAW_GSCM_MX_SELL_OUT),(INGESTION - JOB.ODS_GSCM_MX_SELL_OUT)] | 2 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_ABNORMAL_INVENTORY) | OW_SEDA_S.ODS_WMS_ABNORMAL_INVENTORY | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.3011 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_ABNORMAL_INVENTORY),(INGESTION - JOB.ODS_WMS_ABNORMAL_INVENTORY)] | 2 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD) | OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.015 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SDU_ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD),(INGESTION - JOB.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD)] | 2 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY) | OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0008 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_CE_SELL_OUT) | OW_LAO.RAW_GSCM_CE_SELL_OUT | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.2705 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_MX_SELL_OUT) | OW_LAO.RAW_GSCM_MX_SELL_OUT | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.4139 | RAW | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_03) | OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_03 | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0003 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_04) | OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_04 | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0031 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_05) | OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_05 | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0036 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD) | OW_SEDA_S.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0159 | ODS | 0 | [(INGESTION - JOB.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_MAO) | OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_MAO | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.1685 | ODS | 0 | [(INGESTION - JOB.ODS_WMS_GATE_DOCK_IN_MAO)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_YMS_GATE_DOCK_IN_CAJ) | OW_SEDA_S.ODS_WMS_YMS_GATE_DOCK_IN_CAJ | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0262 | ODS | 0 | [(INGESTION - JOB.ODS_WMS_YMS_GATE_DOCK_IN_CAJ)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_ORDER_OCCURRENCE_RPT) | OW_SEDA_S.SDI_TSS_TC_ORDER_OCCURRENCE_RPT | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0208 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_RETURN_BOOKING_REQUEST) | OW_SEDA_S.SDI_TSS_TC_RETURN_BOOKING_REQUEST | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0085 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | 1 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_V2) | OW_LAO.FT_LAO_SALES_DEDUCTION_V2 | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0135 | FT | 0 |  | 0 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_V3) | OW_LAO.FT_LAO_SALES_DEDUCTION_V3 | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0119 | FT | 0 |  | 0 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_VALIDATION_DATA_REPORT) | OW_LAO.FT_LAO_SALES_DEDUCTION_VALIDATION_DATA_REPORT | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0001 | FT | 0 |  | 0 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.RAW_DATA_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC) | OW_LAO.RAW_DATA_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0.0003 | RAW | 0 |  | 0 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_ACTUAL_SALES_PIVOT_TABLE) | OW_LAO.RAW_GSCM_ACTUAL_SALES_PIVOT_TABLE | [5 empty] | Done |  | 1 | 1 | 45967 | 45967 | ['[]'] | 1 | Migrar ph2 | 0 | RAW | 0 |  | 0 | [10 empty] | 06/11 - 06/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_AP1_ACCURACY) | OW_LAO.RAW_GSCM_AP1_ACCURACY | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.057 | RAW | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0005 | RAW | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.1428 | RAW | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 2.2537 | RAW | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_6W_10W) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_6W_10W | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 3.12 | RAW | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_FOTA) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_FOTA | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 2.2938 | RAW | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.FT_ORDER_OPERATION) | OW_SEDA_S.FT_ORDER_OPERATION | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0422 | FT | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_SDI2) | OW_SEDA_S.FT_TSS_BI_TRACKING_SDI2 | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0022 | FT | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_ESCORT_SERVICE_MNG) | OW_SEDA_S.FT_TSS_ESCORT_SERVICE_MNG | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0366 | FT | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_GI) | OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_GI | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0118 | ODS | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_INQUIRY_SPARE_PARTS) | OW_SEDA_S.ODS_WMS_INQUIRY_SPARE_PARTS | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0068 | ODS | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_JASPER_CANCELATION) | OW_SEDA_S.ODS_WMS_JASPER_CANCELATION | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0029 | ODS | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_SPARE_PARTS_WH_CONSOLIDATE) | OW_SEDA_S.ODS_WMS_SPARE_PARTS_WH_CONSOLIDATE | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0091 | ODS | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WMS_SPARE_PARTS_WH_DAILY) | OW_SEDA_S.ODS_WMS_SPARE_PARTS_WH_DAILY | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0749 | ODS | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_BIG_AREA) | OW_SEDA_S.SDI_TSS_M_BIG_AREA | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0003 | OTHER | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_BOD) | OW_SEDA_S.SDI_TSS_M_BOD | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0013 | OTHER | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_SCHEDULE_ORDER) | OW_SEDA_S.SDI_TSS_TC_SCHEDULE_ORDER | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 1 | Migrar ph2 | 0.0005 | OTHER | 0 |  | 0 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_PRODUCTS) | OW_SEDA_S.MAP_CE_PRODUCTS | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0114 | MAP | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA),(VIEW - OW_SEDA_S.VW_MX_SALES_VS_RTF),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY),(INGESTION - JOB.MAP_CE_PRODUCTS),(VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR),(VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI),(VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022),(VIEW - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_TARGET_WEEK_ADJ),(VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX),(PROCEDURE - OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_TT_GABARITO_CHECKLIST_EXECUCAO_785),(PROCEDURE - OW_SEDA_S.PRC_TT_GABARITO_CHECKLIST_EXECUCAO),(PROCEDURE - OW_SEDA_S.PRC_CE_MANAGEMENT_INFORMATION),(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK),(VIEW - OW_SEDA_S.VW_CE_META_PROMOTOR),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL),(VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING),(VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE),(PROCEDURE - OW_SEDA_S.PRC_STOCK_OUT_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_DEAD_SKU_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_CE),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MON),(PROCEDURE - OW_SEDA_S.PRC_VC_UPDATE_READY),(PROCEDURE - OW_SEDA_S.PRC_UPDATE_PIN_TO_PIN),(PROCEDURE - OW_SEDA_S.PRC_TV_UPDT_INCH_RANGE),(VIEW - OW_SEDA_S.VW_TT_RUPTURA),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2),(VIEW - OW_SEDA_S.VW_CE_MANAGEMENT_INFORMATION),(VIEW - OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_MX_SALES_VS_RTF_BY_CAPACITY),(PROCEDURE - OW_SEDA_S.PRC_VD_SALES_REVENUE),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY)] | 39 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_TRANS) | OW_SEDA_S.ODS_TSS_M_TRANS | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0013 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP)] | 20 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST) | OW_SEDA_S.CELLO_LAST_LEG_MANIFEST | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0165 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst)] | 17 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_SHIPMENT) | OW_SEDA_S.CELLO_SHIPMENT | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.3717 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL)] | 17 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_CODE) | OW_SEDA_S.ODS_TSS_M_CODE | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0009 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FNS_NM2),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO)] | 17 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION) | OW_SEDA_S.ODS_TSS_M_LOCATION | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0213 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI_v2),(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO)] | 17 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_MANIFEST) | OW_SEDA_S.CELLO_MANIFEST | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.4365 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP)] | 16 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION) | OW_SEDA_S.ODS_TSS_M_DIVISION | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0002 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP)] | 16 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_BOOKING) | OW_SEDA_S.CELLO_BOOKING | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.7439 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP)] | 14 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_POD) | OW_SEDA_S.CELLO_POD | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0362 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2),(VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5)] | 14 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_ITEM) | OW_SEDA_S.ODS_TSS_M_ITEM | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0206 | ODS | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI)] | 14 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP) | OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0006 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO),(FUNCTION - OW_SEDA_S.FNS_NM1)] | 14 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA) | OW_SEDA_S.ODS_TSS_M_MID_AREA | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(FUNCTION - OW_SEDA_S.FNS_NM1)] | 13 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS) | OW_SEDA_S.SDI_TSS_OD_ORDERS | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.3391 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI),(VIEW - OW_SEDA_S.VW_UNION_CELLO_TSS_IOD_STATUS)] | 13 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION) | OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0001 | INPUT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_MONITORING_STATUS),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION)] | 12 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION) | OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0272 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO),(VIEW - OW_SEDA_S.VW_SELLOUTGERAL),(VIEW - OW_SEDA_S.VW_WALMART),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL),(VIEW - OW_SEDA_S.VW_GSCM_CH_PSI_WARING_SALES_DEDUCTION),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_VALIDATION),(VIEW - OW_SEDA_S.VW_ONLINE_FISICO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_JULIAO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_JULIAO)] | 12 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION) | OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0006 | INPUT | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION)] | 11 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_CALENDAR) | OW_SEDA_S.MAP_CE_CALENDAR | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0003 | MAP | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK),(VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST),(PROCEDURE - OW_SEDA_S.PRC_VD_SALES_REVENUE),(PROCEDURE - OW_SEDA_S.PRC_DEAD_SKU_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT),(VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE),(PROCEDURE - OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION),(VIEW - OW_SEDA_S.VW_CE_META_PROMOTOR),(PROCEDURE - OW_SEDA_S.PRC_STOCK_OUT_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION),(PROCEDURE - OW_LAO.PRC_ODS_LAO_GSCM_EDI_DATA)] | 11 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS) | OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0006 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_JULIAO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_VALIDATION),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_JULIAO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO)] | 11 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_AREA) | OW_SEDA_S.ODS_TSS_M_AREA | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0005 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI)] | 11 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC) | OW_SEDA_S.SDI_TSS_RS_RESULT_LOC | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.3763 | OTHER | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | 10 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA) | OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W)] | 9 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES) | OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W)] | 9 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API) | OW_SEDA_S.ODS_CE_WEBPRICE_API | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 14.7161 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX_HIST_2),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_UPDT_RECENT_PRICE),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_CE),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MON),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST_2)] | 9 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE) | OW_SEDA_S.SDI_TSS_TC_OCCURRENCE | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.2479 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_STATUS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE)] | 9 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL) | OW_SEDA_S.SDI_TSS_TC_VESSEL | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0007 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI)] | 9 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT) | OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.001 | OTHER | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL_DESTINATION_PORT)] | 9 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS) | OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | 8 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG) | OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.1402 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | 8 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL) | OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.3079 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI)] | 8 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT) | OW_SEDA_S.SDI_TSS_RS_RESULT | [5 empty] | Done |  | 1 | 1 | 45968 | 45968 | ['[]'] | 0 | Migrar ph2 | 0.2217 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI)] | 8 | [10 empty] | 07/11 - 07/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP) | OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0563 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | 8 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS) | OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0095 | OTHER | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI)] | 8 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS) | OW_LAO.MONITORING_EXECUTIONS_RESULTS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0054 | OTHER | 0 | [(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_GENERATED),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_DEFAULT),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_TMC),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_JENKINS),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_PREPARE),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE)] | 7 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_VESSEL) | OW_SEDA_S.CELLO_VESSEL | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0156 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3)] | 7 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_JOURNEY) | OW_SEDA_S.MAP_CE_JOURNEY | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0117 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR),(INGESTION - JOB.MAP_CE_JOURNEY),(VIEW - OW_SEDA_S.VW_CE_JOURNEY_UNIQUE_MAX_WEEKNUM),(VIEW - OW_SEDA_S.VW_CE_JOURNEY_UNIQUE),(VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS),(VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING),(VIEW - OW_SEDA_S.VW_CE_JOURNEY_COORDINATORS_MAXWEEK)] | 7 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION) | OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI)] | 7 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS) | OW_SEDA_S.SDI_TSS_NF_OD_ORDERS | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.3521 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE)] | 7 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC) | OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.1822 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI)] | 7 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE) | OW_SEDA_S.SDI_TSS_TC_EVENT_DATE | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0733 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_DATE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE)] | 7 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS) | OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.6239 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI)] | 7 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS) | OW_SEDA_S.FT_CHEIL_ANSWERS | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 1.6178 | FT | 0 | [(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_MX_POSITIVACAO_S24),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES) | OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.288 | FT | 0 | [(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE),(VIEW - OW_SEDA_S.VW_MX_POSITIVACAO_S24),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS) | OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0003 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_MX_POSITIVACAO_S24),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_POS) | OW_SEDA_S.MAP_CHEIL_POS | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0051 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_MX_POSITIVACAO_S24),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE) | OW_SEDA_S.ODS_TSS_M_AREA_TYPE | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0004 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL) | OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0017 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP) | OW_SEDA_S.ODS_TSS_M_ITEM_GROUP | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FNS_NM1)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING) | OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0005 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE) | OW_SEDA_S.ODS_TSS_M_RATE_SERVICE | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0091 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM2)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING) | OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0033 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED) | OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.1166 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI),(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016)] | 6 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_KAM) | OW_SEDA_S.MAP_CE_KAM | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_MANAGEMENT_INFORMATION),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2),(PROCEDURE - OW_SEDA_S.PRC_CE_MANAGEMENT_INFORMATION),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS) | OW_SEDA_S.MAP_CHEIL_COLLABORATORS | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0003 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS) | OW_SEDA_S.MAP_CHEIL_PRODUCTS | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0006 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO) | OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 | [(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX_HIST_2),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST_2)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA) | OW_SEDA_S.ODS_TSS_M_BIG_AREA | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FN_GET_BOD2)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY) | OW_SEDA_S.ODS_TSS_M_COMPANY | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(FUNCTION - OW_SEDA_S.FNS_NM1)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP) | OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE) | OW_SEDA_S.ODS_TSS_M_VEHICLE | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0005 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM1),(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX) | OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.2357 | RAW | 0 | [(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST_2),(INGESTION - JOB.RAW_MX_TMV_INDEX),(INGESTION - JOB.ODS_WEBPRICE_TRACKING_DAILY_MX),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG) | OW_SEDA_S.SDI_TSS_TC_EVENT_LOG | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 1.1263 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016),(FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE_SDI)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING) | OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0774 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE_SDI),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI)] | 5 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_LAO.MONITORING_EXECUTIONS) | OW_LAO.MONITORING_EXECUTIONS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0002 | OTHER | 0 | [(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_POST_EXECUTION),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_GENERATED)] | 4 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_LAO.MONITORING_PARAMETERS) | OW_LAO.MONITORING_PARAMETERS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0001 | OTHER | 0 | [(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_PREPARE),(PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_GENERATED),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS)] | 4 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W) | OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.023 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION)] | 4 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM) | OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0154 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2)] | 4 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_BOD) | OW_SEDA_S.ODS_TSS_M_BOD | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0013 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI_v2),(FUNCTION - OW_SEDA_S.FN_GET_BOD2)] | 4 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT) | OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0012 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_CELLO_TSS_IOD_STATUS),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI)] | 4 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.FT_CE_PRICE_STORE) | OW_SEDA_S.FT_CE_PRICE_STORE | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.1279 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_TT_UPDT_FLOORSHARE),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(PROCEDURE - OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA)] | 3 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.FT_CE_SELL_IN_FCST) | OW_SEDA_S.FT_CE_SELL_IN_FCST | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0024 | FT | 0 | [(VIEW - OW_SEDA_S.VW_SCM_SALES_AND_SO_LIST_COMPLETE),(VIEW - OW_SEDA_S.VW_SELL_IN_FCST),(INGESTION - JOB.FT_CE_SELL_IN_FCST)] | 3 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_SR_KAM) | OW_SEDA_S.MAP_CE_SR_KAM | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2)] | 3 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_REASON) | OW_SEDA_S.ODS_TSS_M_REASON | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0006 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT)] | 3 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS) | OW_SEDA_S.ODS_TSS_OD_ORDERS | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.1051 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL)] | 3 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_DETAIL) | OW_SEDA_S.ODS_TSS_RS_RESULT_DETAIL | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0016 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(FUNCTION - OW_SEDA_S.FNS_NM1)] | 3 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_LOC) | OW_SEDA_S.ODS_TSS_RS_RESULT_LOC | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.1167 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_BOD2),(FUNCTION - OW_SEDA_S.FNS_NM1),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 3 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_CUSTOMER_REJECT) | OW_SEDA_S.ODS_TSS_TC_CUSTOMER_REJECT | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.0695 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_REJECT_CNT),(FUNCTION - OW_SEDA_S.FN_GET_DO_CURR_ACTION),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 3 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_TV) | OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_TV | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 0.7171 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_CE),(INGESTION - JOB.ODS_WEBPRICE_TRACKING_DAILY_TV),(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_UPDT_RECENT_PRICE)] | 3 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_SEDA_S.RAW_SEDA_API_OMNITRACKING) | OW_SEDA_S.RAW_SEDA_API_OMNITRACKING | [5 empty] | Done |  | 1 | 1 | 45971 | 45971 | ['[]'] | 0 | Migrar ph2 | 6.1356 | RAW | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING_FULL),(PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING),(PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING_WEEKLY)] | 3 | [11 empty] | 10/11 - 10/11
| TABLE | (TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_STATUS) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_STATUS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 | [(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.MONITORING_EXECUTIONS_STATUS) | OW_LAO.MONITORING_EXECUTIONS_STATUS | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 | [(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.MONITORING_PROTOCOL_TYPES) | OW_LAO.MONITORING_PROTOCOL_TYPES | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 | [(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.MONITORING_SOURCES_TYPES) | OW_LAO.MONITORING_SOURCES_TYPES | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 | [(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE),(VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION) | OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0177 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY) | OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0229 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION) | OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA) | OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0175 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 | [(INGESTION - JOB.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_FOTA_01_05W) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_FOTA_01_05W | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT) | OW_LAO.ODS_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0022 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_MONITORING_STATUS),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION),(INGESTION - JOB.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_FOTA_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_FOTA_01_05W | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 | [(INGESTION - JOB.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_FOTA_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_FOTA_01_05W | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_01_05W | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W),(PROCEDURE - OW_LAO.UPDATE_SALES_WEEKLY_MONITORING)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION) | OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION),(INGESTION - JOB.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_FOTA_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_FOTA_01_05W | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM) | OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0154 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_FOTA) | OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_FOTA | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0093 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA),(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.FT_GFK_MX_WEEKLY) | OW_SEDA_S.FT_GFK_MX_WEEKLY | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.016 | FT | 0 | [(VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST),(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_SDI) | OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_SDI | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.144 | FT | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CARRIER) | OW_SEDA_S.MAP_CARRIER | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_SEDA_SALES_IN_TRANSIT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST_MAP_CARRIER)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE) | OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.012 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_TT_RUPTURA),(INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT) | OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.008 | MAP | 0 | [(VIEW - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_TARGET_WEEK_ADJ),(INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_PRICE_COLLECTED) | OW_SEDA_S.MAP_CE_PRICE_COLLECTED | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0152 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS),(VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_SETOR_CENSITARIO_2010) | OW_SEDA_S.MAP_CE_SETOR_CENSITARIO_2010 | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0155 | MAP | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_IBGE_INFO),(VIEW - OW_SEDA_S.VW_IBGE_CEP_5_COORDINATES)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_DA) | OW_SEDA_S.ODS_GSCM_SO_FCST_DA | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0862 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_D2C_SO_FSCT),(INGESTION - JOB.ODS_GSCM_SO_FCST_DA)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_HHP) | OW_SEDA_S.ODS_GSCM_SO_FCST_HHP | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.1631 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_D2C_SO_FSCT),(INGESTION - JOB.ODS_GSCM_SO_FCST_HHP)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_OTHERS) | OW_SEDA_S.ODS_GSCM_SO_FCST_OTHERS | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.077 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_D2C_SO_FSCT),(INGESTION - JOB.ODS_GSCM_SO_FCST_OTHERS)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_VD) | OW_SEDA_S.ODS_GSCM_SO_FCST_VD | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0597 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_D2C_SO_FSCT),(INGESTION - JOB.ODS_GSCM_SO_FCST_VD)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM) | OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 1.5035 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM),(VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY) | OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.5782 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO),(INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY) | OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.655 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO),(INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_TC_LEG_PLANNING) | OW_SEDA_S.ODS_TSS_TB_MVW_TC_LEG_PLANNING | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0144 | ODS | 0 | [(VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_LEG_PLANNING) | OW_SEDA_S.ODS_TSS_TC_LEG_PLANNING | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0141 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE),(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_OCCURRENCE) | OW_SEDA_S.ODS_TSS_TC_OCCURRENCE | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0466 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_STATUS),(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL) | OW_SEDA_S.ODS_TSS_TC_VESSEL | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0006 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_DESTINATION_PORT) | OW_SEDA_S.ODS_TSS_TC_VESSEL_DESTINATION_PORT | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0007 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_ORDERS) | OW_SEDA_S.ODS_TSS_TC_VESSEL_ORDERS | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0059 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM),(VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_DETAIL) | OW_SEDA_S.SDI_TSS_RS_RESULT_DETAIL | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.3206 | OTHER | 0 | [(FUNCTION - OW_SEDA_S.FNS_NM1_SDI),(FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT) | OW_SEDA_S.SDI_TSS_TC_EVENT | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.1673 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE_SDI)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.TF_VW_SELLOUTGERAL) | OW_SEDA_S.TF_VW_SELLOUTGERAL | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0045 | TF | 0 | [(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_LSPOSITO)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_SEDA_S.TF_VW_WALMART) | OW_SEDA_S.TF_VW_WALMART | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TF | 0 | [(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART_LSPOSITO),(VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO)] | 2 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_AL11_VALIDATION_TO_MOVE_FILE) | OW_LAO.FT_LAO_SALES_DEDUCTION_AL11_VALIDATION_TO_MOVE_FILE | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0001 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_NERP_AL11_VALIDATION)] | 1 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.FT_NERP_AL11_VALIDATION) | OW_LAO.FT_NERP_AL11_VALIDATION | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0001 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_NERP_AL11_VALIDATION)] | 1 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION) | OW_LAO.FT_SALES_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0014 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION)] | 1 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS | [5 empty] | Done |  | 1 | 1 | 45972 | 45972 | ['[]'] | 0 | Migrar ph2 | 0.0036 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 11/11 - 11/11
| TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.3582 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO_CONSOLIDADO) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO_CONSOLIDADO | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0013 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE_HISTORICO) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE_HISTORICO | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0003 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP_HISTORICO) | OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP_HISTORICO | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0002 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_PRODUCT_LIST) | OW_LAO.ODS_GSCM_PRODUCT_LIST | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0158 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_PRODUCT)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_GSSC_REPORT_TO_SR) | OW_LAO.ODS_GSSC_REPORT_TO_SR | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0036 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC) | OW_LAO.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(INGESTION - JOB.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_01_05W) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_01_05W | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_06_10W) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_06_10W | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_NERP_AL11_MCS_SEN) | OW_LAO.ODS_NERP_AL11_MCS_SEN | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_NERP_AL11_VALIDATION)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT) | OW_LAO.ODS_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0148 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_01_05W | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_06_10W) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_06_10W | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_01_05W) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_01_05W | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_06_10W) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_06_10W | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_06_10W) | OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_06_10W | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_01) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_01 | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.2802 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_02) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_02 | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.2751 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_ACESSORY) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_ACESSORY | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0133 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_DOWN) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_DOWN | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0021 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_EPP) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_EPP | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_HME) | OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_HME | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.001 | TF | 0 | [(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_EXCEPTION) | OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_BIZ_AREA) | OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_BIZ_AREA | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_CORES) | OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_CORES | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_GSCM) | OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_GSCM | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0142 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION) | OW_LAO.TF_SALES_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.008 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_01) | OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_01 | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0024 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_02) | OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_02 | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TF | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_MD.MAP_CUSTOMER_EXCEPTION) | OW_MD.MAP_CUSTOMER_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_MD.MAP_INCENTIVE_TYPE_MAPPING) | OW_MD.MAP_INCENTIVE_TYPE_MAPPING | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 | [(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_MD.ODS_TDF_MARA) | OW_MD.ODS_TDF_MARA | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.2412 | ODS | 0 | [(PROCEDURE - OW_MD.PROC_DIM_PRODUCT)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_SDI) | OW_SEDA_S.FT_TSS_BI_TRACKING_SDI | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0386 | FT | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_ASP_RANGE) | OW_SEDA_S.MAP_CE_ASP_RANGE | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0029 | MAP | 0 | [(INGESTION - JOB.MAP_CE_ASP_RANGE)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_ASP_RANGE_TABLE) | OW_SEDA_S.MAP_CE_ASP_RANGE_TABLE | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 | [(INGESTION - JOB.MAP_CE_ASP_RANGE_TABLE)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_QUALITY_TRACKER) | OW_SEDA_S.MAP_CE_DISTRIBUTION_QUALITY_TRACKER | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0409 | MAP | 0 | [(INGESTION - JOB.MAP_CE_DISTRIBUTION_QUALITY_TRACKER)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA) | OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0066 | MAP | 0 | [(INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_MBO_KAM) | OW_SEDA_S.MAP_CE_MBO_KAM | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0042 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_PROMOTER_TARGET) | OW_SEDA_S.MAP_CE_PROMOTER_TARGET | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0083 | MAP | 0 | [(INGESTION - JOB.MAP_CE_PROMOTER_TARGET)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_RRP) | OW_SEDA_S.MAP_CE_RRP | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_META_PROMOTOR)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_SALES_DEDUCTION) | OW_SEDA_S.MAP_CE_SALES_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0004 | MAP | 0 | [(INGESTION - JOB.MAP_CE_SALES_DEDUCTION)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_TRIPLE_A_PERFORMANCE_SUMMARY) | OW_SEDA_S.MAP_CE_TRIPLE_A_PERFORMANCE_SUMMARY | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0006 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_TRIPLE_A_TARGET) | OW_SEDA_S.MAP_CE_TRIPLE_A_TARGET | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0003 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_WEBPRICE_URL) | OW_SEDA_S.MAP_CE_WEBPRICE_URL | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0053 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_WEBPRICE_URL)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.MAP_PIN_TO_PIN_BF_19) | OW_SEDA_S.MAP_PIN_TO_PIN_BF_19 | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 | [(PROCEDURE - OW_SEDA_S.PRC_UPDATE_PIN_TO_PIN)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CE_MKT_TRANSMISSORAS) | OW_SEDA_S.ODS_CE_MKT_TRANSMISSORAS | [5 empty] | Done |  | 1 | 1 | 45973 | 45973 | ['[]'] | 0 | Migrar ph2 | 0.0005 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE)] | 1 | [11 empty] | 12/11 - 12/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CE_SHOPPING_BRASIL_API) | OW_SEDA_S.ODS_CE_SHOPPING_BRASIL_API | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0528 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_CE_SHOPPING_BRASIL_API)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CE_WEATHER_FCST_API) | OW_SEDA_S.ODS_CE_WEATHER_FCST_API | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0085 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_CE_WEATHER_FCST_API)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_ACTUAL_SALES) | OW_SEDA_S.ODS_GSCM_ACTUAL_SALES | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0407 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_ACTUAL_SALES)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_FCST_MGMT_AP1) | OW_SEDA_S.ODS_GSCM_FCST_MGMT_AP1 | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.1936 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_FCST_MGMT_AP1)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_PROMOTION_PLAN_RAW) | OW_SEDA_S.ODS_GSCM_PROMOTION_PLAN_RAW | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0196 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_PROMOTION_PLAN_RAW)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SELL_OUT_ACCOUNT) | OW_SEDA_S.ODS_GSCM_SELL_OUT_ACCOUNT | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0154 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_SELL_OUT_ACCOUNT)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_DA) | OW_SEDA_S.ODS_GSCM_SI_FCST_DA | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0849 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_SI_FCST_DA)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_MX) | OW_SEDA_S.ODS_GSCM_SI_FCST_MX | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.1837 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_SI_FCST_MX)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_VD) | OW_SEDA_S.ODS_GSCM_SI_FCST_VD | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0798 | ODS | 0 | [(INGESTION - JOB.ODS_GSCM_SI_FCST_VD)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM) | OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 1.627 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.INGEST_OUTBOUND_TRACKING_SCM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL) | OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0827 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW) | OW_SEDA_S.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0667 | ODS | 0 | [(INGESTION - JOB.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_BOOKING_UPDATE_LOG) | OW_SEDA_S.ODS_TSS_BOOKING_UPDATE_LOG | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0399 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_REASON_GRP) | OW_SEDA_S.ODS_TSS_M_REASON_GRP | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_RETURN_REASON) | OW_SEDA_S.ODS_TSS_M_RETURN_REASON | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0002 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_NF_OD_ORDERS) | OW_SEDA_S.ODS_TSS_NF_OD_ORDERS | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0845 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_DETAIL) | OW_SEDA_S.ODS_TSS_OD_ORDERS_DETAIL | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0935 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_LOC) | OW_SEDA_S.ODS_TSS_OD_ORDERS_LOC | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0599 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT) | OW_SEDA_S.ODS_TSS_RS_RESULT | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0973 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_GROUP) | OW_SEDA_S.ODS_TSS_RS_RESULT_GROUP | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0276 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_IOD_STATUS_REPORT) | OW_SEDA_S.ODS_TSS_TB_MVW_IOD_STATUS_REPORT | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0013 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_DO_EPOD_RECEIVED) | OW_SEDA_S.ODS_TSS_TC_DO_EPOD_RECEIVED | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0273 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT) | OW_SEDA_S.ODS_TSS_TC_EVENT | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0395 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT_DATE) | OW_SEDA_S.ODS_TSS_TC_EVENT_DATE | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0247 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT_LOG) | OW_SEDA_S.ODS_TSS_TC_EVENT_LOG | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0571 | ODS | 0 | [(FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_FOLLOW_UP_STATUS) | OW_SEDA_S.ODS_TSS_TC_FOLLOW_UP_STATUS | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0275 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_NOTES) | OW_SEDA_S.ODS_TSS_TC_NOTES | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0184 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_ORDERS) | OW_SEDA_S.ODS_TSS_TC_ORDERS | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.1371 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_TRACKING_ITEM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MON) | OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MON | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0664 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MON)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.RAW_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM) | OW_SEDA_S.RAW_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 13.3306 | RAW | 0 | [(PROCEDURE - OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_HEADER_DIVISION) | OW_SEDA_S.SDI_TSS_M_HEADER_DIVISION | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0002 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_TRANS) | OW_SEDA_S.SDI_TSS_M_TRANS | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0013 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN) | OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0422 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN_DETAIL) | OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN_DETAIL | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0371 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_PRE_SHIPMENT) | OW_SEDA_S.SDI_TSS_OD_PRE_SHIPMENT | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0156 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_OD_PRE_SHIPMENT)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOC) | OW_SEDA_S.SDI_TSS_TC_EVENT_LOC | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 1.1034 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_LOC)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_IOD) | OW_SEDA_S.SDI_TSS_TC_IOD | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.2817 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_NOTES) | OW_SEDA_S.SDI_TSS_TC_NOTES | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.075 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_WEB_RETURN_REQUEST) | OW_SEDA_S.SDI_TSS_WEB_RETURN_REQUEST | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0015 | OTHER | 0 | [(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CE_FORMAT) | OW_SEDA_S.TMP_CE_FORMAT | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0942 | TMP | 0 | [(INGESTION - JOB.TMP_CE_FORMAT)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_B2B) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_B2B | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0019 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_B2B)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BREA) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BREA | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BREA)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BRSHOP) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BRSHOP | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0238 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BRSHOP)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EPP2) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EPP2 | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0015 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EPP2)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EST) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EST | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0037 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EST)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MEMBERS) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MEMBERS | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0017 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MEMBERS)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_PARC) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_PARC | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.002 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_PARC)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_RESID) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_RESID | [5 empty] | Done |  | 1 | 1 | 45974 | 45974 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 | [(PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_RESID)] | 1 | [11 empty] | 13/11 - 13/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MX_STORE_MAPPING) | OW_SEDA_S.TMP_MX_STORE_MAPPING | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 | [(VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022)] | 1 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_SEDA_S.TMP_ODS_GSCM_PROMOTION_PLAN) | OW_SEDA_S.TMP_ODS_GSCM_PROMOTION_PLAN | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0085 | TMP | 0 | [(INGESTION - JOB.TMP_ODS_GSCM_PROMOTION_PLAN)] | 1 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_SEDA_S.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION) | OW_SEDA_S.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0026 | TMP | 0 | [(INGESTION - JOB.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION)] | 1 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SDI_TSS_OD_ORDERS) | OW_SEDA_S.TMP_SDI_TSS_OD_ORDERS | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.037 | TMP | 0 | [(VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI)] | 1 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ALERT_MONITORING_STATUS_NULL) | OW_LAO.ALERT_MONITORING_STATUS_NULL | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION) | OW_LAO.FT_LAO_SALES_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | FT | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.FT_SPRINKLR) | OW_LAO.FT_SPRINKLR | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.4368 | FT | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION_V2) | OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION_V2 | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | INPUT | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_SECH_FORECASTMGMT) | OW_LAO.ODS_GSCM_SECH_FORECASTMGMT | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_GSCM_SELLIN_BIZ_PLAN) | OW_LAO.ODS_GSCM_SELLIN_BIZ_PLAN | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.2641 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_6_10W) | OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_6_10W | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_6W_10W) | OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_6W_10W | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_DAILY_EDI_VALIDATION) | OW_LAO.ODS_SALES_DEDUCTION_DAILY_EDI_VALIDATION | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_DAILY_EDI_VALIDATION_6_10W) | OW_LAO.ODS_SALES_DEDUCTION_DAILY_EDI_VALIDATION_6_10W | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_6_10W) | OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_6_10W | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_SPRINKLR_DL) | OW_LAO.ODS_SPRINKLR_DL | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 10.3172 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.ODS_SPRINKLR_EVENTS_DL) | OW_LAO.ODS_SPRINKLR_EVENTS_DL | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0 | ODS | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.RAW_DATA_GSSC_REPORT_TO_SR) | OW_LAO.RAW_DATA_GSSC_REPORT_TO_SR | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.1622 | RAW | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT) | OW_LAO.RAW_DATA_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.3041 | RAW | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.RAW_DATA_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT) | OW_LAO.RAW_DATA_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 1.6705 | RAW | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_ACTUAL_SALES) | OW_LAO.RAW_GSCM_ACTUAL_SALES | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0004 | RAW | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_AP1_ACCURACY_PIVOT_TABLE) | OW_LAO.RAW_GSCM_AP1_ACCURACY_PIVOT_TABLE | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0884 | RAW | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.1047 | RAW | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.1536 | RAW | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_EXCEPTION) | OW_LAO.RAW_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0012 | RAW | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_PREMIUM_MODELS) | OW_LAO.RAW_GSCM_PREMIUM_MODELS | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0028 | RAW | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.RAW_GSCM_PREMIUM_MODELS_PIVOT_TABLE) | OW_LAO.RAW_GSCM_PREMIUM_MODELS_PIVOT_TABLE | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.015 | RAW | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TEMP_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION) | OW_LAO.TEMP_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION | LAO EStore | r.bojart |  | yes | 3 | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | OTHER | 0 |  | 0 | [11 empty] | 14/11 - 14/11
Control Tower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0 | OTHER | 0 |  | 0 | [11 empty] | 14/11 - 14/11
Control Tower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_2) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_2 | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0005 | OTHER | 0 |  | 0 | [11 empty] | 14/11 - 14/11
Control Tower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_DELETE) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_DELETE | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0012 | OTHER | 0 |  | 0 | [11 empty] | 14/11 - 14/11
Control Tower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_DELETE_2) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_MONITORING_FILTER_DELETE_2 | LAO EStore | r.bojart |  |  |  | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0007 | OTHER | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_VALIDATION) | OW_LAO.TF_LAO_SALES_DEDUCTION_VALIDATION | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TF | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_CANCELATION) | OW_LAO.TMP_AFTER_SALES_CANCELATION | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0014 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND) | OW_LAO.TMP_AFTER_SALES_REFUND | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_BRB2B) | OW_LAO.TMP_AFTER_SALES_REFUND_BRB2B | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_BREA) | OW_LAO.TMP_AFTER_SALES_REFUND_BREA | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_BRSHOPMKTPL) | OW_LAO.TMP_AFTER_SALES_REFUND_BRSHOPMKTPL | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BRB2B) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BRB2B | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0009 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BREA) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BREA | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0032 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_EPP2) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_EPP2 | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_EST) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_EST | [5 empty] | Done |  | 1 | 1 | 45975 | 45975 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [11 empty] | 14/11 - 14/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_MEMBERS) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_MEMBERS | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0007 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_PARC) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_PARC | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_RESID) | OW_LAO.TMP_AFTER_SALES_REFUND_DETAIL_RESID | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_EPP2) | OW_LAO.TMP_AFTER_SALES_REFUND_EPP2 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_EST) | OW_LAO.TMP_AFTER_SALES_REFUND_EST | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_MEMBERS) | OW_LAO.TMP_AFTER_SALES_REFUND_MEMBERS | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_PARC) | OW_LAO.TMP_AFTER_SALES_REFUND_PARC | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_AFTER_SALES_REFUND_RESID) | OW_LAO.TMP_AFTER_SALES_REFUND_RESID | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_DIR_BASIC_ATT_AGE) | OW_LAO.TMP_DIR_BASIC_ATT_AGE | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT) | OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0229 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_6W_10W) | OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_6W_10W | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.023 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_EXCEPTION) | OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_EXCEPTION | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_FOTA) | OW_LAO.TMP_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_PIVOT_FOTA | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0175 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_GSCM_PRODUCT_LIST) | OW_LAO.TMP_GSCM_PRODUCT_LIST | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0118 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_1) | OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_2) | OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_3) | OW_LAO.TMP_LAO_GSCM_CE_SELL_OUT_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0006 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_1) | OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.001 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_2) | OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_3) | OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0508 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_4) | OW_LAO.TMP_LAO_GSCM_FCST_MGMT_SI_D2C_EXCEL_4 | [5 empty] | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_1) | OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_2) | OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_3) | OW_LAO.TMP_LAO_GSCM_MX_SELL_OUT_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0012 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_SALES_DEDUCTION_WEEKLY_EDI) | OW_LAO.TMP_LAO_SALES_DEDUCTION_WEEKLY_EDI | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_LAO.TMP_LAO_SALES_DEDUCTION_WEEKLY_FOTA) | OW_LAO.TMP_LAO_SALES_DEDUCTION_WEEKLY_FOTA | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_MD.MAP_AR_CLAIM_ADJUSTED) | OW_MD.MAP_AR_CLAIM_ADJUSTED | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_MD.ODS_TDF_ADRC) | OW_MD.ODS_TDF_ADRC | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.1775 | ODS | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_MD.ODS_TDF_KNA1) | OW_MD.ODS_TDF_KNA1 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.1721 | ODS | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_MD.ODS_TDF_LFA1) | OW_MD.ODS_TDF_LFA1 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.2292 | ODS | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_MD.ODS_TDF_MAKT) | OW_MD.ODS_TDF_MAKT | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.1175 | ODS | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_MD.ODS_TDF_MARC) | OW_MD.ODS_TDF_MARC | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.3873 | ODS | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_MD.ODS_TDF_MBEW) | OW_MD.ODS_TDF_MBEW | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.1846 | ODS | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_MD.TMP_GSCM_PRODUCT_CATEGORY) | OW_MD.TMP_GSCM_PRODUCT_CATEGORY | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0187 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_MD.TMP_MAP_GSCM) | OW_MD.TMP_MAP_GSCM | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM_FILTERED) | OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM_FILTERED | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0773 | OTHER | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_VAGNER) | OW_SEDA_S.CELLO_DELIVERY_INBOUND_VAGNER | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0014 | OTHER | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM_2) | OW_SEDA_S.CELLO_DELIVERY_ITEM_2 | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0003 | OTHER | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_INBOUND_BOOKING) | OW_SEDA_S.CELLO_INBOUND_BOOKING | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0704 | OTHER | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST_TEMPO) | OW_SEDA_S.CELLO_LAST_LEG_MANIFEST_TEMPO | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0049 | OTHER | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_SUM_LLM) | OW_SEDA_S.CELLO_SUM_LLM | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0006 | OTHER | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.CELLO_SUM_SHIPMENT) | OW_SEDA_S.CELLO_SUM_SHIPMENT | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0874 | OTHER | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.FT_AMAZON_MX) | OW_SEDA_S.FT_AMAZON_MX | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0096 | FT | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.FT_ASAP_FLAGSHIP_NET_GAIN) | OW_SEDA_S.FT_ASAP_FLAGSHIP_NET_GAIN | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0004 | FT | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.FT_BF_AVG_SELL_OUT) | OW_SEDA_S.FT_BF_AVG_SELL_OUT | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0024 | FT | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.FT_CE_PRICE_TABLE) | OW_SEDA_S.FT_CE_PRICE_TABLE | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.117 | FT | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.FT_CE_RM_MEETING_AV) | OW_SEDA_S.FT_CE_RM_MEETING_AV | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0138 | FT | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.FT_CE_RM_MEETING_DA) | OW_SEDA_S.FT_CE_RM_MEETING_DA | [5 empty] | Done |  | 1 | 1 | 45978 | 45978 | ['[]'] | 0 | Migrar ph2 | 0.0128 | FT | 0 |  | 0 | [12 empty] | 17/11 - 17/11
| TABLE | (TABLE - OW_SEDA_S.FT_CHEIL_CHECKINS) | OW_SEDA_S.FT_CHEIL_CHECKINS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0275 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_CHEIL_VISITS) | OW_SEDA_S.FT_CHEIL_VISITS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0248 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_DIR_BASIC_ATT) | OW_SEDA_S.FT_DIR_BASIC_ATT | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.001 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_DIR_BASIC_ATT_AGE) | OW_SEDA_S.FT_DIR_BASIC_ATT_AGE | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0045 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_DIR_BASIC_ATT_GENDER) | OW_SEDA_S.FT_DIR_BASIC_ATT_GENDER | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0024 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_GFK_MX_MONTHLY_CHANNEL) | OW_SEDA_S.FT_GFK_MX_MONTHLY_CHANNEL | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0174 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_GFK_MX_MONTHLY_ON_OFF) | OW_SEDA_S.FT_GFK_MX_MONTHLY_ON_OFF | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0268 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_GFK_MX_MONTHLY_REGIONAL) | OW_SEDA_S.FT_GFK_MX_MONTHLY_REGIONAL | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0402 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_GFK_NPC_MONTHLY) | OW_SEDA_S.FT_GFK_NPC_MONTHLY | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0027 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_GFK_NPC_WEEKLY) | OW_SEDA_S.FT_GFK_NPC_WEEKLY | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0058 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_GFK_TAB_MONTHLY) | OW_SEDA_S.FT_GFK_TAB_MONTHLY | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0011 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_GFK_TAB_WEEKLY) | OW_SEDA_S.FT_GFK_TAB_WEEKLY | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0024 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_GROSS_MARGIN_PROMO_DEDUCTION) | OW_SEDA_S.FT_GROSS_MARGIN_PROMO_DEDUCTION | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0461 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_AI_USAGE_RATE) | OW_SEDA_S.FT_MX_AI_USAGE_RATE | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0001 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_SAMSUNG_HEALTH) | OW_SEDA_S.FT_MX_SAMSUNG_HEALTH | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0004 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_SAMSUNG_HEALTH_EVENTS) | OW_SEDA_S.FT_MX_SAMSUNG_HEALTH_EVENTS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0013 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_SAMSUNG_WALLET) | OW_SEDA_S.FT_MX_SAMSUNG_WALLET | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0002 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_SAMSUNG_WALLET_EVENTS) | OW_SEDA_S.FT_MX_SAMSUNG_WALLET_EVENTS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0006 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_PARAGUAI_IMPORTS_MX) | OW_SEDA_S.FT_PARAGUAI_IMPORTS_MX | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0098 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_SVC_SO_PAR_DAILY) | OW_SEDA_S.FT_SVC_SO_PAR_DAILY | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0996 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_SVC_SO_PAR_MONTHLY) | OW_SEDA_S.FT_SVC_SO_PAR_MONTHLY | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.4741 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING) | OW_SEDA_S.FT_TSS_BI_TRACKING | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0707 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HIST) | OW_SEDA_S.FT_TSS_BI_TRACKING_HIST | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.1252 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HISTORICO) | OW_SEDA_S.FT_TSS_BI_TRACKING_HISTORICO | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.327 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_BETWEEN_2014_AND_2016) | OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_BETWEEN_2014_AND_2016 | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.1401 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_SDI_6MONTHS) | OW_SEDA_S.FT_TSS_BI_TRACKING_SDI_6MONTHS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0726 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.FT_WRONG_IOD_REPORT) | OW_SEDA_S.FT_WRONG_IOD_REPORT | [5 empty] | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.4007 | FT | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_ACCOUNT_MODE) | OW_SEDA_S.MAP_CE_ACCOUNT_MODE | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0057 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_BF_PLANOS_ABCD) | OW_SEDA_S.MAP_CE_BF_PLANOS_ABCD | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0016 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_CHANNEL_MODE) | OW_SEDA_S.MAP_CE_CHANNEL_MODE | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0066 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_HA) | OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_HA | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0017 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_LOJAS) | OW_SEDA_S.MAP_CE_LOJAS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0395 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_MBO_TARGETS) | OW_SEDA_S.MAP_CE_MBO_TARGETS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0012 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_MBO_WEIGHT_PORTION) | OW_SEDA_S.MAP_CE_MBO_WEIGHT_PORTION | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0002 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_MBO_WOS_TARGET) | OW_SEDA_S.MAP_CE_MBO_WOS_TARGET | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_RAC_LINE) | OW_SEDA_S.MAP_CE_RAC_LINE | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0002 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_SUPER_BIG_INCHES_TRACKER) | OW_SEDA_S.MAP_CE_SUPER_BIG_INCHES_TRACKER | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0033 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_ENVIRONMENTS) | OW_SEDA_S.MAP_CHEIL_ENVIRONMENTS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES) | OW_SEDA_S.MAP_CHEIL_FORMULARIES | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0006 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_GFK_MX_PRODUCTS) | OW_SEDA_S.MAP_GFK_MX_PRODUCTS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_GFK_NPC_PRODUCTS) | OW_SEDA_S.MAP_GFK_NPC_PRODUCTS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0002 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_GFK_PRODUCTS) | OW_SEDA_S.MAP_GFK_PRODUCTS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0004 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_GFK_TAB_PRODUCTS) | OW_SEDA_S.MAP_GFK_TAB_PRODUCTS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_MX_GTM_TARGETS) | OW_SEDA_S.MAP_MX_GTM_TARGETS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_MX_PRODUCTS) | OW_SEDA_S.MAP_MX_PRODUCTS | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0003 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_MX_RRP) | OW_SEDA_S.MAP_MX_RRP | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0001 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS_LSPOSITO) | OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS_LSPOSITO | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0002 | MAP | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ASSURANT_API_INTERFACE) | OW_SEDA_S.ODS_ASSURANT_API_INTERFACE | [5 empty] | Done |  | 1 | 1 | 45979 | 45979 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [12 empty] | 18/11 - 18/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_FLOORSHARE) | OW_SEDA_S.ODS_CHEIL_FLOORSHARE | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0004 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_FLOR_SHARE) | OW_SEDA_S.ODS_CHEIL_FLOR_SHARE | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_JOURNEY) | OW_SEDA_S.ODS_CHEIL_JOURNEY | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0153 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_LDU) | OW_SEDA_S.ODS_CHEIL_LDU | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0004 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_POSITIVATION) | OW_SEDA_S.ODS_CHEIL_POSITIVATION | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0004 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CHEIL_PRICES) | OW_SEDA_S.ODS_CHEIL_PRICES | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.013 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_WEEK_OLD) | OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_WEEK_OLD | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0429 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GFK_HITLIST_CE_RAC) | OW_SEDA_S.ODS_GFK_HITLIST_CE_RAC | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0089 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GFK_HITLIST_CE_REF) | OW_SEDA_S.ODS_GFK_HITLIST_CE_REF | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0106 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GFK_HITLIST_CE_TV) | OW_SEDA_S.ODS_GFK_HITLIST_CE_TV | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0167 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GFK_HITLIST_CE_WM) | OW_SEDA_S.ODS_GFK_HITLIST_CE_WM | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0093 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GFK_REGION_CE_TV) | OW_SEDA_S.ODS_GFK_REGION_CE_TV | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0016 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_AP1_SO_FA_MONTH) | OW_SEDA_S.ODS_GSCM_AP1_SO_FA_MONTH | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_AP1_SO_FA_WEEK) | OW_SEDA_S.ODS_GSCM_AP1_SO_FA_WEEK | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_AP2_SO_FA_MONTH) | OW_SEDA_S.ODS_GSCM_AP2_SO_FA_MONTH | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0002 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_AP2_SO_FA_WEEK) | OW_SEDA_S.ODS_GSCM_AP2_SO_FA_WEEK | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0002 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP1_RAWDATA) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP1_RAWDATA | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0057 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP1_RAWDATA_MON) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP1_RAWDATA_MON | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0063 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP2_RAWDATA) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP2_RAWDATA | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0045 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP2_RAWDATA_MON) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_AP2_RAWDATA_MON | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_AR_GRAPHICS) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_AR_GRAPHICS | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0022 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_MON_GRAPHICS) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_MON_GRAPHICS | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0005 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_SEDA_GRAPHIC) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_SEDA_GRAPHIC | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0063 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_AR_GLOBAL) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_AR_GLOBAL | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0003 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_AR_SEDA) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_AR_SEDA | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0006 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_GLOBAL) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_GLOBAL | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0048 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_SEDA) | OW_SEDA_S.ODS_GSCM_KPI_REPORT_SUMMARY_SEDA | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0011 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP1_SO_FA_MONTH) | OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP1_SO_FA_MONTH | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP1_SO_FA_WEEK) | OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP1_SO_FA_WEEK | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP2_SO_FA_MONTH) | OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP2_SO_FA_MONTH | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP2_SO_FA_WEEK) | OW_SEDA_S.ODS_GSCM_PERFORMANCE_AP2_SO_FA_WEEK | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_RTF) | OW_SEDA_S.ODS_GSCM_RTF | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0009 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_GSCM_STOCK_BASE) | OW_SEDA_S.ODS_GSCM_STOCK_BASE | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0007 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_INCENTIVES_GSCM_CLEAN) | OW_SEDA_S.ODS_INCENTIVES_GSCM_CLEAN | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0002 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_INCENTIVES_GSCM_DATA) | OW_SEDA_S.ODS_INCENTIVES_GSCM_DATA | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0002 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_LOAD_SCM) | OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_LOAD_SCM | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.1194 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SEDA_D2C_VISIB) | OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SEDA_D2C_VISIB | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0354 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_SHIPMENTS) | OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_SHIPMENTS | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.2313 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_IOD_STATUS_REPORT) | OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_IOD_STATUS_REPORT | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0258 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_OTD4_ANALYSIS) | OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_OTD4_ANALYSIS | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0288 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_OTD_CARRIER) | OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_OTD_CARRIER | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_TC_LEG_PLANNING) | OW_SEDA_S.ODS_TSS_HANA_RESTORE_TB_MVW_TC_LEG_PLANNING | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0103 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_MVW_OTD4_ANALYSIS) | OW_SEDA_S.ODS_TSS_MVW_OTD4_ANALYSIS | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0303 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_M_HOLIDAY) | OW_SEDA_S.ODS_TSS_M_HOLIDAY | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0005 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_NF_OD_ORDERS_DETAIL) | OW_SEDA_S.ODS_TSS_NF_OD_ORDERS_DETAIL | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0615 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_INBOUND) | OW_SEDA_S.ODS_TSS_OD_INBOUND | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0081 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_INBOUND_DETAIL) | OW_SEDA_S.ODS_TSS_OD_INBOUND_DETAIL | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0112 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_RETURN) | OW_SEDA_S.ODS_TSS_OD_ORDERS_RETURN | [5 empty] | Done |  | 1 | 1 | 45980 | 45980 | ['[]'] | 0 | Migrar ph2 | 0.0247 | ODS | 0 |  | 0 | [12 empty] | 19/11 - 19/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_RETURN_DETAIL) | OW_SEDA_S.ODS_TSS_OD_ORDERS_RETURN_DETAIL | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.019 | ODS | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_OTD4_ANALYSIS) | OW_SEDA_S.ODS_TSS_TB_MVW_OTD4_ANALYSIS | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0313 | ODS | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_OTD_CARRIER) | OW_SEDA_S.ODS_TSS_TB_MVW_OTD_CARRIER | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0001 | ODS | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_INBOUND) | OW_SEDA_S.ODS_TSS_TC_INBOUND | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0184 | ODS | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_IOD) | OW_SEDA_S.ODS_TSS_TC_IOD | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0321 | ODS | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_ORDER_OCCURRENCE_RPT) | OW_SEDA_S.ODS_TSS_TC_ORDER_OCCURRENCE_RPT | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0088 | ODS | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_RETURN_BOOKING_REQUEST) | OW_SEDA_S.ODS_TSS_TC_RETURN_BOOKING_REQUEST | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0081 | ODS | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_TC_SCHEDULE_ORDER) | OW_SEDA_S.ODS_TSS_TC_SCHEDULE_ORDER | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0004 | ODS | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.ODS_TSS_WEB_RETURN_REQUEST) | OW_SEDA_S.ODS_TSS_WEB_RETURN_REQUEST | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0011 | ODS | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.ODS_WEBPRICE_PRICE_TRACKING_ON_RAC) | OW_SEDA_S.ODS_WEBPRICE_PRICE_TRACKING_ON_RAC | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0276 | ODS | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.RAW_ASAP_GLOBAL_REPURCHASE_ANALYSIS) | OW_SEDA_S.RAW_ASAP_GLOBAL_REPURCHASE_ANALYSIS | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.078 | RAW | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.RAW_ASAP_SEDA_INSTALLED_BASE) | OW_SEDA_S.RAW_ASAP_SEDA_INSTALLED_BASE | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.018 | RAW | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.RAW_GFK_MX_MONTHLY) | OW_SEDA_S.RAW_GFK_MX_MONTHLY | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0213 | RAW | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.RAW_GSCM_DAILY_INVENTORY) | OW_SEDA_S.RAW_GSCM_DAILY_INVENTORY | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0008 | RAW | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.RAW_GSCM_PRODUCT_LIST) | OW_SEDA_S.RAW_GSCM_PRODUCT_LIST | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0003 | RAW | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.RAW_MX_HEALTH_APP_WEEKLY_USAGE) | OW_SEDA_S.RAW_MX_HEALTH_APP_WEEKLY_USAGE | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0199 | RAW | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.RAW_PLUGG_CREDENTIALS) | OW_SEDA_S.RAW_PLUGG_CREDENTIALS | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0001 | RAW | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_CELLO_STAGE) | OW_SEDA_S.SDI_CELLO_STAGE | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 1.6119 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_CELLO_STAGE_PRE) | OW_SEDA_S.SDI_CELLO_STAGE_PRE | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0001 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_CELLO_STAGE_VAGNER) | OW_SEDA_S.SDI_CELLO_STAGE_VAGNER | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0004 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_IF2_PICKUP_SCHEDULE_TRIGGER) | OW_SEDA_S.SDI_TSS_IF2_PICKUP_SCHEDULE_TRIGGER | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0058 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_MVW_OTD4_ANALYSIS) | OW_SEDA_S.SDI_TSS_MVW_OTD4_ANALYSIS | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0141 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_AREA) | OW_SEDA_S.SDI_TSS_M_AREA | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0006 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_AREA_TYPE) | OW_SEDA_S.SDI_TSS_M_AREA_TYPE | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0004 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_AREA_TYPE_DETAIL) | OW_SEDA_S.SDI_TSS_M_AREA_TYPE_DETAIL | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0017 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_CODE) | OW_SEDA_S.SDI_TSS_M_CODE | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.001 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_COMPANY) | OW_SEDA_S.SDI_TSS_M_COMPANY | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0003 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_DIVISION) | OW_SEDA_S.SDI_TSS_M_DIVISION | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0002 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_FOLLOW_UP_STATUS) | OW_SEDA_S.SDI_TSS_M_FOLLOW_UP_STATUS | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0002 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_M_HOLIDAY) | OW_SEDA_S.SDI_TSS_M_HOLIDAY | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0005 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS_DETAIL) | OW_SEDA_S.SDI_TSS_NF_OD_ORDERS_DETAIL | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.3523 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_INBOUND) | OW_SEDA_S.SDI_TSS_OD_INBOUND | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0132 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_OD_INBOUND_DETAIL) | OW_SEDA_S.SDI_TSS_OD_INBOUND_DETAIL | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0278 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_SD_M_ROUTE) | OW_SEDA_S.SDI_TSS_SD_M_ROUTE | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0002 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_BOOKING_REQUEST) | OW_SEDA_S.SDI_TSS_TC_BOOKING_REQUEST | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0758 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.SDI_TSS_TC_INBOUND) | OW_SEDA_S.SDI_TSS_TC_INBOUND | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.024 | OTHER | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SI_FCST_DA) | OW_SEDA_S.TF_GSCM_SI_FCST_DA | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.003 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SI_FCST_MX) | OW_SEDA_S.TF_GSCM_SI_FCST_MX | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0031 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SI_FCST_VD) | OW_SEDA_S.TF_GSCM_SI_FCST_VD | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0026 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SO_FCST_DA) | OW_SEDA_S.TF_GSCM_SO_FCST_DA | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0096 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SO_FCST_HHP) | OW_SEDA_S.TF_GSCM_SO_FCST_HHP | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0127 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SO_FCST_OTHERS) | OW_SEDA_S.TF_GSCM_SO_FCST_OTHERS | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.004 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_GSCM_SO_FCST_VD) | OW_SEDA_S.TF_GSCM_SO_FCST_VD | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0047 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_MAP_SALES_DEDUCTION_CORE_LEVELS_SELLOUTGERAL) | OW_SEDA_S.TF_MAP_SALES_DEDUCTION_CORE_LEVELS_SELLOUTGERAL | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_MAP_SALES_DEDUCTION_CORE_LEVELS_WALMART) | OW_SEDA_S.TF_MAP_SALES_DEDUCTION_CORE_LEVELS_WALMART | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_COMPLETO) | OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_COMPLETO | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL) | OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0006 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_WALMART) | OW_SEDA_S.TF_VW_SALES_DEDUCTION_RESULT_WALMART | [5 empty] | Done |  | 1 | 1 | 45981 | 45981 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TF | 0 |  | 0 | [12 empty] | 20/11 - 20/11
| TABLE | (TABLE - OW_SEDA_S.TF_VW_SELLOUTGERAL_JOIN) | OW_SEDA_S.TF_VW_SELLOUTGERAL_JOIN | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0 | TF | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TF_VW_WALMART_JOIN) | OW_SEDA_S.TF_VW_WALMART_JOIN | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0 | TF | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_1) | OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_2) | OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_3) | OW_SEDA_S.TMP_AP1_SO_FA_MONTH_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0011 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_1) | OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_2) | OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_3) | OW_SEDA_S.TMP_AP1_SO_FA_WEEK_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0011 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_1) | OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_2) | OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_3) | OW_SEDA_S.TMP_AP2_SO_FA_MONTH_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0011 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_1) | OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_2) | OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_3) | OW_SEDA_S.TMP_AP2_SO_FA_WEEK_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0011 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_ASAP_FLAGSHIP_NET_GAIN) | OW_SEDA_S.TMP_ASAP_FLAGSHIP_NET_GAIN | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_ASAP_REGIONAL_FOTA) | OW_SEDA_S.TMP_ASAP_REGIONAL_FOTA | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0105 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_ASAP_SEDA_INSTALLED_BASE) | OW_SEDA_S.TMP_ASAP_SEDA_INSTALLED_BASE | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_ASSURANT_API_INTERFACE) | OW_SEDA_S.TMP_ASSURANT_API_INTERFACE | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CE_FCST) | OW_SEDA_S.TMP_CE_FCST | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0036 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CE_IDEA_PSI_WARNING) | OW_SEDA_S.TMP_CE_IDEA_PSI_WARNING | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0104 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CE_WEEKLY_UPDATE) | OW_SEDA_S.TMP_CE_WEEKLY_UPDATE | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0046 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_ANSWERS) | OW_SEDA_S.TMP_CHEIL_ANSWERS | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0006 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_CHECKINS) | OW_SEDA_S.TMP_CHEIL_CHECKINS | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_COLLABORATORS) | OW_SEDA_S.TMP_CHEIL_COLLABORATORS | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_ENVIRONMENTS) | OW_SEDA_S.TMP_CHEIL_ENVIRONMENTS | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_FLOORSHARE) | OW_SEDA_S.TMP_CHEIL_FLOORSHARE | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_FLOR_SHARE) | OW_SEDA_S.TMP_CHEIL_FLOR_SHARE | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_FORMULARIES) | OW_SEDA_S.TMP_CHEIL_FORMULARIES | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0006 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_FORMULARIES_QUESTIONS) | OW_SEDA_S.TMP_CHEIL_FORMULARIES_QUESTIONS | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_INTERNAL_IMAGES) | OW_SEDA_S.TMP_CHEIL_INTERNAL_IMAGES | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_JOURNEY) | OW_SEDA_S.TMP_CHEIL_JOURNEY | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0007 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_LDU) | OW_SEDA_S.TMP_CHEIL_LDU | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_POS) | OW_SEDA_S.TMP_CHEIL_POS | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0045 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_POSITIVATION) | OW_SEDA_S.TMP_CHEIL_POSITIVATION | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_PRICES) | OW_SEDA_S.TMP_CHEIL_PRICES | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0132 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_PRODUCTS) | OW_SEDA_S.TMP_CHEIL_PRODUCTS | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0006 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_CHEIL_VISITS) | OW_SEDA_S.TMP_CHEIL_VISITS | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_B2B) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_B2B | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_BREA) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_BREA | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_BRSHOP) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_BRSHOP | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0038 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_EPP2) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_EPP2 | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_EST) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_EST | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0006 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_MEMBERS) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_MEMBERS | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_PARC) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_PARC | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_RESID) | OW_SEDA_S.TMP_DATA_API_AFTER_SALES_LIST_RESID | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DIR_BASIC_ATT) | OW_SEDA_S.TMP_DIR_BASIC_ATT | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DIR_BASIC_ATT_AGE) | OW_SEDA_S.TMP_DIR_BASIC_ATT_AGE | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_DIR_BASIC_ATT_GENDER) | OW_SEDA_S.TMP_DIR_BASIC_ATT_GENDER | [5 empty] | Done |  | 1 | 1 | 45982 | 45982 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [12 empty] | 21/11 - 21/11
| TABLE | (TABLE - OW_SEDA_S.TMP_FT_GSCM_RTF) | OW_SEDA_S.TMP_FT_GSCM_RTF | [5 empty] | PROVAVEL DROP NO PROCESSO |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GFK_MX_MONTHLY_CHANNEL) | OW_SEDA_S.TMP_GFK_MX_MONTHLY_CHANNEL | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0023 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GFK_MX_MONTHLY_ON_OFF) | OW_SEDA_S.TMP_GFK_MX_MONTHLY_ON_OFF | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0023 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GFK_MX_MONTHLY_REGIONAL) | OW_SEDA_S.TMP_GFK_MX_MONTHLY_REGIONAL | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0043 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GFK_MX_WEEKLY) | OW_SEDA_S.TMP_GFK_MX_WEEKLY | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GFK_NPC_MONTHLY) | OW_SEDA_S.TMP_GFK_NPC_MONTHLY | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GFK_NPC_WEEKLY) | OW_SEDA_S.TMP_GFK_NPC_WEEKLY | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GFK_TAB_MONTHLY) | OW_SEDA_S.TMP_GFK_TAB_MONTHLY | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GFK_TAB_WEEKLY) | OW_SEDA_S.TMP_GFK_TAB_WEEKLY | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0002 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_DAILY_UPDATE) | OW_SEDA_S.TMP_GSCM_DAILY_UPDATE | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_FCST_CE) | OW_SEDA_S.TMP_GSCM_FCST_CE | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_1) | OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_2) | OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_3) | OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0006 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_4) | OW_SEDA_S.TMP_GSCM_FCST_MGMT_AP1_EXCEL_4 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT) | OW_SEDA_S.TMP_MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_HA) | OW_SEDA_S.TMP_MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_HA | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MAP_CE_PRODUCTS) | OW_SEDA_S.TMP_MAP_CE_PRODUCTS | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MAP_CE_STORES) | OW_SEDA_S.TMP_MAP_CE_STORES | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MAP_CE_WEBPRICE_URL) | OW_SEDA_S.TMP_MAP_CE_WEBPRICE_URL | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MOVING_AVERAGE_CE) | OW_SEDA_S.TMP_MOVING_AVERAGE_CE | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0067 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MX_AI_USAGE_RATE) | OW_SEDA_S.TMP_MX_AI_USAGE_RATE | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MX_DAILY_FOTA) | OW_SEDA_S.TMP_MX_DAILY_FOTA | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MX_HEALTH_APP_WEEKLY_USAGE) | OW_SEDA_S.TMP_MX_HEALTH_APP_WEEKLY_USAGE | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MX_SAMSUNG_HEALTH) | OW_SEDA_S.TMP_MX_SAMSUNG_HEALTH | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0003 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MX_SAMSUNG_HEALTH_EVENTS) | OW_SEDA_S.TMP_MX_SAMSUNG_HEALTH_EVENTS | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MX_SAMSUNG_WALLET) | OW_SEDA_S.TMP_MX_SAMSUNG_WALLET | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MX_SAMSUNG_WALLET_EVENTS) | OW_SEDA_S.TMP_MX_SAMSUNG_WALLET_EVENTS | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_PARAGUAI_IMPORTS_MX) | OW_SEDA_S.TMP_PARAGUAI_IMPORTS_MX | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER) | OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0012 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY) | OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY_CHECK) | OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY_CHECK | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0101 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_SHIPMENTS) | OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_SHIPMENTS | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0006 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY) | OW_SEDA_S.TMP_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0007 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SDI_TSS_NF_OD_ORDERS) | OW_SEDA_S.TMP_SDI_TSS_NF_OD_ORDERS | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.031 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SDI_TSS_TC_ORDERS) | OW_SEDA_S.TMP_SDI_TSS_TC_ORDERS | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0434 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SI_FCST_DA_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0022 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SI_FCST_MX_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0207 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0005 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SI_FCST_VD_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0023 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SO_FCST_DA_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45985 | 45985 | ['[]'] | 0 | Migrar ph2 | 0.0022 | TMP | 0 |  | 0 | [13 empty] | 24/11 - 24/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.001 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SO_FCST_HHP_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0197 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SO_FCST_OTHERS_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0022 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_1) | OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_1 | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_2) | OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_2 | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_3) | OW_SEDA_S.TMP_SEDA_SO_FCST_VD_EXCEL_3 | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0022 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SEDA_STORES) | OW_SEDA_S.TMP_SEDA_STORES | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_TSS_BI_TRACKING) | OW_SEDA_S.TMP_TSS_BI_TRACKING | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0644 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_TSS_BI_TRACKING_2YEARS_SDI) | OW_SEDA_S.TMP_TSS_BI_TRACKING_2YEARS_SDI | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0022 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_TSS_BI_TRACKING_3MONTHS_SDI) | OW_SEDA_S.TMP_TSS_BI_TRACKING_3MONTHS_SDI | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0423 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_TSS_BI_TRACKING_6MONTHS_SDI) | OW_SEDA_S.TMP_TSS_BI_TRACKING_6MONTHS_SDI | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0734 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_TSS_BI_TRACKING_HIST) | OW_SEDA_S.TMP_TSS_BI_TRACKING_HIST | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.127 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_TSS_OD_ORDERS_DETAIL) | OW_SEDA_S.TMP_TSS_OD_ORDERS_DETAIL | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0295 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_TSS_OD_ORDERS_LOC) | OW_SEDA_S.TMP_TSS_OD_ORDERS_LOC | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0168 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_TSS_RS_RESULT) | OW_SEDA_S.TMP_TSS_RS_RESULT | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0413 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_TSS_TC_FOLLOW_UP_STATUS) | OW_SEDA_S.TMP_TSS_TC_FOLLOW_UP_STATUS | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0043 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_WEBPRICE) | OW_SEDA_S.TMP_WEBPRICE | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0124 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_GSCM_SSG_ACTUAL_SALES) | U_PRJ_ECOM.RAW_GSCM_SSG_ACTUAL_SALES | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0032 | RAW | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_GSCM_SSG_FCST_MGMT) | U_PRJ_ECOM.RAW_GSCM_SSG_FCST_MGMT | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0.0061 | RAW | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_GSCM_SSG_ACTUAL_SALES) | U_PRJ_ECOM.TMP_RAW_GSCM_SSG_ACTUAL_SALES | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 | 0 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT) | OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 BI | 0.0036 | FT | 0 | [(VIEW - OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER) | OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 BI | 0.0027 | FT | 0 | [(VIEW - OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_COUNTRY) | OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_COUNTRY | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 BI | 0.0005 | FT | 0 | [(VIEW - OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_COUNTRY)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_DDD) | OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_DDD | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 BI | 0.0002 | FT | 0 | [(VIEW - OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_DDD)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_FBAI_CHURN_IN_DATA) | OW_SEDA_S.FT_FBAI_CHURN_IN_DATA | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 BI | 0.0005 | FT | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_FBAI_CHURN_IN_DATA) | OW_SEDA_S.TMP_FBAI_CHURN_IN_DATA | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 BI | 0.0001 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.MAP_CE_STORES) | OW_SEDA_S.MAP_CE_STORES | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.0884 | MAP | 0 | [(VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022),(VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE),(PROCEDURE - OW_SEDA_S.PRC_TT_RAC_CHECKLIST_DE_EXECUCAO_785),(VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_STORE_NAME),(PROCEDURE - OW_SEDA_S.PRC_TT_WM_CHECKLIST_DE_EXECUCAO_785),(VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE),(VIEW - OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM),(VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES),(PROCEDURE - OW_SEDA_S.PRC_VD_SALES_REVENUE),(INGESTION - JOB.MAP_CE_STORES),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_IBGE_INFO),(VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL),(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_ESES_ON_PIVOT),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDT_SHOPPING_W_BRANDSHOP),(VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING),(VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS),(PROCEDURE - OW_SEDA_S.PRC_VC_UPDATE_READY),(PROCEDURE - OW_SEDA_S.PRC_STOCK_OUT_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_DEAD_SKU_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_TT_REF_CHECKLIST_DE_EXECUCAO_785),(PROCEDURE - OW_SEDA_S.PRC_TT_TV_CHECKLIST_DE_EXECUCAO_785),(PROCEDURE - OW_SEDA_S.PRC_TT_AV_CHECKLIST_DE_EXECUCAO_785),(PROCEDURE - OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA),(PROCEDURE - OW_SEDA_S.PRC_TT_TV_CHECKLIST_DE_EXECUCAO),(VIEW - OW_SEDA_S.VW_TT_STACK_INFO_2023),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY),(VIEW - OW_SEDA_S.VW_CE_PRICE_STORE),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_GFK),(PROCEDURE - OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION)] | 34 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_CE_READY) | OW_SEDA_S.FT_CE_READY | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.6369 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL),(INGESTION - JOB.FT_CE_READY),(VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS),(PROCEDURE - OW_SEDA_S.PRC_DEAD_SKU_CALCULATION),(VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING),(PROCEDURE - OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY),(PROCEDURE - OW_SEDA_S.PRC_VC_UPDATE_READY),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY),(PROCEDURE - OW_SEDA_S.PRC_STOCK_OUT_CALCULATION)] | 10 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_CE_PIVOT) | OW_SEDA_S.FT_CE_PIVOT | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.4591 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_VD_SALES_REVENUE),(VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022),(VIEW - OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM),(VIEW - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_TARGET_WEEK_ADJ),(VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE),(PROCEDURE - OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION),(PROCEDURE - OW_SEDA_S.PRC_CE_STORE_EDI),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_ESES_ON_PIVOT),(VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR)] | 9 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT) | OW_SEDA_S.FT_CE_DAILY_PIVOT | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.7634 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY),(INGESTION - JOB.FT_CE_DAILY_PIVOT),(PROCEDURE - OW_SEDA_S.PRC_VC_UPDATE_READY),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_ESES_ON_PIVOT),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL),(PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY)] | 6 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_DAILY_FOTA) | OW_SEDA_S.FT_MX_DAILY_FOTA | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.085 | FT | 0 | [(VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST),(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK)] | 2 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_PIVOT_BY_ITEM) | OW_SEDA_S.FT_MX_PIVOT_BY_ITEM | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 1.2818 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT),(PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK)] | 2 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_CE_DB_FCST) | OW_SEDA_S.FT_CE_DB_FCST | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.0538 | FT | 0 | [(INGESTION - JOB.FT_CE_DB_FCST)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_CE_DB_FCST_PIVOT) | OW_SEDA_S.FT_CE_DB_FCST_PIVOT | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.0022 | FT | 0 | [(VIEW - OW_SEDA_S.VW_CE_META_PROMOTOR)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_PIVOT) | OW_SEDA_S.FT_MX_PIVOT | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.6868 | FT | 0 | [(VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_MX_PIVOT_2022) | OW_SEDA_S.FT_MX_PIVOT_2022 | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.0014 | FT | 0 | [(VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.FT_SEDA_EDI_DATA) | OW_SEDA_S.FT_SEDA_EDI_DATA | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.6803 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CE_STORE_EDI) | OW_SEDA_S.ODS_CE_STORE_EDI | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.1593 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_STORE_EDI)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.TMP_MX_PIVOT) | OW_SEDA_S.TMP_MX_PIVOT | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2 SEDA RM | 0.0068 | TMP | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_SHIPMENT) | OW_SEDA_S.ODS_CELLO_SHIPMENT | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 1 | Migrar ph2: Cello | 0.1927 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_TRACKING) | OW_SEDA_S.ODS_CELLO_TRACKING | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 1 | Migrar ph2: Cello | 0.2215 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_SHIPMENT_INBOUND) | OW_SEDA_S.ODS_CELLO_SHIPMENT_INBOUND | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 1 | Migrar ph2: Cello | 0.0329 | ODS | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_VESSEL) | OW_SEDA_S.ODS_CELLO_VESSEL | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 1 | Migrar ph2: Cello | 0.0029 | ODS | 0 |  | 0 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_BOOKING) | OW_SEDA_S.ODS_CELLO_BOOKING | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2: Cello | 0.1109 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY) | OW_SEDA_S.ODS_CELLO_DELIVERY | [5 empty] | Done |  | 1 | 1 | 45986 | 45986 | ['[]'] | 0 | Migrar ph2: Cello | 0.7559 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 25/11 - 25/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND) | OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Cello | 0.0621 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND_ITEM) | OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND_ITEM | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Cello | 0.0198 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_ITEM) | OW_SEDA_S.ODS_CELLO_DELIVERY_ITEM | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Cello | 0.185 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_FUTHER_PROCESSING) | OW_SEDA_S.ODS_CELLO_FUTHER_PROCESSING | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Cello | 0.0162 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_LAST_LEG_MANIFEST) | OW_SEDA_S.ODS_CELLO_LAST_LEG_MANIFEST | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Cello | 0.02 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_MANIFEST) | OW_SEDA_S.ODS_CELLO_MANIFEST | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Cello | 0.2314 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_POD) | OW_SEDA_S.ODS_CELLO_POD | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Cello | 0.0059 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL)] | 1 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND_VAGNER) | OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND_VAGNER | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Cello | 0.0004 | ODS | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_INBOUND_BOOKING) | OW_SEDA_S.ODS_CELLO_INBOUND_BOOKING | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Cello | 0.0228 | ODS | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CELLO_MANIFEST_INBOUND) | OW_SEDA_S.ODS_CELLO_MANIFEST_INBOUND | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Cello | 0.0214 | ODS | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL) | OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Controlling | 1.1336 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE),(INGESTION - JOB.ODS_CONTROLLING_FORMAT_ACTUAL),(VIEW - OW_SEDA_S.VW_CE_MANAGEMENT_INFORMATION),(PROCEDURE - OW_SEDA_S.PRC_CE_MANAGEMENT_INFORMATION),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI),(VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX)] | 7 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CONTROLLING_PL) | OW_SEDA_S.ODS_CONTROLLING_PL | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Controlling | 0.0721 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_ONLINE_SELL_IN),(VIEW - OW_SEDA_S.VW_CE_MBO_NETSALES_COP_FCST),(INGESTION - JOB.ODS_CONTROLLING_PL),(VIEW - OW_SEDA_S.VW_CE_MBO_NETSALES_COP),(VIEW - OW_SEDA_S.VW_CE_GERENCIAIS_PL_FCST),(VIEW - OW_SEDA_S.VW_CE_GERENCIAIS_PL)] | 6 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CONTROLLING_PL_2) | OW_SEDA_S.ODS_CONTROLLING_PL_2 | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Controlling | 0.0584 | ODS | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.FT_LAO_DX_PIVOT) | OW_LAO.FT_LAO_DX_PIVOT | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 1.1361 | FT | 0 | [(PROCEDURE - OW_LAO.PRC_ODS_LAO_GSCM_EDI_DATA)] | 1 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.ODS_LAO_GSCM_EDI_DATA) | OW_LAO.ODS_LAO_GSCM_EDI_DATA | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 2.2802 | ODS | 0 | [(PROCEDURE - OW_LAO.PRC_ODS_LAO_GSCM_EDI_DATA)] | 1 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.FT_ASAP_FOTA_GEOLOCATION_SAMCOL) | OW_LAO.FT_ASAP_FOTA_GEOLOCATION_SAMCOL | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0212 | FT | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.FT_ASAP_FOTA_GEOLOCATION_SEM) | OW_LAO.FT_ASAP_FOTA_GEOLOCATION_SEM | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0585 | FT | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.FT_LAO_CE_PIVOT) | OW_LAO.FT_LAO_CE_PIVOT | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.4518 | FT | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.FT_LAO_MX_SELLOUT_FOTA) | OW_LAO.FT_LAO_MX_SELLOUT_FOTA | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0707 | FT | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.FT_LAO_SO_FCST) | OW_LAO.FT_LAO_SO_FCST | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0076 | FT | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.MAP_DA_FLOORING_TARGET_ONE_LAUNCH) | OW_LAO.MAP_DA_FLOORING_TARGET_ONE_LAUNCH | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0001 | MAP | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.MAP_DA_ONE_LAUNCH_PIN_TO_PIN_2025) | OW_LAO.MAP_DA_ONE_LAUNCH_PIN_TO_PIN_2025 | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0 | MAP | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.MAP_LAO_CALENDAR) | OW_LAO.MAP_LAO_CALENDAR | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0001 | MAP | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.MAP_LAO_DA_ONE_LAUNCH_TRAINING_TARGET) | OW_LAO.MAP_LAO_DA_ONE_LAUNCH_TRAINING_TARGET | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0001 | MAP | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.MAP_LAO_PRODUCTS) | OW_LAO.MAP_LAO_PRODUCTS | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0005 | MAP | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.MAP_LAO_STORES) | OW_LAO.MAP_LAO_STORES | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0026 | MAP | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.MAP_SMART_THING_ZONE_STORES) | OW_LAO.MAP_SMART_THING_ZONE_STORES | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0001 | MAP | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.ODS_LAO_PSI_CE_READY) | OW_LAO.ODS_LAO_PSI_CE_READY | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.5075 | ODS | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.RAW_LAO_GSCM_DSM_EDI) | OW_LAO.RAW_LAO_GSCM_DSM_EDI | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0606 | RAW | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.RAW_LAO_GSCM_SO_FCST) | OW_LAO.RAW_LAO_GSCM_SO_FCST | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0001 | RAW | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.RAW_LAO_MX_SELLOUT_FOTA) | OW_LAO.RAW_LAO_MX_SELLOUT_FOTA | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.0034 | RAW | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_LAO.RAW_LAO_PSI_VD_HA_INPUT_R) | OW_LAO.RAW_LAO_PSI_VD_HA_INPUT_R | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: LAO RM | 0.024 | RAW | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_IBGE_CEP_5_COORDINATES) | OW_SEDA_S.ODS_IBGE_CEP_5_COORDINATES | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0.0018 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_IBGE_CEP_5_COORDINATES)] | 1 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.FT_ASAP_REGIONAL_FOTA) | OW_SEDA_S.FT_ASAP_REGIONAL_FOTA | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0.6818 | FT | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.MAP_IBGE_LAT_LONG) | OW_SEDA_S.MAP_IBGE_LAT_LONG | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0.0002 | MAP | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_IBGE_CEP_COORDINATES) | OW_SEDA_S.ODS_IBGE_CEP_COORDINATES | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0.0069 | ODS | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.ODS_IBGE_SETORES_CENSITARIOS_2021) | OW_SEDA_S.ODS_IBGE_SETORES_CENSITARIOS_2021 | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0.0001 | ODS | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.RAW_IBGE_POPULACAO) | OW_SEDA_S.RAW_IBGE_POPULACAO | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: SEDA MI& Big Data | 0.0002 | RAW | 0 |  | 0 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SEDA_S.EDI_DATA_RAW) | OW_SEDA_S.EDI_DATA_RAW | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: SEDA RM | 3.1799 | OTHER | 0 | [(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT),(PROCEDURE - OW_SEDA_S.CONN_TO_SEDA),(PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT_RETAILERS)] | 3 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_USERS) | OW_SDSLA.ODS_TABLEAU_USERS | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Tableau | 0.003 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_USERS),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.ODS_TABLEAU_PROJECT_HIERARCHY),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2)] | 7 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS) | OW_SDSLA.ODS_TABLEAU_GROUP_USERS | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0016 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_USERS),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST)] | 6 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS) | OW_SDSLA.ODS_TABLEAU_V_GROUPS | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0005 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_USERS),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2)] | 6 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS) | OW_SDSLA.ODS_TABLEAU_V_USERS | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Tableau | 0.003 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_USERS),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3)] | 6 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS) | OW_SDSLA.ODS_TABLEAU_EXTRACTS | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0042 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3)] | 5 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS) | OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0282 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3)] | 5 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES) | OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0009 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2)] | 5 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS) | OW_SDSLA.ODS_TABLEAU_HIST_VIEWS | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0075 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST)] | 5 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS) | OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS | [5 empty] | Done |  | 1 | 1 | 45987 | 45987 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0388 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT)] | 5 | [13 empty] | 26/11 - 26/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS) | OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0017 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST)] | 5 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS_STATS) | OW_SDSLA.ODS_TABLEAU_VIEWS_STATS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0192 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST),(VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3)] | 4 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_PROJECTS) | OW_SDSLA.ODS_TABLEAU_PROJECTS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0009 | ODS | 0 | [(VIEW - OW_SDSLA.ODS_TABLEAU_PROJECT_HIERARCHY)] | 1 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_SYSTEM_USERS) | OW_SDSLA.ODS_TABLEAU_SYSTEM_USERS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0022 | ODS | 0 | [(VIEW - OW_SDSLA.ODS_TABLEAU_PROJECT_HIERARCHY)] | 1 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_WORKBOOKS) | OW_SDSLA.ODS_TABLEAU_WORKBOOKS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0049 | ODS | 0 | [(VIEW - OW_SDSLA.VW_TABLEAU_REPORT)] | 1 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.RAW_TABLEAU_DASHBOARDS_MACHINE_STATUS) | OW_SDSLA.RAW_TABLEAU_DASHBOARDS_MACHINE_STATUS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0 | RAW | 0 | [(PROCEDURE - OW_SDSLA.PROC_TABLEAU_DASHBOARDS_MACHINE_STATUS)] | 1 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_SDSLA_TABLEAU_ACCESS_VIEW) | OW_SDSLA.ODS_SDSLA_TABLEAU_ACCESS_VIEW | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0033 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_DESKTOP_REPORTING) | OW_SDSLA.ODS_TABLEAU_DESKTOP_REPORTING | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0034 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_DOMAINS) | OW_SDSLA.ODS_TABLEAU_DOMAINS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0008 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_FLOWS) | OW_SDSLA.ODS_TABLEAU_FLOWS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0004 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_FLOW_OUTPUT_STEPS) | OW_SDSLA.ODS_TABLEAU_FLOW_OUTPUT_STEPS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0007 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_FLOW_OUTPUT_STEP_RUNS) | OW_SDSLA.ODS_TABLEAU_FLOW_OUTPUT_STEP_RUNS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0004 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_FLOW_RUNS) | OW_SDSLA.ODS_TABLEAU_FLOW_RUNS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0005 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_FLOW_RUN_SPECS) | OW_SDSLA.ODS_TABLEAU_FLOW_RUN_SPECS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0007 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_DISK_USAGE) | OW_SDSLA.ODS_TABLEAU_HISTORICAL_DISK_USAGE | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0056 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_USERS) | OW_SDSLA.ODS_TABLEAU_HISTORICAL_USERS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0022 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_COMMENTS) | OW_SDSLA.ODS_TABLEAU_HIST_COMMENTS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0001 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_DATASOURCES) | OW_SDSLA.ODS_TABLEAU_HIST_DATASOURCES | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0068 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_FLOWS) | OW_SDSLA.ODS_TABLEAU_HIST_FLOWS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0006 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_PROJECTS) | OW_SDSLA.ODS_TABLEAU_HIST_PROJECTS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.001 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_SITES) | OW_SDSLA.ODS_TABLEAU_HIST_SITES | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0009 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_USERS) | OW_SDSLA.ODS_TABLEAU_HIST_USERS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0026 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HIST_WORKBOOKS) | OW_SDSLA.ODS_TABLEAU_HIST_WORKBOOKS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0056 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HTTP_REQUESTS) | OW_SDSLA.ODS_TABLEAU_HTTP_REQUESTS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 3.1806 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_HTTP_REQUESTS_TMP) | OW_SDSLA.ODS_TABLEAU_HTTP_REQUESTS_TMP | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0003 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_IDENTITY_BASED_ACTIVATION_ADMIN_VIEW) | OW_SDSLA.ODS_TABLEAU_IDENTITY_BASED_ACTIVATION_ADMIN_VIEW | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0005 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_LICENSES_BY_SUB) | OW_SDSLA.ODS_TABLEAU_LICENSES_BY_SUB | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0005 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_SITES) | OW_SDSLA.ODS_TABLEAU_SITES | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0009 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_SITE_ROLES) | OW_SDSLA.ODS_TABLEAU_SITE_ROLES | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.001 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_USERS_V1) | OW_SDSLA.ODS_TABLEAU_USERS_V1 | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0003 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS) | OW_SDSLA.ODS_TABLEAU_VIEWS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0017 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_BACKGROUND_TASKS) | OW_SDSLA.ODS_TABLEAU_V_BACKGROUND_TASKS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 1.9601 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_DATASOURCES) | OW_SDSLA.ODS_TABLEAU_V_DATASOURCES | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.001 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_DATASOURCES_STATS) | OW_SDSLA.ODS_TABLEAU_V_DATASOURCES_STATS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0013 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_HTTP_REQUESTS) | OW_SDSLA.ODS_TABLEAU_V_HTTP_REQUESTS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0106 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_SESSIONS) | OW_SDSLA.ODS_TABLEAU_V_SESSIONS | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0014 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SDSLA.ODS_TABLEAU_V_SITES) | OW_SDSLA.ODS_TABLEAU_V_SITES | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | Migrar ph2: Tableau | 0.0008 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_CS_INFORMATION_BSC) | U_PRJ_ECOM.ODS_CS_INFORMATION_BSC | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 1 | check | 0.0001 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SEDA_S.ODS_CE_AMAZON_SELL_OUT_FCST) | OW_SEDA_S.ODS_CE_AMAZON_SELL_OUT_FCST | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | check | 0.0001 | ODS | 0 | [(PROCEDURE - OW_SEDA_S.PRC_CE_AMAZON_PRIME_DAY)] | 1 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SEDA_S.ODS_RP_ETR_LOGISTICS_TRACKING) | OW_SEDA_S.ODS_RP_ETR_LOGISTICS_TRACKING | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | check | 0.1935 | ODS | 0 | [(INGESTION - JOB.ODS_RP_ETR_LOGISTICS_TRACKING)] | 1 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SEDA_S.ODS_SCM_FINANCIAL_FCST) | OW_SEDA_S.ODS_SCM_FINANCIAL_FCST | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | check | 0.0003 | ODS | 0 | [(VIEW - OW_SEDA_S.VW_SCM_SALES_AND_SO_LIST_COMPLETE)] | 1 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SEDA_S.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG) | OW_SEDA_S.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | check | 0 | ODS | 0 | [(INGESTION - JOB.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG)] | 1 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_LAO.ODS_GG_ANALYTICS_DL) | OW_LAO.ODS_GG_ANALYTICS_DL | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | check | 0.6227 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ERP_INCOMPLETESDOCS_SOREPORT) | OW_SEDA_S.ODS_ERP_INCOMPLETESDOCS_SOREPORT | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | check | 0.0032 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED) | OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | check | 0.0086 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_DAY) | OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_DAY | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | check | 0.0196 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_WEEK) | OW_SEDA_S.ODS_ERP_LOGISTICS_TAT_ACUMULATED_WEEK | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | check | 0.0232 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SEDA_S.ODS_RP_ETR_CS_AEN_NF_CHECK) | OW_SEDA_S.ODS_RP_ETR_CS_AEN_NF_CHECK | [5 empty] | Done |  | 1 | 1 | 45988 | 45988 | ['[]'] | 0 | check | 0.0544 | ODS | 0 |  | 0 | [13 empty] | 27/11 - 27/11
| TABLE | (TABLE - OW_SEDA_S.ODS_RP_ETR_CS_AGING) | OW_SEDA_S.ODS_RP_ETR_CS_AGING | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 0.1904 | ODS | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.RAW_ANATEL_ACESSOS_TELEFONIA_MOVEL) | OW_SEDA_S.RAW_ANATEL_ACESSOS_TELEFONIA_MOVEL | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 1.7213 | RAW | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.RAW_DATA_SNOWFLAKE_CS_SALES_FORCE) | OW_SEDA_S.RAW_DATA_SNOWFLAKE_CS_SALES_FORCE | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 0.8206 | RAW | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.RAW_MX_TMV_INDEX) | OW_SEDA_S.RAW_MX_TMV_INDEX | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 0.0002 | RAW | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.RAW_TECH_INSIGHTS) | OW_SEDA_S.RAW_TECH_INSIGHTS | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 0.0005 | RAW | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.TMP_RP_ETR_CS_AEN_NF_CHECK) | OW_SEDA_S.TMP_RP_ETR_CS_AEN_NF_CHECK | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 0.0547 | TMP | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.TMP_RP_ETR_CS_AGING) | OW_SEDA_S.TMP_RP_ETR_CS_AGING | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 0.1915 | TMP | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.TMP_RP_ETR_LOGISTICS_TRACKING) | OW_SEDA_S.TMP_RP_ETR_LOGISTICS_TRACKING | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 0.198 | TMP | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.TMP_SNOWFLAKE_CS_SALES_FORCE) | OW_SEDA_S.TMP_SNOWFLAKE_CS_SALES_FORCE | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 0.0004 | TMP | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_PREDIZE_TICKETS) | U_PRJ_ECOM.ODS_PREDIZE_TICKETS | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 1.6089 | ODS | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_PREDIZE_TICKET_MESSAGE) | U_PRJ_ECOM.ODS_PREDIZE_TICKET_MESSAGE | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 4.7185 | ODS | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - U_PRJ_ECOM.ODS_PREDIZE_TICKET_ORDER) | U_PRJ_ECOM.ODS_PREDIZE_TICKET_ORDER | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 2.5348 | ODS | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - U_PRJ_ECOM.RAW_CS_INFORMATION_BSC) | U_PRJ_ECOM.RAW_CS_INFORMATION_BSC | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | check | 0.0009 | RAW | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO) | OW_SEDA_S.FT_UNION_TSS_CELLO | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 1 | migrar ph2 | 0.1817 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP),(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE),(VIEW - OW_LAO.VW_D2C_ORDER_ONE_VIEW),(VIEW - OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO)] | 6 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING) | OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 1 | migrar ph2 | 0.1761 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_SDU_FT_TSS_CELLO_IOD_STATUS_MONITORING)] | 2 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_LAO.FT_D2C_CELLO_NERP_RETURN_OPERATION) | OW_LAO.FT_D2C_CELLO_NERP_RETURN_OPERATION | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 1 | migrar ph2 | 0.0254 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION)] | 1 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_LAO.FT_D2C_CELLO_NERP_RETURN_PENDING) | OW_LAO.FT_D2C_CELLO_NERP_RETURN_PENDING | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 1 | migrar ph2 | 0.0008 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING)] | 1 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING_TMP) | OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING_TMP | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 1 | migrar ph2 | 0.1761 | FT | 0 | [(PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING)] | 1 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TRACKING_INBOUND_TMP) | OW_SEDA_S.FT_UNION_TSS_CELLO_TRACKING_INBOUND_TMP | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 1 | migrar ph2 | 0.0967 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL) | OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 1.5735 | FT | 0 | [(VIEW - OW_SEDA_S.VW_UNION_CELLO_TSS_IOD_STATUS),(PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST),(VIEW - OW_SEDA_S.VW_SEDA_SALES_IN_TRANSIT),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_PHOTO),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228),(VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO)] | 8 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST) | OW_SEDA_S.FT_UNION_TSS_CELLO_HIST | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.2811 | FT | 0 | [(VIEW - OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO_HIST),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST_MAP_CARRIER)] | 2 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TMP) | OW_SEDA_S.FT_UNION_TSS_CELLO_TMP | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.182 | FT | 0 | [(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP),(VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP_TEST)] | 2 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2) | OW_SEDA_S.FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2 | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.2293 | FT | 0 | [(VIEW - OW_SEDA_S.VW_SDU_FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2)] | 1 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI) | OW_LAO.FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.0001 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_LAO.FT_D2C_NERP_CELLO_YAMI_LEAD_TIME_RETURN_KPI) | OW_LAO.FT_D2C_NERP_CELLO_YAMI_LEAD_TIME_RETURN_KPI | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.001 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_BI_TRACKING_CELLO_TSS_HIST) | OW_SEDA_S.FT_BI_TRACKING_CELLO_TSS_HIST | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.1807 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_BI_TRACKING_CLEAN_CELLO_TSS_ORDER_OPERATION) | OW_SEDA_S.FT_BI_TRACKING_CLEAN_CELLO_TSS_ORDER_OPERATION | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.2848 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_CELLO_TRACKING_INBOUND) | OW_SEDA_S.FT_CELLO_TRACKING_INBOUND | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.0978 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_CELLO_TRACKING_INBOUND_TMP) | OW_SEDA_S.FT_CELLO_TRACKING_INBOUND_TMP | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.0978 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_EXCLUDED_DO) | OW_SEDA_S.FT_UNION_TSS_CELLO_EXCLUDED_DO | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.0001 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C) | OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 1.0659 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C_TMP) | OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_D2C_TMP | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.0001 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_TMP) | OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_TMP | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.3809 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TEMP) | OW_SEDA_S.FT_UNION_TSS_CELLO_TEMP | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.0599 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TRACKING_INBOUND) | OW_SEDA_S.FT_UNION_TSS_CELLO_TRACKING_INBOUND | [5 empty] | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 0 | migrar ph2 | 0.1603 | FT | 0 |  | 0 | [13 empty] | 28/11 - 28/11
| TABLE | (TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE) | OW_LAO.FT_AP2_EXCHANGE_RATE | LAO EStore | r.bojart |  | yes | 1 | Done |  | 1 | 1 | 45989 | 45989 | ['[]'] | 1 | r.bojart | 0.0052 | FT | 0 | [(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1_V2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1_V2),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES),(PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE_BKP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM),(VIEW - OW_LAO.VIEW_NERP_ZRCOS43400_TARGET),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HISTORICO),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1),(VIEW - OW_LAO.VW_CRAWLING_AP1_NPC_SEGMENT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WERABLES_PT1),(VIEW - OW_LAO.VIEW_RAW_BIZ_OVERVIEW),(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES),(VIEW - OW_LAO.VW_CRAWLING_AP1_REF_SEGMENT),(VIEW - OW_LAO.VW_CRAWLING_AP1_REF_DISPLAY_SHARE),(VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE),(VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE),(VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET),(VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET_TEST),(VIEW - OW_LAO.VIEW_RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS),(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1_V2),(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG),(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_VC_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_V2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_DUEK),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HIST),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_ESTORE_URL_SKU),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG),(VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE_TABLET),(VIEW - OW_LAO.VW_CRAWLING_AP1_WM_SEGMENT),(VIEW - OW_LAO.VW_CRAWLING_AP1_WM_DISPLAY_SHARE),(VIEW - OW_LAO.VW_CRAWLING_AP1_TV_SEGMENT),(VIEW - OW_LAO.VW_CRAWLING_AP1_TV_DISPLAY_SHARE),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI),(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN),(PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT),(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS),(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS),(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP),(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT2),(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_PT1),(VIEW - OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX),(VIEW - OW_LAO.VIEW_ECOM_EXCHANGE_RATE),(PROCEDURE - U_PRJ_ECOM.PROC_DIM_EXCHANGE_RATE_RAWDATA),(VIEW - OW_LAO.VW_CRAWLING_AP1_ESTORE_DAILY_PRICE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG),(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI),(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL),(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5),(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD),(PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE),(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG)] | 82 | [13 empty] | 28/11 - 28/11
| VIEW | (VIEW - OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA) | OW_SEDA_S.VW_PORTAL_SM_UNION_SURSIS_ANGELIRA | [7 empty] | 3 | 1 | 45992 | 45992 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM)'", "'(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA)'", "'(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_NC)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_ESCORT)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_NC)]']"] | 0 | Check |  |  | 6 |  | 0 | [14 empty] | 01/12 - 01/12
| VIEW | (VIEW - OW_SEDA_S.VW_PORTAL_SM_SURSIS) | OW_SEDA_S.VW_PORTAL_SM_SURSIS | [7 empty] | 3 | 1 | 45992 | 45992 | ["['[(TABLE - OW_SEDA_S.ODS_SURSIS_ESCORT)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_NC)]']"] | 0 | Check |  |  | 3 |  | 0 | [14 empty] | 01/12 - 01/12
| VIEW | (VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA) | OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA | [7 empty] | 3 | 1 | 45992 | 45992 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM)'", "'(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA)'", "'(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_NC)]']"] | 0 | Check |  |  | 3 |  | 0 | [14 empty] | 01/12 - 01/12
| PROCEDURE | (PROCEDURE - OW_SELA.ProcMergeDMSDataV2) | OW_SELA.ProcMergeDMSDataV2 | [7 empty] | 4 | 1 | 45992 | 45992 | ["['[(TABLE - OW_SELA.DIM_PRODUCT)'", "'(TABLE - OW_SELA.FACT_STOCK_SALES)'", "'(TABLE - OW_SELA.STAGE2_FACT_STOCK_SALES)]']"] | 1 | Check |  |  | 3 |  | 0 | [14 empty] | 01/12 - 01/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS) | OW_LAO.PROC_TF_YAMI_PRODUCT_DETAIL_SEDA_UNIFIED_AND_AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS | [7 empty] | 4 | 1 | 45992 | 45992 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE)'", "'(TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_YAMI_PRODUCT_DETAIL_RELATIONSHIP_KEYS)'", "'(TABLE - OW_LAO.AUX_YAMI_PRODUCT_DETAIL_STATUS)]']"] | 1 | Check |  |  | 4 |  | 0 | [14 empty] | 01/12 - 01/12
| PROCEDURE | (PROCEDURE - OW_SELA.PROCSNAPSHOTFCST_OLD) | OW_SELA.PROCSNAPSHOTFCST_OLD | [7 empty] | 4 | 1 | 45992 | 45992 | ["['[(TABLE - OW_SELA.TMP_DLAKE_W3)'", "'(TABLE - OW_SELA.DIM_WEEK)'", "'(TABLE - OW_SELA.DIM_MN_SEGMENT)'", "'(TABLE - OW_SELA.FCST_SNAPSHOT)'", "'(TABLE - OW_SELA.TMP_DLAKE_W8)'", "'(TABLE - OW_SELA.TMP_DLAKE_HIST)'", "'(TABLE - OW_SELA.DIM_DC)]']"] | 0 | Check |  |  | 7 |  | 0 | [14 empty] | 01/12 - 01/12
| PROCEDURE | (PROCEDURE - OW_SELA.PROCSNAPSHOTFCST) | OW_SELA.PROCSNAPSHOTFCST | [7 empty] | 4 | 1 | 45992 | 45992 | ["['[(TABLE - OW_SELA.TMP_DLAKE_W3)'", "'(TABLE - OW_SELA.DIM_PRODUCT)'", "'(TABLE - OW_SELA.FACT_STOCK_SALES)'", "'(TABLE - OW_SELA.WOS_PARAMETERS)'", "'(TABLE - OW_SELA.DIM_GROWTH)'", "'(TABLE - OW_SELA.DIM_WEEK)'", "'(TABLE - OW_SELA.DIM_COUNTRY)'", "'(TABLE - OW_SELA.DIM_COUNTRY_BRANCH)'", "'(TABLE - OW_SELA.DIM_MN_SEGMENT)'", "'(TABLE - OW_SELA.FCST_SNAPSHOT)'", "'(TABLE - OW_SELA.TMP_DLAKE_W8)'", "'(TABLE - OW_SELA.TMP_DLAKE_HIST)'", "'(TABLE - OW_SELA.DIM_DC)]']"] | 0 | Check |  |  | 13 |  | 0 | [14 empty] | 01/12 - 01/12
| VIEW | (VIEW - OW_SEDA_S.VW_CELLO_RETURN_TRACKING) | OW_SEDA_S.VW_CELLO_RETURN_TRACKING | [7 empty] | 3 | 1 | 45992 | 45992 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | Check |  |  | 11 |  | 0 | [14 empty] | 01/12 - 01/12
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING) | OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING | [7 empty] | 3 | 1 | 45992 | 45992 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | Check |  |  | 11 |  | 0 | [14 empty] | 01/12 - 01/12
| VIEW | (VIEW - OW_SEDA_S.VW_STATUS_MAPPING) | OW_SEDA_S.VW_STATUS_MAPPING | [7 empty] | 3 | 1 | 45992 | 45992 | ["['[(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)]']"] | 1 | Check |  |  | 3 |  | 0 | [14 empty] | 01/12 - 01/12
| VIEW | (VIEW - OW_SEDA_S.VW_STATUS_MAPPING_AUX) | OW_SEDA_S.VW_STATUS_MAPPING_AUX | [7 empty] | 3 | 1 | 45993 | 45993 | ["['[(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)]']"] | 1 | Check |  |  | 3 |  | 0 | [14 empty] | 02/12 - 02/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_MONITORING_STATUS) | OW_LAO.PROC_SALES_DEDUCTION_MONITORING_STATUS |  |  |  | No |  |  |  | 4 | 1 | 45993 | 45993 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)]']"] | 1 | Migrar ph2 |  |  | 3 |  | 0 | [14 empty] | 02/12 - 02/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V2 | [7 empty] | 3 | 1 | 45993 | 45993 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Check |  |  | 12 |  | 0 | [14 empty] | 02/12 - 02/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_1 | [7 empty] | 3 | 1 | 45993 | 45993 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Check |  |  | 12 |  | 0 | [14 empty] | 02/12 - 02/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_2 | [7 empty] | 3 | 1 | 45993 | 45993 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Check |  |  | 12 |  | 0 | [14 empty] | 02/12 - 02/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_3 | [7 empty] | 3 | 1 | 45993 | 45993 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Check |  |  | 12 |  | 0 | [14 empty] | 02/12 - 02/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_4 | [7 empty] | 3 | 1 | 45993 | 45993 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Check |  |  | 12 |  | 0 | [14 empty] | 02/12 - 02/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI_TESTE | [7 empty] | 3 | 1 | 45993 | 45993 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Check |  |  | 12 |  | 0 | [14 empty] | 02/12 - 02/12
| VIEW | (VIEW - OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI) | OW_SEDA_S.VW_CELLO_BI_IOD_TOTAL_SDI | [7 empty] | 3 | 1 | 45993 | 45993 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Check |  |  | 12 |  | 0 | [14 empty] | 02/12 - 02/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_MANAGEMENT_INFORMATION) | OW_SEDA_S.VW_CE_MANAGEMENT_INFORMATION | [7 empty] | 3 | 1 | 45993 | 45993 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_KAM)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [14 empty] | 02/12 - 02/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_MANAGEMENT_INFORMATION) | OW_SEDA_S.PRC_CE_MANAGEMENT_INFORMATION | [7 empty] | 4 | 1 | 45994 | 45994 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_KAM)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [14 empty] | 03/12 - 03/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V3 | [7 empty] | 3 | 1 | 45994 | 45994 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Check |  |  | 15 |  | 0 | [14 empty] | 03/12 - 03/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V4 | [7 empty] | 3 | 1 | 45994 | 45994 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Check |  |  | 15 |  | 0 | [14 empty] | 03/12 - 03/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_V5 | [7 empty] | 3 | 1 | 45994 | 45994 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Check |  |  | 15 |  | 0 | [14 empty] | 03/12 - 03/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL_tst | [7 empty] | 3 | 1 | 45994 | 45994 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Check |  |  | 14 |  | 0 | [14 empty] | 03/12 - 03/12
| VIEW | (VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI) | OW_SEDA_S.VW_VESSEL_TRAVEL_INFO_SDI | [7 empty] | 3 | 1 | 45994 | 45994 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)]']"] | 0 | Migrar ph2 |  |  | 7 |  | 0 | [14 empty] | 03/12 - 03/12
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD) | OW_SEDA_S.VW_UNION_TSS_CELLO_IOD | [7 empty] | 3 | 1 | 45994 | 45994 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Check |  |  | 18 |  | 0 | [14 empty] | 03/12 - 03/12
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL) | OW_SEDA_S.VW_UNION_TSS_CELLO_IOD_STATUS_TOTAL | [7 empty] | 3 | 1 | 45994 | 45994 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Check |  |  | 17 |  | 0 | [14 empty] | 03/12 - 03/12
| VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI) | OW_SEDA_S.VW_TRACKING_ITEM_2YEARS_SDI | [7 empty] | 3 | 1 | 45994 | 45994 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 28 |  | 0 | [14 empty] | 03/12 - 03/12
| VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI) | OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI | [7 empty] | 3 | 1 | 45994 | 45994 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 28 |  | 0 | [14 empty] | 03/12 - 03/12
| VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE) | OW_SEDA_S.VW_TRACKING_ITEM_3MONTHS_SDI_TESTE | [7 empty] | 3 | 1 | 45995 | 45995 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 28 |  | 0 | [14 empty] | 04/12 - 04/12
| VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016) | OW_SEDA_S.VW_TRACKING_ITEM_BETWEEN_2014_AND_2016 | [7 empty] | 3 | 1 | 45995 | 45995 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 28 |  | 0 | [14 empty] | 04/12 - 04/12
| VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI) | OW_SEDA_S.VW_TRACKING_ITEM_6MONTHS_SDI | [7 empty] | 3 | 1 | 45995 | 45995 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 27 |  | 0 | [14 empty] | 04/12 - 04/12
| FUNCTION | (FUNCTION - OW_SEDA_S.FNS_NM2) | OW_SEDA_S.FNS_NM2 | [7 empty] | 3 | 1 | 45995 | 45995 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)]']"] | 0 | Migrar ph2 |  |  | 8 |  | 0 | [14 empty] | 04/12 - 04/12
| VIEW | (VIEW - OW_SEDA_S.VW_MX_POSITIVACAO_S24) | OW_SEDA_S.VW_MX_POSITIVACAO_S24 | [7 empty] | 3 | 1 | 45995 | 45995 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [14 empty] | 04/12 - 04/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_06W_10W |  |  |  | No |  |  |  | 4 | 1 | 45995 | 45995 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO)]']"] | 1 | Migrar ph2 |  |  | 8 |  | 0 | [14 empty] | 04/12 - 04/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W) | OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W |  |  |  | No |  |  |  | 4 | 1 | 45995 | 45995 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)]']"] | 1 | Migrar ph2 |  |  | 7 |  | 0 | [14 empty] | 04/12 - 04/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION) | OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION |  |  |  | No |  |  |  | 4 | 1 | 45995 | 45995 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)]']"] | 1 | Migrar ph2 |  |  | 7 |  | 0 | [14 empty] | 04/12 - 04/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2) | OW_LAO.PROC_LAO_SALES_DEDUCTION_6W_10W_NEW_VERSION_V2 |  |  |  | No |  |  |  | 4 | 1 | 45995 | 45995 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_6W_10W_GSCM)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)]']"] | 1 | Migrar ph2 |  |  | 7 |  | 0 | [14 empty] | 04/12 - 04/12
| PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_GENERATED) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_GENERATED | LAO EStore | r.bojart |  | yes | 3 | To be migrated |  | 4 | 1 | 45995 | 45995 | ["['[(TABLE - OW_LAO.MONITORING_EXECUTIONS)'", "'(TABLE - OW_LAO.MONITORING_PARAMETERS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [14 empty] | 04/12 - 04/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX) | OW_SEDA_S.PRC_WEBPRICE_DAILY_MX |  |  |  | No | No |  |  | 4 | 1 | 45996 | 45996 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX)'", "'(TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [14 empty] | 05/12 - 05/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST) | OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST |  |  |  | No | No |  |  | 4 | 1 | 45996 | 45996 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX)'", "'(TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [14 empty] | 05/12 - 05/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST_2) | OW_SEDA_S.PRC_WEBPRICE_DAILY_MX_HIST_2 |  |  |  | No | No |  |  | 4 | 1 | 45996 | 45996 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX)'", "'(TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [14 empty] | 05/12 - 05/12
| VIEW | (VIEW - OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT) | OW_SEDA_S.VW_CELLO_IOD_OCCURRENCE_REPORT | [7 empty] | 3 | 1 | 45996 | 45996 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_REASON)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Check |  |  | 10 |  | 0 | [14 empty] | 05/12 - 05/12
| FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_BOD2) | OW_SEDA_S.FN_GET_BOD2 | [7 empty] | 3 | 1 | 45996 | 45996 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BOD)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_DETAIL)]']"] | 0 | Migrar ph2 |  |  | 19 |  | 0 | [14 empty] | 05/12 - 05/12
| FUNCTION | (FUNCTION - OW_SEDA_S.FNS_NM1) | OW_SEDA_S.FNS_NM1 | [7 empty] | 3 | 1 | 45996 | 45996 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_DETAIL)]']"] | 0 | Migrar ph2 |  |  | 18 |  | 0 | [14 empty] | 05/12 - 05/12
| VIEW | (VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS) | OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS | [7 empty] | 3 | 1 | 45996 | 45996 | ["['[(TABLE - OW_LAO.MONITORING_PROTOCOL_TYPES)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_STATUS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_STATUS)'", "'(TABLE - OW_LAO.MONITORING_PARAMETERS)'", "'(TABLE - OW_LAO.MONITORING_SOURCES_TYPES)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 7 |  | 0 | [14 empty] | 05/12 - 05/12
| VIEW | (VIEW - OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE) | OW_LAO.VW_MONITORING_EXECUTIONS_RESULTS_TO_SEND_MESSAGE | [7 empty] | 3 | 1 | 45996 | 45996 | ["['[(TABLE - OW_LAO.MONITORING_PROTOCOL_TYPES)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_STATUS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_STATUS)'", "'(TABLE - OW_LAO.MONITORING_PARAMETERS)'", "'(TABLE - OW_LAO.MONITORING_SOURCES_TYPES)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 7 |  | 0 | [14 empty] | 05/12 - 05/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI) | OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI | [7 empty] | 3 | 1 | 45996 | 45996 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.MAP_CE_SR_KAM)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_KAM)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [14 empty] | 05/12 - 05/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX) | OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX | [7 empty] | 3 | 1 | 45996 | 45996 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.MAP_CE_SR_KAM)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_KAM)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [14 empty] | 05/12 - 05/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2) | OW_SEDA_S.VW_CE_ACCOUNT_MAPPING_KPI_AUX_2 | [7 empty] | 3 | 1 | 45999 | 45999 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.MAP_CE_SR_KAM)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_KAM)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 08/12 - 08/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_01W_05W |  |  |  | No |  |  |  | 4 | 1 | 45999 | 45999 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO)]']"] | 1 | Migrar ph2 |  |  | 8 |  | 0 | [15 empty] | 08/12 - 08/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_FOTA_01W_05W |  |  |  | No |  |  |  | 4 | 1 | 45999 | 45999 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_FOTA)]']"] | 1 | Migrar ph2 |  |  | 8 |  | 0 | [15 empty] | 08/12 - 08/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY |  |  |  | No |  |  |  | 4 | 1 | 45999 | 45999 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)]']"] | 1 | Migrar ph2 |  |  | 7 |  | 0 | [15 empty] | 08/12 - 08/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_NEW_VERSION_FOTA |  |  |  | No |  |  |  | 4 | 1 | 45999 | 45999 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_FOTA)]']"] | 1 | Migrar ph2 |  |  | 7 |  | 0 | [15 empty] | 08/12 - 08/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION) | OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_EXCEPTION | [7 empty] | 4 | 1 | 45999 | 45999 | ["['[(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION)'", "'(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_EXCEPTION)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION)]']"] | 1 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 08/12 - 08/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W) | OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01W_05W | [7 empty] | 4 | 1 | 45999 | 45999 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_FOTA_01_05W)]']"] | 1 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 08/12 - 08/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W) | OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_FOTA_01_05W | [7 empty] | 4 | 1 | 45999 | 45999 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_FOTA)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_FOTA_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_FOTA_01_05W)]']"] | 1 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 08/12 - 08/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_CE) | OW_SEDA_S.PRC_WEBPRICE_DAILY_CE |  |  |  | No | No |  |  | 4 | 1 | 45999 | 45999 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_TV)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [15 empty] | 08/12 - 08/12
| VIEW | (VIEW - OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI) | OW_SEDA_S.TMP_VW_TRACKING_ITEM_SDI | [7 empty] | 3 | 1 | 45999 | 45999 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Migrar ph2 |  |  | 27 |  | 0 | [15 empty] | 08/12 - 08/12
| FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI) | OW_SEDA_S.FN_GET_BOD2_SDI | [7 empty] | 3 | 1 | 46000 | 46000 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BOD)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)]']"] | 0 | Migrar ph2 |  |  | 19 |  | 0 | [15 empty] | 09/12 - 09/12
| FUNCTION | (FUNCTION - OW_SEDA_S.FNS_NM1_SDI) | OW_SEDA_S.FNS_NM1_SDI | [7 empty] | 3 | 1 | 46000 | 46000 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)]']"] | 0 | Migrar ph2 |  |  | 18 |  | 0 | [15 empty] | 09/12 - 09/12
| VIEW | (VIEW - OW_SEDA_S.VW_VESSEL_TRAVEL_INFO) | OW_SEDA_S.VW_VESSEL_TRAVEL_INFO | [7 empty] | 3 | 1 | 46000 | 46000 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS)]']"] | 0 | Migrar ph2 |  |  | 7 |  | 0 | [15 empty] | 09/12 - 09/12
| VIEW | (VIEW - OW_SEDA_S.VW_D2C_SO_FSCT) | OW_SEDA_S.VW_D2C_SO_FSCT | [7 empty] | 3 | 1 | 46000 | 46000 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_VD)'", "'(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_DA)'", "'(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_HHP)'", "'(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_OTHERS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 09/12 - 09/12
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_LSPOSITO | [7 empty] | 3 | 1 | 46000 | 46000 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.TF_VW_SELLOUTGERAL)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)'", "'(TABLE - OW_SEDA_S.TF_VW_WALMART)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 09/12 - 09/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_NERP_AL11_VALIDATION) | OW_LAO.PROC_SALES_DEDUCTION_NERP_AL11_VALIDATION |  |  |  | No |  |  |  | 4 | 1 | 46000 | 46000 | ["['[(TABLE - OW_LAO.ODS_NERP_AL11_MCS_SEN)'", "'(TABLE - OW_LAO.FT_NERP_AL11_VALIDATION)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_AL11_VALIDATION_TO_MOVE_FILE)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [15 empty] | 09/12 - 09/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION) | OW_LAO.PROC_LAO_SALES_DEDUCTION_DAILY_EDI_EXCEPTION |  |  |  | No |  |  |  | 4 | 1 | 46000 | 46000 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_CORES)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_EXCEPTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_GSCM_EXCEPTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_DAILY_BIZ_AREA)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_HISTORICO)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION)]']"] | 1 | Migrar ph2 |  |  | 8 |  | 0 | [15 empty] | 09/12 - 09/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY) | OW_LAO.PROC_LAO_SALES_DEDUCTION_WEEKLY |  |  |  | No |  |  |  | 4 | 1 | 46000 | 46000 | ["['[(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_GSCM)'", "'(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_BIZ_AREA)'", "'(TABLE - OW_LAO.TF_LAO_SALES_DEDUCTION_WEEKLY_CORES)'", "'(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY)]']"] | 1 | Migrar ph2 |  |  | 7 |  | 0 | [15 empty] | 09/12 - 09/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W) | OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_01W_05W | [7 empty] | 4 | 1 | 46000 | 46000 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY)'", "'(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_01_05W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_01_05W)]']"] | 1 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 09/12 - 09/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W) | OW_LAO.PROC_LAO_SALES_DEDUCITON_DAILY_VALIDATION_EDI_06W_10W | [7 empty] | 4 | 1 | 46000 | 46000 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_DAILY_6W_10W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_06_10W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_06_10W)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_06_10W)'", "'(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_06_10W)]']"] | 1 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 09/12 - 09/12
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP) | OW_SEDA_S.VW_UNION_TSS_CELLO_TEMP | [7 empty] | 3 | 1 | 46001 | 46001 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_VESSEL)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_SDI)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.CELLO_POD)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Check |  |  | 16 |  | 0 | [15 empty] | 10/12 - 10/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE) | OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_COMPLETE | [7 empty] | 3 | 1 | 46001 | 46001 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)'", "'(TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT_FLOORING)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_MBO_KAM)'", "'(TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT)'", "'(TABLE - OW_SEDA_S.ACCOUNT_MANAGEMENT_FLOORSHRE_TT)]']"] | 0 | Check |  |  | 6 |  | 0 | [15 empty] | 10/12 - 10/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR) | OW_SEDA_S.VW_CE_TRIPLE_A_TARGET_AR | [7 empty] | 3 | 1 | 46001 | 46001 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_TRIPLE_A_PERFORMANCE_SUMMARY)'", "'(TABLE - OW_SEDA_S.MAP_CE_TRIPLE_A_TARGET)'", "'(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 10/12 - 10/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_META_PROMOTOR) | OW_SEDA_S.VW_CE_META_PROMOTOR | [7 empty] | 3 | 1 | 46001 | 46001 | ["['[(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_RRP)'", "'(TABLE - OW_SEDA_S.FT_CE_DB_FCST_PIVOT)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 10/12 - 10/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION) | OW_LAO.PROC_SALES_DEDUCTION |  |  |  | No |  |  |  | 4 | 1 | 46001 | 46001 | ["['[(TABLE - OW_LAO.INPUT_MAPPING_BIZ_AREA_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.INPUT_MAP_CORES_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 10/12 - 10/12
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE) | OW_SEDA_S.VW_UNION_TSS_CELLO_OCCURRENCE | [7 empty] | 3 | 1 | 46001 | 46001 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_REASON)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.SDI_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_REASON_GRP)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDER_OCCURRENCE_RPT)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Check |  |  | 28 |  | 0 | [15 empty] | 10/12 - 10/12
| VIEW | (VIEW - OW_SEDA_S.VW_TRACKING_ITEM) | OW_SEDA_S.VW_TRACKING_ITEM | [7 empty] | 3 | 1 | 46001 | 46001 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BIG_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_PLANT_LOC_MAPPING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RATE_SERVICE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT_DATE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BOD)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_HEADER_DIVISION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_DO_EPOD_RECEIVED)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_LOAD_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_COMPANY)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM_GROUP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_CUSTOMER_REJECT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_AREA_TYPE_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_RS_RESULT_DETAIL)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 0 | Migrar ph2 |  |  | 39 |  | 0 | [15 empty] | 10/12 - 10/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL) | OW_SEDA_S.VW_BI_IOD_TOTAL | [7 empty] | 3 | 1 | 46001 | 46001 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_NOTES)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TB_MVW_IOD_STATUS_REPORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_OD_ORDERS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 10/12 - 10/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_DAILY_MON) | OW_SEDA_S.PRC_WEBPRICE_DAILY_MON |  |  |  | No | No |  |  | 4 | 1 | 46001 | 46001 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MON)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [15 empty] | 10/12 - 10/12
| VIEW | (VIEW - OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI) | OW_SEDA_S.TMP_VW_VESSEL_TRAVEL_INFO_SDI | [7 empty] | 3 | 1 | 46001 | 46001 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)'", "'(TABLE - OW_SEDA_S.TMP_SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_VEHICLE_GRP)]']"] | 0 | Migrar ph2 |  |  | 7 |  | 0 | [15 empty] | 10/12 - 10/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_IOD_TOTAL_SDI) | OW_SEDA_S.VW_BI_IOD_TOTAL_SDI | [7 empty] | 3 | 1 | 46002 | 46002 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_NOTES)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 11/12 - 11/12
| VIEW | (VIEW - OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM) | OW_SEDA_S.VW_VD_PIVOT_SELL_OUT_PLATFORM | [7 empty] | 3 | 1 | 46002 | 46002 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.ODS_TV_WEEKLY_GFK)]']"] | 0 | Check |  |  | 4 |  | 0 | [15 empty] | 11/12 - 11/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_PRICE_STORE) | OW_SEDA_S.VW_CE_PRICE_STORE | [7 empty] | 3 | 1 | 46002 | 46002 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS)'", "'(TABLE - OW_SEDA_S.FT_CE_PRICE_STORE)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 9 |  | 0 | [15 empty] | 11/12 - 11/12
| VIEW | (VIEW - OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE) | OW_SEDA_S.VW_TT_OFF_COLLECTED_PRICE | [7 empty] | 3 | 1 | 46002 | 46002 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 8 |  | 0 | [15 empty] | 11/12 - 11/12
| VIEW | (VIEW - OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE) | OW_SEDA_S.VW_TT_SYSTEM_PRICES_MODE | [7 empty] | 3 | 1 | 46002 | 46002 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 8 |  | 0 | [15 empty] | 11/12 - 11/12
| VIEW | (VIEW - OW_SEDA_S.VW_TT_AGGREGATED_PICTURES) | OW_SEDA_S.VW_TT_AGGREGATED_PICTURES | [7 empty] | 3 | 1 | 46002 | 46002 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 7 |  | 0 | [15 empty] | 11/12 - 11/12
| VIEW | (VIEW - OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL) | OW_SEDA_S.VW_TT_COLLECTED_PRICE_URL | [7 empty] | 3 | 1 | 46002 | 46002 | ["['[(TABLE - OW_SEDA_S.FT_CHEIL_ANSWERS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_FORMULARIES_QUESTIONS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CHEIL_INTERNAL_IMAGES)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_COLLABORATORS)'", "'(TABLE - OW_SEDA_S.MAP_CHEIL_POS)]']"] | 0 | Migrar ph2 |  |  | 7 |  | 0 | [15 empty] | 11/12 - 11/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_MX_PIVOT_2022) | OW_SEDA_S.VW_CE_MX_PIVOT_2022 | [7 empty] | 3 | 1 | 46002 | 46002 | ["['[(TABLE - OW_SEDA_S.FT_MX_PIVOT_2022)'", "'(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.TMP_MX_STORE_MAPPING)]']"] | 0 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 11/12 - 11/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_RM_CTV_MEETINGS) | OW_SEDA_S.VW_CE_RM_CTV_MEETINGS | [7 empty] | 3 | 1 | 46002 | 46002 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRICE_COLLECTED)]']"] | 0 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 11/12 - 11/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_RM_DA_MEETING) | OW_SEDA_S.VW_CE_RM_DA_MEETING | [7 empty] | 3 | 1 | 46002 | 46002 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRICE_COLLECTED)]']"] | 0 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 11/12 - 11/12
| VIEW | (VIEW - OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE) | OW_SEDA_S.VW_CE_SELL_OUT_BY_CITY_CODE | [7 empty] | 3 | 1 | 46003 | 46003 | ["['[(TABLE - OW_SEDA_S.ODS_CE_MKT_TRANSMISSORAS)'", "'(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 12/12 - 12/12
| VIEW | (VIEW - OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST) | OW_SEDA_S.VW_MX_FOTA_AND_GFK_HIST | [7 empty] | 3 | 1 | 46003 | 46003 | ["['[(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_MX_DAILY_FOTA)'", "'(TABLE - OW_SEDA_S.FT_GFK_MX_WEEKLY)'", "'(TABLE - OW_SEDA_S.FT_MX_PIVOT)]']"] | 0 | Migrar ph2 |  |  | 5 |  | 0 | [15 empty] | 12/12 - 12/12
| VIEW | (VIEW - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_TARGET_WEEK_ADJ) | OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT_TARGET_WEEK_ADJ | [7 empty] | 3 | 1 | 46003 | 46003 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT)'", "'(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [15 empty] | 12/12 - 12/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK) | OW_SEDA_S.PRC_MX_UPDT_FOTA_AND_GFK |  |  |  | No | No |  |  | 4 | 1 | 46003 | 46003 | ["['[(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_MX_DAILY_FOTA)'", "'(TABLE - OW_SEDA_S.FT_GFK_MX_WEEKLY)'", "'(TABLE - OW_SEDA_S.FT_MX_PIVOT_BY_ITEM)'", "'(TABLE - OW_SEDA_S.VW_MX_FOTA_AND_GFK)]']"] | 0 | Check |  |  | 6 |  | 0 | [15 empty] | 12/12 - 12/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA) | OW_SEDA_S.PRC_CE_BF_PRECO_SISTEMA | [7 empty] | 4 | 1 | 46003 | 46003 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)'", "'(TABLE - OW_SEDA_S.FT_CE_PRICE_STORE)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 12/12 - 12/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY) | OW_SEDA_S.PRC_CE_UPDATE_CHANNEL_READY | [7 empty] | 4 | 1 | 46003 | 46003 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 12/12 - 12/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY) | OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY |  |  |  | No | No |  |  | 4 | 1 | 46003 | 46003 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 12/12 - 12/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL) | OW_SEDA_S.PRC_CE_UPDATE_WEEKLY_READY_BY_CHANEL |  |  |  | No | No |  |  | 4 | 1 | 46003 | 46003 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 12/12 - 12/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION) | OW_SEDA_S.PRC_DEAD_INVENTORY_CALCULATION |  |  |  | No | No |  |  | 4 | 1 | 46003 | 46003 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 12/12 - 12/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_DEAD_SKU_CALCULATION) | OW_SEDA_S.PRC_DEAD_SKU_CALCULATION |  |  |  | No | No |  |  | 4 | 1 | 46003 | 46003 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [15 empty] | 12/12 - 12/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION) | OW_SEDA_S.PRC_EST_SALES_LOST_CALCULATION |  |  |  | No | No |  |  | 4 | 1 | 46006 | 46006 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [16 empty] | 15/12 - 15/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_STOCK_OUT_CALCULATION) | OW_SEDA_S.PRC_STOCK_OUT_CALCULATION |  |  |  | No | No |  |  | 4 | 1 | 46006 | 46006 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [16 empty] | 15/12 - 15/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_VC_UPDATE_READY) | OW_SEDA_S.PRC_VC_UPDATE_READY |  |  |  | No | No |  |  | 4 | 1 | 46006 | 46006 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)'", "'(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [16 empty] | 15/12 - 15/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_VD_SALES_REVENUE) | OW_SEDA_S.PRC_VD_SALES_REVENUE | [7 empty] | 4 | 1 | 46006 | 46006 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 4 |  | 0 | [16 empty] | 15/12 - 15/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_ESES_ON_PIVOT) | OW_SEDA_S.PRC_CE_UPDATE_ESES_ON_PIVOT | [7 empty] | 4 | 1 | 46006 | 46006 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 3 |  | 0 | [16 empty] | 15/12 - 15/12
| VIEW | (VIEW - OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL) | OW_SEDA_S.VW_BI_CELLO_IOD_TOTAL | [7 empty] | 3 | 1 | 46006 | 46006 | ["['[(TABLE - OW_SEDA_S.ODS_CELLO_BOOKING)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_LAST_LEG_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_MANIFEST)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_POD)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_SHIPMENT)'", "'(TABLE - OW_SEDA_S.ODS_CELLO_DELIVERY_INBOUND_ITEM)]']"] | 1 | Migrar ph2: Cello |  |  | 11 |  | 0 | [16 empty] | 15/12 - 15/12
| PROCEDURE | (PROCEDURE - OW_LAO.PRC_ODS_LAO_GSCM_EDI_DATA) | OW_LAO.PRC_ODS_LAO_GSCM_EDI_DATA |  |  |  | No | No |  |  | 4 | 1 | 46006 | 46006 | ["['[(TABLE - OW_LAO.ODS_LAO_GSCM_EDI_DATA)'", "'(TABLE - OW_LAO.FT_LAO_DX_PIVOT)'", "'(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [16 empty] | 15/12 - 15/12
| VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_REPORT) | OW_SDSLA.VW_TABLEAU_REPORT | [7 empty] | 3 | 1 | 46006 | 46006 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_WORKBOOKS)]']"] | 0 | Check |  |  | 12 |  | 0 | [16 empty] | 15/12 - 15/12
| VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_REPORT_TEST) | OW_SDSLA.VW_TABLEAU_REPORT_TEST | [7 empty] | 3 | 1 | 46006 | 46006 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS_STATS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS)]']"] | 0 | Check |  |  | 12 |  | 0 | [16 empty] | 15/12 - 15/12
| VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V2) | OW_SDSLA.VW_TABLEAU_REPORT_V2 | [7 empty] | 3 | 1 | 46006 | 46006 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS_STATS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS)]']"] | 0 | Check |  |  | 12 |  | 0 | [16 empty] | 15/12 - 15/12
| VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V3) | OW_SDSLA.VW_TABLEAU_REPORT_V3 | [7 empty] | 3 | 1 | 46007 | 46007 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS_STATS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS)]']"] | 0 | Check |  |  | 12 |  | 0 | [16 empty] | 16/12 - 16/12
| VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_REPORT_V4) | OW_SDSLA.VW_TABLEAU_REPORT_V4 | [7 empty] | 3 | 1 | 46007 | 46007 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_V_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HIST_VIEWS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_SDSLA_TABLE_ALL_WORKBOOKS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_EXTRACTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_HISTORICAL_EVENT_TYPES)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_VIEWS_STATS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_VIEWS_STATS)]']"] | 0 | Check |  |  | 12 |  | 0 | [16 empty] | 16/12 - 16/12
| VIEW | (VIEW - OW_SDSLA.VW_TABLEAU_USERS) | OW_SDSLA.VW_TABLEAU_USERS | [7 empty] | 3 | 1 | 46007 | 46007 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_GROUP_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_GROUPS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_V_USERS)]']"] | 0 | Migrar ph2: Tableau |  |  | 4 |  | 0 | [16 empty] | 16/12 - 16/12
| VIEW | (VIEW - OW_SDSLA.ODS_TABLEAU_PROJECT_HIERARCHY) | OW_SDSLA.ODS_TABLEAU_PROJECT_HIERARCHY | [7 empty] | 3 | 1 | 46007 | 46007 | ["['[(TABLE - OW_SDSLA.ODS_TABLEAU_SYSTEM_USERS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_PROJECTS)'", "'(TABLE - OW_SDSLA.ODS_TABLEAU_USERS)]']"] | 0 | Migrar ph2: Tableau |  |  | 3 |  | 0 | [16 empty] | 16/12 - 16/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT) | OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT |  |  |  | No | No |  |  | 4 | 1 | 46007 | 46007 | ["['[(TABLE - OW_SEDA_S.MAP_CE_CALENDAR)'", "'(TABLE - OW_SEDA_S.EDI_DATA_RAW)'", "'(TABLE - OW_SEDA_S.FT_SEDA_EDI_DATA)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)'", "'(TABLE - OW_SEDA_S.FT_MX_PIVOT_BY_ITEM)]']"] | 0 | Migrar ph2 |  |  | 5 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.ODS_LAO_MEDALLIA_EXPRESS_REPORT) | JOB.ODS_LAO_MEDALLIA_EXPRESS_REPORT | [7 empty] | 2 | 1 | 46007 | 46007 | ["['[(TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT)]']"] | 1 | Check | 0.688 | ODS | 1 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.STG_CT_TRADEIN_SEASA) | JOB.STG_CT_TRADEIN_SEASA | [7 empty] | 2 | 1 | 46007 | 46007 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 1 | Check | 0.0001 | OTHER | 1 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS) | JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS | [7 empty] | 2 | 1 | 46007 | 46007 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | Check | 0.0004 | OTHER | 1 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS_TOTALS_TEMP) | JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS_TOTALS_TEMP | [7 empty] | 2 | 1 | 46007 | 46007 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | Check | 0.0001 | OTHER | 1 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS_UPDATE_TEMP) | JOB.ETL_GUATEMALA_ECOMMERCE_ORDERS_UPDATE_TEMP | [7 empty] | 2 | 1 | 46007 | 46007 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | Check | 0.0001 | OTHER | 1 |  | 0 | [16 empty] | 16/12 - 16/12
| INGESTION | (INGESTION - JOB.ETL_PANAMA_ECOMMERCE_ORDERS) | JOB.ETL_PANAMA_ECOMMERCE_ORDERS | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | Check | 0.0002 | OTHER | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ETL_PANAMA_ECOMMERCE_ORDERS_UPDATE_TEMP) | JOB.ETL_PANAMA_ECOMMERCE_ORDERS_UPDATE_TEMP | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - U_PRJ_ECOM.\\xa0)]']"] | 0 | Check | 0 | OTHER | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_DIRECTSHIP_RAWDATA_GPL) | JOB.ODS_DIRECTSHIP_RAWDATA_GPL | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_SEDA_S.ODS_DIRECTSHIP_RAWDATA_GPL)]']"] | 0 | Check | 0.0249 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_ECOM_SKU_ENABLES) | JOB.ODS_ECOM_SKU_ENABLES | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES)]']"] | 0 | Check | 0.0005 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_MD_MAPPING_PROMOTION_PRODUCT) | JOB.ODS_MD_MAPPING_PROMOTION_PRODUCT | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_MD.ODS_MD_MAPPING_PROMOTION_PRODUCT)]']"] | 0 | Check | 0.0001 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_MKP_D2C_FASTSHOP) | JOB.ODS_MKP_D2C_FASTSHOP | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - U_PRJ_ECOM.ODS_MKP_D2C_FASTSHOP)]']"] | 0 | Check | 0.0325 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_ONTIMEGI_RAWDATA_GPL) | JOB.ODS_ONTIMEGI_RAWDATA_GPL | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_SEDA_S.ODS_ONTIMEGI_RAWDATA_GPL)]']"] | 0 | Check | 0.0413 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_ONTIMEGR_RAWDATA_GPL) | JOB.ODS_ONTIMEGR_RAWDATA_GPL | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_SEDA_S.ODS_ONTIMEGR_RAWDATA_GPL)]']"] | 0 | Check | 0.027 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_RP_DOA_INSPECTION_RESULT) | JOB.ODS_RP_DOA_INSPECTION_RESULT | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_SEDA_S.ODS_RP_DOA_INSPECTION_RESULT)]']"] | 0 | Check | 0.1115 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_RP_DOA_TRACKING_BY_SERIAL) | JOB.ODS_RP_DOA_TRACKING_BY_SERIAL | [7 empty] | 2 | 1 | 46008 | 46008 | ["['[(TABLE - OW_SEDA_S.ODS_RP_DOA_TRACKING_BY_SERIAL)]']"] | 0 | Check | 0.0802 | ODS | 1 |  | 0 | [16 empty] | 17/12 - 17/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM) | JOB.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM)]']"] | 0 | Check | 0.0093 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_ESCOLTA) | JOB.ODS_SM_PORTAL_ANGELIRA_ESCOLTA | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA)]']"] | 0 | Check | 0.0049 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_NC) | JOB.ODS_SM_PORTAL_ANGELIRA_NC | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_NC)]']"] | 0 | Check | 0.0051 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_CHECKLIST) | JOB.ODS_SM_PORTAL_ANGELIRA_RM_CHECKLIST | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_CHECKLIST)]']"] | 0 | Check | 0.0011 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA) | JOB.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_PRONTA_RESPOSTA)]']"] | 0 | Check | 0.0007 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS) | JOB.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_RM_SINISTROS)]']"] | 0 | Check | 0.0005 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SURICATO_HR) | JOB.ODS_SURICATO_HR | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SURICATO_HR)]']"] | 0 | Check | 0.0038 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SURSIS_DELIVERY_DATA) | JOB.ODS_SURSIS_DELIVERY_DATA | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA)]']"] | 0 | Check | 0.011 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SURSIS_ESCORT) | JOB.ODS_SURSIS_ESCORT | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SURSIS_ESCORT)]']"] | 0 | Check | 0.0065 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_SURSIS_NC) | JOB.ODS_SURSIS_NC | [7 empty] | 2 | 1 | 46009 | 46009 | ["['[(TABLE - OW_SEDA_S.ODS_SURSIS_NC)]']"] | 0 | Check | 0.0052 | ODS | 1 |  | 0 | [16 empty] | 18/12 - 18/12
| INGESTION | (INGESTION - JOB.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT) | JOB.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_SEDA_S.ODS_WEB_JASPER_PARTS_RETURN_UPC_INBOUND_REPORT)]']"] | 0 | Check | 0.2136 | ODS | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.RAW_DATA_LAO_MEDALLIA_EXPRESS_REPORT) | JOB.RAW_DATA_LAO_MEDALLIA_EXPRESS_REPORT | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT)]']"] | 0 | Check | 0.0734 | RAW | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS) | JOB.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | Check | 0.0001 | OTHER | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_CANCELLATIONS_DEDUP) | JOB.TMP_HYBRIS_CANCELLATIONS_DEDUP | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | Check | 0.0002 | TMP | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.TMP_HYBRIS_TRADEIN_DEDUP) | JOB.TMP_HYBRIS_TRADEIN_DEDUP | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.\\xa0)]']"] | 0 | Check | 0.0004 | TMP | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.TMP_ODS_GENERIC_INPUT) | JOB.TMP_ODS_GENERIC_INPUT | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_SEDA_S.TMP_ODS_GENERIC_INPUT)]']"] | 0 | Check | 0.0141 | TMP | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_AP1_ACCURACY) | JOB.ODS_GSCM_AP1_ACCURACY | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY)]']"] | 1 | Migrar ph2 | 0.0173 | ODS | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_FCST_MGMT_D2C) | JOB.ODS_GSCM_FCST_MGMT_D2C | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_LAO.ODS_GSCM_FCST_MGMT_D2C)]']"] | 1 | Migrar ph2 | 3.995 | ODS | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER) | JOB.ODS_PLUGG_MARKETPLACE_ORDER | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | Migrar ph2 | 0.2784 | ODS | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.ODS_WMS_ABNORMAL_INVENTORY) | JOB.ODS_WMS_ABNORMAL_INVENTORY | [7 empty] | 2 | 1 | 46010 | 46010 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_ABNORMAL_INVENTORY)]']"] | 1 | Migrar ph2 | 0.3011 | ODS | 1 |  | 0 | [16 empty] | 19/12 - 19/12
| INGESTION | (INGESTION - JOB.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD) | JOB.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_DATA_MAPPING_UNLOADING_TWMS_YARD)]']"] | 1 | Migrar ph2 | 0.0159 | ODS | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.ODS_WMS_GATE_DOCK_IN_MAO) | JOB.ODS_WMS_GATE_DOCK_IN_MAO | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_MAO)]']"] | 1 | Migrar ph2 | 0.1685 | ODS | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD) | JOB.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD)]']"] | 1 | Migrar ph2 | 0.015 | ODS | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.ODS_WMS_PICKING_PACKING) | JOB.ODS_WMS_PICKING_PACKING | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_PICKING_PACKING)]']"] | 1 | Migrar ph2 | 0.0925 | ODS | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.ODS_WMS_YMS_GATE_DOCK_IN_CAJ) | JOB.ODS_WMS_YMS_GATE_DOCK_IN_CAJ | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_YMS_GATE_DOCK_IN_CAJ)]']"] | 1 | Migrar ph2 | 0.0262 | ODS | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.RAW_DATA_GSCM_ACTUAL_ON_HAND) | JOB.RAW_DATA_GSCM_ACTUAL_ON_HAND | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)]']"] | 1 | Migrar ph2 | 0.3142 | RAW | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.RAW_GSCM_CE_SELL_OUT) | JOB.RAW_GSCM_CE_SELL_OUT | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_LAO.ODS_GSCM_CE_SELL_OUT)]']"] | 1 | Migrar ph2 | 0.2705 | RAW | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.RAW_GSCM_MX_SELL_OUT) | JOB.RAW_GSCM_MX_SELL_OUT | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_LAO.ODS_GSCM_MX_SELL_OUT)]']"] | 1 | Migrar ph2 | 0.4139 | RAW | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.FT_CE_SELL_IN_FCST) | JOB.FT_CE_SELL_IN_FCST | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.FT_CE_SELL_IN_FCST)]']"] | 0 | Migrar ph2 | 0.0024 | FT | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.MAP_CE_ASP_RANGE) | JOB.MAP_CE_ASP_RANGE | [7 empty] | 2 | 1 | 46013 | 46013 | ["['[(TABLE - OW_SEDA_S.MAP_CE_ASP_RANGE)]']"] | 0 | Migrar ph2 | 0.0029 | MAP | 1 |  | 0 | [17 empty] | 22/12 - 22/12
| INGESTION | (INGESTION - JOB.MAP_CE_ASP_RANGE_TABLE) | JOB.MAP_CE_ASP_RANGE_TABLE | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_ASP_RANGE_TABLE)]']"] | 0 | Migrar ph2 | 0.0001 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_DISTRIBUTION_QUALITY_TRACKER) | JOB.MAP_CE_DISTRIBUTION_QUALITY_TRACKER | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_QUALITY_TRACKER)]']"] | 0 | Migrar ph2 | 0.0409 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE) | JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE)]']"] | 0 | Migrar ph2 | 0.012 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA) | JOB.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE_HA)]']"] | 0 | Migrar ph2 | 0.0066 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT) | JOB.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PHASE_OUT)]']"] | 0 | Migrar ph2 | 0.008 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_JOURNEY) | JOB.MAP_CE_JOURNEY | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)]']"] | 0 | Migrar ph2 | 0.0117 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_PRODUCTS) | JOB.MAP_CE_PRODUCTS | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 | 0.0114 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_PROMOTER_TARGET) | JOB.MAP_CE_PROMOTER_TARGET | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PROMOTER_TARGET)]']"] | 0 | Migrar ph2 | 0.0083 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.MAP_CE_SALES_DEDUCTION) | JOB.MAP_CE_SALES_DEDUCTION | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.MAP_CE_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 | 0.0004 | MAP | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_ACTUAL_SALES) | JOB.ODS_GSCM_ACTUAL_SALES | [7 empty] | 2 | 1 | 46014 | 46014 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_ACTUAL_SALES)]']"] | 0 | Migrar ph2 | 0.0407 | ODS | 1 |  | 0 | [17 empty] | 23/12 - 23/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_CE_SELL_OUT) | JOB.ODS_GSCM_CE_SELL_OUT | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_LAO.ODS_GSCM_CE_SELL_OUT)]']"] | 0 | Migrar ph2 | 0.0079 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION) | JOB.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_LAO.ODS_GSCM_CH_PSI_WARNING_SALES_DEDUCTION_DAILY_EXCEPTION)]']"] | 0 | Migrar ph2 | 0.0001 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_FCST_MGMT_AP1) | JOB.ODS_GSCM_FCST_MGMT_AP1 | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_FCST_MGMT_AP1)]']"] | 0 | Migrar ph2 | 0.1936 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_MX_SELL_OUT) | JOB.ODS_GSCM_MX_SELL_OUT | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_LAO.ODS_GSCM_MX_SELL_OUT)]']"] | 0 | Migrar ph2 | 0.0145 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_PROMOTION_PLAN_RAW) | JOB.ODS_GSCM_PROMOTION_PLAN_RAW | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_PROMOTION_PLAN_RAW)]']"] | 0 | Migrar ph2 | 0.0196 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SELL_OUT_ACCOUNT) | JOB.ODS_GSCM_SELL_OUT_ACCOUNT | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SELL_OUT_ACCOUNT)]']"] | 0 | Migrar ph2 | 0.0154 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SI_FCST_DA) | JOB.ODS_GSCM_SI_FCST_DA | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_DA)]']"] | 0 | Migrar ph2 | 0.0849 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SI_FCST_MX) | JOB.ODS_GSCM_SI_FCST_MX | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_MX)]']"] | 0 | Migrar ph2 | 0.1837 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SI_FCST_VD) | JOB.ODS_GSCM_SI_FCST_VD | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SI_FCST_VD)]']"] | 0 | Migrar ph2 | 0.0798 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SO_FCST_DA) | JOB.ODS_GSCM_SO_FCST_DA | [7 empty] | 2 | 1 | 46015 | 46015 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_DA)]']"] | 0 | Migrar ph2 | 0.0862 | ODS | 1 |  | 0 | [17 empty] | 24/12 - 24/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SO_FCST_HHP) | JOB.ODS_GSCM_SO_FCST_HHP | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_HHP)]']"] | 0 | Migrar ph2 | 0.1631 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SO_FCST_OTHERS) | JOB.ODS_GSCM_SO_FCST_OTHERS | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_OTHERS)]']"] | 0 | Migrar ph2 | 0.077 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_GSCM_SO_FCST_VD) | JOB.ODS_GSCM_SO_FCST_VD | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_SO_FCST_VD)]']"] | 0 | Migrar ph2 | 0.0597 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC) | JOB.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_SRS_CREATED_IN_GSSC)]']"] | 0 | Migrar ph2 | 0.0001 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION) | JOB.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_LAO.ODS_LAO_SALES_DEDUCTION_VALIDATION_WEEK_RESULT_EDI_EXCEPTION)]']"] | 0 | Migrar ph2 | 0 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_NERP_ZLMKF03006_CONDITION_CALC) | JOB.ODS_NERP_ZLMKF03006_CONDITION_CALC | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLMKF03006_CONDITION_CALC)]']"] | 0 | Migrar ph2 | 0.0003 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY) | JOB.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY)]']"] | 0 | Migrar ph2 | 0.5782 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY) | JOB.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY)]']"] | 0 | Migrar ph2 | 0.655 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW) | JOB.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_SEDA_S.ODS_SALES_ADMIN_SALES_DEDUCTION_RAW)]']"] | 0 | Migrar ph2 | 0.0667 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION) | JOB.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION | [7 empty] | 2 | 1 | 46016 | 46016 | ["['[(TABLE - OW_LAO.ODS_SALES_DEDUCTION_CURRENT_WEEK_DATA_EDI_EXCEPTION)]']"] | 0 | Migrar ph2 | 0 | ODS | 1 |  | 0 | [17 empty] | 25/12 - 25/12
| INGESTION | (INGESTION - JOB.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION) | JOB.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_LAO.ODS_SALES_DEDUCTION_PREVIOUS_WEEK_DATA_EDI_EXCEPTION)]']"] | 0 | Migrar ph2 | 0 | ODS | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION) | JOB.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_EXCEPTION)]']"] | 0 | Migrar ph2 | 0 | ODS | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.ODS_WEBPRICE_TRACKING_DAILY_MX) | JOB.ODS_WEBPRICE_TRACKING_DAILY_MX | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX)]']"] | 0 | Migrar ph2 | 0.2357 | ODS | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.ODS_WEBPRICE_TRACKING_DAILY_TV) | JOB.ODS_WEBPRICE_TRACKING_DAILY_TV | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_TV)]']"] | 0 | Migrar ph2 | 0.7171 | ODS | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.RAW_GSCM_PRODUCT_LIST) | JOB.RAW_GSCM_PRODUCT_LIST | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | Migrar ph2 | 0.0003 | RAW | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.TMP_CE_FORMAT) | JOB.TMP_CE_FORMAT | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.TMP_CE_FORMAT)]']"] | 0 | Migrar ph2 | 0.0942 | TMP | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.TMP_ODS_GSCM_PROMOTION_PLAN) | JOB.TMP_ODS_GSCM_PROMOTION_PLAN | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.TMP_ODS_GSCM_PROMOTION_PLAN)]']"] | 0 | Migrar ph2 | 0.0085 | TMP | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION) | JOB.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.TMP_ODS_SALES_ADMIN_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 | 0.0026 | TMP | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.FT_CE_DAILY_PIVOT) | JOB.FT_CE_DAILY_PIVOT | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.FT_CE_DAILY_PIVOT)]']"] | 0 | Migrar ph2 SEDA RM | 0.7634 | FT | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.FT_CE_DB_FCST) | JOB.FT_CE_DB_FCST | [7 empty] | 2 | 1 | 46017 | 46017 | ["['[(TABLE - OW_SEDA_S.FT_CE_DB_FCST)]']"] | 0 | Migrar ph2 SEDA RM | 0.0538 | FT | 1 |  | 0 | [17 empty] | 26/12 - 26/12
| INGESTION | (INGESTION - JOB.FT_CE_READY) | JOB.FT_CE_READY | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.FT_CE_READY)]']"] | 0 | Migrar ph2 SEDA RM | 0.6369 | FT | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.MAP_CE_STORES) | JOB.MAP_CE_STORES | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM | 0.0884 | MAP | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.ODS_CONTROLLING_FORMAT_ACTUAL) | JOB.ODS_CONTROLLING_FORMAT_ACTUAL | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_FORMAT_ACTUAL)]']"] | 0 | Migrar ph2: Controlling | 1.1336 | ODS | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.ODS_CONTROLLING_PL) | JOB.ODS_CONTROLLING_PL | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)]']"] | 0 | Migrar ph2: Controlling | 0.0721 | ODS | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.RAW_IBGE_POPULACAO) | JOB.RAW_IBGE_POPULACAO | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | Migrar ph2: SEDA MI& Big Data | 0.0002 | RAW | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.ODS_RP_ETR_LOGISTICS_TRACKING) | JOB.ODS_RP_ETR_LOGISTICS_TRACKING | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.ODS_RP_ETR_LOGISTICS_TRACKING)]']"] | 0 | check | 0.1935 | ODS | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG) | JOB.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.ODS_SNOWFLAKE_INFRAPAY_REDE_TRANSACTIONS_SSG)]']"] | 0 | check | 0 | ODS | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.RAW_ANATEL_ACESSOS_TELEFONIA_MOVEL) | JOB.RAW_ANATEL_ACESSOS_TELEFONIA_MOVEL | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | check | 1.7213 | RAW | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.RAW_MX_TMV_INDEX) | JOB.RAW_MX_TMV_INDEX | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_MX)]']"] | 0 | check | 0.0002 | RAW | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| INGESTION | (INGESTION - JOB.RAW_TECH_INSIGHTS) | JOB.RAW_TECH_INSIGHTS | [7 empty] | 2 | 1 | 46020 | 46020 | ["['[(TABLE - OW_SEDA_S.\\xa0)]']"] | 0 | check | 0.0005 | RAW | 1 |  | 0 | [18 empty] | 29/12 - 29/12
| VIEW | (VIEW - OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING) | OW_SEDA_S.VW_TSS_CELLO_IOD_STATUS_MONITORING | [7 empty] | 3 | 1 | 46021 | 46021 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.SDI_TSS_NF_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.SDI_TSS_BOOKING_UPDATE_LOG)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_MID_AREA)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_ORDERS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_ITEM)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_CODE)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_RETURN_REASON)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_RETURN_BOOKING_REQUEST)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_TRANS)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_REASON)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_DETAIL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_GROUP)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_FOLLOW_UP_STATUS)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT_LOC)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_RETURN)'", "'(TABLE - OW_SEDA_S.SDI_TSS_WEB_RETURN_REQUEST)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_IOD)'", "'(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS_LOC)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)'", "'(TABLE - OW_SEDA_S.SDI_TSS_RS_RESULT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_DIVISION)]']"] | 1 | Check |  |  | 39 |  | 0 | [18 empty] | 30/12 - 30/12
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228) | OW_SEDA_S.VW_UNION_TSS_CELLO_RETURN_TRACKING_BKP_20240228 | [7 empty] | 3 | 1 | 46021 | 46021 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_SDI)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | Check |  |  | 13 |  | 0 | [18 empty] | 30/12 - 30/12
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_CELLO_TSS_IOD_STATUS) | OW_SEDA_S.VW_UNION_CELLO_TSS_IOD_STATUS | [7 empty] | 3 | 1 | 46021 | 46021 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_OD_ORDERS)'", "'(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)'", "'(TABLE - OW_SEDA_S.SDI_TSS_MVW_IOD_STATUS_REPORT)]']"] | 0 | Migrar ph2 |  |  | 3 |  | 0 | [18 empty] | 30/12 - 30/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING) | OW_SEDA_S.PROC_FT_TSS_CELLO_IOD_STATUS_MONITORING | [7 empty] | 4 | 1 | 46021 | 46021 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING_TMP)'", "'(TABLE - OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | Check |  |  | 14 |  | 0 | [18 empty] | 30/12 - 30/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2) | OW_LAO.PROC_CRAWLING_AP1_IM_PT2 | [7 empty] | 4 | 1 | 46021 | 46021 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING_KEY)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Check |  |  | 4 |  | 0 | [18 empty] | 30/12 - 30/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_DUEK) | OW_LAO.PROC_CRAWLING_AP1_IM_PT2_DUEK | [7 empty] | 4 | 1 | 46021 | 46021 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Check |  |  | 3 |  | 0 | [18 empty] | 30/12 - 30/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HIST) | OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HIST | [7 empty] | 4 | 1 | 46021 | 46021 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Check |  |  | 3 |  | 0 | [18 empty] | 30/12 - 30/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HISTORICO) | OW_LAO.PROC_CRAWLING_AP1_IM_PT2_HISTORICO | [7 empty] | 4 | 1 | 46021 | 46021 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Check |  |  | 3 |  | 0 | [18 empty] | 30/12 - 30/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT2_V2) | OW_LAO.PROC_CRAWLING_AP1_IM_PT2_V2 | [7 empty] | 4 | 1 | 46021 | 46021 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Check |  |  | 3 |  | 0 | [18 empty] | 30/12 - 30/12
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT2) | OW_LAO.PROC_CRAWLING_AP1_TABLET_PT2 | [7 empty] | 4 | 1 | 46021 | 46021 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_A_MINMODELCODE)]']"] | 1 | Check |  |  | 3 |  | 0 | [18 empty] | 30/12 - 30/12
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2) | OW_SEDA_S.PROC_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2 | [7 empty] | 4 | 1 | 46022 | 46022 | ["['[(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_01)'", "'(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_02)'", "'(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)'", "'(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_DOWN)'", "'(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_ACESSORY)'", "'(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_EPP)'", "'(TABLE - OW_LAO.TF_CV_BI_TRACKING_CLEAN_SDI_CELLO_TSS_V2_HME)]']"] | 0 | Migrar ph2 |  |  | 7 |  | 0 | [18 empty] | 31/12 - 31/12
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_NPC_SEGMENT) | OW_LAO.VW_CRAWLING_AP1_NPC_SEGMENT | [7 empty] | 3 | 1 | 46022 | 46022 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Check |  |  | 2 |  | 0 | [18 empty] | 31/12 - 31/12
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_REF_SEGMENT) | OW_LAO.VW_CRAWLING_AP1_REF_SEGMENT | [7 empty] | 3 | 1 | 46022 | 46022 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Check |  |  | 2 |  | 0 | [18 empty] | 31/12 - 31/12
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_TV_SEGMENT) | OW_LAO.VW_CRAWLING_AP1_TV_SEGMENT | [7 empty] | 3 | 1 | 46022 | 46022 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING)]']"] | 1 | Check |  |  | 2 |  | 0 | [18 empty] | 31/12 - 31/12
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_WM_SEGMENT) | OW_LAO.VW_CRAWLING_AP1_WM_SEGMENT | [7 empty] | 3 | 1 | 46022 | 46022 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Check |  |  | 2 |  | 0 | [18 empty] | 31/12 - 31/12
| VIEW | (VIEW - OW_SEDA_S.VW_API_GSCM_TO_ASM) | OW_SEDA_S.VW_API_GSCM_TO_ASM | [7 empty] | 3 | 1 | 46022 | 46022 | ["['[(TABLE - OW_SEDA_S.GSCM_TMP)]']"] | 1 | Check |  |  | 1 |  | 0 | [18 empty] | 31/12 - 31/12
| VIEW | (VIEW - OW_SEDA_S.VW_API_GSCM_TO_ASM_2) | OW_SEDA_S.VW_API_GSCM_TO_ASM_2 | [7 empty] | 3 | 1 | 46022 | 46022 | ["['[(TABLE - OW_SEDA_S.GSCM_TMP)]']"] | 1 | Check |  |  | 1 |  | 0 | [18 empty] | 31/12 - 31/12
| VIEW | (VIEW - OW_SEDA_S.TF_PORTAL_SM_SURSIS_JOIN_1) | OW_SEDA_S.TF_PORTAL_SM_SURSIS_JOIN_1 | [7 empty] | 3 | 1 | 46022 | 46022 | ["['[(TABLE - OW_SEDA_S.ODS_SURSIS_ESCORT)'", "'(TABLE - OW_SEDA_S.ODS_SURSIS_DELIVERY_DATA)]']"] | 0 | Check |  |  | 2 |  | 0 | [18 empty] | 31/12 - 31/12
| VIEW | (VIEW - OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA_VIAGEM_ESCOLTA) | OW_SEDA_S.VW_SMPORTAL_DADOS_ANGELIRA_VIAGEM_ESCOLTA | [7 empty] | 3 | 1 | 46022 | 46022 | ["['[(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_DADOS_VIAGEM)'", "'(TABLE - OW_SEDA_S.ODS_SM_PORTAL_ANGELIRA_ESCOLTA)]']"] | 0 | Check |  |  | 2 |  | 0 | [18 empty] | 31/12 - 31/12
| VIEW | (VIEW - OW_SELA.CURRENTWEEK) | OW_SELA.CURRENTWEEK | [7 empty] | 3 | 1 | 46022 | 46022 | ["['[(TABLE - OW_SELA.FACT_STOCK_SALES)'", "'(TABLE - OW_SELA.DIM_WEEK)]']"] | 0 | Check |  |  | 2 |  | 0 | [18 empty] | 31/12 - 31/12
| VIEW | (VIEW - OW_SELA.MISSINGSEGMENT) | OW_SELA.MISSINGSEGMENT | [7 empty] | 3 | 1 | 46023 | 46023 | ["['[(TABLE - OW_SELA.DIM_PRODUCT)'", "'(TABLE - OW_SELA.DIM_MN_SEGMENT)]']"] | 0 | Check |  |  | 2 |  | 0 | [18 empty] | 01/01 - 01/01
| VIEW | (VIEW - OW_SELA.MISSING_MKTNAME) | OW_SELA.MISSING_MKTNAME | [7 empty] | 3 | 1 | 46023 | 46023 | ["['[(TABLE - OW_SELA.DIM_PRODUCT)'", "'(TABLE - OW_SELA.FACT_STOCK_SALES)]']"] | 0 | Check |  |  | 2 |  | 0 | [18 empty] | 01/01 - 01/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT) | OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT | [7 empty] | 3 | 1 | 46023 | 46023 | ["['[(TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT)]']"] | 0 | Check |  |  | 1 |  | 0 | [18 empty] | 01/01 - 01/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_FLOORING) | OW_SEDA_S.VW_CE_ACCOUNT_MANAGEMENT_FLOORING | [7 empty] | 3 | 1 | 46023 | 46023 | ["['[(TABLE - OW_SEDA_S.DS_CE_ACCOUNT_MANAGEMENT_FLOORING)]']"] | 0 | Check |  |  | 1 |  | 0 | [18 empty] | 01/01 - 01/01
| VIEW | (VIEW - OW_SEDA_S.VW_CELLO_SUM_LLM) | OW_SEDA_S.VW_CELLO_SUM_LLM | [7 empty] | 3 | 1 | 46023 | 46023 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_LAST_LEG_MANIFEST)]']"] | 1 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 01/01 - 01/01
| VIEW | (VIEW - OW_SEDA_S.VW_CELLO_SUM_SHIPMENT) | OW_SEDA_S.VW_CELLO_SUM_SHIPMENT | [7 empty] | 3 | 1 | 46023 | 46023 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT)]']"] | 1 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 01/01 - 01/01
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP_TEST) | OW_SEDA_S.VW_UNION_TSS_CELLO_TMP_TEST | [7 empty] | 3 | 1 | 46023 | 46023 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TMP)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)]']"] | 1 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 01/01 - 01/01
| FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_CELLO_EVENT) | OW_SEDA_S.FN_GET_CELLO_EVENT | [7 empty] | 3 | 1 | 46023 | 46023 | ["['[(TABLE - OW_SEDA_S.CELLO_TRACKING)]']"] | 1 | Migrar ph2 |  |  | 1 |  | 0 | [18 empty] | 01/01 - 01/01
| VIEW | (VIEW - OW_LAO.VW_LAO_SALES_DEDUCTION_DAILY_MONITORING_MAPPING_STATUS) | OW_LAO.VW_LAO_SALES_DEDUCTION_DAILY_MONITORING_MAPPING_STATUS | [7 empty] | 3 | 1 | 46023 | 46023 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING)]']"] | 1 | Migrar ph2 |  |  | 1 |  | 0 | [18 empty] | 01/01 - 01/01
| VIEW | (VIEW - OW_SEDA_S.VW_ABNORMAL_INVENTORY) | OW_SEDA_S.VW_ABNORMAL_INVENTORY | [7 empty] | 3 | 1 | 46023 | 46023 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_ABNORMAL_INVENTORY)]']"] | 1 | Migrar ph2 |  |  | 1 |  | 0 | [18 empty] | 01/01 - 01/01
| VIEW | (VIEW - OW_SEDA_S.VW_CELLO_TRACKING_EVENT) | OW_SEDA_S.VW_CELLO_TRACKING_EVENT | [7 empty] | 3 | 1 | 46024 | 46024 | ["['[(TABLE - OW_SEDA_S.CELLO_TRACKING)]']"] | 1 | Migrar ph2 |  |  | 1 |  | 0 | [18 empty] | 02/01 - 02/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD) | OW_SEDA_S.VW_SDU_ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD | [7 empty] | 3 | 1 | 46024 | 46024 | ["['[(TABLE - OW_SEDA_S.ODS_WMS_GATE_DOCK_IN_OUT_TWMS_YARD)]']"] | 1 | Migrar ph2 |  |  | 1 |  | 0 | [18 empty] | 02/01 - 02/01
| FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_BOD2_SDI_v2) | OW_SEDA_S.FN_GET_BOD2_SDI_v2 | [7 empty] | 3 | 1 | 46024 | 46024 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_M_LOCATION)'", "'(TABLE - OW_SEDA_S.ODS_TSS_M_BOD)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 02/01 - 02/01
| FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE) | OW_SEDA_S.FN_GET_LAST_EVENT_DATE | [7 empty] | 3 | 1 | 46024 | 46024 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT)'", "'(TABLE - OW_SEDA_S.ODS_TSS_TC_EVENT_LOG)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 02/01 - 02/01
| FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_LAST_EVENT_DATE_SDI) | OW_SEDA_S.FN_GET_LAST_EVENT_DATE_SDI | [7 empty] | 3 | 1 | 46024 | 46024 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT)'", "'(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOG)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 02/01 - 02/01
| VIEW | (VIEW - OW_SEDA_S.VW_IBGE_CEP_5_COORDINATES) | OW_SEDA_S.VW_IBGE_CEP_5_COORDINATES | [7 empty] | 3 | 1 | 46024 | 46024 | ["['[(TABLE - OW_SEDA_S.ODS_IBGE_CEP_5_COORDINATES)'", "'(TABLE - OW_SEDA_S.MAP_CE_SETOR_CENSITARIO_2010)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 02/01 - 02/01
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO | [7 empty] | 3 | 1 | 46024 | 46024 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 02/01 - 02/01
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_JULIAO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_COMPLETO_JULIAO | [7 empty] | 3 | 1 | 46024 | 46024 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 02/01 - 02/01
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO | [7 empty] | 3 | 1 | 46024 | 46024 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 02/01 - 02/01
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL | [7 empty] | 3 | 1 | 46024 | 46024 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [18 empty] | 02/01 - 02/01
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_JULIAO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_JULIAO | [7 empty] | 3 | 1 | 46027 | 46027 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 05/01 - 05/01
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_LSPOSITO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_SELLOUTGERAL_LSPOSITO | [7 empty] | 3 | 1 | 46027 | 46027 | ["['[(TABLE - OW_SEDA_S.TF_VW_SELLOUTGERAL)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 05/01 - 05/01
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_VALIDATION) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_VALIDATION | [7 empty] | 3 | 1 | 46027 | 46027 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 05/01 - 05/01
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART | [7 empty] | 3 | 1 | 46027 | 46027 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)'", "'(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 05/01 - 05/01
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART_LSPOSITO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_WALMART_LSPOSITO | [7 empty] | 3 | 1 | 46027 | 46027 | ["['[(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)'", "'(TABLE - OW_SEDA_S.TF_VW_WALMART)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 05/01 - 05/01
| VIEW | (VIEW - OW_SEDA_S.VW_SCM_SALES_AND_SO_LIST_COMPLETE) | OW_SEDA_S.VW_SCM_SALES_AND_SO_LIST_COMPLETE | [7 empty] | 3 | 1 | 46027 | 46027 | ["['[(TABLE - OW_SEDA_S.FT_CE_SELL_IN_FCST)'", "'(TABLE - OW_SEDA_S.ODS_SCM_FINANCIAL_FCST)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 05/01 - 05/01
| VIEW | (VIEW - OW_SEDA_S.VW_SEDA_SALES_IN_TRANSIT) | OW_SEDA_S.VW_SEDA_SALES_IN_TRANSIT | [7 empty] | 3 | 1 | 46027 | 46027 | ["['[(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)'", "'(TABLE - OW_SEDA_S.MAP_CARRIER)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 05/01 - 05/01
| VIEW | (VIEW - OW_SEDA_S.VW_TT_RUPTURA) | OW_SEDA_S.VW_TT_RUPTURA | [7 empty] | 3 | 1 | 46027 | 46027 | ["['[(TABLE - OW_SEDA_S.MAP_CE_DISTRIBUTION_TARGET_PER_STORE)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 05/01 - 05/01
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST) | OW_SEDA_S.VW_UNION_TSS_CELLO_HIST | [7 empty] | 3 | 1 | 46027 | 46027 | ["['[(TABLE - OW_SEDA_S.FT_TSS_BI_TRACKING_HIST_SDI)'", "'(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 05/01 - 05/01
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_HIST_MAP_CARRIER) | OW_SEDA_S.VW_UNION_TSS_CELLO_HIST_MAP_CARRIER | [7 empty] | 3 | 1 | 46027 | 46027 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST)'", "'(TABLE - OW_SEDA_S.MAP_CARRIER)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 05/01 - 05/01
| FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_DO_CURR_ACTION) | OW_SEDA_S.FN_GET_DO_CURR_ACTION | [7 empty] | 3 | 1 | 46028 | 46028 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_CUSTOMER_REJECT)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 06/01 - 06/01
| FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_REJECT_CNT) | OW_SEDA_S.FN_GET_OCCURRENCE_REJECT_CNT | [7 empty] | 3 | 1 | 46028 | 46028 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_CUSTOMER_REJECT)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 06/01 - 06/01
| FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_STATUS) | OW_SEDA_S.FN_GET_OCCURRENCE_STATUS | [7 empty] | 3 | 1 | 46028 | 46028 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_OCCURRENCE)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 06/01 - 06/01
| FUNCTION | (FUNCTION - OW_SEDA_S.FN_GET_OCCURRENCE_STATUS_SDI) | OW_SEDA_S.FN_GET_OCCURRENCE_STATUS_SDI | [7 empty] | 3 | 1 | 46028 | 46028 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_OCCURRENCE)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 06/01 - 06/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_JOURNEY_COORDINATORS_MAXWEEK) | OW_SEDA_S.VW_CE_JOURNEY_COORDINATORS_MAXWEEK | [7 empty] | 3 | 1 | 46028 | 46028 | ["['[(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 06/01 - 06/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_JOURNEY_UNIQUE) | OW_SEDA_S.VW_CE_JOURNEY_UNIQUE | [7 empty] | 3 | 1 | 46028 | 46028 | ["['[(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 06/01 - 06/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_JOURNEY_UNIQUE_MAX_WEEKNUM) | OW_SEDA_S.VW_CE_JOURNEY_UNIQUE_MAX_WEEKNUM | [7 empty] | 3 | 1 | 46028 | 46028 | ["['[(TABLE - OW_SEDA_S.MAP_CE_JOURNEY)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 06/01 - 06/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_SHOPPING_BRASIL_API) | OW_SEDA_S.VW_CE_SHOPPING_BRASIL_API | [7 empty] | 3 | 1 | 46028 | 46028 | ["['[(TABLE - OW_SEDA_S.ODS_CE_SHOPPING_BRASIL_API)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 06/01 - 06/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_WEATHER_FCST_API) | OW_SEDA_S.VW_CE_WEATHER_FCST_API | [7 empty] | 3 | 1 | 46028 | 46028 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEATHER_FCST_API)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 06/01 - 06/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_WEBPRICE_URL) | OW_SEDA_S.VW_CE_WEBPRICE_URL | [7 empty] | 3 | 1 | 46028 | 46028 | ["['[(TABLE - OW_SEDA_S.MAP_CE_WEBPRICE_URL)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 06/01 - 06/01
| VIEW | (VIEW - OW_SEDA_S.VW_GSCM_CH_PSI_WARING_SALES_DEDUCTION) | OW_SEDA_S.VW_GSCM_CH_PSI_WARING_SALES_DEDUCTION | [7 empty] | 3 | 1 | 46029 | 46029 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 07/01 - 07/01
| VIEW | (VIEW - OW_SEDA_S.VW_MX_SALES_VS_RTF) | OW_SEDA_S.VW_MX_SALES_VS_RTF | [7 empty] | 3 | 1 | 46029 | 46029 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 07/01 - 07/01
| VIEW | (VIEW - OW_SEDA_S.VW_MX_SALES_VS_RTF_BY_CAPACITY) | OW_SEDA_S.VW_MX_SALES_VS_RTF_BY_CAPACITY | [7 empty] | 3 | 1 | 46029 | 46029 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 07/01 - 07/01
| VIEW | (VIEW - OW_SEDA_S.VW_ONLINE_FISICO) | OW_SEDA_S.VW_ONLINE_FISICO | [7 empty] | 3 | 1 | 46029 | 46029 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 07/01 - 07/01
| VIEW | (VIEW - OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO_LSPOSITO) | OW_SEDA_S.VW_SALES_DEDUCTION_RESULT_ONLINE_FISICO_LSPOSITO | [7 empty] | 3 | 1 | 46029 | 46029 | ["['[(TABLE - OW_SEDA_S.MAP_SALES_DEDUCTION_CORE_LEVELS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 07/01 - 07/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM) | OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM | [7 empty] | 3 | 1 | 46029 | 46029 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 07/01 - 07/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL) | OW_SEDA_S.VW_SDU_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL | [7 empty] | 3 | 1 | 46029 | 46029 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SEDA_D2C_ALL)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 07/01 - 07/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_OD_PRE_SHIPMENT) | OW_SEDA_S.VW_SDU_SDI_TSS_OD_PRE_SHIPMENT | [7 empty] | 3 | 1 | 46029 | 46029 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_OD_PRE_SHIPMENT)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 07/01 - 07/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_DATE) | OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_DATE | [7 empty] | 3 | 1 | 46029 | 46029 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_DATE)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 07/01 - 07/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_LOC) | OW_SEDA_S.VW_SDU_SDI_TSS_TC_EVENT_LOC | [7 empty] | 3 | 1 | 46029 | 46029 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_EVENT_LOC)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 07/01 - 07/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL) | OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL | [7 empty] | 3 | 1 | 46030 | 46030 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 08/01 - 08/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL_DESTINATION_PORT) | OW_SEDA_S.VW_SDU_SDI_TSS_TC_VESSEL_DESTINATION_PORT | [7 empty] | 3 | 1 | 46030 | 46030 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_VESSEL_DESTINATION_PORT)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 08/01 - 08/01
| VIEW | (VIEW - OW_SEDA_S.VW_SELLOUTGERAL) | OW_SEDA_S.VW_SELLOUTGERAL | [7 empty] | 3 | 1 | 46030 | 46030 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 08/01 - 08/01
| VIEW | (VIEW - OW_SEDA_S.VW_SELL_IN_FCST) | OW_SEDA_S.VW_SELL_IN_FCST | [7 empty] | 3 | 1 | 46030 | 46030 | ["['[(TABLE - OW_SEDA_S.FT_CE_SELL_IN_FCST)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 08/01 - 08/01
| VIEW | (VIEW - OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE) | OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE | [7 empty] | 3 | 1 | 46030 | 46030 | ["['[(TABLE - OW_SEDA_S.ODS_TSS_TC_LEG_PLANNING)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 08/01 - 08/01
| VIEW | (VIEW - OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE_SDI) | OW_SEDA_S.VW_TC_LEG_PLANNING_MAX_DATE_SDI | [7 empty] | 3 | 1 | 46030 | 46030 | ["['[(TABLE - OW_SEDA_S.SDI_TSS_TC_LEG_PLANNING)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 08/01 - 08/01
| VIEW | (VIEW - OW_SEDA_S.VW_WALMART) | OW_SEDA_S.VW_WALMART | [7 empty] | 3 | 1 | 46030 | 46030 | ["['[(TABLE - OW_SEDA_S.ODS_GSCM_CH_PSI_WARING_SALES_DEDUCTION)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 08/01 - 08/01
| VIEW | (VIEW - OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT) | OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT | [7 empty] | 3 | 1 | 46030 | 46030 | ["['[(TABLE - OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT)]']"] | 0 | Migrar ph2 BI |  |  | 1 |  | 0 | [19 empty] | 08/01 - 08/01
| VIEW | (VIEW - OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER) | OW_SEDA_S.VW_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER | [7 empty] | 3 | 1 | 46030 | 46030 | ["['[(TABLE - OW_SEDA_S.FT_FBAI_CHURN_IN_CHURN_OUT_PER_CARRIER)]']"] | 0 | Migrar ph2 BI |  |  | 1 |  | 0 | [19 empty] | 08/01 - 08/01
| VIEW | (VIEW - OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_COUNTRY) | OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_COUNTRY | [7 empty] | 3 | 1 | 46030 | 46030 | ["['[(TABLE - OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_COUNTRY)]']"] | 0 | Migrar ph2 BI |  |  | 1 |  | 0 | [19 empty] | 08/01 - 08/01
| VIEW | (VIEW - OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_DDD) | OW_SEDA_S.VW_MX_FBAI_GENERAL_INFO_PER_DDD | [7 empty] | 3 | 1 | 46031 | 46031 | ["['[(TABLE - OW_SEDA_S.FT_MX_FBAI_GENERAL_INFO_PER_DDD)]']"] | 0 | Migrar ph2 BI |  |  | 1 |  | 0 | [19 empty] | 09/01 - 09/01
| VIEW | (VIEW - OW_SEDA_S.VW_TT_STACK_INFO_2023) | OW_SEDA_S.VW_TT_STACK_INFO_2023 | [7 empty] | 3 | 1 | 46031 | 46031 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 |  | 0 | [19 empty] | 09/01 - 09/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_GERENCIAIS_PL) | OW_SEDA_S.VW_CE_GERENCIAIS_PL | [7 empty] | 3 | 1 | 46031 | 46031 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)]']"] | 0 | Migrar ph2: Controlling |  |  | 1 |  | 0 | [19 empty] | 09/01 - 09/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_GERENCIAIS_PL_FCST) | OW_SEDA_S.VW_CE_GERENCIAIS_PL_FCST | [7 empty] | 3 | 1 | 46031 | 46031 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)]']"] | 0 | Migrar ph2: Controlling |  |  | 1 |  | 0 | [19 empty] | 09/01 - 09/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_MBO_NETSALES_COP) | OW_SEDA_S.VW_CE_MBO_NETSALES_COP | [7 empty] | 3 | 1 | 46031 | 46031 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)]']"] | 0 | Migrar ph2: Controlling |  |  | 1 |  | 0 | [19 empty] | 09/01 - 09/01
| VIEW | (VIEW - OW_SEDA_S.VW_CE_MBO_NETSALES_COP_FCST) | OW_SEDA_S.VW_CE_MBO_NETSALES_COP_FCST | [7 empty] | 3 | 1 | 46031 | 46031 | ["['[(TABLE - OW_SEDA_S.ODS_CONTROLLING_PL)]']"] | 0 | Migrar ph2: Controlling |  |  | 1 |  | 0 | [19 empty] | 09/01 - 09/01
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_TMP) | OW_SEDA_S.VW_UNION_TSS_CELLO_TMP | [7 empty] | 3 | 1 | 46031 | 46031 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_TMP)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)]']"] | 1 | migrar ph2 |  |  | 2 |  | 0 | [19 empty] | 09/01 - 09/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_FT_TSS_CELLO_IOD_STATUS_MONITORING) | OW_SEDA_S.VW_SDU_FT_TSS_CELLO_IOD_STATUS_MONITORING | [7 empty] | 3 | 1 | 46031 | 46031 | ["['[(TABLE - OW_SEDA_S.FT_TSS_CELLO_IOD_STATUS_MONITORING)]']"] | 1 | migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 09/01 - 09/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO) | OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO | [7 empty] | 3 | 1 | 46031 | 46031 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)]']"] | 1 | migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 09/01 - 09/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2) | OW_SEDA_S.VW_SDU_FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2 | [7 empty] | 3 | 1 | 46031 | 46031 | ["['[(TABLE - OW_SEDA_S.FT_BI_TRACKING_HIST_CLEAN_SDI_CELLO_TSS_V2)]']"] | 0 | migrar ph2 |  |  | 1 |  | 0 | [19 empty] | 09/01 - 09/01
| VIEW | (VIEW - OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO_HIST) | OW_SEDA_S.VW_SDU_FT_UNION_TSS_CELLO_HIST | [7 empty] | 3 | 1 | 46034 | 46034 | ["['[(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST)]']"] | 0 | migrar ph2 |  |  | 1 |  | 0 | [20 empty] | 12/01 - 12/01
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO) | OW_SEDA_S.VW_UNION_TSS_CELLO | [7 empty] | 3 | 1 | 46034 | 46034 | ["['[(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)]']"] | 0 | migrar ph2 |  |  | 1 |  | 0 | [20 empty] | 12/01 - 12/01
| VIEW | (VIEW - OW_SEDA_S.VW_UNION_TSS_CELLO_PHOTO) | OW_SEDA_S.VW_UNION_TSS_CELLO_PHOTO | [7 empty] | 3 | 1 | 46034 | 46034 | ["['[(TABLE - OW_SEDA_S.FT_BI_CELLO_IOD_TOTAL)]']"] | 0 | migrar ph2 |  |  | 1 |  | 0 | [20 empty] | 12/01 - 12/01
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_ESTORE_DAILY_PRICE) | OW_LAO.VW_CRAWLING_AP1_ESTORE_DAILY_PRICE | [7 empty] | 3 | 1 | 46034 | 46034 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [20 empty] | 12/01 - 12/01
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_REF_DISPLAY_SHARE) | OW_LAO.VW_CRAWLING_AP1_REF_DISPLAY_SHARE | [7 empty] | 3 | 1 | 46034 | 46034 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [20 empty] | 12/01 - 12/01
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_TV_DISPLAY_SHARE) | OW_LAO.VW_CRAWLING_AP1_TV_DISPLAY_SHARE | [7 empty] | 3 | 1 | 46034 | 46034 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [20 empty] | 12/01 - 12/01
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_AP1_WM_DISPLAY_SHARE) | OW_LAO.VW_CRAWLING_AP1_WM_DISPLAY_SHARE | [7 empty] | 3 | 1 | 46034 | 46034 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [20 empty] | 12/01 - 12/01
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE) | OW_LAO.VW_CRAWLING_ONLINE_PRICE | [7 empty] | 3 | 1 | 46034 | 46034 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [20 empty] | 12/01 - 12/01
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE) | OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE | [7 empty] | 3 | 1 | 46034 | 46034 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [20 empty] | 12/01 - 12/01
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE_TABLET) | OW_LAO.VW_CRAWLING_ONLINE_PRICE_DISPLAY_SHARE_TABLET | [5 empty] | Done |  | 3 | 1 | 46034 | 46034 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [20 empty] | 12/01 - 12/01
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET) | OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET | [7 empty] | 3 | 1 | 46035 | 46035 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [20 empty] | 13/01 - 13/01
| VIEW | (VIEW - OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET_TEST) | OW_LAO.VW_CRAWLING_ONLINE_PRICE_TABLET_TEST | [7 empty] | 3 | 1 | 46035 | 46035 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [20 empty] | 13/01 - 13/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_ESTORE_URL_SKU) | OW_LAO.PROC_CRAWLING_AP1_ESTORE_URL_SKU | [7 empty] | 4 | 1 | 46035 | 46035 | ["['[(TABLE - OW_LAO.TMP_MAP_ESTORE_URL_SKU)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Check |  |  | 2 |  | 0 | [20 empty] | 13/01 - 13/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_PT1) | OW_LAO.PROC_CRAWLING_AP1_NPC_PT1 | [7 empty] | 4 | 1 | 46035 | 46035 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Check |  |  | 2 |  | 0 | [20 empty] | 13/01 - 13/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1) | OW_LAO.PROC_CRAWLING_AP1_REF_PT1 | [7 empty] | 4 | 1 | 46035 | 46035 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Check |  |  | 2 |  | 0 | [20 empty] | 13/01 - 13/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_PT1_V2) | OW_LAO.PROC_CRAWLING_AP1_REF_PT1_V2 | [7 empty] | 4 | 1 | 46035 | 46035 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Check |  |  | 2 |  | 0 | [20 empty] | 13/01 - 13/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1) | OW_LAO.PROC_CRAWLING_AP1_TV_PT1 | [7 empty] | 4 | 1 | 46035 | 46035 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING)]']"] | 1 | Check |  |  | 2 |  | 0 | [20 empty] | 13/01 - 13/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_PT1_V2) | OW_LAO.PROC_CRAWLING_AP1_TV_PT1_V2 | [7 empty] | 4 | 1 | 46035 | 46035 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING)]']"] | 1 | Check |  |  | 2 |  | 0 | [20 empty] | 13/01 - 13/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1) | OW_LAO.PROC_CRAWLING_AP1_WM_PT1 | [7 empty] | 4 | 1 | 46035 | 46035 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Check |  |  | 2 |  | 0 | [20 empty] | 13/01 - 13/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_PT1_V2) | OW_LAO.PROC_CRAWLING_AP1_WM_PT1_V2 | [7 empty] | 4 | 1 | 46035 | 46035 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | Check |  |  | 2 |  | 0 | [20 empty] | 13/01 - 13/01
| PROCEDURE | (PROCEDURE - OW_MD.PROC_INGESTION_ODS_MEDALIA_TARGET_NPS) | OW_MD.PROC_INGESTION_ODS_MEDALIA_TARGET_NPS | [7 empty] | 4 | 1 | 46036 | 46036 | ["['[(TABLE - OW_MD.RAW_MEDALIA_TARGET_NPS)'", "'(TABLE - OW_MD.ODS_MEDALIA_TARGET_NPS)]']"] | 1 | Check |  |  | 2 |  | 0 | [20 empty] | 14/01 - 14/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_CRAWLER_STATUS) | OW_LAO.PROC_CRAWLING_AP1_CRAWLER_STATUS | [7 empty] | 4 | 1 | 46036 | 46036 | ["['[(TABLE - OW_LAO.CRAWLER_STATUS)'", "'(TABLE - OW_LAO.CRAWLER_PROCESS_LIST)]']"] | 0 | Check |  |  | 2 |  | 0 | [20 empty] | 14/01 - 14/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING) | OW_LAO.PROC_GSMARENA_MAPPING | [7 empty] | 4 | 1 | 46036 | 46036 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING_KEY)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Check |  |  | 2 |  | 0 | [20 empty] | 14/01 - 14/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_GSMARENA_MAPPING_1_0) | OW_LAO.PROC_GSMARENA_MAPPING_1_0 | [7 empty] | 4 | 1 | 46036 | 46036 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING_KEY)'", "'(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Check |  |  | 2 |  | 0 | [20 empty] | 14/01 - 14/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION) | OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES_VALIDATION | LAO EStore | r.bojart |  | yes | 3 | To be migrated |  | 4 | 1 | 46036 | 46036 | ["['[(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES)]']"] | 0 | Check |  |  | 2 |  | 0 | [20 empty] | 14/01 - 14/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1) | OW_LAO.PROC_CRAWLING_AP1_IM_PT1 | [7 empty] | 4 | 1 | 46036 | 46036 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 14/01 - 14/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_DUEK) | OW_LAO.PROC_CRAWLING_AP1_IM_PT1_DUEK | [7 empty] | 4 | 1 | 46036 | 46036 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 14/01 - 14/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HIST) | OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HIST | [7 empty] | 4 | 1 | 46036 | 46036 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 14/01 - 14/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HISTORICO) | OW_LAO.PROC_CRAWLING_AP1_IM_PT1_HISTORICO | [7 empty] | 4 | 1 | 46036 | 46036 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 14/01 - 14/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC | [7 empty] | 4 | 1 | 46036 | 46036 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 14/01 - 14/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_REF_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_REF_SITE_MAPPING_MERGE_AUTOMATIC | [7 empty] | 4 | 1 | 46037 | 46037 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_REF_SITE_SPEC_MAPPING)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 15/01 - 15/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_RETRY_PRODUCTS) | OW_LAO.PROC_CRAWLING_AP1_RETRY_PRODUCTS | [7 empty] | 4 | 1 | 46037 | 46037 | ["['[(TABLE - OW_LAO.CRAWLER_PROCESS_LIST)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 15/01 - 15/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TABLET_PT1) | OW_LAO.PROC_CRAWLING_AP1_TABLET_PT1 | [7 empty] | 4 | 1 | 46037 | 46037 | ["['[(TABLE - OW_LAO.MP_GSMARENA_MERGE_DATA_MAPPING)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 15/01 - 15/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_TV_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_TV_SITE_MAPPING_MERGE_AUTOMATIC | [7 empty] | 4 | 1 | 46037 | 46037 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_TV_SITE_SPEC_MAPPING)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 15/01 - 15/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WERABLES_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_WERABLES_SITE_MAPPING_MERGE_AUTOMATIC | [7 empty] | 4 | 1 | 46037 | 46037 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_NPC_SITE_SPEC_MAPPING)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 15/01 - 15/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WM_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_WM_SITE_MAPPING_MERGE_AUTOMATIC | [7 empty] | 4 | 1 | 46037 | 46037 | ["['[(TABLE - OW_LAO.MP_CRAWLING_AP1_WM_SITE_SPEC_MAPPING)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 15/01 - 15/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_1) | OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_1 | [7 empty] | 4 | 1 | 46037 | 46037 | ["['[(TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 15/01 - 15/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_2) | OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_2 | [7 empty] | 4 | 1 | 46037 | 46037 | ["['[(TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 15/01 - 15/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_3) | OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_3 | [7 empty] | 4 | 1 | 46037 | 46037 | ["['[(TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 15/01 - 15/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_4) | OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_4 | [7 empty] | 4 | 1 | 46037 | 46037 | ["['[(TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 15/01 - 15/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_5) | OW_SEDA_S.PROC_TF_ORDER_OPERATION_OUTBOUND_HOLIDAY_5 | [7 empty] | 4 | 1 | 46038 | 46038 | ["['[(TABLE - OW_SEDA_S.ODS_ERP_OUTBOUND_PENTAHO1)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 16/01 - 16/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MKP) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MKP | [7 empty] | 4 | 1 | 46038 | 46038 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MKP)]']"] | 0 | Check |  |  | 1 |  | 0 | [20 empty] | 16/01 - 16/01
| PROCEDURE | (PROCEDURE - OW_LAO.UPDATE_SALES_WEEKLY_MONITORING) | OW_LAO.UPDATE_SALES_WEEKLY_MONITORING | LAO EStore | r.bojart |  | yes | 3 | To be migrated |  | 4 | 1 | 46038 | 46038 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING)'", "'(TABLE - OW_LAO.ODS_SALES_DEDUCTION_VALIDATION_DAILY_EDI_01_05W)]']"] | 1 | Migrar ph2 |  |  | 2 |  | 0 | [20 empty] | 16/01 - 16/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ATU_LAO_SALES_DEDUCTION_MONITORING_STATUS_HIST) | OW_LAO.PROC_ATU_LAO_SALES_DEDUCTION_MONITORING_STATUS_HIST | [7 empty] | 4 | 1 | 46038 | 46038 | ["['[(TABLE - OW_LAO.FT_LAO_SALES_DEDUCTION_WEEKLY_MONITORING)]']"] | 1 | Migrar ph2 |  |  | 1 |  | 0 | [20 empty] | 16/01 - 16/01
| PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_PREPARE) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_PREPARE | LAO EStore | r.bojart |  | yes | 3 | To be migrated |  | 4 | 1 | 46038 | 46038 | ["['[(TABLE - OW_LAO.MONITORING_PARAMETERS)'", "'(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [20 empty] | 16/01 - 16/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_IBGE_INFO) | OW_SEDA_S.PRC_CE_UPDATE_IBGE_INFO |  |  |  | No | No |  |  | 4 | 1 | 46038 | 46038 | ["['[(TABLE - OW_SEDA_S.MAP_CE_SETOR_CENSITARIO_2010)'", "'(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [20 empty] | 16/01 - 16/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_UPDATE_PIN_TO_PIN) | OW_SEDA_S.PRC_UPDATE_PIN_TO_PIN |  |  |  | No | No |  |  | 4 | 1 | 46038 | 46038 | ["['[(TABLE - OW_SEDA_S.MAP_PIN_TO_PIN_BF_19)'", "'(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [20 empty] | 16/01 - 16/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX) | OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX |  |  |  | No | No |  |  | 4 | 1 | 46038 | 46038 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [20 empty] | 16/01 - 16/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX_HIST_2) | OW_SEDA_S.PRC_WEBPRICE_HOURLY_MX_HIST_2 |  |  |  | No | No |  |  | 4 | 1 | 46038 | 46038 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.MAP_MX_WEBPRICE_CODIGO_INTERNO)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [20 empty] | 16/01 - 16/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_WEBPRICE_UPDT_RECENT_PRICE) | OW_SEDA_S.PRC_WEBPRICE_UPDT_RECENT_PRICE |  |  |  | No | No |  |  | 4 | 1 | 46038 | 46038 | ["['[(TABLE - OW_SEDA_S.ODS_CE_WEBPRICE_API)'", "'(TABLE - OW_SEDA_S.ODS_WEBPRICE_TRACKING_DAILY_TV)]']"] | 0 | Migrar ph2 |  |  | 2 |  | 0 | [20 empty] | 16/01 - 16/01
| PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_POST_EXECUTION) | OW_LAO.MONITORING_EXECUTIONS_POST_EXECUTION | LAO EStore | r.bojart |  | yes | 3 | To be migrated |  | 4 | 1 | 46041 | 46041 | ["['[(TABLE - OW_LAO.MONITORING_EXECUTIONS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 19/01 - 19/01
| PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_DEFAULT) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_DEFAULT | LAO EStore | r.bojart |  | yes | 3 | To be migrated |  | 4 | 1 | 46041 | 46041 | ["['[(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 19/01 - 19/01
| PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_JENKINS) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_JENKINS | LAO EStore | r.bojart |  | yes | 3 | To be migrated |  | 4 | 1 | 46041 | 46041 | ["['[(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 19/01 - 19/01
| PROCEDURE | (PROCEDURE - OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_TMC) | OW_LAO.MONITORING_EXECUTIONS_RESULTS_UPDATE_TMC | LAO EStore | r.bojart |  | yes | 3 | To be migrated |  | 4 | 1 | 46041 | 46041 | ["['[(TABLE - OW_LAO.MONITORING_EXECUTIONS_RESULTS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 19/01 - 19/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.INGEST_OUTBOUND_TRACKING_SCM) | OW_SEDA_S.INGEST_OUTBOUND_TRACKING_SCM | [7 empty] | 4 | 1 | 46041 | 46041 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING_SCM)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 19/01 - 19/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING) | OW_SEDA_S.PRC_MX_API_OMNITRACKING | [7 empty] | 4 | 1 | 46041 | 46041 | ["['[(TABLE - OW_SEDA_S.RAW_SEDA_API_OMNITRACKING)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 19/01 - 19/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING_FULL) | OW_SEDA_S.PRC_MX_API_OMNITRACKING_FULL | [7 empty] | 4 | 1 | 46041 | 46041 | ["['[(TABLE - OW_SEDA_S.RAW_SEDA_API_OMNITRACKING)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 19/01 - 19/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_API_OMNITRACKING_WEEKLY) | OW_SEDA_S.PRC_MX_API_OMNITRACKING_WEEKLY | [7 empty] | 4 | 1 | 46041 | 46041 | ["['[(TABLE - OW_SEDA_S.RAW_SEDA_API_OMNITRACKING)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 19/01 - 19/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_GABARITO_CHECKLIST_EXECUCAO) | OW_SEDA_S.PRC_TT_GABARITO_CHECKLIST_EXECUCAO |  |  |  | No | No |  |  | 4 | 1 | 46041 | 46041 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 19/01 - 19/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_GABARITO_CHECKLIST_EXECUCAO_785) | OW_SEDA_S.PRC_TT_GABARITO_CHECKLIST_EXECUCAO_785 |  |  |  | No | No |  |  | 4 | 1 | 46041 | 46041 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 19/01 - 19/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_UPDT_FLOORSHARE) | OW_SEDA_S.PRC_TT_UPDT_FLOORSHARE |  |  |  | No | No |  |  | 4 | 1 | 46042 | 46042 | ["['[(TABLE - OW_SEDA_S.FT_CE_PRICE_STORE)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 20/01 - 20/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TV_UPDT_INCH_RANGE) | OW_SEDA_S.PRC_TV_UPDT_INCH_RANGE | [7 empty] | 4 | 1 | 46042 | 46042 | ["['[(TABLE - OW_SEDA_S.MAP_CE_PRODUCTS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 20/01 - 20/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_B2B) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_B2B | [7 empty] | 4 | 1 | 46042 | 46042 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_B2B)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 20/01 - 20/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BREA) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BREA | [7 empty] | 4 | 1 | 46042 | 46042 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BREA)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 20/01 - 20/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BRSHOP) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_BRSHOP | [7 empty] | 4 | 1 | 46042 | 46042 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_BRSHOP)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 20/01 - 20/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EPP2) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EPP2 | [7 empty] | 4 | 1 | 46042 | 46042 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EPP2)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 20/01 - 20/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EST) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_EST | [7 empty] | 4 | 1 | 46042 | 46042 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_EST)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 20/01 - 20/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MEMBERS) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_MEMBERS | [7 empty] | 4 | 1 | 46042 | 46042 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_MEMBERS)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 20/01 - 20/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_PARC) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_PARC | [7 empty] | 4 | 1 | 46042 | 46042 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_PARC)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 20/01 - 20/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_RESID) | OW_SEDA_S.PROC_UPDATE_DATE_AFTER_SALES_RESID | [7 empty] | 4 | 1 | 46042 | 46042 | ["['[(TABLE - OW_SEDA_S.TMP_DATA_API_AFTER_SALES_DETAIL_RESID)]']"] | 0 | Migrar ph2 |  |  | 1 |  | 0 | [21 empty] | 20/01 - 20/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_STORE_EDI) | OW_SEDA_S.PRC_CE_STORE_EDI |  |  |  | No | No |  |  | 4 | 1 | 46043 | 46043 | ["['[(TABLE - OW_SEDA_S.FT_CE_PIVOT)'", "'(TABLE - OW_SEDA_S.ODS_CE_STORE_EDI)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 2 |  | 0 | [21 empty] | 21/01 - 21/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_GFK) | OW_SEDA_S.PRC_CE_UPDATE_GFK | [7 empty] | 4 | 1 | 46043 | 46043 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 |  | 0 | [21 empty] | 21/01 - 21/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDATE_STORE_NAME) | OW_SEDA_S.PRC_CE_UPDATE_STORE_NAME |  |  |  | No | No |  |  | 4 | 1 | 46043 | 46043 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 |  | 0 | [21 empty] | 21/01 - 21/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_UPDT_SHOPPING_W_BRANDSHOP) | OW_SEDA_S.PRC_CE_UPDT_SHOPPING_W_BRANDSHOP |  |  |  | No | No |  |  | 4 | 1 | 46043 | 46043 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 |  | 0 | [21 empty] | 21/01 - 21/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_AV_CHECKLIST_DE_EXECUCAO_785) | OW_SEDA_S.PRC_TT_AV_CHECKLIST_DE_EXECUCAO_785 |  |  |  | No | No |  |  | 4 | 1 | 46043 | 46043 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 |  | 0 | [21 empty] | 21/01 - 21/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_RAC_CHECKLIST_DE_EXECUCAO_785) | OW_SEDA_S.PRC_TT_RAC_CHECKLIST_DE_EXECUCAO_785 |  |  |  | No | No |  |  | 4 | 1 | 46043 | 46043 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 |  | 0 | [21 empty] | 21/01 - 21/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_REF_CHECKLIST_DE_EXECUCAO_785) | OW_SEDA_S.PRC_TT_REF_CHECKLIST_DE_EXECUCAO_785 |  |  |  | No | No |  |  | 4 | 1 | 46043 | 46043 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 |  | 0 | [21 empty] | 21/01 - 21/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_TV_CHECKLIST_DE_EXECUCAO) | OW_SEDA_S.PRC_TT_TV_CHECKLIST_DE_EXECUCAO |  |  |  | No | No |  |  | 4 | 1 | 46043 | 46043 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 |  | 0 | [21 empty] | 21/01 - 21/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_TV_CHECKLIST_DE_EXECUCAO_785) | OW_SEDA_S.PRC_TT_TV_CHECKLIST_DE_EXECUCAO_785 |  |  |  | No | No |  |  | 4 | 1 | 46043 | 46043 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 |  | 0 | [21 empty] | 21/01 - 21/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_TT_WM_CHECKLIST_DE_EXECUCAO_785) | OW_SEDA_S.PRC_TT_WM_CHECKLIST_DE_EXECUCAO_785 |  |  |  | No | No |  |  | 4 | 1 | 46043 | 46043 | ["['[(TABLE - OW_SEDA_S.MAP_CE_STORES)]']"] | 0 | Migrar ph2 SEDA RM |  |  | 1 |  | 0 | [21 empty] | 21/01 - 21/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.CONN_TO_SEDA) | OW_SEDA_S.CONN_TO_SEDA |  |  |  | No | No |  |  | 4 | 1 | 46044 | 46044 | ["['[(TABLE - OW_SEDA_S.EDI_DATA_RAW)]']"] | 0 | Migrar ph2: SEDA RM |  |  | 1 |  | 0 | [21 empty] | 22/01 - 22/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT_RETAILERS) | OW_SEDA_S.PRC_MX_FT_SEDA_EDI_INPUT_RETAILERS |  |  |  | No | No |  |  | 4 | 1 | 46044 | 46044 | ["['[(TABLE - OW_SEDA_S.EDI_DATA_RAW)]']"] | 0 | Migrar ph2: SEDA RM |  |  | 1 |  | 0 | [21 empty] | 22/01 - 22/01
| PROCEDURE | (PROCEDURE - OW_SDSLA.PROC_TABLEAU_DASHBOARDS_MACHINE_STATUS) | OW_SDSLA.PROC_TABLEAU_DASHBOARDS_MACHINE_STATUS | [7 empty] | 4 | 1 | 46044 | 46044 | ["['[(TABLE - OW_SDSLA.RAW_TABLEAU_DASHBOARDS_MACHINE_STATUS)]']"] | 0 | Migrar ph2: Tableau |  |  | 1 |  | 0 | [21 empty] | 22/01 - 22/01
| PROCEDURE | (PROCEDURE - OW_SEDA_S.PRC_CE_AMAZON_PRIME_DAY) | OW_SEDA_S.PRC_CE_AMAZON_PRIME_DAY | [7 empty] | 4 | 1 | 46044 | 46044 | ["['[(TABLE - OW_SEDA_S.ODS_CE_AMAZON_SELL_OUT_FCST)]']"] | 0 | check |  |  | 1 |  | 0 | [21 empty] | 22/01 - 22/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_VC_PT1) | OW_LAO.PROC_CRAWLING_AP1_VC_PT1 | [5 empty] | Done |  | 4 | 1 | 46044 | 46044 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [21 empty] | 22/01 - 22/01
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WERABLES_PT1) | OW_LAO.PROC_CRAWLING_AP1_WERABLES_PT1 | [7 empty] | 4 | 1 | 46044 | 46044 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [21 empty] | 22/01 - 22/01
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELIGIBLE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELIGIBLE | TBC | [6 empty] | 4 | 1 | 45931 | 45931 |  | 0 | Prioritarias | [27 empty] | Checar e incluir para a migração
Control Tower | PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_EPROMOTER_UPDATE) | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_EPROMOTER_UPDATE | TBC | [6 empty] | 4 | 1 | 45931 | 45931 |  | 0 | Prioritarias | [27 empty] | Checar e incluir para a migração
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMETNO_ADDITIONAL_INFO) | OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMETNO_ADDITIONAL_INFO | [7 empty] | 4 | 1 | 45931 | 45931 |  | 0 | Prioritarias
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING |  |  |  | yes |  | Done |  | 4 | 1 | 45937 | 45937 |  | 1 | r.bojart |  |  | 1 |  | 0
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING ) | OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING | [5 empty] | Done | SIM | 4 | 1 | 45937 | 45937 |  | 1 | r.bojart |  |  | 1 |  | 0
| PROCEDURE | (PROCEDURE - OW_MD.PROC_DIM_CUSTOMER_POLICY) | OW_MD.PROC_DIM_CUSTOMER_POLICY | [5 empty] | Done |  | 4 | 1 | 45951 | 45951 |  |  | r.bojart |  |  | 1 |  | 0
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC | [5 empty] | ERRO |  | 4 | 1 | 45964 | 45964 | [5 empty] | 1 |  | 0
| PROCEDURE | (PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC) | OW_LAO.PROC_CRAWLING_AP1_NPC_SITE_MAPPING_MERGE_AUTOMATIC | [5 empty] | ERRO |  | 4 | 1 | 45964 | 45964
| TABLE | (TABLE - U_PRJ_ECOM.VTEX_SSG_UY_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.VTEX_SSG_UY_RATES_AND_BENEFITS_DATA | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.VTEX_SSG_PY_RATES_AND_BENEFITS_DATA) | U_PRJ_ECOM.VTEX_SSG_PY_RATES_AND_BENEFITS_DATA | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_TEST) | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_TEST | LAO EStore | r.bojart |  | yes | 2 | TBC
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_SALES) | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_SALES | LAO EStore | r.bojart |  | yes | 2 | TBC
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_ORDER | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_ORDER | LAO EStore | r.bojart |  | yes | 2 | TBC
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_EPP_ORDER) | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST_EPP_ORDER | LAO EStore | r.bojart |  | yes | 2 | TBC
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST) | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_TST | LAO EStore | r.bojart |  | yes | 2 | TBC
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_FT_TST) | U_PRJ_ECOM.TMP_RAW_VTEX_TRADE_IN_SEDA_FT_TST | LAO EStore | r.bojart |  | yes | 2 | TBC
| TABLE | (TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_MASTER_DATA_CL_TST) | U_PRJ_ECOM.TMP_RAW_VTEX_MASTER_DATA_CL_TST | LAO EStore | r.bojart |  | yes | 2 | TBC
| TABLE | (TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR_TST) | OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR_TST | LAO EStore | r.bojart |  | yes | 5 | TBC
| TABLE | (TABLE - OW_LAO.TEMP_PARTNER_LEVEL_SMB_SEASA) | OW_LAO.TEMP_PARTNER_LEVEL_SMB_SEASA | LAO EStore | r.bojart |  | yes | 2 | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.TEMP_ODS_SELA_API_MAGENTO_INSERT) | U_PRJ_ECOM.TEMP_ODS_SELA_API_MAGENTO_INSERT | LAO EStore | r.bojart |  | yes | 1 | To be migrated
Control Tower | TABLE | (TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_FILTER) | OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE_FILTER | LAO EStore | r.bojart |  | yes | 1 | Done
| TABLE | (TABLE - OW_LAO.TEMP_DIM_UNIQUE_ID_TF) | OW_LAO.TEMP_DIM_UNIQUE_ID_TF | LAO EStore | r.bojart |  | yes | 2 | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.STG_VTEX_ORDER_SEASA_VISUAR_CANCEL) | U_PRJ_ECOM.STG_VTEX_ORDER_SEASA_VISUAR_CANCEL | LAO EStore | r.bojart |  | yes | 2 | Done
| TABLE | (TABLE - U_PRJ_ECOM.STG_VTEX_ORDER_SEASA_MIRGOR_CANCEL) | U_PRJ_ECOM.STG_VTEX_ORDER_SEASA_MIRGOR_CANCEL | LAO EStore | r.bojart |  | yes | 2 | Done
| TABLE | (TABLE - OW_LAO.STG_STOCKOUT_VTEX_GLOBALBI_SEDA) | OW_LAO.STG_STOCKOUT_VTEX_GLOBALBI_SEDA | LAO EStore | r.bojart |  | yes | 4 | Done
| TABLE | (TABLE - OW_LAO.STG_STOCKOUT_VTEX_GLOBALBI_SEASA) | OW_LAO.STG_STOCKOUT_VTEX_GLOBALBI_SEASA | LAO EStore | r.bojart |  | yes | 4 | Done
| TABLE | (TABLE - OW_LAO.STG_SELA_SALES_COUPONS_ITEMS) | OW_LAO.STG_SELA_SALES_COUPONS_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done
| TABLE | (TABLE - OW_LAO.STG_SELA_SALES_COUPONS) | OW_LAO.STG_SELA_SALES_COUPONS | LAO EStore | r.bojart |  | yes | 2 | Done
| TABLE | (TABLE - OW_LAO.STG_SELA_ORDERS_COUPONS_STATUS_HISTORY) | OW_LAO.STG_SELA_ORDERS_COUPONS_STATUS_HISTORY | LAO EStore | r.bojart |  | yes | 2 | Done
| TABLE | (TABLE - OW_LAO.STG_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS) | OW_LAO.STG_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS | LAO EStore | r.bojart |  | yes | 2 | Done
| TABLE | (TABLE - OW_LAO.STG_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO) | OW_LAO.STG_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO | LAO EStore | r.bojart |  | yes | 2 | Done
| TABLE | (TABLE - OW_LAO.STG_SELA_CUSTOM_ORDERS_ITEMS) | OW_LAO.STG_SELA_CUSTOM_ORDERS_ITEMS | LAO EStore | r.bojart |  | yes | 2 | Done
| TABLE | (TABLE - OW_LAO.STG_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS) | OW_LAO.STG_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS | LAO EStore | r.bojart |  | yes | 2 | Done
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_SHIPPING | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_PAYMENT | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_PACKAGE | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_ITEM_COMPONENTS | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER_ITEM | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_UY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_SHIPPING) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_SHIPPING | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_PAYMENT) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_PAYMENT | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_PACKAGE) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_PACKAGE | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_ITEM_COMPONENTS) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_ITEM_COMPONENTS | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_ITEM) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER_ITEM | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER) | U_PRJ_ECOM.RAW_VTEX_SSG_PY_SALES_ORDER | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - OW_LAO.ODS_ECOM_ORDERS_B5Q5_HYBRIS) | OW_LAO.ODS_ECOM_ORDERS_B5Q5_HYBRIS | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - OW_LAO.ODS_ECOM_ORDERS_B5Q5_ARGENTINA) | OW_LAO.ODS_ECOM_ORDERS_B5Q5_ARGENTINA | LAO EStore | r.bojart |  |  |  | TBC
| TABLE | (TABLE - OW_LAO.ODS_ECOM_ORDERS_B5Q5) | OW_LAO.ODS_ECOM_ORDERS_B5Q5 | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - U_PRJ_ECOM.ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN) | U_PRJ_ECOM.ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - OW_LAO.ODS_ECOM_ANALYTICS_ADOBE) | OW_LAO.ODS_ECOM_ANALYTICS_ADOBE | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - OW_LAO.ODS_ECOM_ADOBE_ANALYTICS_OVERALL) | OW_LAO.ODS_ECOM_ADOBE_ANALYTICS_OVERALL | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - OW_LAO.ODS_ECOM_ADOBE_ANALYTICS_B5Q5) | OW_LAO.ODS_ECOM_ADOBE_ANALYTICS_B5Q5 | LAO EStore | r.bojart |  |  |  | TBC
| TABLE | (TABLE - U_PRJ_ECOM.LOG_PROCESSCONTROL) | U_PRJ_ECOM.LOG_PROCESSCONTROL | LAO EStore | r.bojart |  | yes | 1 | Done
| TABLE | (TABLE - U_PRJ_ECOM_SYNAPCOM.FT_ECOM_ORDER_PAYMENT) | U_PRJ_ECOM_SYNAPCOM.FT_ECOM_ORDER_PAYMENT | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM_SYNAPCOM.FT_ECOM_ORDER_KIT_COMPONENT) | U_PRJ_ECOM_SYNAPCOM.FT_ECOM_ORDER_KIT_COMPONENT | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM_SYNAPCOM.FT_ECOM_ORDER_ITEM) | U_PRJ_ECOM_SYNAPCOM.FT_ECOM_ORDER_ITEM | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM_SYNAPCOM.FT_ECOM_ORDER) | U_PRJ_ECOM_SYNAPCOM.FT_ECOM_ORDER | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - TGT_SDSLA_ECOM.FT_ECOM_ORDER) | TGT_SDSLA_ECOM.FT_ECOM_ORDER | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - OW_LAO.DIM_SUBSIDIARY_B5Q5) | OW_LAO.DIM_SUBSIDIARY_B5Q5 | LAO EStore | r.bojart |  |  |  | TBC
| TABLE | (TABLE - OW_LAO.DIM_SKU_B5Q5) | OW_LAO.DIM_SKU_B5Q5 | LAO EStore | r.bojart |  |  |  | TBC
| TABLE | (TABLE - OW_LAO.DIM_LAO_CAMPAIGN_TAG_NAME_CADASTRA) | OW_LAO.DIM_LAO_CAMPAIGN_TAG_NAME_CADASTRA | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.DIM_ECOM_STORE) | U_PRJ_ECOM.DIM_ECOM_STORE | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.DIM_ECOM_SKU) | U_PRJ_ECOM.DIM_ECOM_SKU | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM_SYNAPCOM.DIM_ECOM_SKU) | U_PRJ_ECOM_SYNAPCOM.DIM_ECOM_SKU | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.DIM_ECOM_EPP_2) | U_PRJ_ECOM.DIM_ECOM_EPP_2 | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.DIM_ECOM_CHANNEL) | U_PRJ_ECOM.DIM_ECOM_CHANNEL | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM_SYNAPCOM.DIM_CUSTOMER) | U_PRJ_ECOM_SYNAPCOM.DIM_CUSTOMER | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - OW_LAO.DIM_AFFILIATE_CHANNEL) | OW_LAO.DIM_AFFILIATE_CHANNEL | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - OW_LAO.DIM_ACCESS_CODE) | OW_LAO.DIM_ACCESS_CODE | LAO EStore | r.bojart |  |  |  | Done
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_SITE_FIELD_TYPE) | U_PRJ_ECOM.BI_ECOM_SITE_FIELD_TYPE | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_SITE_EPP) | U_PRJ_ECOM.BI_ECOM_SITE_EPP | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_SITE) | U_PRJ_ECOM.BI_ECOM_SITE | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_SELA_EPP) | U_PRJ_ECOM.BI_ECOM_SELA_EPP | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_SELA) | U_PRJ_ECOM.BI_ECOM_SELA | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_EPP_TYPE) | U_PRJ_ECOM.BI_ECOM_EPP_TYPE | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_EPP_SITE) | U_PRJ_ECOM.BI_ECOM_EPP_SITE | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_EPP_LAO) | U_PRJ_ECOM.BI_ECOM_EPP_LAO | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_EPP_GLOBAL) | U_PRJ_ECOM.BI_ECOM_EPP_GLOBAL | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_EPP) | U_PRJ_ECOM.BI_ECOM_EPP | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_CHANNEL_TYPE) | U_PRJ_ECOM.BI_ECOM_CHANNEL_TYPE | LAO EStore | r.bojart |  |  |  | To be migrated
| TABLE | (TABLE - U_PRJ_ECOM.BI_ECOM_B2C_SELA) | U_PRJ_ECOM.BI_ECOM_B2C_SELA | LAO EStore | r.bojart |  |  |  | To be migrated
Control Tower | PROCEDURE | (PROCEDURE - CON_SDSLA.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS) | CON_SDSLA.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS | LAO EStore | r.bojart |  | yes | 7 | To be migrated
Control Tower | PROCEDURE | (PROCEDURE -CON_SDSLA.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS) | CON_SDSLA.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS | LAO EStore | r.bojart |  | yes | 7 | To be migrated
| PROCEDURE | (PROCEDURE -OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN_TARGETS) | OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN_TARGETS | LAO EStore | r.bojart |  |  |  | Not to be migrated | [35 empty] | Confirmed by r.bojart via knox on 21/11
| PROCEDURE | (PROCEDURE -OW_LAO.MASTERDATA_SMB_CUIT_DELET) | OW_LAO.MASTERDATA_SMB_CUIT_DELET | LAO EStore | r.bojart |  | yes | 2 | To be migrated
| PROCEDURE | (PROCEDURE -OW_LAO.MASTERDATA_SMB_CUIT_UPDATE) | OW_LAO.MASTERDATA_SMB_CUIT_UPDATE | LAO EStore | r.bojart |  | yes | 2 | To be migrated
| PROCEDURE | (PROCEDURE -OW_LAO.PROC_DIM_CAMPAIGN_TAG_NAME_CADASTRA_UPDATE) | OW_LAO.PROC_DIM_CAMPAIGN_TAG_NAME_CADASTRA_UPDATE | LAO EStore | r.bojart |  | yes | 5 | To be migrated
| PROCEDURE | (PROCEDURE -OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP_HOMOLOG) | OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP_HOMOLOG | LAO EStore | r.bojart |  |  |  | Not to be migrated | [35 empty] | Confirmed by r.bojart via knox on 21/11
| PROCEDURE | (PROCEDURE -OW_MD.DIM_SALES_CHANNELS_PROMOTIONS_GENERATE) | OW_MD.DIM_SALES_CHANNELS_PROMOTIONS_GENERATE | LAO EStore | r.bojart |  | yes | 2 | To be migrated
| PROCEDURE | (PROCEDURE -U_PRJ_ECOM.PROC_SERIES_GENERATE_DATE_FORMATED) | U_PRJ_ECOM.PROC_SERIES_GENERATE_DATE_FORMATED | LAO EStore | r.bojart |  |  |  | To be migrated
| PROCEDURE | (PROCEDURE -U_R_BOJART.HYBRIS_MELI_FINANCIAL_RECONCILIATION) | U_R_BOJART.HYBRIS_MELI_FINANCIAL_RECONCILIATION | LAO EStore | r.bojart |  |  |  | To be migrated