## Planilha1
Task Name | Responsável | Status | Observação | Level | Duration | Start | End | Dependencies | PRIORITY | MIGRATION_CLASS | DISK_GB | TABLE_TYPE | Qty Dependencies | Referenced | Qty Referenced | W35-2025 | W36-2025 | W37-2025 | W38-2025 | W39-2025 | W40-2025 | W41-2025 | W42-2025 | W43-2025 | W44-2025 | W45-2025 | W46-2025 | W47-2025 | W48-2025 | W49-2025 | W50-2025 | W51-2025 | W52-2025 | W01-2026 | W02-2026 | W03-2026 | W04-2026
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA_GLOBAL_BI) | Felipe | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOMAIN) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_DOMAIN)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_ODS_AFTER_SALES_CANCELATION) | Cassio | ERRO | Table "OW_LAO.TMP_AFTER_SALES_ORDER_NEW" does not exist -- Criada | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_PO_ORDER_ID_PO_VTEX_TEMP)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_COURIER) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_COURIER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_DOCK) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_DOCK)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOCK)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_REGION) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - U_PRJ_ECOM.PROC_RAW_VTEX_SEASA_TRADEIN_FEED_HOMOLOG) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS) | Cassio | ERRO | Relation "OW_LAO.DIM_PAYMENT_PAYMENT_STATUS_MAPPING_HOMOLOG" does not exist -- Criada | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS_HOMOLOG)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_SKU) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.TF_VTEX_SSG_BR_INVENTORY_SKU)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SKU_BY_REF_ID)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_SKU)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_BY_SKU)'", "'(TABLE - OW_MD.TF_VTEX_SSG_BR_INVENTORY_WAREHOUSE)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_BY_SKU)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.DIM_ECOM_PARTNER_LEVEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_SEDA_S.PROC_FT_OST_INDUE_PENDING_PAYMENT) | Bruno | ERRO | Relation "OW_LAO.RAW_SEDA_OST_MKTP_MAGAZINE_LUIZA" does not exist | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
Relation "OW_LAO.RAW_SEDA_OST_MKTP_MERCADO_LIVRE" does not exist
Relation "OW_LAO.RAW_SEDA_OST_MKTP_AMAZON" does not exist - ERROR: Schema "U_JM_BRANDAO" does not exist
(PROCEDURE - OW_LAO.PROC_D2C_NERP_WAREHOUSE_OPERATION) | Felipe | ERRO | Relation "OW_LAO.RAW_SEDA_OST_MKTP_MERCADO_LIVRE" does not exist -- CRIADA | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_WAREHOUSE_OPERATION)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.ODS_WMS_PICKING_PACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_WH_OPERATION_PENDING) | Felipe | ERRO | Relation "OW_MD.DIM_PLANT" does not exist | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.FT_D2C_NERP_WH_OPERATION_PENDING)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
ERROR: Non-equality correlated subquery expression is not supported
(PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TMP_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE_HOMOLOG) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_GSCM_PSI) | Felipe | ERRO | Relation "OW_MD.DIM_PLANT" does not exist | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_MB51_GR_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_D2C_NERP_GSCM_PSI)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
ERROR: Syntax error at or near "EOL" at character 35
(PROCEDURE - OW_LAO.PROC_FT_NERP_SALES_PROGRESS_KPI) |  |  | ScriptVazio - Criar script para Vertica ¦Quase 2 mil linhas | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES)'", "'(TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.RAW_DATA_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.RAW_DATA_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_PAYMENT_ITAU) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_TESTE) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM_ORDER_GLOBAL_BI) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_RAW_VTEX_SSG_BR_SHOP_SALES_GLOBAL_BI) | Felipe | ERRO | Relation "u_prj_ecom.raw_feed_send_estore" does not exist ¦ -- Já existe no schema OW_LAO | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_PO_HYBRIS_SALES) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES_BY_HOUR_KPI)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION) | Felipe | OK | 2 Procedures (uma sem parâmetros e uma com parâmetros) | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_PROCESS) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PROMOTION_TMP) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_B2B_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_EPP_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PROMOTION_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_PROMOTION_ITEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT1) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_AR_TABLE_WEEK)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_D2C_AR_TABLE_WEEK)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.FT_D2C_NERP_ORDER_PENDING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PAYMENT_SKU) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TF_D2C_VTEX_PAYMENT_SKU)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 7 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_ORDER_STATUS) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_MD.TF_VTEX_ORDER_STATUS_01)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_STATUS) | Bruno | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.TF_VTEX_PAYMENT_STATUS_01)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_DELIVERY_PENDING) | Felipe | ERRO | Relation "OW_MD.DIM_PLANT" does not exist | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.FT_D2C_NERP_DELIVERY_PENDING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  | 0 |  |  | 08/09 - 08/09
ERROR: Non-equality correlated subquery expression is not supported
(PROCEDURE - OW_LAO.PROC_D2C_NERP_INVENTORY) | Cassio | OK |  | 4 | 1 | 2025-09-08 | 2025-09-08 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.FT_D2C_NERP_INVENTORY)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 08/09 - 08/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_LEAD_TIME) | Bruno | OK | [Vertica][VJDBC](2783) ERROR: Correlated subquery column in select/gby/oby not supported | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_03)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME)'", "'(TABLE - OW_LAO.FT_D2C_NERP_LEAD_TIME)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_01)'", "'(TABLE - OW_LAO.TF_D2C_NERP_LEAD_TIME_02)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_ORDER_PENDING_OVERVIEW) | Felipe | ERRO | Relation "OW_MD.DIM_PLANT" does not exist | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_D2C_NERP_ORDER_PENDING_OVERVIEW)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_01)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_ORDER_PENDING_OVERVIEW_02)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  | 09/09 - 09/09
Column "PO_WITHOUT_SO" is of type int but expression is of type varchar
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_COMBO) | Bruno | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_COMBO)'", "'(TABLE - OW_LAO.RAW_HYBRIS_COMBO)'", "'(TABLE - OW_LAO.TMP_ODS_HYBRIS_COMBO)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 5 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SELA_API_MAGENTO) | Cassio | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_SELA_API_MAGENTO)]']"] | 1 | 1.3 Ingestion MAGENTO |  |  | 5 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP) | Bruno | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM) | Cassio | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PACKAGE)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PACKAGE)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_WAREHOUSE) | Bruno | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_LAO.PROC_PMS_DW_UNIFICADA) | Cassio | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.FT_D2C_ONE_VIEW_TABLE)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_LAO.PROC_LAO_CONTROL_TOWER_SELA_SUFIX_SKU_MAPPING) | Felipe | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_MD.PROC_FT_VTEX_PURCHASE_ORDER_TRACKING) | Cassio | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_TRACKING_01)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 12 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_MD.PROC_VTEX_PURCHASE_ORDER_PAYMENT) | Cassio | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_01)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_02)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_03)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_PAYMENT_04)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_AFFILIATE) | Bruno | OK | ERROR: Cannot set a NOT NULL column (SUR_KEY) to a NULL value in INSERT/UPDATE statement | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_AFFILIATE_01)'", "'(TABLE - OW_MD.TF_VTEX_AFFILIATE_02)'", "'(TABLE - OW_MD.TF_VTEX_AFFILIATE_03)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_PAYMENT_GROUP) |  | ERRO | Script Vazio - Criar script para Vertica | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.TF_VTEX_PAYMENT_GROUP_01)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_PURCHASE_ORDER_TRADE_IN) | Bruno | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_MD.TF_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_MD.PROC_DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU) |  | ERRO | Script Vazio - Criar script para Vertica | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU)'", "'(TABLE - OW_MD.TF_VTEX_SSG_BR_SHOP_INVENTORY_SKU)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_INVENTORY) | Bruno | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_WAREHOUSE)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_INVENTORY_SKU)'", "'(TABLE - OW_MD.FT_VTEX_SSG_BR_INVENTORY)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_INVENTORY_WITH_DISPATCHED_RESERVATIONS)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_MD.PROC_FT_VTEX_SSG_BR_SHOP_INVENTORY) | Bruno | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_SKU)'", "'(TABLE - OW_MD.FT_VTEX_SSG_BR_SHOP_INVENTORY)'", "'(TABLE - OW_MD.DIM_VTEX_SSG_BR_SHOP_INVENTORY_WAREHOUSE)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_INVENTORY_WITH_DISPATCHED_RESERVATIONS)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_LAO.PROC_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH) | Bruno | OK | ERROR: Table "OW_LAO.FT_D2C_AR_CREATION_X_OPEN" does not exist ¦" Não existe no Banco " | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_MONTH)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_ALLITEM_WEEK)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_MONTH)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_D2C_AR_CREATION_X_OPEN_OPENITEM_WEEK)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 11 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT1) | Bruno | OK |  | 4 | 1 | 2025-09-09 | 2025-09-09 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_D2C_AR_TABLE_MONTH)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.FT_D2C_AR_TABLE_MONTH)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  | 09/09 - 09/09
(PROCEDURE - OW_LAO.PROC_FT_LAO_GOVERNANCE_ORDERS_KPI) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_DIM_UNIQUE_ID) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_VTEX_PROFILE)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_UNIQUE_ID)'", "'(TABLE - OW_LAO.TMP_DIM_UNIQUE_ID)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_DIM_PRODUCT_MAPPING_LAO) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)'", "'(TABLE - OW_LAO.RAW_LAO_DIM_PRODUCT_MAPPING_APOIO)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_SELA_DETAILS) | Felipe | ERRO | ERROR: Column "datasource_origin_timestamp" is of type timestamp but expression is of type varchar | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)]']"] | 0 | 2.1 Migrar ph1 |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_GLOBALBI) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_UPDATE_PREMIUM_MODELS_WEEKLY_REPROCESS) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR)]']"] | 0 | 3.1 Migrar ph1 |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_NAME_AJUSTE) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_BRASIL) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_BRASIL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_CHILE) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_CHILE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_COLOMBIA) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_COLOMBIA)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_MEXICO) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_MEXICO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_PERU) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_PERU)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_BRASIL) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_BRASIL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_CHILE) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_CHILE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_COLOMBIA) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_COLOMBIA)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_MEXICO) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_MEXICO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_PERU) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_PERU)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_TOKEN_URUGUAY) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_LISTINGS_SALES)'", "'(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_LISTINGS_SALES_URUGUAY)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_NUBIMETRICS_SALES_LISTINGS_URUGUAY) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_RAW_NUBIMETRICS_SALES_LISTINGS_URUGUAY)'", "'(TABLE - OW_LAO.RAW_NUBIMETRICS_SALES_LISTINGS)'", "'(TABLE - OW_LAO.ODS_NUBIMETRICS_SALES_LISTINGS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE_HOMOLOG) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_UPDATE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_TARGETS) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_TARGETS_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_CHANNELS)'", "'(TABLE - OW_LAO.ODS_CAMPAIGN_TARGET_PRODUCTS)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_ADJUSTS)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_CURRENT_YEAR)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_TARGET_CHANNELS_PREVIOUS_YEAR)'", "'(TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN)'", "'(TABLE - OW_LAO.DIM_EXCEL_TARGETS_CAMPAIGN)]']"] | 0 | 2.1 Migrar ph1 |  |  | 9 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_SEDA_S.PROC_FT_OST_AFTERSALES_REFUND) | Bruno |  | ScriptVazio - Criar script para Vertica ¦Quase 4 mil linhas | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA)]']"] | 1 | 3.1 Migrar ph1 |  |  | 18 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_RESID)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA)]']"] | 1 | 3.1 Migrar ph1 |  |  | 18 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.HOMOLOG_PROC_SALES_CAMPAIGN) | Felipe | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME_PREVIOUS_YEAR)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME)'", "'(TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME)]']"] | 0 | 3.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_UPDATE_DIM_CAMPAIGN_NAME) | Felipe | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.TMP_SALES_CAMPAIGN)'", "'(TABLE - OW_LAO.TMP_CAMPAIGN_NAME)'", "'(TABLE - OW_LAO.TMP_UPDATE_CAMPAIGN_NAME)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.TMP_PAYMENT_PAYMENT_TYPE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_STATUS_MAP) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.TMP_PAYMENT_FUNNEL_STATUS)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 0 | 2.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_MONITORING_SKU) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_FIXED_PRICES)'", "'(TABLE - OW_MD.MASTER_TRADE_POLICIES)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_TRADE_POLICIES)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_SKU_BY_REF_ID)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_MD.PROC_DIM_SALES_CHANNEL) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_MD.TMP_SALES_CHANNEL_LAO)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_MD.TMP_SALES_CHANNEL_SEDA)]']"] | 1 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS) | Bruno | ERRO | ERROR: Relation "u_prj_ecom_synapcom.ft_ecom_order" does not exist - Depende de outras PROCS: PERFORM CALL ow_lao.proc_monitoring_bi_lao_proccess_system_reviews(); | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 11 |  | 0 |  |  | 10/09 - 10/09
PERFORM CALL ow_lao.proc_monitoring_bi_lao_proccess_ft_ecom();
PERFORM CALL ow_lao.proc_monitoring_bi_lao_proccess_hybris();
PERFORM CALL ow_lao.proc_monitoring_bi_lao_proccess_sales_order_tracking();
PERFORM CALL ow_lao.proc_monitoring_bi_lao_proccess_depara();
PERFORM CALL ow_lao.proc_monitoring_bi_lao_proccess_globalbi();
PERFORM CALL ow_lao.proc_monitoring_bi_lao_proccess_vtex_seda();
PERFORM CALL ow_lao.proc_monitoring_bi_lao_proccess_hybris_files_sales_validation();
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_VTEX_SEDA) | Bruno | OK | ERROR: "U_PRJ_ECOM_SYNAPCOM.FT_ECOM_ORDER" does not exist -- Não UTILIZAR EM PROCEDURE | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 5 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_HYBRIS) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 4 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SALES_ORDER_TRACKING) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_FT_ECOM) | Felipe | ERRO | Forte dependência com a tabela u_prj_ecom_synapcom.ft_ecom_order | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES) | Felipe | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_HYBRIS_SALES_MONITORING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS_HYBRIS_FILES_SALES)'", "'(TABLE - OW_LAO.RAW_HYBRIS_SALES)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 6 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_SEDA_S.PROC_DM_PURCHASE_ORDER_TRACKING_ITEM) | Felipe | ERRO | Table "DM_PURCHASE_ORDER_TRACKING_ITEM" does not exist -¦" Não existe no Banco " | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_DOMAIN)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_TRACKING_ITEM)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_COURIER)'", "'(TABLE - OW_MD.DIM_VTEX_PAYMENT_GROUP)'", "'(TABLE - OW_MD.FT_VTEX_PURCHASE_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_VTEX_ORDER_STATUS)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_TRADE_IN)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_WAREHOUSE)'", "'(TABLE - OW_MD.DIM_VTEX_PURCHASE_ORDER_REGION)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)'", "'(TABLE - OW_MD.DIM_VTEX_AFFILIATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 13 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_ALERT) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT)'", "'(TABLE - OW_LAO.DIM_MONITORING_BI_LAO_PROCCESS_ALERT)'", "'(TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ID)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.RAW_FILES_MINIO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_MONITORING_BI_LAO_PROCCESS_ALERT)'", "'(TABLE - OW_LAO.TIME_DEFINITION)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.ODS_MONITORING_BI_LAO_PROCCESS_ALERT_CONTROL_TOWER_X_ORIGEM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_EXCLUSIVES_ITEMS) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.RAW_LAO_PRODUCT_EXCLUSIVES_ITEMS)'", "'(TABLE - OW_LAO.STG_LAO_PRODUCT_EXCLUSIVES_ITEMS)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_STG_TABLE_ODS_PREMIUM_ITEMS) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.STG_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.RAW_LAO_PRODUCT_PREMIUM_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - U_PRJ_ECOM.PROC_RAW_CUSTOMER_ID_SEDA) | Bruno | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_CUSTOMER_ID_SEDA)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 3 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES) | Felipe | OK | 2 Procedures (uma sem parâmetros e uma com parâmetros) | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 21 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TMP) | Cassio | OK |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 21 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_TEMP_20250711) | Felipe |  |  | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 20 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_D2C_MELI_COLETAS) | Bruno | OK | Relation "OW_SEDA_S.VW_CELLO_RETURN_TRACKING" does not exist -- view | 4 | 1 | 2025-09-10 | 2025-09-10 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_LAO.TF_D2C_MELI_COLETAS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_RDD)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 |  | 0 |  |  | 10/09 - 10/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_GROSS_MARGIN) | Cassio | OK |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_MD.REBATE)'", "'(TABLE - OW_LAO.ODS_NERP_ZLSDK66820_DISPLAY_CLOSING_REPORT)'", "'(TABLE - OW_MD.COGS)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_MD.SOLD_TO_CHANNEL)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  | 0 |  |  | 11/09 - 11/09
(PROCEDURE - OW_LAO.PROC_FT_D2C_NERP_CELLO_LEAD_TIME_RETURN_PENDING_KPI) | Bruno | OK |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_LAO.AUX_CELLO_DELIVERY_INBOUND_ORDER_TYPE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  | 0 |  |  | 11/09 - 11/09
(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW) | Cassio | OK |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY)'", "'(TABLE - OW_MD.ODS_MEDALIA_TARGET_NPS)'", "'(TABLE - OW_LAO.ODS_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 3.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 11/09 - 11/09
(PROCEDURE - OW_LAO.PROC_FT_D2C_BIZOVERVIEW_V2) | Cassio | OK |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_LAO_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GSCM_AP1_ACCURACY)'", "'(TABLE - OW_MD.ODS_MEDALIA_TARGET_NPS)'", "'(TABLE - OW_LAO.ODS_MEDALLIA_EXPRESS_REPORT)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 3.1 Migrar ph1 |  |  | 6 |  | 0 |  |  | 11/09 - 11/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI) | Cassio | OK |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.RAW_GSCM_CE_SELL_OUT)'", "'(TABLE - OW_MD.ODS_MP_ESTORE)'", "'(TABLE - OW_LAO.ODS_TARGET_STRETCH)'", "'(TABLE - OW_LAO.RAW_GSCM_MX_SELL_OUT)'", "'(TABLE - OW_LAO.RAW_NERP_ZRCOA20250_FORECAST_SALES)'", "'(TABLE - OW_LAO.ODS_NERP_ZRCOS43400_TARGET_FOLDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_WEEKLY_SALES_KPI)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 1.4 Ingestion NERP |  |  | 10 |  | 0 |  |  | 11/09 - 11/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_VS_GSCM_WOS) | Felipe | ERRO | Relation "OW_MD.DIM_PLANT" does not exist | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRMMJ310410_DISPLAY_AVALIABLE_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.TF_D2C_NERP_TO_WOS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_TO_STOCK_OVERVIEW)'", "'(TABLE - OW_LAO.FT_D2C_NERP_TO_STOCK_OVERVIEW_BY_PLANT)'", "'(TABLE - OW_LAO.TF_D2C_GSCM_TO_WOS)'", "'(TABLE - OW_LAO.ODS_GSCM_FCST_MGMT_D2C)'", "'(TABLE - OW_LAO.FT_D2C_WOS)]']"] | 1 | 1.4 Ingestion NERP |  |  | 7 |  | 0 |  |  | 11/09 - 11/09
ERROR: Function TO_DATE(varchar) does not exist, or permission is denied for TO_DATE(varchar)
(PROCEDURE - OW_SEDA_S.PROC_FT_OST_PLUGGTO) | Cassio | OK |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_LOG_HISTORY)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER_STATUS_HISTORY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  | 11/09 - 11/09
(PROCEDURE - OW_SEDA_S.PROC_NERP_ZRSDD6A120_OUTBOUND_TRACKING_SCM) | Bruno | OK |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_SEDA_S.RAW_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)'", "'(TABLE - OW_SEDA_S.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)'", "'(TABLE - OW_SEDA_S.TMP_NERP_ZRSDD6A120_SALES_ORDER_TRACKING_SCM)]']"] | 0 | 1.4 Ingestion NERP |  |  | 3 |  | 0 |  |  | 11/09 - 11/09
(PROCEDURE - OW_MD.PROC_DIM_PRODUCT) | Cassio | OK |  | 4 | 1 | 2025-09-11 | 2025-09-11 | ["['[(TABLE - OW_LAO.ODS_GSCM_PRODUCT_LIST)'", "'(TABLE - OW_MD.ODS_TDF_MARA)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_PRODUCT_SKU)'", "'(TABLE - OW_MD.OLD_DIM_PRODUCT)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 4 |  | 0 |  |  | 11/09 - 11/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE) | Cassio | OK | OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM(); | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_MASTER_DATA_CL)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM)'", "'(TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE)'", "'(TABLE - OW_LAO.ODS_HYBRIS_COMBO)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.DIM_ECOM_PARTNER_LEVEL)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 56 |  | 0 |  |  |  | 16/09 - 16/09
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_UPDATE();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_OUTBOUND_UPDATE();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_GLOBALBI_UPDATE();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PREMIUM_MODELS_UPDATE();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DOLAR_VALUES_UPDATE();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIM_PRODUCT_MAPPING_LAO_UPDATE();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_TAXES_UPDATE();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_PAYMENTS();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_STATUS_CANCELED();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PARTNER_LEVEL();
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_ELEGIBLE();
OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_ITEMS_EXCLUSIVES_UPDATE();
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG) | Cassio | OK | Relation "u_prj_ecom_synapcom.ft_ecom_order" does not exist | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 30 |  | 0 |  |  |  | 16/09 - 16/09
Dependencias:
OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER
(PROCEDURE - OW_LAO.PROC_D2C_AR_ONE_VIEW_TABLE) | Bruno | OK | Relation "OW_SEDA_S.VW_CELLO_RETURN_TRACKING" does not exist | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.RAW_DATA_API_AFTER_SALES_DETAIL_CONSOLIDATED)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_LAO.FT_D2C_AR_ONE_VIEW_TABLE)'", "'(TABLE - OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_01)'", "'(TABLE - OW_LAO.TF_D2C_VTEX_PAYMENT_SKU)'", "'(TABLE - OW_LAO.TF_D2C_AR_ONE_VIEW_TABLE_02)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 28 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_D2C_ONE_VIEW_TABLE) | Bruno | OK | Relation "OW_SEDA_S.VW_CELLO_RETURN_TRACKING" does not exist | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEB57910_CLAIM_FOLDER)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)'", "'(TABLE - OW_SEDA_S.ODS_PLUGG_MARKETPLACE_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 22 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_ECOM_ORDERS_B5Q5) | Felipe | ERRO | OW_LAO.VIEW_ECOM_ORDERS_B5Q5_VTEX | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.DIM_EXCHANGE_RATE)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM_BUNDLES_BREAKDOWN_HOMOLOG) | Felipe | ERRO | Criar script pro Vertica - está tudo com erro, tem quase 2 mil linhas | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - U_PRJ_ECOM.ODS_ECOM_SKU_ENABLES)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 18 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP) | Cassio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 17 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_HOMOLOG) | Enio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 16 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_BDP_UT) | Enio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_VTEX_SSG_BR_SHOP_GROUPED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 16 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN) | Cassio | OK | Foram criadas projeções para execução da procedure | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 14 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI) | Cassio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 14 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_RDD) | Cassio |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_PO_VTEX_RDD)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG) | Enio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_V2) | Enio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_HOMOLOG)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_2) | Bruno | ERRO | PASSAR LM PARA PROCEDURE -- Está muito diferente | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_BDP_3) | Bruno | OK | ERROR: Column "payment_card_brand" is of type varchar but expression is of type long varchar | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_BR_SHOP_HOMOLOG_2)'", "'(TABLE - U_PRJ_ECOM.ODS_VTEX_SSG_BR_SHOP_DATA_ENTITIES_STORES_SDS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_SHIPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 13 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SALES_ORDER) | Cassio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_ITEM)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SALES_ORDER)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_AR_SMB_SALES_ORDER) | Cassio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_SHIPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SMB_SALES_ORDER_ITEM)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 10 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS) | Felipe | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_VTEX_BR_DETAILS) | Felipe |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_BR_DETAILS)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 9 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_DAILY_SALES) | Cassio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM_COMPONENTS)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_ITEM)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.TF_D2C_NERP_DAILY_SALES_KPI)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 8 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_BY_CHANNEL) | Felipe | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES_BY_CHANNEL_KPI)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER_LIST)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 6 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_VTEX_AR_DETAILS) | Enio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_AR_SALES_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_VTEX_AR_DETAILS_HOMOLOG)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_PY_SALES_ORDER) | Cassio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_PY_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_UY_SALES_ORDER) | Bruno | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_RAW_VTEX_SSG_UY_SALES_ORDER)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 5 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS) | Bruno | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_TYPE_MAPPING)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_FUNNEL_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.TMP_SALES_PAYMENTS_GRAFANA_DETAILS)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 12 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_OW_LAO_ODS_HYBRIS_SALES) | Felipe | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)'", "'(TABLE - OW_LAO.ODS_HYBRIS_COMBO)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 10 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.HOMOLOG_PROC_ODS_SALES_PAYMENTS_GRAFANA_DETAILS) | Felipe |  |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_PAYMENTS_DETAILS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.ODS_HYBRIS_SALES)'", "'(TABLE - OW_LAO.RAW_GRAFANA_DOCUMENT_LOG_PAYMENTS_DETAILS)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 7 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_SALES_DEDUCTION_CONDITIONS) | Enio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_04)'", "'(TABLE - OW_LAO.ODS_NERP_ZRMKF02002_DISPLAY_PAYMENT_STATUS_BY_CLAIM)'", "'(TABLE - OW_LAO.ODS_NERP_ZLMKC00040_CONDITION_PROGRESS_REPORT)'", "'(TABLE - OW_MD.MAP_INCENTIVE_TYPE_MAPPING)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_05)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP_HISTORICO)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE_HISTORICO)'", "'(TABLE - OW_MD.MAP_CUSTOMER_EXCEPTION)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TO_NERP)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_TEMPLATE)'", "'(TABLE - OW_LAO.ODS_NERP_ZLMKF03010_INCENTIVE_CALCULATION_RESULT_REPORT)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_01)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.FT_SALES_DEDUCTION_CONDITIONS_HISTORICO_CONSOLIDADO)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_02)'", "'(TABLE - OW_LAO.ODS_GSSC_REPORT_TO_SR)'", "'(TABLE - OW_LAO.TF_SALES_DEDUCTION_CONDITIONS_03)]']"] | 1 | 1.4 Ingestion NERP |  |  | 19 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_OPERATION) | Enio | Erro | Erro SQL [4568] [42V01]: [Vertica][VJDBC](4568) ERROR: Relation "OW_SEDA_S.VW_CELLO_RETURN_TRACKING" does not exist | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_ITEM)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_SEDA_S.CELLO_FUTHER_PROCESSING)'", "'(TABLE - OW_SEDA_S.CELLO_SHIPMENT_INBOUND)'", "'(TABLE - OW_LAO.FT_D2C_CELLO_NERP_RETURN_OPERATION)'", "'(TABLE - OW_SEDA_S.CELLO_TRACKING)'", "'(TABLE - OW_SEDA_S.ODS_GLP_RETURN_RATIO_WEEKLY)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_SEDA_S.FT_UNION_TSS_CELLO_HIST_FULL)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY)'", "'(TABLE - OW_SEDA_S.CELLO_MANIFEST_INBOUND)'", "'(TABLE - OW_SEDA_S.M_CODE_CELLO)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)'", "'(TABLE - OW_SEDA_S.TF_CELLO_TRACKING_EVENT)]']"] | 1 | 1.4 Ingestion NERP |  |  | 14 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES) | Cassio | OK | Dependencias: | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.DIM_SALES_CHANNEL)]']"] | 1 | 1.4 Ingestion NERP |  |  | 6 |  | 0 |  |  |  | 16/09 - 16/09
OW_LAO.PROC_D2C_NERP_WEEKLY_SALES_KPI
OW_LAO.PROC_D2C_NERP_SALES_BY_HOUR_KPI
OW_LAO.PROC_D2C_VTEX_O2O_SALES_KPI
OW_LAO.PROC_D2C_NERP_SALES_REWARDS_KPI
OW_LAO.PROC_D2C_PO_VTEX_SALES_KPI
OW_LAO.PROC_D2C_PO_VTEX_SALES
OW_LAO.PROC_D2C_VTEX_PROMOTION_KPI
OW_LAO.PROC_D2C_NERP_SALES_TRADEIN_KPI
OW_LAO.PROC_D2C_NERP_SALES_COUPON_KPI
OW_LAO.PROC_D2C_VTEX_SELLOUT_PLATFORM_KPI
(PROCEDURE - OW_LAO.PROC_D2C_CELLO_NERP_RETURN_PENDING) | Enio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEE50090_DISPLAY_DO_TRACKING_INFO_RETURN)'", "'(TABLE - OW_LAO.FT_D2C_CELLO_NERP_RETURN_PENDING)'", "'(TABLE - OW_SEDA_S.CELLO_DELIVERY_INBOUND_ITEM)]']"] | 1 | 1.4 Ingestion NERP |  |  | 4 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM) | Cassio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)'", "'(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_ITEM)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_U_PRJ_ECOM)'", "'(TABLE - U_PRJ_ECOM.DIM_CUSTOMER)'", "'(TABLE - OW_LAO.TMP_ODS_SALES_CONTROL_TOWER_TABLE_BUNDLE)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - U_PRJ_ECOM.FT_ECOM_ORDER_PAYMENT)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)'", "'(TABLE - OW_LAO.TEMP_DIM_ECOM_STORE_SEASA_MKM)]']"] | 1 | 2.1 Migrar ph1 |  |  | 14 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.HOMOLOG_PROC_FUNNEL_PAYMENTS_MAP) | Bruno | OK | Table "OW_LAO.DIM_PAYMENT_STATUS_MAPPING" does not exist ¦" Não existe no Banco " | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_STATUS_MAPPING_MINIO)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAYMENT_TYPE)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 8 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_FUNNEL_PAYMENTS_MAP) | Enio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAYMENT_TYPE)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 7 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT) | Felipe | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 6 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_LAO_PAYMENT_FUNNEL_PBI) | Enio | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.ODS_PAYMENT_FUNNEL)'", "'(TABLE - OW_LAO.DIM_PAYMENT_GATEWAY_CODE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_VISUAR) | ENIO | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 5 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIGGIT_HIST_HOMOLG) | Bruno | OK |  | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_STIENDA) | Bruno | OK | PASSAR LM PARA PROCEDURE -- | 4 | 1 | 2025-09-16 | 2025-09-16 | ["['[(TABLE - OW_LAO.DIM_ODS_SALES_CONTROL_TOWER_TABLE_STATUS_MAPPING)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)'", "'(TABLE - OW_MD.SALES_CHANNEL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 4 |  | 0 |  |  |  | 16/09 - 16/09
(PROCEDURE - OW_LAO.PROC_TESTE_) | Bruno | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_SHOP_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - U_PRJ_ECOM.PROC_ODS_ECOM_HQ_ORDERS_PRODUCTS_TRADEIN) | Bruno | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - U_PRJ_ECOM.RAW_VTEX_SEASA_TRADEIN_FEED)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_LAO.PROC_RAW_VTEX_SSG_BR_B2B_SALES_ORDER_MONITORING_DATASOURCE) | Bruno | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_B2B_SALES_ORDER)]']"] | 1 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_LAO.PROC_INTEGRATION_RAW_VTEX_SALES_COLLECTION) |  | ERRO | Criar script pro Vertica | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.RAW_VTEX_SSG_BR_EPP2_SALES_COLLECTION)'", "'(TABLE - U_PRJ_ECOM.TMP_RAW_VTEX_SSG_BR_SHOP_DETAIL_HIST_TALEND_PRL_2020)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_GENERATE) | Bruno | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI_SEDA_GENERATE) | Bruno | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_LAO.PROC_ODS_STOCKOUT_VTEX_GLOBALBI) | Bruno | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_STOCKOUT_VTEX_GLOBALBI)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_FILES_DEDUP) | Bruno | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS_FILES)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_FILES_GET) | Bruno | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS_FILES)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_LAO.RAW_VTEX_PAYMENTS_GENERATE) | Bruno | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.RAW_VTEX_PAYMENTS)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_MD.PROC_FT_PRODUCT_STATUS) | Bruno | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - U_PRJ_ECOM.ODS_VTEX_PRODUCT_SKU)]']"] | 0 | 1.1 Ingestion VTEX |  |  | 1 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PAYMENTS) | ENIO | OK |  | 4 | 1 | 2025-09-17 | 2025-09-17 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PAYMENTS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_PAYMENTS)]']"] | 1 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 17/09 - 17/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_CANCELLATIONS) | ENIO | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_CANCELLATIONS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_CANCELLATIONS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_OFFERS) | ENIO | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_OFFERS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_OFFERS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_PREORDERS) | Felipe | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_PREORDERS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_PREORDERS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REFUNDS) | Felipe | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_REFUNDS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_REFUNDS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_RETURNS) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_RETURNS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_RETURNS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_REWARDS) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_REWARDS)'", "'(TABLE - OW_LAO.RAW_HYBRIS_REWARDS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS) | Felipe | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_SALES_PRODUCTS_DISCOUNTS)'", "'(TABLE - OW_LAO.STG_HYBRIS_SALES_PRODUCTS_DISCOUNTS)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_TRADEIN) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_HYBRIS_TRADEIN)'", "'(TABLE - OW_LAO.RAW_HYBRIS_TRADEIN)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_HYBRIS_SALES_ITEMS_DISCOUNTS) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.RAW_HYBRIS_SALES_HOMOLOG)]']"] | 0 | 1.2 Ingestion HYBRIS |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_DIM_SOLD_TO) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_FORECAST_OST) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_FBL5N_CUSTOMER_LINE_ITEM_DISPLAY_OPEN_ITEMS_HIST)'", "'(TABLE - OW_LAO.RAW_REPASSES_D2C_2022_2024)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.RAW_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)'", "'(TABLE - OW_LAO.ODS_NERP_ZKE24_DISPLAY_ACTUAL_LINE_ITEMS)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_OUTBOUND_UPDATE) | Cassio | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_NERP_OUTBOUND_UPDATE_HOMOLOG) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_NERP_ZLLEJ50090_OUTBOUND_TRACKING)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)]']"] | 1 | 1.4 Ingestion NERP |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_TF_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN_SALES_PROGRESS_KPI_UNPIVOT) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_TF_NERP_ZRCOS43400_SALES_PROGRESS_KPI_UNPIVOT_AGG_DIVISION_GROUP) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_SEDA_S.ODS_NERP_ZRCOS43400_DISPLAY_SELL_OUT_PLAN)]']"] | 0 | 1.4 Ingestion NERP |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_MONTH_PT2) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TMP_D2C_AR_TABLE_MONTH)'", "'(TABLE - OW_LAO.FT_D2C_AR_TABLE_MONTH)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_AR_TABLE_WEEK_PT2) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.FT_D2C_AR_TABLE_WEEK)'", "'(TABLE - OW_LAO.TMP_D2C_AR_TABLE_WEEK)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_GSCM_INVENTORY) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.RAW_DATA_GSCM_ACTUAL_ON_HAND)'", "'(TABLE - OW_LAO.FT_D2C_GSCM_INVENTORY)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_PO_VTEX_SALES_KPI) | Cassio | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_VTEX_SELLOUT_PLATFORM_KPI) | Cassio | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_PO_VTEX_TRADE_IN)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_INSERT_SALES_CANCELLED_FROM_ODS) | Bruno | OK | ERROR: Function REPLACE(numeric, unknown, unknown) does not exist, or permission is denied for REPLACE(numeric, unknown, unknown) | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_INSERT_SALES_FROM_ODS) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)'", "'(TABLE - OW_LAO.TF_D2C_PAYMENT_ITAU)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_ALL) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_ALL)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_ALL)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_DIM_PRODUCT_MAPPING_LAO_UPDATE) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_TMP_DIM_SALES_CHANNELS_PROMOTIONS_RESULT_VALIDATION_TF_D2C_NERP_SALES) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.FT_D2C_VTEX_PROMOTION)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_MD.PROC_DIM_PRODUCT_ESTORE_GLOBAL) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.DIM_PRODUCT_MAPPING_LAO)'", "'(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - U_PRJ_ECOM.PROC_DIM_EXCHANGE_RATE_RAWDATA) | Bruno | OK | VERIFICAR -- WHERE A.VALID_FROM = CURRENT_DATE | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_COUPON_KPI) | Cassio | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_NERP_SALES_REWARDS_KPI) | Cassio | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_VTEX_O2O_SALES_KPI) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_VTEX_PO_TARGET_LAUNCH_S25) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_DIM_TAX_GROSS_MARGIN) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_FT_D2C_VTEX_O2O_SALES_KPI) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_TF_NERP_GROSS_MARGIN_MONITORING_DATASOURCE) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_NERP_GROSS_MARGIN)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_MD.PROC_INGESTION_DIM_PRODUCT_ESTORE) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_MD.PROC_INGESTION_DIM_PRODUCT_GLOBAL) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_D2C_NERP_SALES)]']"] | 1 | 2.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_CHECK_CONTROL_TOWER_TABLE_ALERT_LAST_UPDATE_SOURCE) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.DIM_SUBSIDIARY)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_STORENAME_UPDATE) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.DIM_LAO_CRP_CS_STORENAME)'", "'(TABLE - OW_LAO.RAW_LAO_CRP_CS_STORENAME)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_LAO_CRP_CS_VOUCHER_COUPON_UPDATE) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON)'", "'(TABLE - OW_LAO.RAW_LAO_CRP_CS_VOUCHER_COUPON)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_LAO_DELIVERY_MODE_DIM_UPDATE) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.DIM_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)'", "'(TABLE - OW_LAO.RAW_LAO_DELIVERY_MODE_MAPPING_CONTROL_TOWER)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_DA) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_DA)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_DA)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_MX) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_MX)'", "'(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_MX)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_LAO_ODS_GLOBAL_BI_TRAFFIC_VD) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TF_GLOBAL_BI_TRAFFIC_VD)'", "'(TABLE - OW_LAO.ODS_GLOBAL_BI_TRAFFIC_VD)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_GATEWAY_STATUS_MAP_HOMOLOG) | Bruno | OK | Criar script pro Vertica | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_PAY_GATEWAY)'", "'(TABLE - OW_LAO.DIM_PAYMENT_PAY_GATEWAY_MAPPING)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_TF_PO_COUPON_ID_CONTROL_TOWER_LIST) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.DIM_LAO_CRP_CS_VOUCHER_COUPON)]']"] | 0 | 2.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ERP_AP2_EXCHANGE_RATE_BKP) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)'", "'(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_LAO_PREMIUM_PRODUCTS_TABLE_FROM_GSCM_UPDATE) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)'", "'(TABLE - OW_LAO.ODS_GSCM_PREMIUM_MODELS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_GLOBALBI_UPDATE) | Cassio | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PBI) | Enio | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN_GLOBALBI_UPDATE_HOMOLOG) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)'", "'(TABLE - OW_LAO.TMP_ECOMMERCE_SALES_CONTROL_TOWER_TABLE_BUNDLES_BREAKDOWN)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_MD.PROC_INGESTION_ODS_MP_ESTORE) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_MD.RAW_MP_ESTORE)'", "'(TABLE - OW_MD.ODS_MP_ESTORE)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREPP2) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EPP2)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EPP2)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2ESTUDANTES) | Enio | Ok |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_EST)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_EST)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - U_PRJ_ECOM.ODS_DIGGIT_ECOM_ORDERS)'", "'(TABLE - U_PRJ_ECOM.STG_DIGGIT_ECOM_ORDERS)]']"] | 1 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_D2C_FT_STOCKOUT) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_STOCKOUT)]']"] | 1 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_ODS_GLOBAL_BI_SALES_EMPTY_DIMENSIONS_ALERT) | Bruno | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_GLOBAL_BI_SALES)]']"] | 1 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE_ODS_SELA_CUSTOM_ORDERS_ITEMS_UPDATE) | Cassio | OK |  | 4 | 1 | 2025-09-18 | 2025-09-18 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)'", "'(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 18/09 - 18/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_DEPARA) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_MONITORING_BI_LAO_PROCCESS_SYSTEM_REVIEWS_NERP) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.MONITORING_BI_LAO_PROCCESS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_CONTROL_TOWER_TABLE_ITEMS_EXCLUSIVES_UPDATE) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_EXCLUSIVES_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)'", "'(TABLE - OW_LAO.TMP_DIM_SUBSIDIARY_TIMEZONE_EXCEPTIONS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_ORDERS_VISUAR) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.RAW_ORDERS_VISUAR)'", "'(TABLE - OW_LAO.ODS_ORDERS_VISUAR)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_PREMIUM_MODELS_UPDATE) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.ODS_LAO_PRODUCT_PREMIUM_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_TAXES_UPDATE) | Cassio | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.AUX_SALES_CONTROL_TOWER_TABLE_TAXES)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_FEED_SEND_ESTORE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_HQ_BKP10032025) | ENIO | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - OW_LAO.RAW_FEED_SEND_ESTORE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_CUT)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V2) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_CUT)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_PBI_V3) | ENIO | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_CAMPAIGN_CUT)'", "'(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_MD.PROC_ODS_SALES_CHANNELS) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_MD.INPUT_SALES_CHANNELS)'", "'(TABLE - OW_MD.ODS_SALES_CHANNELS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRB2B) | Bruno |  | ScriptVazio - Criar script para Vertica ¦Quase 2 mil linhas | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRB2B)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRB2B)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BREA) | Bruno |  | ScriptVazio - Criar script para Vertica ¦Quase 2 mil linhas | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BREA)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BREA)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOP) | Bruno |  | ScriptVazio - Criar script para Vertica ¦Quase 2 mil linhas | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_BRSHOPMKTPL) | Bruno |  | ScriptVazio - Criar script para Vertica ¦Quase 2 mil linhas | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_BRSHOPMKTPL)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_BRSHOPMKTPL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2MEMBERS) | Bruno |  | ScriptVazio - Criar script para Vertica ¦Quase 2 mil linhas | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_MEMBERS)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_MEMBERS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2PARCERIAS) | Bruno |  | ScriptVazio - Criar script para Vertica ¦Quase 2 mil linhas | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_SEDA_S.PROC_OST_AFTERSALES_REFUND_TEMP_EPP2RESIDENCIAL) | Bruno |  | ScriptVazio - Criar script para Vertica ¦Quase 2 mil linhas | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_DETAIL_PARC)'", "'(TABLE - OW_LAO.ODS_AFTER_SALES_REFUND_PARC)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - U_PRJ_ECOM.PROC_ECOM_HQ_ORDERS_PRODUCTS_COMBO) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_PRODUCTS_COMBO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - U_PRJ_ECOM.PROC_ODS_SALES_CONTROL_TOWER_TABLE_RAW_VTEX_SSG_BR_SHOP) | Cassio | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_PRODUCTS_COMBO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - U_PRJ_ECOM.PROC_RAW_ECOM_HQ_ORDERS_TRADEIN_FEED) | Felipe | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)'", "'(TABLE - U_PRJ_ECOM.RAW_ECOM_HQ_ORDERS_TRADEIN_FEED)]']"] | 0 | 3.1 Migrar ph1 |  |  | 2 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_BLACK_FRIDAY_PBI) | Cassio | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_DIM_TARGETS_CAMPAIGN_CADASTRA_UPDATE) | Cassio | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_TARGETS_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_DIVISION_NERP_CONTROL_TOWER_STATUS) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_FT_AP2_EXCHANGE_RATE_HOMOLOG) | Bruno | OK | ERROR: Relation "ow_lao.ft_ap2_exchange_rate_homolog" does not exist ¦ "Não existe no Banco" | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_ALL) | Bruno | OK | ERROR: Relation "OW_LAO.FT_GLOBAL_BI_TRAFFIC_ALL" ¦ "Não existe no Banco" -- tive que criar | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_ALL)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_DA) | Bruno | OK | ERROR: Table "OW_LAO.FT_GLOBAL_BI_TRAFFIC_DA" ¦ "Não existe no Banco" -- tive que criar | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_DA)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_MX) | Bruno | OK | ERROR: Table "OW_LAO.FT_GLOBAL_BI_TRAFFIC_MX" ¦ "Não existe no Banco" -- tive que criar | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_MX)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_LAO_TF_GLOBAL_BI_TRAFFIC_VD) | Bruno | OK | ERROR: Table "OW_LAO.FT_GLOBAL_BI_TRAFFIC_VD" ¦ "Não existe no Banco" -- tive que criar | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_GLOBAL_BI_TRAFFIC_VD)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_MONITORING_SALES_CONTROL_TOWER_TABLE_ALERT_ORDERS) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_EXCHANGE_RATE_HOMOLOG) | Bruno | ERRO | ERROR: Relation "ow_lao.ft_ap2_exchange_rate_homolog" does not exist ¦ "Não existe no Banco" | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_ERP_EXCHANGE_RATE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_CHECK_DATASOURCE) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_CHECK_DATASOURCE_HOMOLOG) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_SALES_MONITORING_DATASOURCE) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_EMPTY_DIMENSIONS_ALERT) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_TABLE_NERP_STATUS_CANCELED) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_MIRGOR_CANCEL_ORDERS) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SALES_CONTROL_TOWER_VTEX_SSG_VISUAR_CANCEL_ORDERS) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CONTROL_TOWER_TABLE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS) | Cassio | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_HISTORY_COMMENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SELA_CUSTOM_ORDERS_ITEMS_VALIDATION) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_CUSTOM_ORDERS_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO) | Bruno | OK | SUBSTITUÍMOS FUNCAO HASH_SHA256 POR SHA256 | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_PAYMENTO_ADDITIONAL_INFO)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_EXTENSION_ATTRIBUTES_SHIPPING_ASSIGNMENTS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_ORDERS_COUPONS_STATUS_HISTORY)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SELA_SALES_COUPONS) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_SALES_COUPONS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_ODS_SELA_SALES_COUPONS_ITEMS) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SELA_SALES_COUPONS_ITEMS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_PAYMENT_FUNNEL_PAYMENT_TYPE_MAP_HOMOLOG) | Felipe |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.TMP_PAYMENT_PAYMENT_TYPE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_RAW_FEED_SEND_ESTORE_SALES_SAMPLE_HQ) | Bruno | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.RAW_FEED_SEND_ESTORE)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_SALES_CAMPAIGN_DAILY_CHECK) | Enio | OK |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - OW_LAO.ODS_SALES_CAMPAIGN)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - U_PRJ_ECOM.PROC_ODS_DIGGIT_ECOM_ORDERS_HIST_HOMOLG) | Felipe |  |  | 4 | 1 | 2025-09-19 | 2025-09-19 | ["['[(TABLE - U_PRJ_ECOM.TMP_DIGGIT_ECOM_ORDERS)]']"] | 0 | 3.1 Migrar ph1 |  |  | 1 |  | 0 |  |  |  | 19/09 - 19/09
(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_VC_PT1) | Bruno | ERRO | ERROR: Table "OW_LAO.INPUT_CRAWLING_AP1_NPC_SITE_MAPPING" does not exist ¦ DEVE SER DENTRO DA VIEW: VW_CRAWLING_AP1_NPC_SEGMENT -- ELA TAMBÉM NÃO EXISTE | 4 | 1 | 2026-01-22 | 2026-01-22 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [21 empty] | 22/01 - 22/01
(PROCEDURE - OW_LAO.PROC_CRAWLING_AP1_WERABLES_PT1) | Bruno | ERRO | Table "OW_LAO.FT_CRAWLING_AP1_WERABLES_SEGMENT" does not exist -- varias erros | 4 | 1 | 2026-01-22 | 2026-01-22 | ["['[(TABLE - OW_LAO.FT_AP2_EXCHANGE_RATE)]']"] | 1 | r.bojart |  |  | 1 |  | 0 | [21 empty] | 22/01 - 22/01
(PROCEDURE - OW_LAO.PROC_NERP_ZLLEJ50090_OUTBOUND_TRACKING) | Cassio | OK |  | 4 | 1 | 2025-10-07 | 2025-10-07 |  | 1 | r.bojart |  |  | 1 |  | 0
(PROCEDURE - OW_LAO.PROC_INGESTION_ODS_NERP_ZRSDD6A120_SALES_ORDER_TRACKING ) | Bruno | OK |  | 4 | 1 | 2025-10-07 | 2025-10-07 |  | 1 | r.bojart |  |  | 1 |  | 0
(PROCEDURE - OW_MD.PROC_DIM_CUSTOMER_POLICY) | Cassio | OK |  | 4 | 1 | 2025-10-21 | 2025-10-21 |  |  | r.bojart |  |  | 1 |  | 0
_